## BOQ Activity
ID | Activity | Duration | Resource (คน) | Resource type | ค่าวัสดุรวม (บาท) | ค่าวัสดุต่อวัน (บาท/วัน) | ค่าแรงงานรวม (บาท) | ค่าแรงงานต่อวัน (บาท/วัน) | ค่าแรงงานต่อคนต่อวัน (บาท/คน/วัน)
1 | Chiang Mai Library Renovation Project
2 | Preparation
3 | Work on the building and surrounding area | 14 | 4 | Engineer
4 | Public utility system works | 16 | 4 | Engineer
5 | Interior system test
6 | 4th floor | 15 | 4 | Engineer
7 | 3rd floor | 15 | 4 | Engineer
8 | 2nd floor | 15 | 4 | Engineer
9 | 1st floor | 15 | 4 | Engineer
10 | Basement and outside areas | 15 | 4 | Engineer
11 | Eletricity supply, sanitary and original item checking tasks
12 | 4th floor | 15 | 4 | Engineer
13 | 3rd floor | 15 | 4 | Engineer
14 | 2nd floor | 15 | 4 | Engineer
15 | 1st floor | 15 | 4 | Engineer
16 | Basement and outside areas | 15 | 4 | Engineer
17 | Paperwork on item usage permission, shop drawing and project items
18 | Shop drawing of the 4th floor | 20 | 4 | Engineer
19 | Shop drawing of the 3rd floor | 20 | 4 | Engineer
20 | Shop drawing of the 2nd floor | 20 | 4 | Engineer
21 | Shop drawing of the 1st floor | 20 | 4 | Engineer
22 | Shop drawing of the basement | 20 | 4 | Engineer
23 | Shop drawing of the outside areas | 20 | 4 | Engineer
24 | Shop drawing of the landscpae | 20 | 4 | Engineer
25 | Shop drawing of item renovation | 92 | 4 | Engineer
26 | Shop drawing of item purchasing | 92 | 4 | Engineer
27 | System test work, workshop for building users and As-Built Drawing
28 | 4th floor | 30 | 4 | Engineer
29 | 3rd floor | 30 | 4 | Engineer
30 | 2nd floor | 30 | 4 | Engineer
31 | 1st floor | 30 | 4 | Engineer
32 | Basement | 30 | 4 | Engineer
33 | The whole building | 30 | 4 | Engineer
34 | Building management and other works | 0 | 4 | Engineer
35 | Renovation on the fourth floor
36 | Demolition work on the 4th floor (Dismantled) | 30 | 12 | General worker | 0 | 0 | 140513 | 4683.7667 | 390.3139
37 | Architecture Work on the Fourth Floor
38 | Ceiling work | 30 | 3 | Skilled carpenter | 1002957 | 33431.9 | 293515 | 9783.8333 | 3261.2778
39 | Floor work | 60 | 2 | General worker | 760861 | 12681.0167 | 139900 | 2331.6667 | 1165.8333
40 | Wall work | 30 | 2 | General worker | 133591 | 4453.0333 | 89938 | 2997.9333 | 1498.9667
41 | Door and Window Work | 30 | 1 | Skilled carpenter | 240500 | 8016.6667 | 3150 | 105 | 105
42 | Staircase | 30 | 1 | General worker | 8470 | 282.3333 | 3850 | 128.3333 | 128.3333
43 | Painting work | 30 | 3 | General worker | 111300 | 3710 | 66780 | 2226 | 742
44 | Sanitary ware
45 | Zone T-1 the area in front of the original buidling | 15 | 2 | Sanitary-Plumber | 198086.8333 | 13205.7889 | 14473.3333 | 964.8889 | 482.4444
46 | Zone T-2 the area in the middle | 15 | 2 | Sanitary-Plumber | 198086.8333 | 13205.7889 | 14473.3333 | 964.8889 | 482.4444
47 | Zone T3 the area behind the new building | 15 | 2 | Sanitary-Plumber | 198086.8333 | 13205.7889 | 14473.3333 | 964.8889 | 482.4444
48 | Sanitation system work on the fourth floor
49 | Water supply pipe system work
50 | Zone T-1 the area in front of the original buidling | 126 | 1 | Sanitary-Plumber | 19785.6667 | 157.0291 | 4870 | 38.6508 | 38.6508
51 | Zone T-2 the area in the middle | 126 | 1 | Sanitary-Plumber | 19785.6667 | 157.0291 | 4870 | 38.6508 | 38.6508
52 | Zone T3 the area behind the new building | 126 | 1 | Sanitary-Plumber | 19785.6667 | 157.0291 | 4870 | 38.6508 | 38.6508
53 | Sewage pipe system, general sewer and air pipe
54 | Zone T-1 the area in front of the original buidling | 126 | 1 | Sanitary-Plumber | 21587.6667 | 171.3307 | 10088.3333 | 80.0661 | 80.0661
55 | Zone T-2 the area in the middle | 126 | 1 | Sanitary-Plumber | 21587.6667 | 171.3307 | 10088.3333 | 80.0661 | 80.0661
56 | Zone T3 the area behind the new building | 126 | 1 | Sanitary-Plumber | 21587.6667 | 171.3307 | 10088.3333 | 80.0661 | 80.0661
57 | Electrical system work on the 4th floor
58 | Electric lamp | 30 | 4 | Electrician | 564390 | 18813 | 38260 | 637.6667 | 212.5556
59 | Switch and Electrical Socket | 30 | 1 | Electrician | 231260 | 7708.6667 | 32100 | 535 | 535
60 | Electrical work and conduits | 80 | 1 | Electrician | 76804 | 960.05 | 68344 | 854.3 | 854.3
61 | Speaker cable work and conduit | 80 | 1 | Electrician | 81600 | 1020 | 62944 | 786.8 | 393.4
62 | CCTV system work and conduit pipe | 80 | 1 | Electrician | 24000 | 300 | 15000 | 187.5 | 187.5
63 | Durable goods and made to order work on the fourth floor | 165 | 2 | Skilled carpenter | 1701350 | 10311.2121 | 0 | 0 | 0
64 | Third Floor Renovation
65 | Demolition work on the third floor (Dismantled) | 30 | 14 | General worker | 0 | 0 | 161888 | 5396.2667 | 385.4476
66 | Architecture Work on the Third Floor
67 | Ceiling work | 30 | 9 | Skilled carpenter | 1787531 | 59584.3667 | 417945 | 13931.5 | 1547.9444
68 | Floor work | 60 | 3 | General worker | 1561419 | 26023.65 | 276080 | 4601.3333 | 1533.7778
69 | Wall work | 30 | 3 | General worker | 172822 | 5760.7333 | 105669 | 3522.3 | 1174.1
70 | Door and Window Work | 30 | 1 | Skilled carpenter | 571000 | 19033.3333 | 3600 | 120 | 120
71 | Staircase | 30 | 1 | General worker | 20660 | 688.6667 | 11800 | 393.3333 | 393.3333
72 | Painting work | 30 | 4 | General worker | 149150 | 4971.6667 | 89490 | 2983 | 745.75
73 | Sanitary ware
74 | Zone T-1 the area in front of the original buidling | 15 | 2 | Sanitary-Plumber | 199036.8333 | 13269.1222 | 14473.3333 | 964.8889 | 482.4444
75 | Zone T-2 the area in the middle | 15 | 2 | Sanitary-Plumber | 199036.8333 | 13269.1222 | 14473.3333 | 964.8889 | 482.4444
76 | Zone T3 the area behind the new building | 15 | 2 | Sanitary-Plumber | 199036.8333 | 13269.1222 | 14473.3333 | 964.8889 | 482.4444
77 | Sanitation system on the third floor
78 | Water supply pipe system work
79 | Zone T-1 the area in front of the original buidling | 126 | 1 | Sanitary-Plumber | 16852.3333 | 133.7487 | 4696.6667 | 37.2751 | 37.2751
80 | Zone T-2 the area in the middle | 126 | 1 | Sanitary-Plumber | 16852.3333 | 133.7487 | 4696.6667 | 37.2751 | 37.2751
81 | Zone T3 the area behind the new building | 126 | 1 | Sanitary-Plumber | 16852.3333 | 133.7487 | 4696.6667 | 37.2751 | 37.2751
82 | Sewage pipe system work, general sewer and air pipe
83 | Zone T-1 the area in front of the original buidling | 126 | 1 | Sanitary-Plumber | 20121 | 159.6905 | 29465 | 233.8492 | 233.8492
84 | Zone T-2 the area in the middle | 126 | 1 | Sanitary-Plumber | 20121 | 159.6905 | 29465 | 233.8492 | 233.8492
85 | Zone T3 the area behind the new building | 126 | 1 | Sanitary-Plumber | 20121 | 159.6905 | 29465 | 233.8492 | 233.8492
86 | Electrical system work on the 3rd floor
87 | Electric lamp | 60 | 2 | Electrician | 611230 | 10187.1667 | 48200 | 803.3333 | 401.6667
88 | Switch and Electrical Socket | 60 | 1 | Electrician | 244850 | 4080.8333 | 34790 | 579.8333 | 579.8333
89 | Electrical work and conduits | 80 | 1 | Electrician | 99863 | 1248.2875 | 89378 | 1117.225 | 1117.225
90 | Speaker cable work and conduit | 80 | 1 | Electrician | 63400 | 792.5 | 48144 | 601.8 | 601.8
91 | CCTV system work and conduit pipe | 80 | 1 | Electrician | 32000 | 400 | 20000 | 250 | 250
92 | Durable goods procurement or made to order work on the 3rd floor | 180 | 2 | Skilled carpenter | 2443100 | 13572.7778
93 | Building renovation on the second floor
94 | Demolition on the 2nd floor (Dismantled) | 30 | 16 | General worker | 0 | 0 | 207078 | 6902.6 | 431.4125
95 | Second Floor Architecture
96 | Ceiling work | 30 | 6 | Skilled carpenter | 1617717 | 53923.9 | 482035 | 16067.8333 | 2677.9722
97 | Floor work | 60 | 4 | General worker | 1243001 | 20716.6833 | 230255 | 3837.5833 | 959.3958
98 | Wall work | 30 | 8 | General worker | 460791 | 15359.7 | 144098 | 4803.2667 | 600.4083
99 | Door and Window Work | 30 | 4 | Skilled carpenter | 840000 | 28000 | 4050 | 135 | 33.75
100 | Staircase | 30 | 1 | General worker | 10080 | 336 | 4900 | 163.3333 | 163.3333
101 | Painting work | 30 | 5 | General worker | 175050 | 5835 | 105030 | 3501 | 700.2
102 | Sanitary ware
103 | Zone T-1 the area in front of the original buidling | 15 | 2 | Sanitary-Plumber | 199036.8333 | 13269.1222 | 14473.3333 | 964.8889 | 482.4444
104 | Zone T-2 the area in the middle | 15 | 2 | Sanitary-Plumber | 199036.8333 | 13269.1222 | 14473.3333 | 964.8889 | 482.4444
105 | Zone T3 the area behind the new building | 15 | 2 | Sanitary-Plumber | 199036.8333 | 13269.1222 | 14473.3333 | 964.8889 | 482.4444
106 | Sanitation system work on the second floor
107 | Water supply pipe system work
108 | Zone T-1 the area in front of the original buidling | 126 | 1 | Sanitary-Plumber | 17352.3333 | 137.7169 | 4696.6667 | 37.2751 | 37.2751
109 | Zone T-2 the area in the middle | 126 | 1 | Sanitary-Plumber | 17352.3333 | 137.7169 | 4696.6667 | 37.2751 | 37.2751
110 | Zone T3 the area behind the new building | 126 | 1 | Sanitary-Plumber | 17352.3333 | 137.7169 | 4696.6667 | 37.2751 | 37.2751
111 | Sewage Pipe System, general sewer and air pipe
112 | Zone T-1 the area in front of the original buidling | 126 | 1 | Sanitary-Plumber | 20121 | 159.6905 | 9821.6667 | 77.9497 | 77.9497
113 | Zone T-2 the area in the middle | 126 | 1 | Sanitary-Plumber | 20121 | 159.6905 | 9821.6667 | 77.9497 | 77.9497
114 | Zone T3 the area behind the new building | 126 | 1 | Sanitary-Plumber | 20121 | 159.6905 | 9821.6667 | 77.9497 | 77.9497
115 | Electrical system work on the second floor
116 | Electric lamp | 60 | 3 | Electrician | 768520 | 12808.6667 | 61100 | 1018.3333 | 339.4444
117 | Switch and Electrical Socket | 60 | 1 | Electrician | 403000 | 6716.6667 | 57540 | 959 | 959
118 | Electrical work and conduits | 80 | 1 | Electrician | 110971 | 1387.1375 | 99181 | 1239.7625 | 1239.7625
119 | Speaker cable work and conduit | 80 | 2 | Electrician | 122400 | 1530 | 94776 | 1184.7 | 592.35
120 | CCTV system work and conduit pipe | 80 | 1 | Electrician | 36000 | 450 | 22500 | 281.25 | 281.25
121 | Durable goods procurement or made to order work on the 2nd floor | 180 | 2 | Skilled carpenter | 4144850 | 23026.9444 | 0 | 0 | 0
122 | Renovation of the First Floor of the Building
123 | Demolition work on the 1st floor (Dismantled) | 30 | 17 | General worker | 0 | 0 | 253608 | 8453.6 | 497.2706
124 | Structural Engineering Work on the First Floor | 75 | 8 | General worker | 834155.5762 | 11122.0743 | 278048.2 | 3707.3093 | 463.4137
125 | Architecture in the First Floor
126 | Ceiling work | 30 | 5 | Skilled carpenter | 1377524 | 45917.4667 | 402505 | 13416.8333 | 2683.3667
127 | Floor work | 60 | 5 | General worker | 1406155 | 23435.9167 | 255370 | 4256.1667 | 851.2333
128 | Wall work | 30 | 7 | General worker | 434956 | 14498.5333 | 154571 | 5152.3667 | 736.0524
129 | Door and Window Work | 30 | 8 | Skilled carpenter | 725400 | 24180 | 4950 | 165 | 20.625
130 | Staircase | 30 | 2 | General worker | 100720 | 3357.3333 | 26500 | 883.3333 | 441.6667
131 | Other decorations | 60 | 2 | General worker | 262561 | 4376.0167 | - | - | -
132 | Painting work | 30 | 4 | General worker | 167400 | 5580 | 100440 | 3348 | 837
133 | Sanitary ware
134 | Zone T-1 the area in front of the original buidling | 15 | 2 | Sanitary-Plumber | 199036.8333 | 13269.1222 | 14473.3333 | 964.8889 | 482.4444
135 | Zone T-2 the area in the middle | 15 | 2 | Sanitary-Plumber | 199036.8333 | 13269.1222 | 14473.3333 | 964.8889 | 482.4444
136 | Zone T3 the area behind the new building | 15 | 2 | Sanitary-Plumber | 199036.8333 | 13269.1222 | 14473.3333 | 964.8889 | 482.4444
137 | Sanitation system on the first floor
138 | Water supply pipe system work
139 | Zone T-1 the area in front of the original buidling | 126 | 1 | Sanitary-Plumber | 16852.3333 | 133.7487 | 4696.6667 | 37.2751 | 37.2751
140 | Zone T-2 the area in the middle | 126 | 1 | Sanitary-Plumber | 16852.3333 | 133.7487 | 4696.6667 | 37.2751 | 37.2751
141 | Zone T3 the area behind the new building | 126 | 1 | Sanitary-Plumber | 16852.3333 | 133.7487 | 4696.6667 | 37.2751 | 37.2751
142 | Sewage Pipe System, general sewer and air pipe
143 | Zone T-1 the area in front of the original buidling | 126 | 1 | Sanitary-Plumber | 24601 | 195.246 | 11148.3333 | 88.4788 | 88.4788
144 | Zone T-2 the area in the middle | 126 | 1 | Sanitary-Plumber | 24601 | 195.246 | 11148.3333 | 88.4788 | 88.4788
145 | Zone T3 the area behind the new building | 126 | 1 | Sanitary-Plumber | 24601 | 195.246 | 11148.3333 | 88.4788 | 88.4788
146 | Electrical system work on the first floor
147 | Electric lamp | 60 | 2 | Electrician | 572310 | 9538.5 | 44580 | 743 | 371.5
148 | Switch and Electrical Socket | 60 | 1 | Electrician | 182700 | 3045 | 29010 | 483.5 | 483.5
149 | Electrical work and conduits | 80 | 1 | Electrician | 87289 | 1091.1125 | 77639 | 970.4875 | 970.4875
150 | Speaker cable work and conduit | 80 | 1 | Electrician | 95925 | 1199.0625 | 74020 | 925.25 | 925.25
151 | CCTV system work and conduit pipe | 80 | 1 | Electrician | 64000 | 800 | 40000 | 500 | 500
152 | Durable goods procurement or order work on the 1st floor | 165 | 2 | Skilled carpenter | 2093600 | 12688.4848 | - | - | -
153 | Basement Renovation
154 | Demolition of the wall (Dismantled) | 30 | 6 | General worker | 0 | 0 | 86253 | 2875.1 | 479.1833
155 | Basement Engineering | 75 | 9 | General worker | 1343566.19 | 17914.2159 | 316570.4 | 4220.9387 | 468.9932
156 | Basement Architecture
157 | Ceiling work | 30 | 3 | Skilled carpenter | 604780 | 20159.3333 | 193050 | 6435 | 2145
158 | Floor work | 60 | 3 | General worker | 1116260 | 18604.3333 | 184190 | 3069.8333 | 1023.2778
159 | Wall work | 30 | 4 | General worker | 165294 | 5509.8 | 101472 | 3382.4 | 845.6
160 | Door and Window Work | 30 | 12 | Skilled carpenter | 882900 | 29430 | 900 | 30 | 2.5
161 | Staircase | 30 | 2 | General worker | 83503 | 2783.4333 | 30345 | 1011.5 | 505.75
162 | Painting work | 30 | 2 | General worker | 69850 | 2328.3333 | 39240 | 1308 | 654
163 | Sanitary ware
164 | Zone T-1 the area in front of the original buidling | 15 | 3 | Sanitary-Plumber | 170173 | 11344.8667 | 11990 | 799.3333 | 266.4444
165 | Basement sanitation system work
166 | Water supply pipe system
167 | Zone T-1 the area in front of the original buidling | 126 | 1 | Sanitary-Plumber | 16876 | 133.9365 | 4120 | 32.6984 | 32.6984
168 | Sewage Pipe System, general sewer and air pipe
169 | Zone T-1 the area in front of the original buidling | 126 | 1 | Sanitary-Plumber | 25928 | 205.7778 | 9945 | 78.9286 | 78.9286
170 | Rainwater drainage system work | 75 | 1 | Sanitary-Plumber | 15500 | 206.6667 | 15500 | 206.6667 | 206.6667
171 | Basement Electrical System
172 | Electric Lamp | 60 | 2 | Electrician | 343720 | 5728.6667 | 31130 | 518.8333 | 259.4167
173 | Switch and electrical socket | 60 | 1 | Electrician | 103650 | 1727.5 | 17600 | 293.3333 | 293.3333
174 | Electrical work and conduits | 80 | 1 | Electrician | 54989 | 687.3625 | 49169 | 614.6125 | 614.6125
175 | Speaker cable work and conduit | 80 | 1 | Electrician | 7600 | 95 | 4864 | 60.8 | 60.8
176 | CCTV system work and conduit pipe | 80 | 1 | Electrician | 40000 | 500 | 25000 | 312.5 | 312.5
177 | Durable goods procurement or order the basement | 165 | 2 | Skilled carpenter | 878600 | 5324.8485 | 0 | 0 | 0
178 | Computer system and fire alarm system
179 | Computer system
180 | Fourth floor | 160 | 2 | Electrician | 204472 | 1277.95 | 75564 | 472.275 | 236.1375
181 | Third floor | 175 | 2 | Electrician | 204472 | 1168.4114 | 75564 | 431.7943 | 215.8971
182 | Second floor | 175 | 2 | Electrician | 204472 | 1168.4114 | 75564 | 431.7943 | 215.8971
183 | First floor | 160 | 2 | Electrician | 204472 | 1277.95 | 75564 | 472.275 | 236.1375
184 | Basement | 160 | 2 | Electrician | 204472 | 1277.95 | 75564 | 472.275 | 236.1375
185 | Fire Alarm System
186 | Fourth floor | 160 | 1 | Electrician | 197660 | 1235.375 | 51456 | 321.6 | 321.6
187 | Third floor | 175 | 1 | Electrician | 197660 | 1129.4857 | 51456 | 294.0343 | 294.0343
188 | Second floor | 175 | 1 | Electrician | 197660 | 1129.4857 | 51456 | 294.0343 | 294.0343
189 | First floor | 160 | 1 | Electrician | 197660 | 1235.375 | 51456 | 321.6 | 321.6
190 | Basement | 160 | 1 | Electrician | 197660 | 1235.375 | 51456 | 321.6 | 321.6
191 | Exterior paint, repair and exterior decoration of the building
192 | Exterior paint and exterior surface repair
193 | Polishing the old wall paint | 165 | 1 | General worker | 0 | 0 | 61870 | 374.9697 | 374.9697
194 | Old plaster solution (primer) | 165 | 1 | General worker | 123740 | 749.9394 | - | - | -
195 | Exterior painting work (2 coats) not including basement | 165 | 1 | General worker | 247480 | 1499.8788 | 185610 | 1124.9091 | 1124.9091
196 | Cleaning and repairing of brick wall tiles (Refer to the price of polishing work) | 165 | 1 | General worker | 0 | 0 | 9230 | 55.9394 | 55.9394
197 | Tile wall coating liquid (Refer to the cost of applying antifungal agent) | 165 | 1 | General worker | 18460 | 111.8788 | 18460 | 111.8788 | 111.8788
198 | Demolition of roof waterproofing (Dismantled) | 90 | 1 | General worker | 0 | 0 | 76300 | 847.7778 | 847.7778
199 | Sand blasting waterproofing sheet material | 90 | 1 | General worker | 654000 | 7266.6667 | 218000 | 2422.2222 | 2422.2222
200 | Polyurethane waterproofing, ultra-flexible oil formula, resistant to UV light, Xander, Ardex or equivalent. | 90 | 1 | General worker | 2719600 | 30217.7778 | - | - | -
201 | Exterior Decoration
202 | Expanded Metal XS-32 | 165 | 1 | General worker | 154700 | 937.5758 | 28560 | 173.0909 | 173.0909
203 | Surrounding area
204 | Demolition of the Surrounding Area | 165 | 1 | General worker | 0 | 0 | 5000 | 30.303 | 30.303
205 | Structural Engineering of the Surrounding Area | 165 | 4 | General worker | 965923.2499 | 5854.0803 | 340271.7 | 2062.2527 | 515.5632
206 | Architecture of the Surrounding Area | 165 | 1 | General worker | 1820315 | 11032.2121 | 310508 | 1881.8667 | 1881.8667
207 | Electrical System of the Surrounding Area | 165 | 1 | Electrician | 136654 | 828.2061 | 17384 | 105.3576 | 105.3576
208 | Durable Goods
209 | Floating furniture
210 | Floating furniture in the basement | 15 | 2 | Skilled carpenter | 67000 | 4466.6667 | 0 | 0 | 0
211 | Floating furniture on the first floor | 15 | 2 | Skilled carpenter | 1283000 | 85533.3333 | 0 | 0 | 0
212 | Floating furniture on the second floor | 15 | 2 | Skilled carpenter | 2133290 | 142219.3333 | 0 | 0 | 0
213 | Floating furniture on the third floor | 15 | 2 | Skilled carpenter | 1026290 | 68419.3333 | 0 | 0 | 0
214 | Floating furniture on the fourth floor | 15 | 2 | Skilled carpenter | 771760 | 51450.6667 | 0 | 0 | 0
215 | Repair furniture work
216 | Furniture repair work on the first floor | 30 | 2 | Skilled carpenter | 64500 | 2150 | 0 | 0 | 0
217 | Furniture repair work on the second floor | 30 | 2 | Skilled carpenter | 168600 | 5620 | 0 | 0 | 0
218 | Furniture repair work on the third floor | 30 | 2 | Skilled carpenter | 173400 | 5780 | 0 | 0 | 0
219 | Furniture repair work on the fourth floor | 30 | 2 | Skilled carpenter | 76500 | 2550 | 0 | 0 | 0
220 | Curtain work
221 | Curtain work on the first floor | 15 | 2 | Skilled carpenter | 479400 | 31960 | 0 | 0 | 0
222 | Curtain on the second floor | 15 | 2 | Skilled carpenter | 395600 | 26373.3333 | 0 | 0 | 0
223 | Curtain on the third floor | 15 | 2 | Skilled carpenter | 143000 | 9533.3333 | 0 | 0 | 0
224 | Curtain on the fourth floor | 15 | 2 | Skilled carpenter | 106300 | 7086.6667 | 0 | 0 | 0
225 | Signs
226 | Signs on the basement | 15 | 2 | Skilled carpenter | 12000 | 800 | 0 | 0 | 0
227 | Signs on the first floor | 15 | 2 | Skilled carpenter | 110000 | 7333.3333 | 0 | 0 | 0
228 | Signs on the second floor | 15 | 2 | Skilled carpenter | 68000 | 4533.3333 | 0 | 0 | 0
229 | Signs on the third floor | 15 | 2 | Skilled carpenter | 32000 | 2133.3333 | 0 | 0 | 0
230 | Signs on the fourth floor | 15 | 2 | Skilled carpenter | 25000 | 1666.6667 | 0 | 0 | 0
231 | Others
232 | Aluminum cabinet folded up and painted used to cover water dispenser | 15 | 2 | General worker | 360000 | 24000 | 0 | 0 | 0
233 | TWO WIRE REMOTE CONTROL LIGHTING SYSTEM
234 | Two wire remote control lighting system for basement | 160 | 1 | Electrician | 202430 | 1265.1875 | 29080 | 181.75 | 181.75
235 | Two wire remote control lighting system for the first floor | 160 | 1 | Electrician | 202430 | 1265.1875 | 29080 | 181.75 | 181.75
236 | Two wire remote control lighting system for the second floor | 175 | 1 | Electrician | 202430 | 1156.7429 | 29080 | 166.1714 | 166.1714
237 | Two wire remote control lighting system for the third floor | 175 | 1 | Electrician | 202430 | 1156.7429 | 29080 | 166.1714 | 166.1714
238 | Two wire remote control lighting system for the fourth floor | 160 | 1 | Electrician | 202430 | 1265.1875 | 29080 | 181.75 | 181.75
239 | Sound system (Using previous speakers)
240 | Sound system for basement | 7 | 1 | Electrician | 0 | 0 | 150 | 21.4286 | 21.4286
241 | Sound system for the first floor | 7 | 3 | Electrician | 17000 | 2428.5714 | 4850 | 692.8571 | 230.9524
242 | Sound system for the second floor | 7 | 3 | Electrician | 0 | 0 | 5550 | 792.8571 | 264.2857
243 | Sound system for the third floor | 7 | 2 | Electrician | 0 | 0 | 4050 | 578.5714 | 289.2857
244 | Sound system for the forth floor | 7 | 2 | Electrician | 0 | 0 | 3000 | 428.5714 | 214.2857
245 | CCTV system (Using the previous CCTV system)
246 | CCTV Basement | 7 | 1 | Electrician | 0 | 0 | 1200 | 171.4286 | 171.4286
247 | CCTV on the first floor | 7 | 2 | Electrician | 0 | 0 | 2400 | 342.8571 | 171.4286
248 | CCTV on the second floor | 7 | 1 | Electrician | 0 | 0 | 1650 | 235.7143 | 235.7143
249 | CCTV on the thrid floor | 7 | 1 | Electrician | 0 | 0 | 1050 | 150 | 150
250 | CCTV on the fourth floor | 7 | 2 | Electrician | 0 | 0 | 1800 | 257.1429 | 128.5714
|  |  |  | รวม | 57188107.0161 |  | 9125924.3
|  |  |  | รวมค่าวัสดุ และ ค่าแรง (บาท) |  |  | 66314031.3161
|  |  |  | ค่าดำเนินการ * 1.2058 | 13647427.6449 | บาท
|  |  |  | ระยะะวลาโครงการ | 720 | วัน
|  |  |  | ค่าดำเนินการ วันละ | 18954.7606 | บาท | Daily Indirec Cost = 18,954.76 บาท
|  |  |  | ค่าปรับวันละ 0.1% | 79961.459 | บาท
|  |  |  | ค่าปรับที่ต้องจ่ายให้ผู้ควบคุมงานวันละ | 4233.33 | บาท
|  |  |  | รวมค่าปรับทั้งสินวันละ | 84194.789 | บาท | Daily penalty cost = 84,194.791 บาท

## Sheet1
| General worker | ค่าแรงต่อคนต่อวัน | Skilled carpenter | ค่าแรงต่อคนต่อวัน | Sanitary-Plumber | ค่าแรงต่อคนต่อวัน | Electrician | ค่าแรงต่อคนต่อวัน
| งานรื้อถอน ชั้นใต้ดิน | 479.1833 | งานฝ้าเพดาน ชั้นใต้ดิน | 2145 | งานสุขภัณฑ์ AMERICAN STANDARD สีขาว หรือเทียบเท่า ชั้นใต้ดิน | 266.4444 | งานดวงโคมไฟฟ้า ชั้นใต้ดิน | 259.4167
| งานโครงสร้างวิศวกรรม ชั้นใต้ดิน | 468.9932 | งานประตู - หน้าต่าง ชั้นใต้ดิน | 2.5 | งานระบบท่อจ่ายน้ำประปา ชั้นใต้ดิน | 32.6984 | งานสวิทช์, เต้ารับไฟฟ้า ชั้นใต้ดิน | 293.3333
| งานพื้นชั้นใต้ดิน | 1023.2778 | งานฝ้าเพดาน ชั้น 1 | 2683.3667 | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ ชั้นใต้ดิน | 78.9286 | งานสายไฟฟ้า, ท่อร้อยสาย ชั้นใต้ดิน | 614.6125
| งานผนังชั้นใต้ดิน | 845.6 | งานประตู - หน้าต่าง ชั้น 1 | 20.625 | งานระบบระบายน้ำฝน | 206.6667 | งานสายลำโพง, ท่อร้อยสาย ชั้นใต้ดิน | 60.8
| งานบันใดชั้นใต้ดิน | 505.75 | งานฝ้าเพดาน ชั้น 2 | 2677.9722 | งานสุขภัณฑ์ AMERICAN STANDARD สีขาว หรือเทียบเท่า ชั้น 1 | 482.4444 | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย ชั้นใต้ดิน | 312.5
| งานสี (ทาสีรองพื้น 1 เที่ยว และ ทาสีจริง 2 เที่ยว) | 654 | งานประตู - หน้าต่าง ชั้น 2 | 33.75 | งานระบบท่อจ่ายน้ำประปา ชั้น 1 | 37.2751 | งานดวงโคมไฟฟ้า ชั้น 1 | 371.5
| งานรื้อถอน ชั้น 1 | 497.2706 | งานฝ้าเพดาน ชั้น 3 | 1547.9444 | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ ชั้น 1 | 88.4788 | งานสวิทช์, เต้ารับไฟฟ้า ชั้น 1 | 483.5
| งานโครงสร้างวิศวกรรม ชั้น 1 | 463.4137 | งานประตู - หน้าต่าง ชั้น 3 | 120 | งานสุขภัณฑ์ AMERICAN STANDARD สีขาว หรือเทียบเท่า ชั้น 2 | 482.4444 | งานสายไฟฟ้า, ท่อร้อยสาย ชั้น 1 | 970.4875
| งานพื้น ชั้น 1 | 851.2333 | งานฝ้าเพดาน ชั้น 4 | 3261.2778 | งานระบบท่อจ่ายน้ำประปา ชั้น 2 | 37.2751 | งานสายลำโพง, ท่อร้อยสาย ชั้น 1 | 925.25
| งานผนัง ชั้น 1 | 736.0524 | งานประตู - หน้าต่าง ชั้น 4 | 105 | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ ชั้น 2 | 77.9497 | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย ชั้น 1 | 500
| งานบันได ชั้น 1 | 441.6667 |  |  | งานสุขภัณฑ์ AMERICAN STANDARD สีขาว หรือเทียบเท่า ชั้น 3 | 482.4444 | งานดวงโคมไฟฟ้า ชั้น 2 | 339.4444
| งานสี (ทาสีรองพื้น 1 เที่ยว และ ทาสีจริง 2 เที่ยว) ชั้น 1 | 837 |  |  | งานระบบท่อจ่ายน้ำประปา ชั้น 3 | 37.2751 | งานสวิทช์, เต้ารับไฟฟ้า ชั้น 2 | 959
| งานรื้อถอน ชั้น 2 | 431.4125 |  |  | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ ชั้น 3 | 77.9497 | งานสายไฟฟ้า, ท่อร้อยสาย ชั้น 2 | 1239.7625
| งานพื้น ชั้น 2 | 959.3958 |  |  | งานสุขภัณฑ์ AMERICAN STANDARD สีขาว หรือเทียบเท่า ชั้น 4 | 482.4444 | งานสายลำโพง, ท่อร้อยสาย ชั้น 2 | 592.35
| งานผนัง ชั้น 2 | 600.4083 |  |  | งานระบบท่อจ่ายน้ำประปา ชั้น 4 | 38.6508 | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย ชั้น 2 | 281.25
| งานบันได ชั้น 2 | 163.3333 |  |  | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ ชั้น 4 | 80.0661 | งานดวงโคมไฟฟ้า ชั้น 3 | 401.6667
| งานสี (ทาสีรองพื้น 1 เที่ยว และ ทาสีจริง 2 เที่ยว) ชั้น 2 | 700.2 |  |  |  |  | งานสวิทช์, เต้ารับไฟฟ้า ชั้น 3 | 579.8333
| งานรื้อถอน ชั้น 3 | 385.4476 |  |  |  |  | งานสายไฟฟ้า, ท่อร้อยสาย ชั้น 3 | 1117.225
| งานพื้น ชั้น 3 | 1533.7778 |  |  |  |  | งานสายลำโพง, ท่อร้อยสาย ชั้น 3 | 601.8
| งานผนัง ชั้น 3 | 1174.1 |  |  |  |  | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย ชั้น 3 | 250
| งานบันได ชั้น 3 | 393.3333 |  |  |  |  | งานดวงโคมไฟฟ้า ชั้น 4 | 212.5556
| งานสี (ทาสีรองพื้น 1 เที่ยว และ ทาสีจริง 2 เที่ยว) ชั้น 3 | 745.75 |  |  |  |  | งานสวิทช์, เต้ารับไฟฟ้า ชั้น 4 | 535
| งานรื้อถอน ชั้น 4 | 390.3139 |  |  |  |  | งานสายไฟฟ้า, ท่อร้อยสาย ชั้น 4 | 854.3
| งานพื้น ชั้น 4 | 1165.8333 |  |  |  |  | งานสายลำโพง, ท่อร้อยสาย ชั้น 4 | 393.4
| งานผนัง ชั้น 4 | 1498.9667 |  |  |  |  | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย ชั้น 4 | 187.5
| งานบันได ชั้น 4 | 128.3333 |  |  |  |  | งานระบบคอมพิวเตอร์ | 70.4888
| งานสี (ทาสีรองพื้น 1 เที่ยว และ ทาสีจริง 2 เที่ยว) ชั้น 4 | 742 |  |  |  |  | งานระบบแจ้งเหตุเพลิงไหม้ | 48
| งานขัดลอกสีทาผนังเดิม | 374.9697 |  |  |  |  | งานระบบไฟฟ้า งานบริเวณ | 105.3576
| งานทาสีภายนอก (ทา 2 เที่ยว) ไม่รวมชั้นใต้ดิน | 1124.9091 |  |  |  |  | หมวดงานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ (TWO WIRE REMOTE CONTROL LIGHTING SYSTEM ) | 43.403
| งานทำความสะอาดและซ่อมแซมผนังกรุอิฐโชว์แนว (อ้างอิงราคางานขัดลอกสี) | 55.9394 |  |  |  |  | งานเครื่องเสียงประกาศ ชั้นใต้ดิน | 21.4286
| น้ำยาเคลือบผิวผนังอิฐโชว์แนว (อ้างอิงค่าทาน้ำยากันเชื้อรา) | 111.8788 |  |  |  |  | งานเครื่องเสียงประกาศ ชั้น 1 | 230.9524
| งานรื้อถอนแผ่นวัสดุกันซึมหลังคาดาดฟ้า (รื้อขนไป) | 847.7778 |  |  |  |  | งานเครื่องเสียงประกาศ ชั้น 2 | 264.2857
| งานแผ่นวัสดุกันซึมแบบเป่าไฟผิวทราย | 2422.2222 |  |  |  |  | งานเครื่องเสียงประกาศ ชั้น 3 | 289.2857
| ตะแกรงเหล็กฉีกกันนก XS-32 | 173.0909 |  |  |  |  | งานเครื่องเสียงประกาศ ชั้น 4 | 214.2857
| งานรื้อถอน งานบริเวณ | 30.303 |  |  |  |  | งานกล้องวงจรปิดชั้นใต้ดิน | 171.4286
| งานโครงสร้างวิศวกรรม งานบริเวณ | 515.5632 |  |  |  |  | งานกล้องวงจรปิด ชั้น 1 | 171.4286
| งานสถาปัตยกรรม งานบริเวณ | 1881.8667 |  |  |  |  | งานกล้องวงจรปิด ชั้น 2 | 235.7143
[7 empty] | งานกล้องวงจรปิด ชั้น 3 | 150
[7 empty] | งานกล้องวงจรปิด ชั้น 4 | 128.5714
ค่าเฉลี่ย ค่าแรงต่อ คนต่อวัน | General Worker | 712.2856
| Skilled Carpenter | 1259.7436
| Sanitary-Plumber | 186.8398
| Electrician | 396.9517