## Resource CMU
No | Activity | Quantity | Output | Worker(100%) | Worker(50%) | Worker(70%) | Worker(200%) | Worker(True) | Resource type | Cost
1 | Chiang Mai Library Renovation Project
2 | Preparation
3 | Work on the building and surrounding area |  |  | 4 | 2 | 3 | 8 |  | Engineer
4 | Public utility system works |  |  | 4 | 2 | 3 | 8 |  | Engineer
5 | Interior system test
6 | 4th floor |  |  | 4 | 2 | 3 | 8 |  | Engineer
7 | 3rd floor |  |  | 4 | 2 | 3 | 8 |  | Engineer
8 | 2nd floor |  |  | 4 | 2 | 3 | 8 |  | Engineer
9 | 1st floor |  |  | 4 | 2 | 3 | 8 |  | Engineer
10 | Basement and outside areas |  |  | 4 | 2 | 3 | 8 |  | Engineer
11 | Eletricity supply, sanitary and original item checking tasks
12 | 4th floor |  |  | 4 | 2 | 3 | 8 |  | Engineer
13 | 3rd floor |  |  | 4 | 2 | 3 | 8 |  | Engineer
14 | 2nd floor |  |  | 4 | 2 | 3 | 8 |  | Engineer
15 | 1st floor |  |  | 4 | 2 | 3 | 8 |  | Engineer
16 | Basement and outside areas |  |  | 4 | 2 | 3 | 8 |  | Engineer
17 | Paperwork on item usage permission, shop drawing and project items
18 | Shop drawing of the 4th floor |  |  | 4 | 2 | 3 | 8 |  | Engineer
19 | Shop drawing of the 3rd floor |  |  | 4 | 2 | 3 | 8 |  | Engineer
20 | Shop drawing of the 2nd floor |  |  | 4 | 2 | 3 | 8 |  | Engineer
21 | Shop drawing of the 1st floor |  |  | 4 | 2 | 3 | 8 |  | Engineer
22 | Shop drawing of the basement |  |  | 4 | 2 | 3 | 8 |  | Engineer
23 | Shop drawing of the outside areas |  |  | 4 | 2 | 3 | 8 |  | Engineer
24 | Shop drawing of the landscpae |  |  | 4 | 2 | 3 | 8 |  | Engineer
25 | Shop drawing of item renovation |  |  | 4 | 2 | 3 | 8 |  | Engineer
26 | Shop drawing of item purchasing |  |  | 4 | 2 | 3 | 8 |  | Engineer
27 | System test work, workshop for building users and As-Built Drawing
28 | 4th floor |  |  | 4 | 2 | 3 | 8 |  | Engineer
29 | 3rd floor |  |  | 4 | 2 | 3 | 8 |  | Engineer
30 | 2nd floor |  |  | 4 | 2 | 3 | 8 |  | Engineer
31 | 1st floor |  |  | 4 | 2 | 3 | 8 |  | Engineer
32 | Basement |  |  | 4 | 2 | 3 | 8 |  | Engineer
33 | The whole building |  |  | 4 | 2 | 3 | 8 |  | Engineer
34 | Building management and other works |  |  | 4 | 2 | 3 | 8 |  | Engineer
35 | Renovation on the fourth floor
36 | Demolition work on the 4th floor (Dismantled) | 6060.77 | 16.8355 | 12 | 6 | 9 | 24 |  | General worker
37 | Architecture Work on the Fourth Floor
38 | Ceiling work | 1922.93 | 21.3659 | 3 | 2 | 3 | 6 |  | Skilled carpenter
39 | Floor work | 2063.37 | 17.1947 | 2 | 1 | 2 | 4 |  | General worker
40 | Wall work | 767.97 | 12.7995 | 2 | 1 | 2 | 4 |  | General worker
41 | Door and Window Work | 11 | 0.36667 | 1 | 1 | 1 | 2 |  | Skilled carpenter
42 | Staircase | 110 | 3.6667 | 1 | 1 | 1 | 2 |  | General worker
43 | Painting work | 3179 | 35.3222 | 3 | 2 | 3 | 6 |  | General worker
44 | Sanitary ware
45 | Zone T-1 the area in front of the original buidling | 102.1533 | 3.4051 | 2 | 1 | 2 | 4 |  | Sanitary-Plumber
46 | Zone T-2 the area in the middle | 102.1533 | 3.4051 | 2 | 1 | 2 | 4 |  | Sanitary-Plumber
47 | Zone T3 the area behind the new building | 102.1533 | 3.4051 | 2 | 1 | 2 | 4 |  | Sanitary-Plumber
48 | Sanitation system work on the fourth floor
49 | Water supply pipe system work
50 | Zone T-1 the area in front of the original buidling | 143.5833 | 1.1396 | 1 | 1 | 1 | 2 |  | Sanitary-Plumber
51 | Zone T-2 the area in the middle | 143.5833 | 1.1396 | 1 | 1 | 1 | 2 |  | Sanitary-Plumber
52 | Zone T3 the area behind the new building | 143.5833 | 1.1396 | 1 | 1 | 1 | 2 |  | Sanitary-Plumber
53 | Sewage pipe system, general sewer and air pipe
54 | Zone T-1 the area in front of the original buidling | 285.1833 | 2.2634 | 1 | 1 | 1 | 2 |  | Sanitary-Plumber
55 | Zone T-2 the area in the middle | 285.1833 | 2.2634 | 1 | 1 | 1 | 2 |  | Sanitary-Plumber
56 | Zone T3 the area behind the new building | 285.1833 | 2.2634 | 1 | 1 | 1 | 2 |  | Sanitary-Plumber
57 | Electrical system work on the 4th floor
58 | Electric lamp | 343.39 | 2.8616 | 4 | 2 | 3 | 8 |  | Electrician
59 | Switch and Electrical Socket | 164 | 5.4667 | 1 | 1 | 1 | 2 |  | Electrician
60 | Electrical work and conduits | 6034 | 75.425 | 1 | 1 | 1 | 2 |  | Electrician
61 | Speaker cable work and conduit | 3264 | 40.8 | 1 | 1 | 1 | 2 |  | Electrician
62 | CCTV system work and conduit pipe | 1200 | 15 | 1 | 1 | 1 | 2 |  | Electrician
63 | Durable goods and made to order work on the fourth floor | 109.11 | 0.33064 | 2 | 1 | 2 | 4 |  | Skilled carpenter
64 | Third Floor Renovation
65 | Demolition work on the third floor (Dismantled) | 7089.13 | 16.8789 | 14 | 7 | 10 | 28 |  | General worker
66 | Architecture Work on the Third Floor
67 | Ceiling work | 2751.58 | 10.191 | 9 | 5 | 7 | 18 |  | Skilled carpenter
68 | Floor work | 2929.93 | 16.2774 | 3 | 2 | 3 | 6 |  | General worker
69 | Wall work | 928.11 | 10.3123 | 3 | 2 | 3 | 6 |  | General worker
70 | Door and Window Work | 18 | 0.6 | 1 | 1 | 1 | 2 |  | Skilled carpenter
71 | Staircase | 163 | 5.4333 | 1 | 1 | 1 | 2 |  | General worker
72 | Painting work | 4091 | 34.0917 | 4 | 2 | 3 | 8 |  | General worker
73 | Sanitary ware
74 | Zone T-1 the area in front of the original buidling | 102.1 | 3.4033 | 2 | 1 | 2 | 4 |  | Sanitary-Plumber
75 | Zone T-2 the area in the middle | 102.1 | 3.4033 | 2 | 1 | 2 | 4 |  | Sanitary-Plumber
76 | Zone T3 the area behind the new building | 102.1 | 3.4033 | 2 | 1 | 2 | 4 |  | Sanitary-Plumber
77 | Sanitation system on the third floor
78 | Water supply pipe system work
79 | Zone T-1 the area in front of the original buidling | 125.49 | 0.99595 | 1 | 1 | 1 | 2 |  | Sanitary-Plumber
80 | Zone T-2 the area in the middle | 125.49 | 0.99595 | 1 | 1 | 1 | 2 |  | Sanitary-Plumber
81 | Zone T3 the area behind the new building | 125.49 | 0.99595 | 1 | 1 | 1 | 2 |  | Sanitary-Plumber
82 | Sewage pipe system work, general sewer and air pipe
83 | Zone T-1 the area in front of the original buidling | 269.58 | 2.1395 | 1 | 1 | 1 | 2 |  | Sanitary-Plumber
84 | Zone T-2 the area in the middle | 269.58 | 2.1395 | 1 | 1 | 1 | 2 |  | Sanitary-Plumber
85 | Zone T3 the area behind the new building | 269.58 | 2.1395 | 1 | 1 | 1 | 2 |  | Sanitary-Plumber
86 | Electrical system work on the 3rd floor
87 | Electric lamp | 420.76 | 3.5063 | 2 | 1 | 2 | 4 |  | Electrician
88 | Switch and Electrical Socket | 186 | 3.1 | 1 | 1 | 1 | 2 |  | Electrician
89 | Electrical work and conduits | 7925 | 99.0625 | 1 | 1 | 1 | 2 |  | Electrician
90 | Speaker cable work and conduit | 2536 | 31.7 | 1 | 1 | 1 | 2 |  | Electrician
91 | CCTV system work and conduit pipe | 1600 | 20 | 1 | 1 | 1 | 2 |  | Electrician
92 | Durable goods procurement or made to order work on the 3rd floor | 357.6 | 0.99333 | 2 | 1 | 2 | 4 |  | Skilled carpenter
93 | Building renovation on the second floor
94 | Demolition on the 2nd floor (Dismantled) | 8497.15 | 17.7024 | 16 | 8 | 12 | 32 |  | General worker
95 | Second Floor Architecture
96 | Ceiling work | 2805.55 | 15.5864 | 6 | 3 | 5 | 12 |  | Skilled carpenter
97 | Floor work | 3102.01 | 12.925 | 4 | 2 | 3 | 8 |  | General worker
98 | Wall work | 2094.11 | 8.7255 | 8 | 4 | 6 | 16 |  | General worker
99 | Door and Window Work | 45.3 | 0.3775 | 4 | 2 | 3 | 8 |  | Skilled carpenter
100 | Staircase | 117 | 3.9 | 1 | 1 | 1 | 2 |  | General worker
101 | Painting work | 4717 | 31.4467 | 5 | 3 | 4 | 10 |  | General worker
102 | Sanitary ware
103 | Zone T-1 the area in front of the original buidling | 102.1 | 3.4033 | 2 | 1 | 2 | 4 |  | Sanitary-Plumber
104 | Zone T-2 the area in the middle | 102.1 | 3.4033 | 2 | 1 | 2 | 4 |  | Sanitary-Plumber
105 | Zone T3 the area behind the new building | 102.1 | 3.4033 | 2 | 1 | 2 | 4 |  | Sanitary-Plumber
106 | Sanitation system work on the second floor
107 | Water supply pipe system work
108 | Zone T-1 the area in front of the original buidling | 128.4033 | 1.0191 | 1 | 1 | 1 | 2 |  | Sanitary-Plumber
109 | Zone T-2 the area in the middle | 128.4033 | 1.0191 | 1 | 1 | 1 | 2 |  | Sanitary-Plumber
110 | Zone T3 the area behind the new building | 128.4033 | 1.0191 | 1 | 1 | 1 | 2 |  | Sanitary-Plumber
111 | Sewage Pipe System, general sewer and air pipe
112 | Zone T-1 the area in front of the original buidling | 269.58 | 2.1395 | 1 | 1 | 1 | 2 |  | Sanitary-Plumber
113 | Zone T-2 the area in the middle | 269.58 | 2.1395 | 1 | 1 | 1 | 2 |  | Sanitary-Plumber
114 | Zone T3 the area behind the new building | 269.58 | 2.1395 | 1 | 1 | 1 | 2 |  | Sanitary-Plumber
115 | Electrical system work on the second floor
116 | Electric lamp | 553.17 | 3.0732 | 3 | 2 | 3 | 6 |  | Electrician
117 | Switch and Electrical Socket | 310 | 5.1667 | 1 | 1 | 1 | 2 |  | Electrician
118 | Electrical work and conduits | 8911 | 111.3875 | 1 | 1 | 1 | 2 |  | Electrician
119 | Speaker cable work and conduit | 4896 | 30.6 | 2 | 1 | 2 | 4 |  | Electrician
120 | CCTV system work and conduit pipe | 1800 | 22.5 | 1 | 1 | 1 | 2 |  | Electrician
121 | Durable goods procurement or made to order work on the 2nd floor | 286.16 | 0.79489 | 2 | 1 | 2 | 4 |  | Skilled carpenter
122 | Renovation of the First Floor of the Building
123 | Demolition work on the 1st floor (Dismantled) | 8241.84 | 16.1605 | 17 | 9 | 12 | 34 |  | General worker
124 | Structural Engineering Work on the First Floor | 2054.3 | 3.4238 | 8 | 4 | 6 | 16 |  | General worker
125 | Architecture in the First Floor
126 | Ceiling work | 2566.62 | 17.1108 | 5 | 3 | 4 | 10 |  | Skilled carpenter
127 | Floor work | 3965.34 | 13.2178 | 5 | 3 | 4 | 10 |  | General worker
128 | Wall work | 1859.58 | 8.8551 | 7 | 4 | 5 | 14 |  | General worker
129 | Door and Window Work | 42.28 | 0.17617 | 8 | 4 | 6 | 16 |  | Skilled carpenter
130 | Staircase | 315.35 | 5.2558 | 2 | 1 | 2 | 4 |  | General worker
131 | Other decorations | 35 | 0.29167 | 2 | 1 | 2 | 4 |  | General worker
132 | Painting work | 4482 | 37.35 | 4 | 2 | 3 | 8 |  | General worker
133 | Sanitary ware
134 | Zone T-1 the area in front of the original buidling | 102 | 3.4 | 2 | 1 | 2 | 4 |  | Sanitary-Plumber
135 | Zone T-2 the area in the middle | 102 | 3.4 | 2 | 1 | 2 | 4 |  | Sanitary-Plumber
136 | Zone T3 the area behind the new building | 102 | 3.4 | 2 | 1 | 2 | 4 |  | Sanitary-Plumber
137 | Sanitation system on the first floor
138 | Water supply pipe system work
139 | Zone T-1 the area in front of the original buidling | 125.49 | 0.99595 | 1 | 1 | 1 | 2 |  | Sanitary-Plumber
140 | Zone T-2 the area in the middle | 125.49 | 0.99595 | 1 | 1 | 1 | 2 |  | Sanitary-Plumber
141 | Zone T3 the area behind the new building | 125.49 | 0.99595 | 1 | 1 | 1 | 2 |  | Sanitary-Plumber
142 | Sewage Pipe System, general sewer and air pipe
143 | Zone T-1 the area in front of the original buidling | 299.66 | 2.3783 | 1 | 1 | 1 | 2 |  | Sanitary-Plumber
144 | Zone T-2 the area in the middle | 299.66 | 2.3783 | 1 | 1 | 1 | 2 |  | Sanitary-Plumber
145 | Zone T3 the area behind the new building | 299.66 | 2.3783 | 1 | 1 | 1 | 2 |  | Sanitary-Plumber
146 | Electrical system work on the first floor
147 | Electric lamp | 405.09 | 3.3757 | 2 | 1 | 2 | 4 |  | Electrician
148 | Switch and Electrical Socket | 183 | 3.05 | 1 | 1 | 1 | 2 |  | Electrician
149 | Electrical work and conduits | 6883 | 86.0375 | 1 | 1 | 1 | 2 |  | Electrician
150 | Speaker cable work and conduit | 3837 | 47.9625 | 1 | 1 | 1 | 2 |  | Electrician
151 | CCTV system work and conduit pipe | 3200 | 40 | 1 | 1 | 1 | 2 |  | Electrician
152 | Durable goods procurement or order work on the 1st floor | 160.76 | 0.48715 | 2 | 1 | 2 | 4 |  | Skilled carpenter
153 | Basement Renovation
154 | Demolition of the wall (Dismantled) | 2345.36 | 13.0298 | 6 | 3 | 5 | 12 |  | General worker
155 | Basement Engineering | 2002.05 | 2.966 | 9 | 5 | 7 | 18 |  | General worker
156 | Basement Architecture
157 | Ceiling work | 1528 | 16.9778 | 3 | 2 | 3 | 6 |  | Skilled carpenter
158 | Floor work | 2342 | 13.0111 | 3 | 2 | 3 | 6 |  | General worker
159 | Wall work | 1112.75 | 9.2729 | 4 | 2 | 3 | 8 |  | General worker
160 | Door and Window Work | 37.97 | 0.10547 | 12 | 6 | 9 | 24 |  | Skilled carpenter
161 | Staircase | 334.85 | 5.5808 | 2 | 1 | 2 | 4 |  | General worker
162 | Painting work | 1753 | 29.2167 | 2 | 1 | 2 | 4 |  | General worker
163 | Sanitary ware
164 | Zone T-1 the area in front of the original buidling | 89.67 | 1.9927 | 3 | 2 | 3 | 6 |  | Sanitary-Plumber
165 | Basement sanitation system work
166 | Water supply pipe system
167 | Zone T-1 the area in front of the original buidling | 137.71 | 1.0929 | 1 | 1 | 1 | 2 |  | Sanitary-Plumber
168 | Sewage Pipe System, general sewer and air pipe
169 | Zone T-1 the area in front of the original buidling | 305.18 | 2.4221 | 1 | 1 | 1 | 2 |  | Sanitary-Plumber
170 | Rainwater drainage system work | 89.92 | 1.1989 | 1 | 1 | 1 | 2 |  | Sanitary-Plumber
171 | Basement Electrical System
172 | Electric Lamp | 249 | 2.075 | 2 | 1 | 2 | 4 |  | Electrician
173 | Switch and electrical socket | 123 | 2.05 | 1 | 1 | 1 | 2 |  | Electrician
174 | Electrical work and conduits | 4400 | 55 | 1 | 1 | 1 | 2 |  | Electrician
175 | Speaker cable work and conduit | 304 | 3.8 | 1 | 1 | 1 | 2 |  | Electrician
176 | CCTV system work and conduit pipe | 2000 | 25 | 1 | 1 | 1 | 2 |  | Electrician
177 | Durable goods procurement or order the basement | 328 | 0.99394 | 2 | 1 | 2 | 4 |  | Skilled carpenter
178 | Computer system and fire alarm system
179 | Computer system
180 | Fourth floor | 8482.98 | 26.5093 | 2 | 1 | 2 | 4 |  | Electrician
181 | Third floor | 8482.98 | 24.2371 | 2 | 1 | 2 | 4 |  | Electrician
182 | Second floor | 8482.98 | 24.2371 | 2 | 1 | 2 | 4 |  | Electrician
183 | First floor | 8482.98 | 26.5093 | 2 | 1 | 2 | 4 |  | Electrician
184 | Basement | 8482.98 | 26.5093 | 2 | 1 | 2 | 4 |  | Electrician
185 | Fire Alarm System
186 | Fourth floor | 7472.74 | 46.7046 | 1 | 1 | 1 | 2 |  | Electrician
187 | Third floor | 7472.74 | 42.7014 | 1 | 1 | 1 | 2 |  | Electrician
188 | Second floor | 7472.74 | 42.7014 | 1 | 1 | 1 | 2 |  | Electrician
189 | First floor | 7472.74 | 46.7046 | 1 | 1 | 1 | 2 |  | Electrician
190 | Basement | 7472.74 | 46.7046 | 1 | 1 | 1 | 2 |  | Electrician
191 | Exterior paint, repair and exterior decoration of the building
192 | Exterior paint and exterior surface repair
193 | Polishing the old wall paint | 6187 | 37.497 | 1 | 1 | 1 | 2 |  | General worker
194 | Old plaster solution (primer) | 6187 | 37.497 | 1 | 1 | 1 | 2 |  | General worker
195 | Exterior painting work (2 coats) not including basement | 6187 | 37.497 | 1 | 1 | 1 | 2 |  | General worker
196 | Cleaning and repairing of brick wall tiles (Refer to the price of polishing work) | 923 | 5.5939 | 1 | 1 | 1 | 2 |  | General worker
197 | Tile wall coating liquid (Refer to the cost of applying antifungal agent) | 923 | 5.5939 | 1 | 1 | 1 | 2 |  | General worker
198 | Demolition of roof waterproofing (Dismantled) | 2180 | 24.2222 | 1 | 1 | 1 | 2 |  | General worker
199 | Sand blasting waterproofing sheet material | 2180 | 24.2222 | 1 | 1 | 1 | 2 |  | General worker
200 | Polyurethane waterproofing, ultra-flexible oil formula, resistant to UV light, Xander, Ardex or equivalent. | 4184 | 46.4889 | 1 | 1 | 1 | 2 |  | General worker
201 | Exterior Decoration
202 | Expanded Metal XS-32 | 238 | 1.4424 | 1 | 1 | 1 | 2 |  | General worker
203 | Surrounding area
204 | Demolition of the Surrounding Area | 1 | 0.0060606 | 1 | 1 | 1 | 2 |  | General worker
205 | Structural Engineering of the Surrounding Area | 2620.43 | 3.9703 | 4 | 2 | 3 | 8 |  | General worker
206 | Architecture of the Surrounding Area | 1638.16 | 9.9282 | 1 | 1 | 1 | 2 |  | General worker
207 | Electrical System of the Surrounding Area | 72.55 | 0.4397 | 1 | 1 | 1 | 2 |  | Electrician
208 | Durable Goods
209 | Floating furniture
210 | Floating furniture in the basement | 10 | 0.33333 | 2 | 1 | 2 | 4 |  | Skilled carpenter
211 | Floating furniture on the first floor | 368 | 12.2667 | 2 | 1 | 2 | 4 |  | Skilled carpenter
212 | Floating furniture on the second floor | 784 | 26.1333 | 2 | 1 | 2 | 4 |  | Skilled carpenter
213 | Floating furniture on the third floor | 448 | 14.9333 | 2 | 1 | 2 | 4 |  | Skilled carpenter
214 | Floating furniture on the fourth floor | 366 | 12.2 | 2 | 1 | 2 | 4 |  | Skilled carpenter
215 | Repair furniture work
216 | Furniture repair work on the first floor | 50 | 0.83333 | 2 | 1 | 2 | 4 |  | Skilled carpenter
217 | Furniture repair work on the second floor | 101 | 1.6833 | 2 | 1 | 2 | 4 |  | Skilled carpenter
218 | Furniture repair work on the third floor | 137 | 2.2833 | 2 | 1 | 2 | 4 |  | Skilled carpenter
219 | Furniture repair work on the fourth floor | 81 | 1.35 | 2 | 1 | 2 | 4 |  | Skilled carpenter
220 | Curtain work
221 | Curtain work on the first floor | 28 | 0.93333 | 2 | 1 | 2 | 4 |  | Skilled carpenter
222 | Curtain on the second floor | 33 | 1.1 | 2 | 1 | 2 | 4 |  | Skilled carpenter
223 | Curtain on the third floor | 10 | 0.33333 | 2 | 1 | 2 | 4 |  | Skilled carpenter
224 | Curtain on the fourth floor | 9 | 0.3 | 2 | 1 | 2 | 4 |  | Skilled carpenter
225 | Signs
226 | Signs on the basement | 12 | 0.4 | 2 | 1 | 2 | 4 |  | Skilled carpenter
227 | Signs on the first floor | 34 | 1.1333 | 2 | 1 | 2 | 4 |  | Skilled carpenter
228 | Signs on the second floor | 32 | 1.0667 | 2 | 1 | 2 | 4 |  | Skilled carpenter
229 | Signs on the third floor | 23 | 0.76667 | 2 | 1 | 2 | 4 |  | Skilled carpenter
230 | Signs on the fourth floor | 16 | 0.53333 | 2 | 1 | 2 | 4 |  | Skilled carpenter
231 | Others
232 | Aluminum cabinet folded up and painted used to cover water dispenser | 10 | 0.33333 | 2 | 1 | 2 | 4 |  | General worker
233 | TWO WIRE REMOTE CONTROL LIGHTING SYSTEM
234 | Two wire remote control lighting system for basement | 33.182 | 0.20739 | 1 | 1 | 1 | 2 |  | Electrician
235 | Two wire remote control lighting system for the first floor | 33.182 | 0.20739 | 1 | 1 | 1 | 2 |  | Electrician
236 | Two wire remote control lighting system for the second floor | 33.182 | 0.18961 | 1 | 1 | 1 | 2 |  | Electrician
237 | Two wire remote control lighting system for the third floor | 33.182 | 0.18961 | 1 | 1 | 1 | 2 |  | Electrician
238 | Two wire remote control lighting system for the fourth floor | 33.182 | 0.20739 | 1 | 1 | 1 | 2 |  | Electrician
239 | Sound system (Using previous speakers)
240 | Sound system for basement | 1 | 0.14286 | 1 | 1 | 1 | 2 |  | Electrician
241 | Sound system for the first floor | 30 | 1.4286 | 3 | 2 | 3 | 6 |  | Electrician
242 | Sound system for the second floor | 37 | 1.7619 | 3 | 2 | 3 | 6 |  | Electrician
243 | Sound system for the third floor | 27 | 1.9286 | 2 | 1 | 2 | 4 |  | Electrician
244 | Sound system for the forth floor | 20 | 1.4286 | 2 | 1 | 2 | 4 |  | Electrician
245 | CCTV system (Using the previous CCTV system)
246 | CCTV Basement | 8 | 1.1429 | 1 | 1 | 1 | 2 |  | Electrician
247 | CCTV on the first floor | 16 | 1.1429 | 2 | 1 | 2 | 4 |  | Electrician
248 | CCTV on the second floor | 11 | 1.5714 | 1 | 1 | 1 | 2 |  | Electrician
249 | CCTV on the thrid floor | 7 | 1 | 1 | 1 | 1 | 2 |  | Electrician
250 | CCTV on the fourth floor | 12 | 0.85714 | 2 | 1 | 2 | 4 |  | Electrician

## Resource F4 CMU
No | Activity | Quantity | Output | Worker | Resource type
1 | Chiang Mai Library Renovation Project
2 | Renovation on the fourth floor
3 | Demolition work on the 4th floor | 6060.77 | 16.8355 | 12 | General worker
4 | Architecture Work on the Fourth Floor
5 | Ceiling work | 1922.93 | 21.3659 | 3 | Skilled carpenter
6 | Floor work | 2063.37 | 17.1947 | 2 | General worker
7 | Wall work | 767.97 | 12.7995 | 2 | General worker
8 | Door-Window Work | 11 | 0.36667 | 1 | Skilled carpenter
9 | Staircase Work | 110 | 3.6667 | 1 | General worker
10 | Painting work | 3179 | 35.3222 | 3 | General worker
11 | Sanitary ware
12 | Zone T-1 the area in front of the original buidling | 102.1533 | 3.4051 | 2 | Sanitary-Plumber
13 | Zone T-2 the area in the middle | 102.1533 | 3.4051 | 2 | Sanitary-Plumber
14 | Zone T3 the area behind the new building | 102.1533 | 3.4051 | 2 | Sanitary-Plumber
15 | Sanitation system work on the fourth floor
16 | Water supply pipe system work
17 | Zone T-1 the area in front of the original buidling | 143.5833 | 1.1396 | 1 | Sanitary-Plumber
18 | Zone T-2 the area in the middle | 143.5833 | 1.1396 | 1 | Sanitary-Plumber
19 | Zone T3 the area behind the new building | 143.5833 | 1.1396 | 1 | Sanitary-Plumber
20 | Sewage pipe system, general sewer and air pipe
21 | Zone T-1 the area in front of the original buidling | 285.1833 | 2.2634 | 1 | Sanitary-Plumber
22 | Zone T-2 the area in the middle | 285.1833 | 2.2634 | 1 | Sanitary-Plumber
23 | Zone T3 the area behind the new building | 285.1833 | 2.2634 | 1 | Sanitary-Plumber
24 | Electrical system work on the 4th floor
25 | Electric lamps | 343.39 | 2.8616 | 4 | Electrician
26 | Switch and electrical socket | 164 | 5.4667 | 1 | Electrician
27 | Electrical work and conduits | 6034 | 75.425 | 1 | Electrician
28 | Speaker cable work and conduit | 3264 | 40.8 | 1 | Electrician
29 | CCTV system work, conduit pipe | 1200 | 15 | 1 | Electrician
30 | Durable goods and made to order work on the fourth floor | 109.11 | 0.33064 | 2 | Skilled carpenter
31 | Computer system and fire alarm system
32 | Computer system
33 | Fourth floor | 8482.98 | 26.5093 | 2 | Electrician
34 | Fire Alarm System
35 | Fourth floor | 7472.74 | 46.7046 | 1 | Electrician
36 | Exterior paint, repair and exterior decoration of the building
37 | Exterior paint and exterior surface repair
38 | Demolition of roof waterproofing (Dismantled) | 2180 | 24.2222 | 1 | General worker
39 | Sand blasting waterproofing sheet material | 2180 | 24.2222 | 1 | General worker
40 | Polyurethane waterproofing, ultra-flexible oil formula, resistant to UV light, Xander, Ardex or equivalent. | 4184 | 46.4889 | 1 | General worker
41 | Durable Goods
42 | Floating furniture
43 | Floating furniture on the fourth floor | 366 | 12.2 | 2 | Skilled carpenter
44 | Repair furniture work
45 | Furniture repair work on the fourth floor | 81 | 1.35 | 2 | Skilled carpenter
46 | Curtain work
47 | Curtain on the fourth floor | 9 | 0.3 | 2 | Skilled carpenter
48 | Signs
49 | Signs on the fourth floor | 16 | 0.53333 | 2 | Skilled carpenter
50 | TWO WIRE REMOTE CONTROL LIGHTING SYSTEM
51 | Two wire remote control lighting system for the fourth floor | 33.182 | 0.20739 | 1 | Electrician
52 | Sound system (Using previous speakers)
53 | Sound system for the forth floor | 20 | 1.4286 | 2 | Electrician
54 | CCTV Basement
55 | CCTV on the fourth floor | 12 | 0.85714 | 2 | Electrician

## Resource จริง
No | Activity | General Worker | Skilled carpenter | Sanitary-Plumber | Electrician
1 | Chiang Mai Library Renovation Project
2 | Renovation on the fourth floor
3 | Demolition work on the 4th floor | 4
4 | Architecture Work on the Fourth Floor
5 | Ceiling work |  | 4
6 | Floor work | 3
7 | Wall work | 3
8 | Door-Window Work |  | 2
9 | Staircase Work | 3
10 | Painting work | 5
11 | Sanitary ware
12 | Zone T-1 the area in front of the original buidling
13 | Zone T-2 the area in the middle
14 | Zone T3 the area behind the new building
15 | Sanitation system work on the fourth floor
16 | Water supply pipe system work
17 | Zone T-1 the area in front of the original buidling |  |  | 1
18 | Zone T-2 the area in the middle |  |  | 1
19 | Zone T3 the area behind the new building |  |  | 1
20 | Sewage pipe system, general sewer and air pipe
21 | Zone T-1 the area in front of the original buidling |  |  | 1
22 | Zone T-2 the area in the middle |  |  | 1
23 | Zone T3 the area behind the new building |  |  | 1
24 | Electrical system work on the 4th floor
25 | Electric lamps |  |  |  | 3
26 | Switch and electrical socket |  |  |  | 3
27 | Electrical work and conduits |  |  |  | 5
28 | Speaker cable work and conduit |  |  |  | 3
29 | CCTV system work, conduit pipe |  |  |  | 4
30 | Durable goods and made to order work on the fourth floor
31 | Computer system and fire alarm system
32 | Computer system
33 | Fourth floor |  |  |  | 6
34 | Fire Alarm System
35 | Fourth floor
36 | Exterior paint, repair and exterior decoration of the building
37 | Exterior paint and exterior surface repair
38 | Demolition of roof waterproofing (Dismantled)
39 | Sand blasting waterproofing sheet material
40 | Polyurethane waterproofing, ultra-flexible oil formula, resistant to UV light, Xander, Ardex or equivalent.
41 | Durable Goods
42 | Floating furniture
43 | Floating furniture on the fourth floor
44 | Repair furniture work
45 | Furniture repair work on the fourth floor
46 | Curtain work
47 | Curtain on the fourth floor
48 | Signs
49 | Signs on the fourth floor
50 | TWO WIRE REMOTE CONTROL LIGHTING SYSTEM
51 | Two wire remote control lighting system for the fourth floor
52 | Sound system (Using previous speakers)
53 | Sound system for the forth floor
54 | CCTV Basement
55 | CCTV on the fourth floor