## solutoion_1
ID | Active | WBS | Task_Mode | Name | Duration | Outline_Level | Predecessors | Predecessors2 | Successors | Start_Date | Finish_Date | Early_Start | Early_Finish | Late_Start | Late_Finish | Constraint_Type | Constraint_Date | Summary | Start_Slack | Finish_Slack | Free_Slack | Resource_Names
1 | Yes | CMU1 | Auto Scheduled | โครงการปรับปรุงสำนักหอสมุด มหาวิทยาลัยเชียงใหม่ | 716 days | 1 |  |  |  | October 17, 2018 8:00 AM | October 1, 2020 5:00 PM | October 17, 2018 05:00 PM | October 01, 2020 05:00 PM | October 21, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 0 days | 0 days | 0 days
2 | Yes | CMU1.1 | Auto Scheduled | หมวดเตรียมการ | 675 days | 2 |  |  |  | October 17, 2018 8:00 AM | August 21, 2020 5:00 PM | October 17, 2018 05:00 PM | August 21, 2020 05:00 PM | December 01, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 41 days | 41 days | 41 days
3 | Yes | CMU1.1.1 | Auto Scheduled | งานอาคารสนามและผังบริเวณโครงการ | 14 days | 3 | 4FS-7 days |  |  | October 26, 2018 8:00 AM | November 8, 2018 5:00 PM | November 01, 2018 05:00 PM | November 14, 2018 05:00 PM | September 22, 2020 05:00 PM | October 05, 2020 05:00 PM | Start No Earlier Than | Oct 24 '18 | No | 693 days | 693 days | 693 days | Engineer
4 | Yes | CMU1.1.2 | Auto Scheduled | งานเชื่อมต่อระบบสาธารณูปโภคโครงการ | 16 days | 3 |  |  | 3FS-7 days | October 17, 2018 8:00 AM | November 1, 2018 5:00 PM | October 21, 2018 05:00 PM | November 05, 2018 05:00 PM | September 13, 2020 05:00 PM | September 28, 2020 05:00 PM | As Soon As Possible |  | No | 693 days | 693 days | 0 days | Engineer
5 | Yes | CMU1.1.3 | Auto Scheduled | งานตรวจทดสอบระบบภายในอาคารก่อนดำเนินการปรับปรุง | 675 days | 3 |  |  |  | October 17, 2018 8:00 AM | August 21, 2020 5:00 PM | October 17, 2018 05:00 PM | August 21, 2020 05:00 PM | December 01, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 41 days | 41 days | 41 days
6 | Yes | CMU1.1.3.1 | Auto Scheduled | ชั้นที่ 4 | 15 days | 4 |  |  | 7FS+150 days | October 17, 2018 8:00 AM | October 31, 2018 5:00 PM | October 17, 2018 05:00 PM | October 31, 2018 05:00 PM | December 01, 2018 05:00 PM | December 15, 2018 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
7 | Yes | CMU1.1.3.2 | Auto Scheduled | ชั้นที่ 3 | 15 days | 4 | 6FS+150 days |  | 8FS+150 days | March 31, 2019 8:00 AM | April 14, 2019 5:00 PM | April 01, 2019 05:00 PM | April 15, 2019 05:00 PM | May 15, 2019 05:00 PM | May 29, 2019 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
8 | Yes | CMU1.1.3.3 | Auto Scheduled | ชั้นที่ 2 | 15 days | 4 | 7FS+150 days |  | 9FS+150 days | September 12, 2019 8:00 AM | September 26, 2019 5:00 PM | September 18, 2019 05:00 PM | October 02, 2019 05:00 PM | October 27, 2019 05:00 PM | November 10, 2019 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
9 | Yes | CMU1.1.3.4 | Auto Scheduled | ชั้นที่ 1 | 15 days | 4 | 8FS+150 days |  | 10FS+150 days | February 24, 2020 8:00 AM | March 9, 2020 5:00 PM | March 05, 2020 05:00 PM | March 19, 2020 05:00 PM | April 09, 2020 05:00 PM | April 23, 2020 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
10 | Yes | CMU1.1.3.5 | Auto Scheduled | ชั้นใต้ดินและภายนอก | 15 days | 4 | 9FS+150 days |  |  | August 7, 2020 8:00 AM | August 21, 2020 5:00 PM | August 25, 2020 05:00 PM | September 08, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 41 days | Engineer
11 | Yes | CMU1.1.4 | Auto Scheduled | งานสำรวจอุปกรณ์ไฟฟ้า, สุขภัณฑ์และครุภัณฑ์ (ของเดิม) ก่อนดำเนินการปรับปรุง | 675 days | 3 |  |  |  | October 17, 2018 8:00 AM | August 21, 2020 5:00 PM | October 17, 2018 05:00 PM | August 21, 2020 05:00 PM | December 01, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 41 days | 41 days | 41 days
12 | Yes | CMU1.1.4.1 | Auto Scheduled | ชั้นที่ 4 | 15 days | 4 |  |  | 13FS+150 days | October 17, 2018 8:00 AM | October 31, 2018 5:00 PM | October 18, 2018 05:00 PM | November 01, 2018 05:00 PM | December 01, 2018 05:00 PM | December 15, 2018 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
13 | Yes | CMU1.1.4.2 | Auto Scheduled | ชั้นที่ 3 | 15 days | 4 | 12FS+150 days |  | 14FS+150 days | March 31, 2019 8:00 AM | April 14, 2019 5:00 PM | April 04, 2019 05:00 PM | April 18, 2019 05:00 PM | May 15, 2019 05:00 PM | May 29, 2019 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
14 | Yes | CMU1.1.4.3 | Auto Scheduled | ชั้นที่ 2 | 15 days | 4 | 13FS+150 days |  | 15FS+150 days | September 12, 2019 8:00 AM | September 26, 2019 5:00 PM | September 21, 2019 05:00 PM | October 05, 2019 05:00 PM | October 27, 2019 05:00 PM | November 10, 2019 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
15 | Yes | CMU1.1.4.4 | Auto Scheduled | ชั้นที่ 1 | 15 days | 4 | 14FS+150 days |  | 16FS+150 days | February 24, 2020 8:00 AM | March 9, 2020 5:00 PM | March 08, 2020 05:00 PM | March 22, 2020 05:00 PM | April 09, 2020 05:00 PM | April 23, 2020 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
16 | Yes | CMU1.1.4.5 | Auto Scheduled | ชั้นใต้ดินและภายนอก | 15 days | 4 | 15FS+150 days |  |  | August 7, 2020 8:00 AM | August 21, 2020 5:00 PM | August 28, 2020 05:00 PM | September 11, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 41 days | Engineer
17 | Yes | CMU1.1.5 | Auto Scheduled | งานเอกสารขออนุมัติใช้วัสดุ, Shop Drawing และครุภัณฑ์ของโครงการ | 106 days | 3 |  |  |  | October 17, 2018 8:00 AM | January 30, 2019 5:00 PM | October 20, 2018 05:00 PM | February 02, 2019 05:00 PM | June 22, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 610 days | 610 days | 610 days
18 | Yes | CMU1.1.5.1 | Auto Scheduled | แบบ Shop Drawing ชั้นที่ 4 | 20 days | 4 |  |  | 19,25SS+14 days,26SS+14 days | October 17, 2018 8:00 AM | November 5, 2018 5:00 PM | October 17, 2018 05:00 PM | November 05, 2018 05:00 PM | October 01, 2018 05:00 PM | October 20, 2018 05:00 PM | As Soon As Possible |  | No | 610 days | 610 days | 0 days | Engineer
19 | Yes | CMU1.1.5.2 | Auto Scheduled | แบบ Shop Drawing ชั้นที่ 3 | 20 days | 4 | 18 |  | 20FS-7 days | November 6, 2018 8:00 AM | November 25, 2018 5:00 PM | November 11, 2018 05:00 PM | November 30, 2018 05:00 PM | July 13, 2020 05:00 PM | August 01, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
20 | Yes | CMU1.1.5.3 | Auto Scheduled | แบบ Shop Drawing ชั้นที่ 2 | 20 days | 4 | 19FS-7 days |  | 21FS-7 days | November 19, 2018 8:00 AM | December 8, 2018 5:00 PM | November 28, 2018 05:00 PM | December 17, 2018 05:00 PM | July 26, 2020 05:00 PM | August 14, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
21 | Yes | CMU1.1.5.4 | Auto Scheduled | แบบ Shop Drawing ชั้นที่ 1 | 20 days | 4 | 20FS-7 days |  | 22FS-7 days | December 2, 2018 8:00 AM | December 21, 2018 5:00 PM | December 24, 2018 05:00 PM | January 12, 2019 05:00 PM | August 08, 2020 05:00 PM | August 27, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
22 | Yes | CMU1.1.5.5 | Auto Scheduled | แบบ Shop Drawing ชั้นใต้ดิน | 20 days | 4 | 21FS-7 days |  | 23FS-7 days | December 15, 2018 8:00 AM | January 3, 2019 5:00 PM | January 10, 2019 05:00 PM | January 29, 2019 05:00 PM | August 21, 2020 05:00 PM | September 09, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
23 | Yes | CMU1.1.5.6 | Auto Scheduled | แบบ Shop Drawing ภายนอกอาคาร | 20 days | 4 | 22FS-7 days |  | 24FS-7 days | December 28, 2018 8:00 AM | January 16, 2019 5:00 PM | January 25, 2019 05:00 PM | February 13, 2019 05:00 PM | September 03, 2020 05:00 PM | September 22, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
24 | Yes | CMU1.1.5.7 | Auto Scheduled | แบบ Shop Drawing landscape | 20 days | 4 | 23FS-7 days |  |  | January 10, 2019 8:00 AM | January 29, 2019 5:00 PM | February 11, 2019 05:00 PM | March 02, 2019 05:00 PM | September 16, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 611 days | Engineer
25 | Yes | CMU1.1.5.8 | Auto Scheduled | แบบ Shop Drawing งานปรับปรุง ครุภัณฑ์ | 92 days | 4 | 18SS+14 days |  |  | October 31, 2018 8:00 AM | January 30, 2019 5:00 PM | November 03, 2018 05:00 PM | February 02, 2019 05:00 PM | July 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 610 days | 610 days | 610 days | Engineer
26 | Yes | CMU1.1.5.9 | Auto Scheduled | แบบ Shop Drawing งานจัดซื้อครุภัณฑ์ | 92 days | 4 | 18SS+14 days |  |  | October 31, 2018 8:00 AM | January 30, 2019 5:00 PM | November 05, 2018 05:00 PM | February 04, 2019 05:00 PM | July 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 610 days | 610 days | 610 days | Engineer
27 | Yes | CMU1.1.6 | Auto Scheduled | งานตรวจทดสอบระบบ, งานอบรมผู้ใช้อาคาร และ As-Built Drawing | 30 days | 3 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 20, 2018 05:00 PM | November 18, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 686 days | 686 days | 686 days
28 | Yes | CMU1.1.6.1 | Auto Scheduled | ชั้นที่ 4 | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 22, 2018 05:00 PM | November 20, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
29 | Yes | CMU1.1.6.2 | Auto Scheduled | ชั้นที่ 3 | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 30, 2018 05:00 PM | November 28, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
30 | Yes | CMU1.1.6.3 | Auto Scheduled | ชั้นที่ 2 | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 19, 2018 05:00 PM | November 17, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
31 | Yes | CMU1.1.6.4 | Auto Scheduled | ชั้นที่ 1 | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 22, 2018 05:00 PM | November 20, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
32 | Yes | CMU1.1.6.5 | Auto Scheduled | ชั้นใต้ดิน | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 21, 2018 05:00 PM | November 19, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
33 | Yes | CMU1.1.6.6 | Auto Scheduled | ทั้งอาคาร | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 19, 2018 05:00 PM | November 17, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
34 | Yes | CMU1.1.7 | Auto Scheduled | งานบริหารงานก่อสร้างและงานอื่น ๆ | 0 days | 3 |  |  |  | October 17, 2018 8:00 AM | October 17, 2018 8:00 AM | October 19, 2018 05:00 PM | October 18, 2018 05:00 PM | October 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 716 days | 716 days | 716 days | Engineer
35 | Yes | CMU1.2 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้น 4 | 471 days | 2 |  |  |  | October 17, 2018 8:00 AM | January 30, 2020 5:00 PM | October 17, 2018 05:00 PM | January 30, 2020 05:00 PM | June 23, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 0 days | 245 days | 0 days
36 | Yes | CMU1.2.1 | Auto Scheduled | งานรื้อถอน ชั้น 4 (รื้อขนไป) | 30 days | 3 |  |  | 39FS+45 days,40FS+45 days,51,63SS+14 days,80,109,140,180FS+14 days,186FS+14 days,198FS+14 days,199FS+14 days,200FS+14 days,238FS+14 days | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 17, 2018 05:00 PM | November 15, 2018 05:00 PM | March 11, 2018 05:00 PM | April 09, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | General worker
37 | Yes | CMU1.2.2 | Auto Scheduled | งานสถาปัตยกรรม ชั้น 4 | 396 days | 3 |  |  |  | December 31, 2018 8:00 AM | January 30, 2020 5:00 PM | October 17, 2018 05:00 PM | November 16, 2019 05:00 PM | September 06, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 326 days | 245 days | 245 days
38 | Yes | CMU1.2.2.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 39,41,42 |  |  | March 1, 2019 8:00 AM | March 30, 2019 5:00 PM | March 09, 2019 05:00 PM | April 07, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 551 days | Skilled carpenter
39 | Yes | CMU1.2.2.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 36FS+45 days |  | 38,43 | December 31, 2018 8:00 AM | February 28, 2019 5:00 PM | January 01, 2019 05:00 PM | March 01, 2019 05:00 PM | July 15, 2020 05:00 PM | September 12, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 0 days | General worker
40 | Yes | CMU1.2.2.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 36FS+45 days |  | 41,42 | December 31, 2018 8:00 AM | January 29, 2019 5:00 PM | January 03, 2019 05:00 PM | February 01, 2019 05:00 PM | August 14, 2020 05:00 PM | September 12, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 0 days | General worker
41 | Yes | CMU1.2.2.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 40 |  | 38,43 | January 30, 2019 8:00 AM | February 28, 2019 5:00 PM | February 03, 2019 05:00 PM | March 04, 2019 05:00 PM | August 14, 2020 05:00 PM | September 12, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 0 days | Skilled carpenter
42 | Yes | CMU1.2.2.5 | Auto Scheduled | งานบันได | 30 days | 4 | 40 |  | 38,43 | January 30, 2019 8:00 AM | February 28, 2019 5:00 PM | February 04, 2019 05:00 PM | March 05, 2019 05:00 PM | August 14, 2020 05:00 PM | September 12, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 0 days | General worker
43 | Yes | CMU1.2.2.6 | Auto Scheduled | งานสี | 30 days | 4 | 39,41,42 |  |  | March 1, 2019 8:00 AM | March 30, 2019 5:00 PM | March 07, 2019 05:00 PM | April 05, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 551 days | General worker
44 | Yes | CMU1.2.2.7 | Auto Scheduled | งานสุขภัณฑ์ | 315 days | 4 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 18, 2018 05:00 PM | August 28, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
45 | Yes | CMU1.2.2.7.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 46FS+135 days |  | 47FS+135 days | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | September 04, 2019 05:00 PM | September 18, 2019 05:00 PM | April 24, 2020 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
46 | Yes | CMU1.2.2.7.2 | Auto Scheduled | ZONE T-2 กลาง | 15 days | 5 | 51,55 |  | 45FS+135 days | March 22, 2019 8:00 AM | April 5, 2019 5:00 PM | March 31, 2019 05:00 PM | April 14, 2019 05:00 PM | November 26, 2019 05:00 PM | December 10, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
47 | Yes | CMU1.2.2.7.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 15 days | 5 | 45FS+135 days |  |  | January 16, 2020 8:00 AM | January 30, 2020 5:00 PM | February 04, 2020 05:00 PM | February 18, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 245 days | Sanitary-Plumber
48 | Yes | CMU1.2.3 | Auto Scheduled | งานระบบสุขาภิบาล ชั้น 4 | 408 days | 3 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
49 | Yes | CMU1.2.3.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
50 | Yes | CMU1.2.3.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 51FS+15 days |  | 52FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 11, 2019 05:00 PM | August 14, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
51 | Yes | CMU1.2.3.1.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 36 |  | 50FS+15 days,46,55SS | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 20, 2018 05:00 PM | March 25, 2019 05:00 PM | August 25, 2019 05:00 PM | December 28, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
52 | Yes | CMU1.2.3.1.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 50FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 01, 2019 05:00 PM | January 04, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
53 | Yes | CMU1.2.3.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
54 | Yes | CMU1.2.3.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 55FS+15 days |  | 56FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 15, 2019 05:00 PM | August 18, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
55 | Yes | CMU1.2.3.2.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 51SS |  | 54FS+15 days,46 | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 22, 2018 05:00 PM | March 27, 2019 05:00 PM | August 25, 2019 05:00 PM | December 28, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
56 | Yes | CMU1.2.3.2.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 54FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 08, 2019 05:00 PM | January 11, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
57 | Yes | CMU1.2.4 | Auto Scheduled | งานระบบไฟฟ้า ชั้น 4 | 117 days | 3 |  |  |  | November 30, 2018 8:00 AM | March 26, 2019 5:00 PM | October 19, 2018 05:00 PM | February 12, 2019 05:00 PM | June 11, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 555 days | 555 days | 555 days
58 | Yes | CMU1.2.4.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 30 days | 4 | 60FS+7 days |  |  | February 25, 2019 8:00 AM | March 26, 2019 5:00 PM | March 02, 2019 05:00 PM | March 31, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 555 days | 555 days | 555 days | Electrician
59 | Yes | CMU1.2.4.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 30 days | 4 | 60FS+7 days |  |  | February 25, 2019 8:00 AM | March 26, 2019 5:00 PM | February 28, 2019 05:00 PM | March 29, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 555 days | 555 days | 555 days | Electrician
60 | Yes | CMU1.2.4.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 63SS+30 days |  | 58FS+7 days,59FS+7 days | November 30, 2018 8:00 AM | February 17, 2019 5:00 PM | December 02, 2018 05:00 PM | February 19, 2019 05:00 PM | June 11, 2020 05:00 PM | August 29, 2020 05:00 PM | As Soon As Possible |  | No | 555 days | 555 days | 0 days | Electrician
61 | Yes | CMU1.2.4.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 63SS+30 days |  |  | November 30, 2018 8:00 AM | February 17, 2019 5:00 PM | December 02, 2018 05:00 PM | February 19, 2019 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 592 days | 592 days | 592 days | Electrician
62 | Yes | CMU1.2.4.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 63SS+30 days |  |  | November 30, 2018 8:00 AM | February 17, 2019 5:00 PM | December 04, 2018 05:00 PM | February 21, 2019 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 592 days | 592 days | 592 days | Electrician
63 | Yes | CMU1.2.5 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้น 4 | 165 days | 3 | 36SS+14 days |  | 62SS+30 days,60SS+30 days,61SS+30 days,65,214,219FS-15 days,224,230,244FS-7 days,250FS-7 days | October 31, 2018 8:00 AM | April 13, 2019 5:00 PM | October 31, 2018 05:00 PM | April 13, 2019 05:00 PM | June 19, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Skilled carpenter
64 | Yes | CMU1.3 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้น 3 | 441 days | 2 |  |  |  | November 16, 2018 8:00 AM | January 30, 2020 5:00 PM | October 17, 2018 05:00 PM | December 31, 2019 05:00 PM | July 23, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 149 days | 245 days | 149 days
65 | Yes | CMU1.3.1 | Auto Scheduled | งานรื้อถอน ชั้น 3 (รื้อขนไป) | 30 days | 3 | 63 | 121 | 68FS+45 days,69FS+45 days,92SS | April 14, 2019 8:00 AM | May 13, 2019 5:00 PM | April 14, 2019 05:00 PM | May 13, 2019 05:00 PM | July 19, 2018 05:00 PM | August 17, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | General worker
66 | Yes | CMU1.3.2 | Auto Scheduled | งานสถาปัตยกรรม ชั้น 3 | 315 days | 3 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 19, 2018 05:00 PM | August 29, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
67 | Yes | CMU1.3.2.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 68,70,71 |  |  | August 27, 2019 8:00 AM | September 25, 2019 5:00 PM | August 28, 2019 05:00 PM | September 26, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 372 days | Skilled carpenter
68 | Yes | CMU1.3.2.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 65FS+45 days |  | 67,72 | June 28, 2019 8:00 AM | August 26, 2019 5:00 PM | June 28, 2019 05:00 PM | August 26, 2019 05:00 PM | October 02, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 0 days | General worker
69 | Yes | CMU1.3.2.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 65FS+45 days |  | 70,71 | June 28, 2019 8:00 AM | July 27, 2019 5:00 PM | June 28, 2019 05:00 PM | July 27, 2019 05:00 PM | April 15, 2019 05:00 PM | May 14, 2019 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 0 days | General worker
70 | Yes | CMU1.3.2.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 69 |  | 67,72 | July 28, 2019 8:00 AM | August 26, 2019 5:00 PM | July 28, 2019 05:00 PM | August 26, 2019 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 0 days | Skilled carpenter
71 | Yes | CMU1.3.2.5 | Auto Scheduled | งานบันได | 30 days | 4 | 69 |  | 67,72 | July 28, 2019 8:00 AM | August 26, 2019 5:00 PM | July 28, 2019 05:00 PM | August 26, 2019 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 0 days | General worker
72 | Yes | CMU1.3.2.6 | Auto Scheduled | งานสี | 30 days | 4 | 68,70,71 |  |  | August 27, 2019 8:00 AM | September 25, 2019 5:00 PM | August 28, 2019 05:00 PM | September 26, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 372 days | General worker
73 | Yes | CMU1.3.2.7 | Auto Scheduled | งานสุขภัณฑ์ | 315 days | 4 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 20, 2018 05:00 PM | August 30, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
74 | Yes | CMU1.3.2.7.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 75FS+135 days |  | 76FS+135 days | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | August 22, 2019 05:00 PM | September 05, 2019 05:00 PM | April 24, 2020 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
75 | Yes | CMU1.3.2.7.2 | Auto Scheduled | ZONE T-2 กลาง | 15 days | 5 | 80,84 |  | 74FS+135 days | March 22, 2019 8:00 AM | April 5, 2019 5:00 PM | March 23, 2019 05:00 PM | April 06, 2019 05:00 PM | November 26, 2019 05:00 PM | December 10, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
76 | Yes | CMU1.3.2.7.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 15 days | 5 | 74FS+135 days |  |  | January 16, 2020 8:00 AM | January 30, 2020 5:00 PM | January 22, 2020 05:00 PM | February 05, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 245 days | Sanitary-Plumber
77 | Yes | CMU1.3.3 | Auto Scheduled | งานระบบสุขาภิบาล ชั้น 3 | 408 days | 3 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
78 | Yes | CMU1.3.3.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
79 | Yes | CMU1.3.3.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 80FS+15 days |  | 81FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 09, 2019 05:00 PM | August 12, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
80 | Yes | CMU1.3.3.1.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 36 |  | 79FS+15 days,84SS,75 | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 16, 2018 05:00 PM | March 21, 2019 05:00 PM | January 09, 2019 05:00 PM | May 14, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
81 | Yes | CMU1.3.3.1.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 79FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | August 31, 2019 05:00 PM | January 03, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
82 | Yes | CMU1.3.3.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
83 | Yes | CMU1.3.3.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 84FS+15 days |  | 85FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 08, 2019 05:00 PM | August 11, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
84 | Yes | CMU1.3.3.2.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 80SS |  | 83FS+15 days,75 | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 16, 2018 05:00 PM | March 21, 2019 05:00 PM | January 09, 2019 05:00 PM | May 14, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
85 | Yes | CMU1.3.3.2.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 83FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | August 31, 2019 05:00 PM | January 03, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
86 | Yes | CMU1.3.4 | Auto Scheduled | งานระบบไฟฟ้า ชั้น 3 | 147 days | 3 |  |  |  | May 14, 2019 8:00 AM | October 7, 2019 5:00 PM | October 20, 2018 05:00 PM | March 15, 2019 05:00 PM | May 12, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 360 days | 360 days | 360 days
87 | Yes | CMU1.3.4.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 60 days | 4 | 89FS+7 days |  |  | August 9, 2019 8:00 AM | October 7, 2019 5:00 PM | August 10, 2019 05:00 PM | October 08, 2019 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 360 days | 360 days | 360 days | Electrician
88 | Yes | CMU1.3.4.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 60 days | 4 | 89FS+7 days |  |  | August 9, 2019 8:00 AM | October 7, 2019 5:00 PM | August 13, 2019 05:00 PM | October 11, 2019 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 360 days | 360 days | 360 days | Electrician
89 | Yes | CMU1.3.4.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 92SS+30 days |  | 88FS+7 days,87FS+7 days | May 14, 2019 8:00 AM | August 1, 2019 5:00 PM | May 14, 2019 05:00 PM | August 01, 2019 05:00 PM | May 12, 2020 05:00 PM | July 30, 2020 05:00 PM | As Soon As Possible |  | No | 360 days | 360 days | 0 days | Electrician
90 | Yes | CMU1.3.4.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 92SS+30 days |  |  | May 14, 2019 8:00 AM | August 1, 2019 5:00 PM | May 17, 2019 05:00 PM | August 04, 2019 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 427 days | 427 days | 427 days | Electrician
91 | Yes | CMU1.3.4.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 92SS+30 days |  |  | May 14, 2019 8:00 AM | August 1, 2019 5:00 PM | May 18, 2019 05:00 PM | August 05, 2019 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 427 days | 427 days | 427 days | Electrician
92 | Yes | CMU1.3.5 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้น 3 | 180 days | 3 | 65SS |  | 91SS+30 days,90SS+30 days,89SS+30 days,94,213FS-15 days,218FS-30 days,223FS-15 days,229FS-15 days,243FS-7 days,249FS-7 days | April 14, 2019 8:00 AM | October 10, 2019 5:00 PM | April 14, 2019 05:00 PM | October 10, 2019 05:00 PM | October 12, 2019 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Skilled carpenter
93 | Yes | CMU1.4 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้น 2 | 509 days | 2 |  |  |  | November 16, 2018 8:00 AM | April 7, 2020 5:00 PM | October 17, 2018 05:00 PM | March 08, 2020 05:00 PM | May 16, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 177 days | 177 days
94 | Yes | CMU1.4.1 | Auto Scheduled | งานรื้อถอน ชั้น 2 (รื้อขนไป) | 30 days | 3 | 92 | 152 | 97FS+45 days,98FS+45 days,121SS | October 11, 2019 8:00 AM | November 9, 2019 5:00 PM | October 11, 2019 05:00 PM | November 09, 2019 05:00 PM | June 04, 2018 05:00 PM | July 03, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | General worker
95 | Yes | CMU1.4.2 | Auto Scheduled | งานสถาปัตยกรรม ชั้น 2 | 368 days | 3 |  |  |  | March 22, 2019 8:00 AM | March 23, 2020 5:00 PM | October 17, 2018 05:00 PM | October 19, 2019 05:00 PM | October 04, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 192 days | 192 days
96 | Yes | CMU1.4.2.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 97,99,100 |  |  | February 23, 2020 8:00 AM | March 23, 2020 5:00 PM | February 28, 2020 05:00 PM | March 28, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 192 days | Skilled carpenter
97 | Yes | CMU1.4.2.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 94FS+45 days |  | 96,101 | December 25, 2019 8:00 AM | February 22, 2020 5:00 PM | December 25, 2019 05:00 PM | February 22, 2020 05:00 PM | February 09, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 0 days | General worker
98 | Yes | CMU1.4.2.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 94FS+45 days |  | 99,100 | December 25, 2019 8:00 AM | January 23, 2020 5:00 PM | December 26, 2019 05:00 PM | January 24, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 0 days | General worker
99 | Yes | CMU1.4.2.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 98 |  | 96,101 | January 24, 2020 8:00 AM | February 22, 2020 5:00 PM | January 26, 2020 05:00 PM | February 24, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 0 days | Skilled carpenter
100 | Yes | CMU1.4.2.5 | Auto Scheduled | งานบันได | 30 days | 4 | 98 |  | 96,101 | January 24, 2020 8:00 AM | February 22, 2020 5:00 PM | January 27, 2020 05:00 PM | February 25, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 0 days | General worker
101 | Yes | CMU1.4.2.6 | Auto Scheduled | งานสี | 30 days | 4 | 97,99,100 |  |  | February 23, 2020 8:00 AM | March 23, 2020 5:00 PM | February 28, 2020 05:00 PM | March 28, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 192 days | General worker
102 | Yes | CMU1.4.2.7 | Auto Scheduled | งานสุขภัณฑ์ | 315 days | 4 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 19, 2018 05:00 PM | August 29, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
103 | Yes | CMU1.4.2.7.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 104FS+135 days |  | 105FS+135 days | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | August 30, 2019 05:00 PM | September 13, 2019 05:00 PM | April 24, 2020 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
104 | Yes | CMU1.4.2.7.2 | Auto Scheduled | ZONE T-2 กลาง | 15 days | 5 | 113,109 |  | 103FS+135 days | March 22, 2019 8:00 AM | April 5, 2019 5:00 PM | March 30, 2019 05:00 PM | April 13, 2019 05:00 PM | November 26, 2019 05:00 PM | December 10, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
105 | Yes | CMU1.4.2.7.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 15 days | 5 | 103FS+135 days |  |  | January 16, 2020 8:00 AM | January 30, 2020 5:00 PM | January 31, 2020 05:00 PM | February 14, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 245 days | Sanitary-Plumber
106 | Yes | CMU1.4.3 | Auto Scheduled | งานระบบสุขาภิบาล ชั้น 2 | 408 days | 3 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
107 | Yes | CMU1.4.3.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
108 | Yes | CMU1.4.3.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 109FS+15 days |  | 110FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 10, 2019 05:00 PM | August 13, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
109 | Yes | CMU1.4.3.1.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 36 |  | 113SS,104,108FS+15 days | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 19, 2018 05:00 PM | March 24, 2019 05:00 PM | August 25, 2019 05:00 PM | December 28, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
110 | Yes | CMU1.4.3.1.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 108FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | August 31, 2019 05:00 PM | January 03, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
111 | Yes | CMU1.4.3.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
112 | Yes | CMU1.4.3.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 113FS+15 days |  | 114FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 14, 2019 05:00 PM | August 17, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
113 | Yes | CMU1.4.3.2.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 109SS |  | 104,112FS+15 days | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 21, 2018 05:00 PM | March 26, 2019 05:00 PM | August 25, 2019 05:00 PM | December 28, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
114 | Yes | CMU1.4.3.2.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 112FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 04, 2019 05:00 PM | January 07, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
115 | Yes | CMU1.4.4 | Auto Scheduled | งานระบบไฟฟ้า ชั้น 2 | 147 days | 3 |  |  |  | November 10, 2019 8:00 AM | April 4, 2020 5:00 PM | October 18, 2018 05:00 PM | March 13, 2019 05:00 PM | May 12, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 180 days | 180 days | 180 days
116 | Yes | CMU1.4.4.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 60 days | 4 | 118FS+7 days |  |  | February 5, 2020 8:00 AM | April 4, 2020 5:00 PM | February 07, 2020 05:00 PM | April 06, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 180 days | 180 days | 180 days | Electrician
117 | Yes | CMU1.4.4.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 60 days | 4 | 118FS+7 days |  |  | February 5, 2020 8:00 AM | April 4, 2020 5:00 PM | February 09, 2020 05:00 PM | April 08, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 180 days | 180 days | 180 days | Electrician
118 | Yes | CMU1.4.4.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 121SS+30 days |  | 117FS+7 days,116FS+7 days | November 10, 2019 8:00 AM | January 28, 2020 5:00 PM | November 11, 2019 05:00 PM | January 29, 2020 05:00 PM | May 12, 2020 05:00 PM | July 30, 2020 05:00 PM | As Soon As Possible |  | No | 180 days | 180 days | 0 days | Electrician
119 | Yes | CMU1.4.4.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 121SS+30 days |  |  | November 10, 2019 8:00 AM | January 28, 2020 5:00 PM | November 14, 2019 05:00 PM | February 01, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 247 days | 247 days | 247 days | Electrician
120 | Yes | CMU1.4.4.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 121SS+30 days |  |  | November 10, 2019 8:00 AM | January 28, 2020 5:00 PM | November 12, 2019 05:00 PM | January 30, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 247 days | 247 days | 247 days | Electrician
121 | Yes | CMU1.4.5 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้น 2 | 180 days | 3 | 94SS |  | 120SS+30 days,119SS+30 days,118SS+30 days,123,212FS-15 days,217FS-30 days,222FS-15 days,228FS-15 days,242FS-7 days,248FS-7 days | October 11, 2019 8:00 AM | April 7, 2020 5:00 PM | October 11, 2019 05:00 PM | April 07, 2020 05:00 PM | June 04, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Skilled carpenter
122 | Yes | CMU1.5 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้น 1 | 686 days | 2 |  |  |  | November 16, 2018 8:00 AM | October 1, 2020 5:00 PM | October 17, 2018 05:00 PM | September 01, 2020 05:00 PM | November 20, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 0 days | 0 days
123 | Yes | CMU1.5.1 | Auto Scheduled | งานรื้อถอน ชั้น 1 (รื้อขนไป) | 30 days | 3 | 121 | 63 | 124,127FS+45 days,128FS+45 days,131FS+45 days,152SS,193SS,194SS,195SS,196SS,197SS,202SS,204SS,205SS,206SS,207SS | April 8, 2020 8:00 AM | May 7, 2020 5:00 PM | April 08, 2020 05:00 PM | May 07, 2020 05:00 PM | July 19, 2018 05:00 PM | August 17, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | General worker
124 | Yes | CMU1.5.2 | Auto Scheduled | งานโครงสร้างวิศวกรรม ชั้น 1 | 75 days | 3 | 123 |  |  | May 8, 2020 8:00 AM | July 21, 2020 5:00 PM | May 08, 2020 05:00 PM | July 21, 2020 05:00 PM | July 23, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 72 days | 72 days | 72 days | General worker
125 | Yes | CMU1.5.3 | Auto Scheduled | งานสถาปัตยกรรม ชั้น 1 | 548 days | 3 |  |  |  | March 22, 2019 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | April 16, 2020 05:00 PM | April 07, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 12 days | 12 days
126 | Yes | CMU1.5.3.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 127,129,130 |  |  | August 21, 2020 8:00 AM | September 19, 2020 5:00 PM | August 21, 2020 05:00 PM | September 19, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | Skilled carpenter
127 | Yes | CMU1.5.3.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 123FS+45 days |  | 126,132 | June 22, 2020 8:00 AM | August 20, 2020 5:00 PM | June 22, 2020 05:00 PM | August 20, 2020 05:00 PM | October 02, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
128 | Yes | CMU1.5.3.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 123FS+45 days |  | 129,130 | June 22, 2020 8:00 AM | July 21, 2020 5:00 PM | June 22, 2020 05:00 PM | July 21, 2020 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
129 | Yes | CMU1.5.3.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 128 |  | 126,132 | July 22, 2020 8:00 AM | August 20, 2020 5:00 PM | July 22, 2020 05:00 PM | August 20, 2020 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | Skilled carpenter
130 | Yes | CMU1.5.3.5 | Auto Scheduled | งานบันได | 30 days | 4 | 128 |  | 126,132 | July 22, 2020 8:00 AM | August 20, 2020 5:00 PM | July 22, 2020 05:00 PM | August 20, 2020 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
131 | Yes | CMU1.5.3.6 | Auto Scheduled | งานตกแต่งอื่น ๆ | 60 days | 4 | 123FS+45 days |  |  | June 22, 2020 8:00 AM | August 20, 2020 5:00 PM | June 22, 2020 05:00 PM | August 20, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 42 days | 42 days | 42 days | General worker
132 | Yes | CMU1.5.3.7 | Auto Scheduled | งานสี | 30 days | 4 | 127,129,130 |  |  | August 21, 2020 8:00 AM | September 19, 2020 5:00 PM | August 21, 2020 05:00 PM | September 19, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
133 | Yes | CMU1.5.3.8 | Auto Scheduled | งานสุขภัณฑ์ | 315 days | 4 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 20, 2018 05:00 PM | August 30, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
134 | Yes | CMU1.5.3.8.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 135FS+135 days |  | 136FS+135 days | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | August 21, 2019 05:00 PM | September 04, 2019 05:00 PM | April 24, 2020 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
135 | Yes | CMU1.5.3.8.2 | Auto Scheduled | ZONE T-2 กลาง | 15 days | 5 | 140,144 |  | 134FS+135 days,164FS+135 days | March 22, 2019 8:00 AM | April 5, 2019 5:00 PM | March 23, 2019 05:00 PM | April 06, 2019 05:00 PM | November 26, 2019 05:00 PM | December 10, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
136 | Yes | CMU1.5.3.8.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 15 days | 5 | 134FS+135 days |  |  | January 16, 2020 8:00 AM | January 30, 2020 5:00 PM | January 19, 2020 05:00 PM | February 02, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 245 days | Sanitary-Plumber
137 | Yes | CMU1.5.4 | Auto Scheduled | งานระบบสุขาภิบาล ชั้น 1 | 408 days | 3 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 278 days | 44 days
138 | Yes | CMU1.5.4.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 278 days | 44 days
139 | Yes | CMU1.5.4.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 140FS+15 days |  | 141FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 11, 2019 05:00 PM | August 14, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
140 | Yes | CMU1.5.4.1.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 36 |  | 139FS+15 days,144SS,135,167FS+15 days | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 16, 2018 05:00 PM | March 21, 2019 05:00 PM | January 03, 2019 05:00 PM | May 08, 2019 05:00 PM | As Soon As Possible |  | No | 44 days | 44 days | 0 days | Sanitary-Plumber
141 | Yes | CMU1.5.4.1.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 139FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 02, 2019 05:00 PM | January 05, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
142 | Yes | CMU1.5.4.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 278 days | 44 days
143 | Yes | CMU1.5.4.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 144FS+15 days |  | 145FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 10, 2019 05:00 PM | August 13, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
144 | Yes | CMU1.5.4.2.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 140SS |  | 143FS+15 days,135,169FS+15 days | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 16, 2018 05:00 PM | March 21, 2019 05:00 PM | January 03, 2019 05:00 PM | May 08, 2019 05:00 PM | As Soon As Possible |  | No | 44 days | 44 days | 0 days | Sanitary-Plumber
145 | Yes | CMU1.5.4.2.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 143FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | August 30, 2019 05:00 PM | January 02, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
146 | Yes | CMU1.5.5 | Auto Scheduled | งานระบบไฟฟ้า ชั้น 1 | 147 days | 3 |  |  |  | May 8, 2020 8:00 AM | October 1, 2020 5:00 PM | October 19, 2018 05:00 PM | March 14, 2019 05:00 PM | May 12, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 0 days | 0 days | 0 days
147 | Yes | CMU1.5.5.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 60 days | 4 | 149FS+7 days |  |  | August 3, 2020 8:00 AM | October 1, 2020 5:00 PM | August 03, 2020 05:00 PM | October 01, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Electrician
148 | Yes | CMU1.5.5.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 60 days | 4 | 149FS+7 days |  |  | August 3, 2020 8:00 AM | October 1, 2020 5:00 PM | August 03, 2020 05:00 PM | October 01, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Electrician
149 | Yes | CMU1.5.5.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 152SS+30 days |  | 148FS+7 days,147FS+7 days | May 8, 2020 8:00 AM | July 26, 2020 5:00 PM | May 08, 2020 05:00 PM | July 26, 2020 05:00 PM | May 12, 2020 05:00 PM | July 30, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Electrician
150 | Yes | CMU1.5.5.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 152SS+30 days |  |  | May 8, 2020 8:00 AM | July 26, 2020 5:00 PM | May 08, 2020 05:00 PM | July 26, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 67 days | 67 days | 67 days | Electrician
151 | Yes | CMU1.5.5.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 152SS+30 days |  |  | May 8, 2020 8:00 AM | July 26, 2020 5:00 PM | May 08, 2020 05:00 PM | July 26, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 67 days | 67 days | 67 days | Electrician
152 | Yes | CMU1.5.6 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้น 1 | 165 days | 3 | 123SS |  | 151SS+30 days,150SS+30 days,149SS+30 days,154SS,211FS-30 days,210FS-30 days,216FS-45 days,221FS-30 days,227FS-30 days,226FS-30 days,232FS-45 days,241FS-7 days,247FS-7 days | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 08, 2020 05:00 PM | September 19, 2020 05:00 PM | November 26, 2019 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Skilled carpenter
153 | Yes | CMU1.6 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้นใต้ดิน | 533 days | 2 |  |  |  | April 6, 2019 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | April 01, 2020 05:00 PM | April 22, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 12 days | 12 days
154 | Yes | CMU1.6.1 | Auto Scheduled | งานรื้อถอน ชั้นใต้ดิน (รื้อขนไป) | 30 days | 3 | 152SS |  | 155,158FS+45 days,159FS+45 days,177SS,176SS,175SS,174SS | April 8, 2020 8:00 AM | May 7, 2020 5:00 PM | April 08, 2020 05:00 PM | May 07, 2020 05:00 PM | November 26, 2019 05:00 PM | December 25, 2019 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
155 | Yes | CMU1.6.2 | Auto Scheduled | งานโครงสร้างวิศวกรรม ชั้นใต้ดิน | 75 days | 3 | 154 |  |  | May 8, 2020 8:00 AM | July 21, 2020 5:00 PM | May 08, 2020 05:00 PM | July 21, 2020 05:00 PM | July 23, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 72 days | 72 days | 72 days | General worker
156 | Yes | CMU1.6.3 | Auto Scheduled | งานสถาปัตยกรรม ชั้นใต้ดิน | 398 days | 3 |  |  |  | August 19, 2019 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | November 18, 2019 05:00 PM | September 04, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 320 days | 12 days | 12 days
157 | Yes | CMU1.6.3.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 158,160,161 |  |  | August 21, 2020 8:00 AM | September 19, 2020 5:00 PM | August 30, 2020 05:00 PM | September 28, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | Skilled carpenter
158 | Yes | CMU1.6.3.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 154FS+45 days |  | 157,162 | June 22, 2020 8:00 AM | August 20, 2020 5:00 PM | June 22, 2020 05:00 PM | August 20, 2020 05:00 PM | February 09, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
159 | Yes | CMU1.6.3.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 154FS+45 days |  | 160,161 | June 22, 2020 8:00 AM | July 21, 2020 5:00 PM | July 01, 2020 05:00 PM | July 30, 2020 05:00 PM | August 22, 2020 05:00 PM | September 20, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
160 | Yes | CMU1.6.3.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 159 |  | 157,162 | July 22, 2020 8:00 AM | August 20, 2020 5:00 PM | July 31, 2020 05:00 PM | August 29, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | Skilled carpenter
161 | Yes | CMU1.6.3.5 | Auto Scheduled | งานบันได | 30 days | 4 | 159 |  | 157,162 | July 22, 2020 8:00 AM | August 20, 2020 5:00 PM | July 31, 2020 05:00 PM | August 29, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
162 | Yes | CMU1.6.3.6 | Auto Scheduled | งานสี | 30 days | 4 | 158,160,161 |  |  | August 21, 2020 8:00 AM | September 19, 2020 5:00 PM | August 30, 2020 05:00 PM | September 28, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
163 | Yes | CMU1.6.3.7 | Auto Scheduled | งานสุขภัณฑ์ | 15 days | 4 |  |  |  | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | October 18, 2018 05:00 PM | November 01, 2018 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 395 days | 395 days | 395 days
164 | Yes | CMU1.6.3.7.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 135FS+135 days |  |  | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | August 23, 2019 05:00 PM | September 06, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 395 days | 395 days | 395 days | Sanitary-Plumber
165 | Yes | CMU1.6.4 | Auto Scheduled | งานระบบสุขาภิบาล ชั้นใต้ดิน | 501 days | 3 |  |  |  | April 6, 2019 8:00 AM | August 18, 2020 5:00 PM | October 17, 2018 05:00 PM | February 29, 2020 05:00 PM | May 24, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 44 days | 44 days
166 | Yes | CMU1.6.4.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 126 days | 4 |  |  |  | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | October 18, 2018 05:00 PM | February 20, 2019 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 419 days | 419 days | 419 days
167 | Yes | CMU1.6.4.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 140FS+15 days |  |  | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 08, 2019 05:00 PM | August 11, 2019 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 419 days | 419 days | 419 days | Sanitary-Plumber
168 | Yes | CMU1.6.4.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 126 days | 4 |  |  |  | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | October 20, 2018 05:00 PM | February 22, 2019 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 44 days | 44 days
169 | Yes | CMU1.6.4.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 144FS+15 days |  | 170FS+300 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 06, 2019 05:00 PM | August 09, 2019 05:00 PM | May 24, 2019 05:00 PM | September 26, 2019 05:00 PM | As Soon As Possible |  | No | 44 days | 44 days | 0 days | Sanitary-Plumber
170 | Yes | CMU1.6.4.3 | Auto Scheduled | งานระบบระบายน้ำฝน | 75 days | 4 | 169FS+300 days |  |  | June 5, 2020 8:00 AM | August 18, 2020 5:00 PM | June 05, 2020 05:00 PM | August 18, 2020 05:00 PM | July 23, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 44 days | 44 days | 44 days | Sanitary-Plumber
171 | Yes | CMU1.6.5 | Auto Scheduled | งานระบบไฟฟ้า ชั้นใต้ดิน | 147 days | 3 |  |  |  | April 8, 2020 8:00 AM | September 1, 2020 5:00 PM | October 18, 2018 05:00 PM | March 13, 2019 05:00 PM | May 12, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 30 days | 30 days | 30 days
172 | Yes | CMU1.6.5.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 60 days | 4 | 174FS+7 days |  |  | July 4, 2020 8:00 AM | September 1, 2020 5:00 PM | July 04, 2020 05:00 PM | September 01, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 30 days | 30 days | 30 days | Electrician
173 | Yes | CMU1.6.5.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 60 days | 4 | 174FS+7 days |  |  | July 4, 2020 8:00 AM | September 1, 2020 5:00 PM | July 04, 2020 05:00 PM | September 01, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 30 days | 30 days | 30 days | Electrician
174 | Yes | CMU1.6.5.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 154SS |  | 173FS+7 days,172FS+7 days | April 8, 2020 8:00 AM | June 26, 2020 5:00 PM | April 08, 2020 05:00 PM | June 26, 2020 05:00 PM | May 12, 2020 05:00 PM | July 30, 2020 05:00 PM | As Soon As Possible |  | No | 30 days | 30 days | 0 days | Electrician
175 | Yes | CMU1.6.5.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 154SS |  |  | April 8, 2020 8:00 AM | June 26, 2020 5:00 PM | April 09, 2020 05:00 PM | June 27, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 97 days | 97 days | 97 days | Electrician
176 | Yes | CMU1.6.5.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 154SS |  |  | April 8, 2020 8:00 AM | June 26, 2020 5:00 PM | April 09, 2020 05:00 PM | June 27, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 97 days | 97 days | 97 days | Electrician
177 | Yes | CMU1.6.6 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้นใต้ดิน | 165 days | 3 | 154SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 08, 2020 05:00 PM | September 19, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | Skilled carpenter
178 | Yes | CMU1.7 | Auto Scheduled | หมวดงานระบบคอมพิวเตอร์และแจ้งเหตุเพลิงไหม้ | 670 days | 2 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
179 | Yes | CMU1.7.1 | Auto Scheduled | งานระบบคอมพิวเตอร์ | 670 days | 3 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
180 | Yes | CMU1.7.1.1 | Auto Scheduled | ชั้นที่ 4 | 160 days | 4 | 36FS+14 days |  | 181 | November 30, 2018 8:00 AM | May 8, 2019 5:00 PM | November 30, 2018 05:00 PM | May 08, 2019 05:00 PM | April 24, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
181 | Yes | CMU1.7.1.2 | Auto Scheduled | ชั้นที่ 3 | 175 days | 4 | 180 | 182 | 182 | May 9, 2019 8:00 AM | October 30, 2019 5:00 PM | May 09, 2019 05:00 PM | October 30, 2019 05:00 PM | April 09, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
182 | Yes | CMU1.7.1.3 | Auto Scheduled | ชั้นที่ 2 | 175 days | 4 | 181 | 183 | 183,184 | October 31, 2019 8:00 AM | April 22, 2020 5:00 PM | October 31, 2019 05:00 PM | April 22, 2020 05:00 PM | April 09, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
183 | Yes | CMU1.7.1.4 | Auto Scheduled | ชั้นที่ 1 | 160 days | 4 | 182 | 180 |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 23, 2020 05:00 PM | September 29, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
184 | Yes | CMU1.7.1.5 | Auto Scheduled | ชั้นใต้ดิน | 160 days | 4 | 182 | 183SS |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 23, 2020 05:00 PM | September 29, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
185 | Yes | CMU1.7.2 | Auto Scheduled | ระบบแจ้งเหตุเพลิงไหม้ | 670 days | 3 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
186 | Yes | CMU1.7.2.1 | Auto Scheduled | ชั้นที่ 4 | 160 days | 4 | 36FS+14 days |  | 187 | November 30, 2018 8:00 AM | May 8, 2019 5:00 PM | November 30, 2018 05:00 PM | May 08, 2019 05:00 PM | April 24, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
187 | Yes | CMU1.7.2.2 | Auto Scheduled | ชั้นที่ 3 | 175 days | 4 | 186 | 188 | 188 | May 9, 2019 8:00 AM | October 30, 2019 5:00 PM | May 09, 2019 05:00 PM | October 30, 2019 05:00 PM | April 09, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
188 | Yes | CMU1.7.2.3 | Auto Scheduled | ชั้นที่ 2 | 175 days | 4 | 187 | 189 | 189,190 | October 31, 2019 8:00 AM | April 22, 2020 5:00 PM | October 31, 2019 05:00 PM | April 22, 2020 05:00 PM | April 09, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
189 | Yes | CMU1.7.2.4 | Auto Scheduled | ชั้นที่ 1 | 160 days | 4 | 188 | 186 |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 23, 2020 05:00 PM | September 29, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
190 | Yes | CMU1.7.2.5 | Auto Scheduled | ชั้นใต้ดิน | 160 days | 4 | 188 | 189SS |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 23, 2020 05:00 PM | September 29, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
191 | Yes | CMU1.8 | Auto Scheduled | หมวดงานสีภายนอก งานซ่อมแซมและตกแต่งภายนอกอาคาร | 660 days | 2 |  |  |  | November 30, 2018 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | August 06, 2020 05:00 PM | December 16, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 507 days | 12 days | 12 days
192 | Yes | CMU1.8.1 | Auto Scheduled | งานสีภายนอกและงานซ่อมแซมพื้นผิวภายนอกอาคาร | 660 days | 3 |  |  |  | November 30, 2018 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | August 06, 2020 05:00 PM | December 16, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 507 days | 12 days | 12 days
193 | Yes | CMU1.8.1.1 | Auto Scheduled | งานขัดลอกสีทาผนังเดิม | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 08, 2020 05:00 PM | September 19, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
194 | Yes | CMU1.8.1.2 | Auto Scheduled | น้ำยาทาปูนเก่า (สีรองพื้น) | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 08, 2020 05:00 PM | September 19, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
195 | Yes | CMU1.8.1.3 | Auto Scheduled | งานทาสีภายนอก (ทา 2 เที่ยว) ไม่รวมชั้นใต้ดิน | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 08, 2020 05:00 PM | September 19, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
196 | Yes | CMU1.8.1.4 | Auto Scheduled | งานทำความสะอาดและซ่อมแซมผนังกรุอิฐโชว์แนว (อ้างอิงราคางานขัดลอกสี) | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 08, 2020 05:00 PM | September 19, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
197 | Yes | CMU1.8.1.5 | Auto Scheduled | น้ำยาเคลือบผิวผนังอิฐโชว์แนว (อ้างอิงค่าทาน้ำยากันเชื้อรา) | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 08, 2020 05:00 PM | September 19, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
198 | Yes | CMU1.8.1.6 | Auto Scheduled | งานรื้อถอนแผ่นวัสดุกันซึมหลังคาดาดฟ้า (รื้อขนไป) | 90 days | 4 | 36FS+14 days |  |  | November 30, 2018 8:00 AM | February 27, 2019 5:00 PM | December 01, 2018 05:00 PM | February 28, 2019 05:00 PM | July 08, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 582 days | 582 days | 582 days | General worker
199 | Yes | CMU1.8.1.7 | Auto Scheduled | งานแผ่นวัสดุกันซึมแบบเป่าไฟผิวทราย | 90 days | 4 | 36FS+14 days |  |  | November 30, 2018 8:00 AM | February 27, 2019 5:00 PM | December 02, 2018 05:00 PM | March 01, 2019 05:00 PM | July 08, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 582 days | 582 days | 582 days | General worker
200 | Yes | CMU1.8.1.8 | Auto Scheduled | งานกันซึมชนิด Polyurethane สูตรน้ำมัน ชนิดยืดหยุ่นสูงเป็นพิเศษ | 90 days | 4 | 36FS+14 days |  |  | November 30, 2018 8:00 AM | February 27, 2019 5:00 PM | December 02, 2018 05:00 PM | March 01, 2019 05:00 PM | July 08, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 582 days | 582 days | 582 days | General worker
201 | Yes | CMU1.8.2 | Auto Scheduled | งานตกแต่งภายนอกอาคาร | 165 days | 3 |  |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | October 19, 2018 05:00 PM | April 01, 2019 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 12 days | 12 days | 12 days
202 | Yes | CMU1.8.2.1 | Auto Scheduled | ตะแกรงเหล็กฉีกกันนก XS-32 | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 08, 2020 05:00 PM | September 19, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
203 | Yes | CMU1.9 | Auto Scheduled | หมวดงานบริเวณ | 165 days | 2 |  |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | October 20, 2018 05:00 PM | April 02, 2019 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 12 days | 12 days | 12 days
204 | Yes | CMU1.9.1 | Auto Scheduled | งานรื้อถอน งานบริเวณ | 165 days | 3 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 08, 2020 05:00 PM | September 19, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
205 | Yes | CMU1.9.2 | Auto Scheduled | งานโครงสร้างวิศวกรรม งานบริเวณ | 165 days | 3 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 08, 2020 05:00 PM | September 19, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
206 | Yes | CMU1.9.3 | Auto Scheduled | งานสถาปัตยกรรม งานบริเวณ | 165 days | 3 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 08, 2020 05:00 PM | September 19, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
207 | Yes | CMU1.9.4 | Auto Scheduled | งานระบบไฟฟ้า งานบริเวณ | 165 days | 3 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 08, 2020 05:00 PM | September 19, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | Electrician
208 | Yes | CMU1.10 | Auto Scheduled | หมวดงานครุภัณฑ์จัดซื้อ | 670 days | 2 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
209 | Yes | CMU1.10.1 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัว | 510 days | 3 |  |  |  | April 14, 2019 8:00 AM | September 4, 2020 5:00 PM | October 17, 2018 05:00 PM | March 09, 2020 05:00 PM | May 15, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 522 days | 27 days | 27 days
210 | Yes | CMU1.10.1.1 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้นใต้ดิน | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | August 24, 2020 05:00 PM | September 07, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
211 | Yes | CMU1.10.1.2 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้น 1 | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | August 25, 2020 05:00 PM | September 08, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
212 | Yes | CMU1.10.1.3 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้น 2 | 15 days | 4 | 121FS-15 days |  |  | March 24, 2020 8:00 AM | April 7, 2020 5:00 PM | March 25, 2020 05:00 PM | April 08, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Skilled carpenter
213 | Yes | CMU1.10.1.4 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้น 3 | 15 days | 4 | 92FS-15 days |  |  | September 26, 2019 8:00 AM | October 10, 2019 5:00 PM | September 29, 2019 05:00 PM | October 13, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Skilled carpenter
214 | Yes | CMU1.10.1.5 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้น 4 | 15 days | 4 | 63 |  |  | April 14, 2019 8:00 AM | April 28, 2019 5:00 PM | April 18, 2019 05:00 PM | May 02, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 522 days | 522 days | 522 days | Skilled carpenter
215 | Yes | CMU1.10.2 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ | 525 days | 3 |  |  |  | March 30, 2019 8:00 AM | September 4, 2020 5:00 PM | October 17, 2018 05:00 PM | March 24, 2020 05:00 PM | April 30, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 522 days | 27 days | 27 days
216 | Yes | CMU1.10.2.1 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ ชั้น 1 | 30 days | 4 | 152FS-45 days |  |  | August 6, 2020 8:00 AM | September 4, 2020 5:00 PM | August 09, 2020 05:00 PM | September 07, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
217 | Yes | CMU1.10.2.2 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ ชั้น 2 | 30 days | 4 | 121FS-30 days |  |  | March 9, 2020 8:00 AM | April 7, 2020 5:00 PM | March 09, 2020 05:00 PM | April 07, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Skilled carpenter
218 | Yes | CMU1.10.2.3 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ ชั้น 3 | 30 days | 4 | 92FS-30 days |  |  | September 11, 2019 8:00 AM | October 10, 2019 5:00 PM | September 12, 2019 05:00 PM | October 11, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Skilled carpenter
219 | Yes | CMU1.10.2.4 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ ชั้น 4 | 30 days | 4 | 63FS-15 days |  |  | March 30, 2019 8:00 AM | April 28, 2019 5:00 PM | March 31, 2019 05:00 PM | April 29, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 522 days | 522 days | 522 days | Skilled carpenter
220 | Yes | CMU1.10.3 | Auto Scheduled | งานผ้าม่าน | 510 days | 3 |  |  |  | April 14, 2019 8:00 AM | September 4, 2020 5:00 PM | October 17, 2018 05:00 PM | March 09, 2020 05:00 PM | May 15, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 522 days | 27 days | 27 days
221 | Yes | CMU1.10.3.1 | Auto Scheduled | งานผ้าม่าน ชั้น 1 | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | August 23, 2020 05:00 PM | September 06, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
222 | Yes | CMU1.10.3.2 | Auto Scheduled | งานผ้าม่าน ชั้น 2 | 15 days | 4 | 121FS-15 days |  |  | March 24, 2020 8:00 AM | April 7, 2020 5:00 PM | March 26, 2020 05:00 PM | April 09, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Skilled carpenter
223 | Yes | CMU1.10.3.3 | Auto Scheduled | งานผ้าม่าน ชั้น 3 | 15 days | 4 | 92FS-15 days |  |  | September 26, 2019 8:00 AM | October 10, 2019 5:00 PM | September 27, 2019 05:00 PM | October 11, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Skilled carpenter
224 | Yes | CMU1.10.3.4 | Auto Scheduled | งานผ้าม่าน ชั้น 4 | 15 days | 4 | 63 |  |  | April 14, 2019 8:00 AM | April 28, 2019 5:00 PM | April 18, 2019 05:00 PM | May 02, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 522 days | 522 days | 522 days | Skilled carpenter
225 | Yes | CMU1.10.4 | Auto Scheduled | งานป้าย | 510 days | 3 |  |  |  | April 14, 2019 8:00 AM | September 4, 2020 5:00 PM | October 17, 2018 05:00 PM | March 09, 2020 05:00 PM | May 15, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 522 days | 27 days | 27 days
226 | Yes | CMU1.10.4.1 | Auto Scheduled | งานป้าย ชั้นใต้ดิน | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | August 23, 2020 05:00 PM | September 06, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
227 | Yes | CMU1.10.4.2 | Auto Scheduled | งานป้าย ชั้น 1 | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | August 25, 2020 05:00 PM | September 08, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
228 | Yes | CMU1.10.4.3 | Auto Scheduled | งานป้าย ชั้น 2 | 15 days | 4 | 121FS-15 days |  |  | March 24, 2020 8:00 AM | April 7, 2020 5:00 PM | March 25, 2020 05:00 PM | April 08, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Skilled carpenter
229 | Yes | CMU1.10.4.4 | Auto Scheduled | งานป้าย ชั้น 3 | 15 days | 4 | 92FS-15 days |  |  | September 26, 2019 8:00 AM | October 10, 2019 5:00 PM | September 29, 2019 05:00 PM | October 13, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Skilled carpenter
230 | Yes | CMU1.10.4.5 | Auto Scheduled | งานป้าย ชั้น 4 | 15 days | 4 | 63 |  |  | April 14, 2019 8:00 AM | April 28, 2019 5:00 PM | April 17, 2019 05:00 PM | May 01, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 522 days | 522 days | 522 days | Skilled carpenter
231 | Yes | CMU1.10.5 | Auto Scheduled | งานอื่นๆ | 15 days | 3 |  |  |  | August 6, 2020 8:00 AM | August 20, 2020 5:00 PM | October 17, 2018 05:00 PM | October 31, 2018 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 42 days | 42 days | 42 days
232 | Yes | CMU1.10.5.1 | Auto Scheduled | ตู้อลูมิเนียมพับขึ้นรูป พ่นสี ครอบตู้กดน้ำ | 15 days | 4 | 152FS-45 days |  |  | August 6, 2020 8:00 AM | August 20, 2020 5:00 PM | August 09, 2020 05:00 PM | August 23, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 42 days | 42 days | 42 days | General worker
233 | Yes | CMU1.10.6 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ | 670 days | 3 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
234 | Yes | CMU1.10.6.1 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้นใต้ดิน | 160 days | 4 | 236 |  |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 25, 2020 05:00 PM | October 01, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
235 | Yes | CMU1.10.6.2 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้น 1 | 160 days | 4 | 236 |  |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 25, 2020 05:00 PM | October 01, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
236 | Yes | CMU1.10.6.3 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้น 2 | 175 days | 4 | 237 |  | 235,234 | October 31, 2019 8:00 AM | April 22, 2020 5:00 PM | November 02, 2019 05:00 PM | April 24, 2020 05:00 PM | March 12, 2020 05:00 PM | September 02, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
237 | Yes | CMU1.10.6.4 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้น 3 | 175 days | 4 | 238 |  | 236 | May 9, 2019 8:00 AM | October 30, 2019 5:00 PM | May 11, 2019 05:00 PM | November 01, 2019 05:00 PM | March 12, 2020 05:00 PM | September 02, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
238 | Yes | CMU1.10.6.5 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้น 4 | 160 days | 4 | 36FS+14 days |  | 237 | November 30, 2018 8:00 AM | May 8, 2019 5:00 PM | December 01, 2018 05:00 PM | May 09, 2019 05:00 PM | March 27, 2020 05:00 PM | September 02, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
239 | Yes | CMU1.10.7 | Auto Scheduled | งานระบบเครื่องเสียงประกาศ (ใช้ลำโพงของเดิม) | 539 days | 3 |  |  |  | April 7, 2019 8:00 AM | September 26, 2020 5:00 PM | October 17, 2018 05:00 PM | April 07, 2020 05:00 PM | April 16, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 530 days | 5 days | 5 days
240 | Yes | CMU1.10.7.1 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้นใต้ดิน | 7 days | 4 | 241 |  |  | September 20, 2020 8:00 AM | September 26, 2020 5:00 PM | September 22, 2020 05:00 PM | September 28, 2020 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 5 days | 5 days | 5 days | Electrician
241 | Yes | CMU1.10.7.2 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้น 1 | 7 days | 4 | 152FS-7 days |  | 240 | September 13, 2020 8:00 AM | September 19, 2020 5:00 PM | September 13, 2020 05:00 PM | September 19, 2020 05:00 PM | September 09, 2020 05:00 PM | September 15, 2020 05:00 PM | As Soon As Possible |  | No | 5 days | 5 days | 0 days | Electrician
242 | Yes | CMU1.10.7.3 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้น 2 | 7 days | 4 | 121FS-7 days |  |  | April 1, 2020 8:00 AM | April 7, 2020 5:00 PM | April 01, 2020 05:00 PM | April 07, 2020 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Electrician
243 | Yes | CMU1.10.7.4 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้น 3 | 7 days | 4 | 92FS-7 days |  |  | October 4, 2019 8:00 AM | October 10, 2019 5:00 PM | October 05, 2019 05:00 PM | October 11, 2019 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Electrician
244 | Yes | CMU1.10.7.5 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้น 4 | 7 days | 4 | 63FS-7 days |  |  | April 7, 2019 8:00 AM | April 13, 2019 5:00 PM | April 13, 2019 05:00 PM | April 19, 2019 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 537 days | 537 days | 537 days | Electrician
245 | Yes | CMU1.10.8 | Auto Scheduled | งานระบบกล้องวงจรปิด (ใช้กล้องวงจรปิดของเดิม) | 539 days | 3 |  |  |  | April 7, 2019 8:00 AM | September 26, 2020 5:00 PM | October 17, 2018 05:00 PM | April 07, 2020 05:00 PM | April 16, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 530 days | 5 days | 5 days
246 | Yes | CMU1.10.8.1 | Auto Scheduled | งานกล้องวงจรปิด ชั้นใต้ดิน | 7 days | 4 | 247 |  |  | September 20, 2020 8:00 AM | September 26, 2020 5:00 PM | September 22, 2020 05:00 PM | September 28, 2020 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 5 days | 5 days | 5 days | Electrician
247 | Yes | CMU1.10.8.2 | Auto Scheduled | งานกล้องวงจรปิด ชั้น 1 | 7 days | 4 | 152FS-7 days |  | 246 | September 13, 2020 8:00 AM | September 19, 2020 5:00 PM | September 13, 2020 05:00 PM | September 19, 2020 05:00 PM | September 09, 2020 05:00 PM | September 15, 2020 05:00 PM | As Soon As Possible |  | No | 5 days | 5 days | 0 days | Electrician
248 | Yes | CMU1.10.8.3 | Auto Scheduled | งานกล้องวงจรปิด ชั้น 2 | 7 days | 4 | 121FS-7 days |  |  | April 1, 2020 8:00 AM | April 7, 2020 5:00 PM | April 03, 2020 05:00 PM | April 09, 2020 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Electrician
249 | Yes | CMU1.10.8.4 | Auto Scheduled | งานกล้องวงจรปิด ชั้น 3 | 7 days | 4 | 92FS-7 days |  |  | October 4, 2019 8:00 AM | October 10, 2019 5:00 PM | October 06, 2019 05:00 PM | October 12, 2019 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Electrician
250 | Yes | CMU1.10.8.5 | Auto Scheduled | งานกล้องวงจรปิด ชั้น 4 | 7 days | 4 | 63FS-7 days |  |  | April 7, 2019 8:00 AM | April 13, 2019 5:00 PM | April 10, 2019 05:00 PM | April 16, 2019 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 537 days | 537 days | 537 days | Electrician

## solutoion_2
ID | Active | WBS | Task_Mode | Name | Duration | Outline_Level | Predecessors | Predecessors2 | Successors | Start_Date | Finish_Date | Early_Start | Early_Finish | Late_Start | Late_Finish | Constraint_Type | Constraint_Date | Summary | Start_Slack | Finish_Slack | Free_Slack | Resource_Names
1 | Yes | CMU1 | Auto Scheduled | โครงการปรับปรุงสำนักหอสมุด มหาวิทยาลัยเชียงใหม่ | 716 days | 1 |  |  |  | October 17, 2018 8:00 AM | October 1, 2020 5:00 PM | October 17, 2018 05:00 PM | October 01, 2020 05:00 PM | October 21, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 0 days | 0 days | 0 days
2 | Yes | CMU1.1 | Auto Scheduled | หมวดเตรียมการ | 675 days | 2 |  |  |  | October 17, 2018 8:00 AM | August 21, 2020 5:00 PM | October 17, 2018 05:00 PM | August 21, 2020 05:00 PM | December 01, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 41 days | 41 days | 41 days
3 | Yes | CMU1.1.1 | Auto Scheduled | งานอาคารสนามและผังบริเวณโครงการ | 14 days | 3 | 4FS-7 days |  |  | October 26, 2018 8:00 AM | November 8, 2018 5:00 PM | November 04, 2018 05:00 PM | November 17, 2018 05:00 PM | September 22, 2020 05:00 PM | October 05, 2020 05:00 PM | Start No Earlier Than | Oct 24 '18 | No | 693 days | 693 days | 693 days | Engineer
4 | Yes | CMU1.1.2 | Auto Scheduled | งานเชื่อมต่อระบบสาธารณูปโภคโครงการ | 16 days | 3 |  |  | 3FS-7 days | October 17, 2018 8:00 AM | November 1, 2018 5:00 PM | October 23, 2018 05:00 PM | November 07, 2018 05:00 PM | September 13, 2020 05:00 PM | September 28, 2020 05:00 PM | As Soon As Possible |  | No | 693 days | 693 days | 0 days | Engineer
5 | Yes | CMU1.1.3 | Auto Scheduled | งานตรวจทดสอบระบบภายในอาคารก่อนดำเนินการปรับปรุง | 675 days | 3 |  |  |  | October 17, 2018 8:00 AM | August 21, 2020 5:00 PM | October 17, 2018 05:00 PM | August 21, 2020 05:00 PM | December 01, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 41 days | 41 days | 41 days
6 | Yes | CMU1.1.3.1 | Auto Scheduled | ชั้นที่ 4 | 15 days | 4 |  |  | 7FS+150 days | October 17, 2018 8:00 AM | October 31, 2018 5:00 PM | October 18, 2018 05:00 PM | November 01, 2018 05:00 PM | December 01, 2018 05:00 PM | December 15, 2018 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
7 | Yes | CMU1.1.3.2 | Auto Scheduled | ชั้นที่ 3 | 15 days | 4 | 6FS+150 days |  | 8FS+150 days | March 31, 2019 8:00 AM | April 14, 2019 5:00 PM | April 04, 2019 05:00 PM | April 18, 2019 05:00 PM | May 15, 2019 05:00 PM | May 29, 2019 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
8 | Yes | CMU1.1.3.3 | Auto Scheduled | ชั้นที่ 2 | 15 days | 4 | 7FS+150 days |  | 9FS+150 days | September 12, 2019 8:00 AM | September 26, 2019 5:00 PM | September 24, 2019 05:00 PM | October 08, 2019 05:00 PM | October 27, 2019 05:00 PM | November 10, 2019 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
9 | Yes | CMU1.1.3.4 | Auto Scheduled | ชั้นที่ 1 | 15 days | 4 | 8FS+150 days |  | 10FS+150 days | February 24, 2020 8:00 AM | March 9, 2020 5:00 PM | March 12, 2020 05:00 PM | March 26, 2020 05:00 PM | April 09, 2020 05:00 PM | April 23, 2020 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
10 | Yes | CMU1.1.3.5 | Auto Scheduled | ชั้นใต้ดินและภายนอก | 15 days | 4 | 9FS+150 days |  |  | August 7, 2020 8:00 AM | August 21, 2020 5:00 PM | September 05, 2020 05:00 PM | September 19, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 41 days | Engineer
11 | Yes | CMU1.1.4 | Auto Scheduled | งานสำรวจอุปกรณ์ไฟฟ้า, สุขภัณฑ์และครุภัณฑ์ (ของเดิม) ก่อนดำเนินการปรับปรุง | 675 days | 3 |  |  |  | October 17, 2018 8:00 AM | August 21, 2020 5:00 PM | October 17, 2018 05:00 PM | August 21, 2020 05:00 PM | December 01, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 41 days | 41 days | 41 days
12 | Yes | CMU1.1.4.1 | Auto Scheduled | ชั้นที่ 4 | 15 days | 4 |  |  | 13FS+150 days | October 17, 2018 8:00 AM | October 31, 2018 5:00 PM | October 19, 2018 05:00 PM | November 02, 2018 05:00 PM | December 01, 2018 05:00 PM | December 15, 2018 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
13 | Yes | CMU1.1.4.2 | Auto Scheduled | ชั้นที่ 3 | 15 days | 4 | 12FS+150 days |  | 14FS+150 days | March 31, 2019 8:00 AM | April 14, 2019 5:00 PM | April 05, 2019 05:00 PM | April 19, 2019 05:00 PM | May 15, 2019 05:00 PM | May 29, 2019 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
14 | Yes | CMU1.1.4.3 | Auto Scheduled | ชั้นที่ 2 | 15 days | 4 | 13FS+150 days |  | 15FS+150 days | September 12, 2019 8:00 AM | September 26, 2019 5:00 PM | September 23, 2019 05:00 PM | October 07, 2019 05:00 PM | October 27, 2019 05:00 PM | November 10, 2019 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
15 | Yes | CMU1.1.4.4 | Auto Scheduled | ชั้นที่ 1 | 15 days | 4 | 14FS+150 days |  | 16FS+150 days | February 24, 2020 8:00 AM | March 9, 2020 5:00 PM | March 11, 2020 05:00 PM | March 25, 2020 05:00 PM | April 09, 2020 05:00 PM | April 23, 2020 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
16 | Yes | CMU1.1.4.5 | Auto Scheduled | ชั้นใต้ดินและภายนอก | 15 days | 4 | 15FS+150 days |  |  | August 7, 2020 8:00 AM | August 21, 2020 5:00 PM | September 02, 2020 05:00 PM | September 16, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 41 days | Engineer
17 | Yes | CMU1.1.5 | Auto Scheduled | งานเอกสารขออนุมัติใช้วัสดุ, Shop Drawing และครุภัณฑ์ของโครงการ | 106 days | 3 |  |  |  | October 17, 2018 8:00 AM | January 30, 2019 5:00 PM | October 20, 2018 05:00 PM | February 02, 2019 05:00 PM | June 22, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 610 days | 610 days | 610 days
18 | Yes | CMU1.1.5.1 | Auto Scheduled | แบบ Shop Drawing ชั้นที่ 4 | 20 days | 4 |  |  | 19,25SS+14 days,26SS+14 days | October 17, 2018 8:00 AM | November 5, 2018 5:00 PM | October 17, 2018 05:00 PM | November 05, 2018 05:00 PM | October 01, 2018 05:00 PM | October 20, 2018 05:00 PM | As Soon As Possible |  | No | 610 days | 610 days | 0 days | Engineer
19 | Yes | CMU1.1.5.2 | Auto Scheduled | แบบ Shop Drawing ชั้นที่ 3 | 20 days | 4 | 18 |  | 20FS-7 days | November 6, 2018 8:00 AM | November 25, 2018 5:00 PM | November 12, 2018 05:00 PM | December 01, 2018 05:00 PM | July 13, 2020 05:00 PM | August 01, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
20 | Yes | CMU1.1.5.3 | Auto Scheduled | แบบ Shop Drawing ชั้นที่ 2 | 20 days | 4 | 19FS-7 days |  | 21FS-7 days | November 19, 2018 8:00 AM | December 8, 2018 5:00 PM | December 02, 2018 05:00 PM | December 21, 2018 05:00 PM | July 26, 2020 05:00 PM | August 14, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
21 | Yes | CMU1.1.5.4 | Auto Scheduled | แบบ Shop Drawing ชั้นที่ 1 | 20 days | 4 | 20FS-7 days |  | 22FS-7 days | December 2, 2018 8:00 AM | December 21, 2018 5:00 PM | December 19, 2018 05:00 PM | January 07, 2019 05:00 PM | August 08, 2020 05:00 PM | August 27, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
22 | Yes | CMU1.1.5.5 | Auto Scheduled | แบบ Shop Drawing ชั้นใต้ดิน | 20 days | 4 | 21FS-7 days |  | 23FS-7 days | December 15, 2018 8:00 AM | January 3, 2019 5:00 PM | January 06, 2019 05:00 PM | January 25, 2019 05:00 PM | August 21, 2020 05:00 PM | September 09, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
23 | Yes | CMU1.1.5.6 | Auto Scheduled | แบบ Shop Drawing ภายนอกอาคาร | 20 days | 4 | 22FS-7 days |  | 24FS-7 days | December 28, 2018 8:00 AM | January 16, 2019 5:00 PM | January 21, 2019 05:00 PM | February 09, 2019 05:00 PM | September 03, 2020 05:00 PM | September 22, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
24 | Yes | CMU1.1.5.7 | Auto Scheduled | แบบ Shop Drawing landscape | 20 days | 4 | 23FS-7 days |  |  | January 10, 2019 8:00 AM | January 29, 2019 5:00 PM | February 09, 2019 05:00 PM | February 28, 2019 05:00 PM | September 16, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 611 days | Engineer
25 | Yes | CMU1.1.5.8 | Auto Scheduled | แบบ Shop Drawing งานปรับปรุง ครุภัณฑ์ | 92 days | 4 | 18SS+14 days |  |  | October 31, 2018 8:00 AM | January 30, 2019 5:00 PM | November 05, 2018 05:00 PM | February 04, 2019 05:00 PM | July 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 610 days | 610 days | 610 days | Engineer
26 | Yes | CMU1.1.5.9 | Auto Scheduled | แบบ Shop Drawing งานจัดซื้อครุภัณฑ์ | 92 days | 4 | 18SS+14 days |  |  | October 31, 2018 8:00 AM | January 30, 2019 5:00 PM | November 06, 2018 05:00 PM | February 05, 2019 05:00 PM | July 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 610 days | 610 days | 610 days | Engineer
27 | Yes | CMU1.1.6 | Auto Scheduled | งานตรวจทดสอบระบบ, งานอบรมผู้ใช้อาคาร และ As-Built Drawing | 30 days | 3 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 21, 2018 05:00 PM | November 19, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 686 days | 686 days | 686 days
28 | Yes | CMU1.1.6.1 | Auto Scheduled | ชั้นที่ 4 | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 24, 2018 05:00 PM | November 22, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
29 | Yes | CMU1.1.6.2 | Auto Scheduled | ชั้นที่ 3 | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
30 | Yes | CMU1.1.6.3 | Auto Scheduled | ชั้นที่ 2 | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 20, 2018 05:00 PM | November 18, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
31 | Yes | CMU1.1.6.4 | Auto Scheduled | ชั้นที่ 1 | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 25, 2018 05:00 PM | November 23, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
32 | Yes | CMU1.1.6.5 | Auto Scheduled | ชั้นใต้ดิน | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 22, 2018 05:00 PM | November 20, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
33 | Yes | CMU1.1.6.6 | Auto Scheduled | ทั้งอาคาร | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 21, 2018 05:00 PM | November 19, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
34 | Yes | CMU1.1.7 | Auto Scheduled | งานบริหารงานก่อสร้างและงานอื่น ๆ | 0 days | 3 |  |  |  | October 17, 2018 8:00 AM | October 17, 2018 8:00 AM | October 23, 2018 05:00 PM | October 22, 2018 05:00 PM | October 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 716 days | 716 days | 716 days | Engineer
35 | Yes | CMU1.2 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้น 4 | 471 days | 2 |  |  |  | October 17, 2018 8:00 AM | January 30, 2020 5:00 PM | October 17, 2018 05:00 PM | January 30, 2020 05:00 PM | June 23, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 0 days | 245 days | 0 days
36 | Yes | CMU1.2.1 | Auto Scheduled | งานรื้อถอน ชั้น 4 (รื้อขนไป) | 30 days | 3 |  |  | 39FS+45 days,40FS+45 days,51,63SS+14 days,80,109,140,180FS+14 days,186FS+14 days,198FS+14 days,199FS+14 days,200FS+14 days,238FS+14 days | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 17, 2018 05:00 PM | November 15, 2018 05:00 PM | March 11, 2018 05:00 PM | April 09, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | General worker
37 | Yes | CMU1.2.2 | Auto Scheduled | งานสถาปัตยกรรม ชั้น 4 | 396 days | 3 |  |  |  | December 31, 2018 8:00 AM | January 30, 2020 5:00 PM | October 17, 2018 05:00 PM | November 16, 2019 05:00 PM | September 06, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 326 days | 245 days | 245 days
38 | Yes | CMU1.2.2.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 39,41,42 |  |  | March 1, 2019 8:00 AM | March 30, 2019 5:00 PM | March 08, 2019 05:00 PM | April 06, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 551 days | Skilled carpenter
39 | Yes | CMU1.2.2.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 36FS+45 days |  | 38,43 | December 31, 2018 8:00 AM | February 28, 2019 5:00 PM | January 03, 2019 05:00 PM | March 03, 2019 05:00 PM | July 15, 2020 05:00 PM | September 12, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 0 days | General worker
40 | Yes | CMU1.2.2.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 36FS+45 days |  | 41,42 | December 31, 2018 8:00 AM | January 29, 2019 5:00 PM | January 01, 2019 05:00 PM | January 30, 2019 05:00 PM | August 14, 2020 05:00 PM | September 12, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 0 days | General worker
41 | Yes | CMU1.2.2.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 40 |  | 38,43 | January 30, 2019 8:00 AM | February 28, 2019 5:00 PM | February 02, 2019 05:00 PM | March 03, 2019 05:00 PM | August 14, 2020 05:00 PM | September 12, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 0 days | Skilled carpenter
42 | Yes | CMU1.2.2.5 | Auto Scheduled | งานบันได | 30 days | 4 | 40 |  | 38,43 | January 30, 2019 8:00 AM | February 28, 2019 5:00 PM | February 02, 2019 05:00 PM | March 03, 2019 05:00 PM | August 14, 2020 05:00 PM | September 12, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 0 days | General worker
43 | Yes | CMU1.2.2.6 | Auto Scheduled | งานสี | 30 days | 4 | 39,41,42 |  |  | March 1, 2019 8:00 AM | March 30, 2019 5:00 PM | March 06, 2019 05:00 PM | April 04, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 551 days | General worker
44 | Yes | CMU1.2.2.7 | Auto Scheduled | งานสุขภัณฑ์ | 315 days | 4 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 19, 2018 05:00 PM | August 29, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
45 | Yes | CMU1.2.2.7.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 46FS+135 days |  | 47FS+135 days | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | September 11, 2019 05:00 PM | September 25, 2019 05:00 PM | April 24, 2020 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
46 | Yes | CMU1.2.2.7.2 | Auto Scheduled | ZONE T-2 กลาง | 15 days | 5 | 51,55 |  | 45FS+135 days | March 22, 2019 8:00 AM | April 5, 2019 5:00 PM | April 05, 2019 05:00 PM | April 19, 2019 05:00 PM | November 26, 2019 05:00 PM | December 10, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
47 | Yes | CMU1.2.2.7.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 15 days | 5 | 45FS+135 days |  |  | January 16, 2020 8:00 AM | January 30, 2020 5:00 PM | February 13, 2020 05:00 PM | February 27, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 245 days | Sanitary-Plumber
48 | Yes | CMU1.2.3 | Auto Scheduled | งานระบบสุขาภิบาล ชั้น 4 | 408 days | 3 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
49 | Yes | CMU1.2.3.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
50 | Yes | CMU1.2.3.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 51FS+15 days |  | 52FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 16, 2019 05:00 PM | August 19, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
51 | Yes | CMU1.2.3.1.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 36 |  | 50FS+15 days,46,55SS | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 23, 2018 05:00 PM | March 28, 2019 05:00 PM | August 25, 2019 05:00 PM | December 28, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
52 | Yes | CMU1.2.3.1.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 50FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 07, 2019 05:00 PM | January 10, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
53 | Yes | CMU1.2.3.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
54 | Yes | CMU1.2.3.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 55FS+15 days |  | 56FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 19, 2019 05:00 PM | August 22, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
55 | Yes | CMU1.2.3.2.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 51SS |  | 54FS+15 days,46 | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 26, 2018 05:00 PM | March 31, 2019 05:00 PM | August 25, 2019 05:00 PM | December 28, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
56 | Yes | CMU1.2.3.2.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 54FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 12, 2019 05:00 PM | January 15, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
57 | Yes | CMU1.2.4 | Auto Scheduled | งานระบบไฟฟ้า ชั้น 4 | 117 days | 3 |  |  |  | November 30, 2018 8:00 AM | March 26, 2019 5:00 PM | October 20, 2018 05:00 PM | February 13, 2019 05:00 PM | June 11, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 555 days | 555 days | 555 days
58 | Yes | CMU1.2.4.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 30 days | 4 | 60FS+7 days |  |  | February 25, 2019 8:00 AM | March 26, 2019 5:00 PM | March 02, 2019 05:00 PM | March 31, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 555 days | 555 days | 555 days | Electrician
59 | Yes | CMU1.2.4.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 30 days | 4 | 60FS+7 days |  |  | February 25, 2019 8:00 AM | March 26, 2019 5:00 PM | March 01, 2019 05:00 PM | March 30, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 555 days | 555 days | 555 days | Electrician
60 | Yes | CMU1.2.4.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 63SS+30 days |  | 58FS+7 days,59FS+7 days | November 30, 2018 8:00 AM | February 17, 2019 5:00 PM | December 02, 2018 05:00 PM | February 19, 2019 05:00 PM | June 11, 2020 05:00 PM | August 29, 2020 05:00 PM | As Soon As Possible |  | No | 555 days | 555 days | 0 days | Electrician
61 | Yes | CMU1.2.4.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 63SS+30 days |  |  | November 30, 2018 8:00 AM | February 17, 2019 5:00 PM | December 03, 2018 05:00 PM | February 20, 2019 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 592 days | 592 days | 592 days | Electrician
62 | Yes | CMU1.2.4.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 63SS+30 days |  |  | November 30, 2018 8:00 AM | February 17, 2019 5:00 PM | December 06, 2018 05:00 PM | February 23, 2019 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 592 days | 592 days | 592 days | Electrician
63 | Yes | CMU1.2.5 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้น 4 | 165 days | 3 | 36SS+14 days |  | 62SS+30 days,60SS+30 days,61SS+30 days,65,214,219FS-15 days,224,230,244FS-7 days,250FS-7 days | October 31, 2018 8:00 AM | April 13, 2019 5:00 PM | October 31, 2018 05:00 PM | April 13, 2019 05:00 PM | June 19, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Skilled carpenter
64 | Yes | CMU1.3 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้น 3 | 441 days | 2 |  |  |  | November 16, 2018 8:00 AM | January 30, 2020 5:00 PM | October 17, 2018 05:00 PM | December 31, 2019 05:00 PM | July 23, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 149 days | 245 days | 149 days
65 | Yes | CMU1.3.1 | Auto Scheduled | งานรื้อถอน ชั้น 3 (รื้อขนไป) | 30 days | 3 | 63 | 121 | 68FS+45 days,69FS+45 days,92SS | April 14, 2019 8:00 AM | May 13, 2019 5:00 PM | April 14, 2019 05:00 PM | May 13, 2019 05:00 PM | July 19, 2018 05:00 PM | August 17, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | General worker
66 | Yes | CMU1.3.2 | Auto Scheduled | งานสถาปัตยกรรม ชั้น 3 | 315 days | 3 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 19, 2018 05:00 PM | August 29, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
67 | Yes | CMU1.3.2.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 68,70,71 |  |  | August 27, 2019 8:00 AM | September 25, 2019 5:00 PM | August 29, 2019 05:00 PM | September 27, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 372 days | Skilled carpenter
68 | Yes | CMU1.3.2.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 65FS+45 days |  | 67,72 | June 28, 2019 8:00 AM | August 26, 2019 5:00 PM | June 28, 2019 05:00 PM | August 26, 2019 05:00 PM | October 02, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 0 days | General worker
69 | Yes | CMU1.3.2.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 65FS+45 days |  | 70,71 | June 28, 2019 8:00 AM | July 27, 2019 5:00 PM | June 28, 2019 05:00 PM | July 27, 2019 05:00 PM | April 15, 2019 05:00 PM | May 14, 2019 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 0 days | General worker
70 | Yes | CMU1.3.2.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 69 |  | 67,72 | July 28, 2019 8:00 AM | August 26, 2019 5:00 PM | July 28, 2019 05:00 PM | August 26, 2019 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 0 days | Skilled carpenter
71 | Yes | CMU1.3.2.5 | Auto Scheduled | งานบันได | 30 days | 4 | 69 |  | 67,72 | July 28, 2019 8:00 AM | August 26, 2019 5:00 PM | July 28, 2019 05:00 PM | August 26, 2019 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 0 days | General worker
72 | Yes | CMU1.3.2.6 | Auto Scheduled | งานสี | 30 days | 4 | 68,70,71 |  |  | August 27, 2019 8:00 AM | September 25, 2019 5:00 PM | August 29, 2019 05:00 PM | September 27, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 372 days | General worker
73 | Yes | CMU1.3.2.7 | Auto Scheduled | งานสุขภัณฑ์ | 315 days | 4 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 21, 2018 05:00 PM | August 31, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
74 | Yes | CMU1.3.2.7.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 75FS+135 days |  | 76FS+135 days | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | August 22, 2019 05:00 PM | September 05, 2019 05:00 PM | April 24, 2020 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
75 | Yes | CMU1.3.2.7.2 | Auto Scheduled | ZONE T-2 กลาง | 15 days | 5 | 80,84 |  | 74FS+135 days | March 22, 2019 8:00 AM | April 5, 2019 5:00 PM | March 23, 2019 05:00 PM | April 06, 2019 05:00 PM | November 26, 2019 05:00 PM | December 10, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
76 | Yes | CMU1.3.2.7.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 15 days | 5 | 74FS+135 days |  |  | January 16, 2020 8:00 AM | January 30, 2020 5:00 PM | January 23, 2020 05:00 PM | February 06, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 245 days | Sanitary-Plumber
77 | Yes | CMU1.3.3 | Auto Scheduled | งานระบบสุขาภิบาล ชั้น 3 | 408 days | 3 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
78 | Yes | CMU1.3.3.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
79 | Yes | CMU1.3.3.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 80FS+15 days |  | 81FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 12, 2019 05:00 PM | August 15, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
80 | Yes | CMU1.3.3.1.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 36 |  | 79FS+15 days,84SS,75 | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 16, 2018 05:00 PM | March 21, 2019 05:00 PM | January 09, 2019 05:00 PM | May 14, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
81 | Yes | CMU1.3.3.1.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 79FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 04, 2019 05:00 PM | January 07, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
82 | Yes | CMU1.3.3.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
83 | Yes | CMU1.3.3.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 84FS+15 days |  | 85FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 10, 2019 05:00 PM | August 13, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
84 | Yes | CMU1.3.3.2.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 80SS |  | 83FS+15 days,75 | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 16, 2018 05:00 PM | March 21, 2019 05:00 PM | January 09, 2019 05:00 PM | May 14, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
85 | Yes | CMU1.3.3.2.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 83FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 03, 2019 05:00 PM | January 06, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
86 | Yes | CMU1.3.4 | Auto Scheduled | งานระบบไฟฟ้า ชั้น 3 | 147 days | 3 |  |  |  | May 14, 2019 8:00 AM | October 7, 2019 5:00 PM | October 20, 2018 05:00 PM | March 15, 2019 05:00 PM | May 12, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 360 days | 360 days | 360 days
87 | Yes | CMU1.3.4.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 60 days | 4 | 89FS+7 days |  |  | August 9, 2019 8:00 AM | October 7, 2019 5:00 PM | August 13, 2019 05:00 PM | October 11, 2019 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 360 days | 360 days | 360 days | Electrician
88 | Yes | CMU1.3.4.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 60 days | 4 | 89FS+7 days |  |  | August 9, 2019 8:00 AM | October 7, 2019 5:00 PM | August 16, 2019 05:00 PM | October 14, 2019 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 360 days | 360 days | 360 days | Electrician
89 | Yes | CMU1.3.4.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 92SS+30 days |  | 88FS+7 days,87FS+7 days | May 14, 2019 8:00 AM | August 1, 2019 5:00 PM | May 16, 2019 05:00 PM | August 03, 2019 05:00 PM | May 12, 2020 05:00 PM | July 30, 2020 05:00 PM | As Soon As Possible |  | No | 360 days | 360 days | 0 days | Electrician
90 | Yes | CMU1.3.4.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 92SS+30 days |  |  | May 14, 2019 8:00 AM | August 1, 2019 5:00 PM | May 20, 2019 05:00 PM | August 07, 2019 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 427 days | 427 days | 427 days | Electrician
91 | Yes | CMU1.3.4.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 92SS+30 days |  |  | May 14, 2019 8:00 AM | August 1, 2019 5:00 PM | May 22, 2019 05:00 PM | August 09, 2019 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 427 days | 427 days | 427 days | Electrician
92 | Yes | CMU1.3.5 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้น 3 | 180 days | 3 | 65SS |  | 91SS+30 days,90SS+30 days,89SS+30 days,94,213FS-15 days,218FS-30 days,223FS-15 days,229FS-15 days,243FS-7 days,249FS-7 days | April 14, 2019 8:00 AM | October 10, 2019 5:00 PM | April 15, 2019 05:00 PM | October 11, 2019 05:00 PM | October 12, 2019 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Skilled carpenter
93 | Yes | CMU1.4 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้น 2 | 509 days | 2 |  |  |  | November 16, 2018 8:00 AM | April 7, 2020 5:00 PM | October 17, 2018 05:00 PM | March 08, 2020 05:00 PM | May 16, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 177 days | 177 days
94 | Yes | CMU1.4.1 | Auto Scheduled | งานรื้อถอน ชั้น 2 (รื้อขนไป) | 30 days | 3 | 92 | 152 | 97FS+45 days,98FS+45 days,121SS | October 11, 2019 8:00 AM | November 9, 2019 5:00 PM | October 12, 2019 05:00 PM | November 10, 2019 05:00 PM | June 04, 2018 05:00 PM | July 03, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | General worker
95 | Yes | CMU1.4.2 | Auto Scheduled | งานสถาปัตยกรรม ชั้น 2 | 368 days | 3 |  |  |  | March 22, 2019 8:00 AM | March 23, 2020 5:00 PM | October 17, 2018 05:00 PM | October 19, 2019 05:00 PM | October 04, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 192 days | 192 days
96 | Yes | CMU1.4.2.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 97,99,100 |  |  | February 23, 2020 8:00 AM | March 23, 2020 5:00 PM | March 02, 2020 05:00 PM | March 31, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 192 days | Skilled carpenter
97 | Yes | CMU1.4.2.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 94FS+45 days |  | 96,101 | December 25, 2019 8:00 AM | February 22, 2020 5:00 PM | December 26, 2019 05:00 PM | February 23, 2020 05:00 PM | February 09, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 0 days | General worker
98 | Yes | CMU1.4.2.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 94FS+45 days |  | 99,100 | December 25, 2019 8:00 AM | January 23, 2020 5:00 PM | December 28, 2019 05:00 PM | January 26, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 0 days | General worker
99 | Yes | CMU1.4.2.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 98 |  | 96,101 | January 24, 2020 8:00 AM | February 22, 2020 5:00 PM | January 29, 2020 05:00 PM | February 27, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 0 days | Skilled carpenter
100 | Yes | CMU1.4.2.5 | Auto Scheduled | งานบันได | 30 days | 4 | 98 |  | 96,101 | January 24, 2020 8:00 AM | February 22, 2020 5:00 PM | January 29, 2020 05:00 PM | February 27, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 0 days | General worker
101 | Yes | CMU1.4.2.6 | Auto Scheduled | งานสี | 30 days | 4 | 97,99,100 |  |  | February 23, 2020 8:00 AM | March 23, 2020 5:00 PM | March 03, 2020 05:00 PM | April 01, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 192 days | General worker
102 | Yes | CMU1.4.2.7 | Auto Scheduled | งานสุขภัณฑ์ | 315 days | 4 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 20, 2018 05:00 PM | August 30, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
103 | Yes | CMU1.4.2.7.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 104FS+135 days |  | 105FS+135 days | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | September 03, 2019 05:00 PM | September 17, 2019 05:00 PM | April 24, 2020 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
104 | Yes | CMU1.4.2.7.2 | Auto Scheduled | ZONE T-2 กลาง | 15 days | 5 | 113,109 |  | 103FS+135 days | March 22, 2019 8:00 AM | April 5, 2019 5:00 PM | April 02, 2019 05:00 PM | April 16, 2019 05:00 PM | November 26, 2019 05:00 PM | December 10, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
105 | Yes | CMU1.4.2.7.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 15 days | 5 | 103FS+135 days |  |  | January 16, 2020 8:00 AM | January 30, 2020 5:00 PM | February 05, 2020 05:00 PM | February 19, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 245 days | Sanitary-Plumber
106 | Yes | CMU1.4.3 | Auto Scheduled | งานระบบสุขาภิบาล ชั้น 2 | 408 days | 3 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
107 | Yes | CMU1.4.3.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
108 | Yes | CMU1.4.3.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 109FS+15 days |  | 110FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 13, 2019 05:00 PM | August 16, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
109 | Yes | CMU1.4.3.1.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 36 |  | 113SS,104,108FS+15 days | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 21, 2018 05:00 PM | March 26, 2019 05:00 PM | August 25, 2019 05:00 PM | December 28, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
110 | Yes | CMU1.4.3.1.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 108FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 04, 2019 05:00 PM | January 07, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
111 | Yes | CMU1.4.3.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
112 | Yes | CMU1.4.3.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 113FS+15 days |  | 114FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 19, 2019 05:00 PM | August 22, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
113 | Yes | CMU1.4.3.2.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 109SS |  | 104,112FS+15 days | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 24, 2018 05:00 PM | March 29, 2019 05:00 PM | August 25, 2019 05:00 PM | December 28, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
114 | Yes | CMU1.4.3.2.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 112FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 10, 2019 05:00 PM | January 13, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
115 | Yes | CMU1.4.4 | Auto Scheduled | งานระบบไฟฟ้า ชั้น 2 | 147 days | 3 |  |  |  | November 10, 2019 8:00 AM | April 4, 2020 5:00 PM | October 20, 2018 05:00 PM | March 15, 2019 05:00 PM | May 12, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 180 days | 180 days | 180 days
116 | Yes | CMU1.4.4.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 60 days | 4 | 118FS+7 days |  |  | February 5, 2020 8:00 AM | April 4, 2020 5:00 PM | February 08, 2020 05:00 PM | April 07, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 180 days | 180 days | 180 days | Electrician
117 | Yes | CMU1.4.4.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 60 days | 4 | 118FS+7 days |  |  | February 5, 2020 8:00 AM | April 4, 2020 5:00 PM | February 10, 2020 05:00 PM | April 09, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 180 days | 180 days | 180 days | Electrician
118 | Yes | CMU1.4.4.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 121SS+30 days |  | 117FS+7 days,116FS+7 days | November 10, 2019 8:00 AM | January 28, 2020 5:00 PM | November 12, 2019 05:00 PM | January 30, 2020 05:00 PM | May 12, 2020 05:00 PM | July 30, 2020 05:00 PM | As Soon As Possible |  | No | 180 days | 180 days | 0 days | Electrician
119 | Yes | CMU1.4.4.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 121SS+30 days |  |  | November 10, 2019 8:00 AM | January 28, 2020 5:00 PM | November 15, 2019 05:00 PM | February 02, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 247 days | 247 days | 247 days | Electrician
120 | Yes | CMU1.4.4.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 121SS+30 days |  |  | November 10, 2019 8:00 AM | January 28, 2020 5:00 PM | November 15, 2019 05:00 PM | February 02, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 247 days | 247 days | 247 days | Electrician
121 | Yes | CMU1.4.5 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้น 2 | 180 days | 3 | 94SS |  | 120SS+30 days,119SS+30 days,118SS+30 days,123,212FS-15 days,217FS-30 days,222FS-15 days,228FS-15 days,242FS-7 days,248FS-7 days | October 11, 2019 8:00 AM | April 7, 2020 5:00 PM | October 12, 2019 05:00 PM | April 08, 2020 05:00 PM | June 04, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Skilled carpenter
122 | Yes | CMU1.5 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้น 1 | 686 days | 2 |  |  |  | November 16, 2018 8:00 AM | October 1, 2020 5:00 PM | October 17, 2018 05:00 PM | September 01, 2020 05:00 PM | November 20, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 0 days | 0 days
123 | Yes | CMU1.5.1 | Auto Scheduled | งานรื้อถอน ชั้น 1 (รื้อขนไป) | 30 days | 3 | 121 | 63 | 124,127FS+45 days,128FS+45 days,131FS+45 days,152SS,193SS,194SS,195SS,196SS,197SS,202SS,204SS,205SS,206SS,207SS | April 8, 2020 8:00 AM | May 7, 2020 5:00 PM | April 09, 2020 05:00 PM | May 08, 2020 05:00 PM | July 19, 2018 05:00 PM | August 17, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | General worker
124 | Yes | CMU1.5.2 | Auto Scheduled | งานโครงสร้างวิศวกรรม ชั้น 1 | 75 days | 3 | 123 |  |  | May 8, 2020 8:00 AM | July 21, 2020 5:00 PM | May 09, 2020 05:00 PM | July 22, 2020 05:00 PM | July 23, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 72 days | 72 days | 72 days | General worker
125 | Yes | CMU1.5.3 | Auto Scheduled | งานสถาปัตยกรรม ชั้น 1 | 548 days | 3 |  |  |  | March 22, 2019 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | April 16, 2020 05:00 PM | April 07, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 12 days | 12 days
126 | Yes | CMU1.5.3.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 127,129,130 |  |  | August 21, 2020 8:00 AM | September 19, 2020 5:00 PM | August 22, 2020 05:00 PM | September 20, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | Skilled carpenter
127 | Yes | CMU1.5.3.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 123FS+45 days |  | 126,132 | June 22, 2020 8:00 AM | August 20, 2020 5:00 PM | June 23, 2020 05:00 PM | August 21, 2020 05:00 PM | October 02, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
128 | Yes | CMU1.5.3.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 123FS+45 days |  | 129,130 | June 22, 2020 8:00 AM | July 21, 2020 5:00 PM | June 23, 2020 05:00 PM | July 22, 2020 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
129 | Yes | CMU1.5.3.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 128 |  | 126,132 | July 22, 2020 8:00 AM | August 20, 2020 5:00 PM | July 23, 2020 05:00 PM | August 21, 2020 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | Skilled carpenter
130 | Yes | CMU1.5.3.5 | Auto Scheduled | งานบันได | 30 days | 4 | 128 |  | 126,132 | July 22, 2020 8:00 AM | August 20, 2020 5:00 PM | July 23, 2020 05:00 PM | August 21, 2020 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
131 | Yes | CMU1.5.3.6 | Auto Scheduled | งานตกแต่งอื่น ๆ | 60 days | 4 | 123FS+45 days |  |  | June 22, 2020 8:00 AM | August 20, 2020 5:00 PM | June 23, 2020 05:00 PM | August 21, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 42 days | 42 days | 42 days | General worker
132 | Yes | CMU1.5.3.7 | Auto Scheduled | งานสี | 30 days | 4 | 127,129,130 |  |  | August 21, 2020 8:00 AM | September 19, 2020 5:00 PM | August 22, 2020 05:00 PM | September 20, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
133 | Yes | CMU1.5.3.8 | Auto Scheduled | งานสุขภัณฑ์ | 315 days | 4 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 21, 2018 05:00 PM | August 31, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
134 | Yes | CMU1.5.3.8.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 135FS+135 days |  | 136FS+135 days | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | August 23, 2019 05:00 PM | September 06, 2019 05:00 PM | April 24, 2020 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
135 | Yes | CMU1.5.3.8.2 | Auto Scheduled | ZONE T-2 กลาง | 15 days | 5 | 140,144 |  | 134FS+135 days,164FS+135 days | March 22, 2019 8:00 AM | April 5, 2019 5:00 PM | March 24, 2019 05:00 PM | April 07, 2019 05:00 PM | November 26, 2019 05:00 PM | December 10, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
136 | Yes | CMU1.5.3.8.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 15 days | 5 | 134FS+135 days |  |  | January 16, 2020 8:00 AM | January 30, 2020 5:00 PM | January 22, 2020 05:00 PM | February 05, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 245 days | Sanitary-Plumber
137 | Yes | CMU1.5.4 | Auto Scheduled | งานระบบสุขาภิบาล ชั้น 1 | 408 days | 3 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 278 days | 44 days
138 | Yes | CMU1.5.4.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 278 days | 44 days
139 | Yes | CMU1.5.4.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 140FS+15 days |  | 141FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 11, 2019 05:00 PM | August 14, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
140 | Yes | CMU1.5.4.1.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 36 |  | 139FS+15 days,144SS,135,167FS+15 days | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 16, 2018 05:00 PM | March 21, 2019 05:00 PM | January 03, 2019 05:00 PM | May 08, 2019 05:00 PM | As Soon As Possible |  | No | 44 days | 44 days | 0 days | Sanitary-Plumber
141 | Yes | CMU1.5.4.1.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 139FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 03, 2019 05:00 PM | January 06, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
142 | Yes | CMU1.5.4.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 278 days | 44 days
143 | Yes | CMU1.5.4.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 144FS+15 days |  | 145FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 11, 2019 05:00 PM | August 14, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
144 | Yes | CMU1.5.4.2.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 140SS |  | 143FS+15 days,135,169FS+15 days | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 16, 2018 05:00 PM | March 21, 2019 05:00 PM | January 03, 2019 05:00 PM | May 08, 2019 05:00 PM | As Soon As Possible |  | No | 44 days | 44 days | 0 days | Sanitary-Plumber
145 | Yes | CMU1.5.4.2.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 143FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 01, 2019 05:00 PM | January 04, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
146 | Yes | CMU1.5.5 | Auto Scheduled | งานระบบไฟฟ้า ชั้น 1 | 147 days | 3 |  |  |  | May 8, 2020 8:00 AM | October 1, 2020 5:00 PM | October 20, 2018 05:00 PM | March 15, 2019 05:00 PM | May 12, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 0 days | 0 days | 0 days
147 | Yes | CMU1.5.5.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 60 days | 4 | 149FS+7 days |  |  | August 3, 2020 8:00 AM | October 1, 2020 5:00 PM | August 04, 2020 05:00 PM | October 02, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Electrician
148 | Yes | CMU1.5.5.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 60 days | 4 | 149FS+7 days |  |  | August 3, 2020 8:00 AM | October 1, 2020 5:00 PM | August 04, 2020 05:00 PM | October 02, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Electrician
149 | Yes | CMU1.5.5.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 152SS+30 days |  | 148FS+7 days,147FS+7 days | May 8, 2020 8:00 AM | July 26, 2020 5:00 PM | May 09, 2020 05:00 PM | July 27, 2020 05:00 PM | May 12, 2020 05:00 PM | July 30, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Electrician
150 | Yes | CMU1.5.5.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 152SS+30 days |  |  | May 8, 2020 8:00 AM | July 26, 2020 5:00 PM | May 09, 2020 05:00 PM | July 27, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 67 days | 67 days | 67 days | Electrician
151 | Yes | CMU1.5.5.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 152SS+30 days |  |  | May 8, 2020 8:00 AM | July 26, 2020 5:00 PM | May 09, 2020 05:00 PM | July 27, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 67 days | 67 days | 67 days | Electrician
152 | Yes | CMU1.5.6 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้น 1 | 165 days | 3 | 123SS |  | 151SS+30 days,150SS+30 days,149SS+30 days,154SS,211FS-30 days,210FS-30 days,216FS-45 days,221FS-30 days,227FS-30 days,226FS-30 days,232FS-45 days,241FS-7 days,247FS-7 days | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 09, 2020 05:00 PM | September 20, 2020 05:00 PM | November 26, 2019 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Skilled carpenter
153 | Yes | CMU1.6 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้นใต้ดิน | 533 days | 2 |  |  |  | April 6, 2019 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | April 01, 2020 05:00 PM | April 22, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 12 days | 12 days
154 | Yes | CMU1.6.1 | Auto Scheduled | งานรื้อถอน ชั้นใต้ดิน (รื้อขนไป) | 30 days | 3 | 152SS |  | 155,158FS+45 days,159FS+45 days,177SS,176SS,175SS,174SS | April 8, 2020 8:00 AM | May 7, 2020 5:00 PM | April 09, 2020 05:00 PM | May 08, 2020 05:00 PM | November 26, 2019 05:00 PM | December 25, 2019 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
155 | Yes | CMU1.6.2 | Auto Scheduled | งานโครงสร้างวิศวกรรม ชั้นใต้ดิน | 75 days | 3 | 154 |  |  | May 8, 2020 8:00 AM | July 21, 2020 5:00 PM | May 09, 2020 05:00 PM | July 22, 2020 05:00 PM | July 23, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 72 days | 72 days | 72 days | General worker
156 | Yes | CMU1.6.3 | Auto Scheduled | งานสถาปัตยกรรม ชั้นใต้ดิน | 398 days | 3 |  |  |  | August 19, 2019 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | November 18, 2019 05:00 PM | September 04, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 320 days | 12 days | 12 days
157 | Yes | CMU1.6.3.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 158,160,161 |  |  | August 21, 2020 8:00 AM | September 19, 2020 5:00 PM | September 02, 2020 05:00 PM | October 01, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | Skilled carpenter
158 | Yes | CMU1.6.3.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 154FS+45 days |  | 157,162 | June 22, 2020 8:00 AM | August 20, 2020 5:00 PM | June 23, 2020 05:00 PM | August 21, 2020 05:00 PM | February 09, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
159 | Yes | CMU1.6.3.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 154FS+45 days |  | 160,161 | June 22, 2020 8:00 AM | July 21, 2020 5:00 PM | July 04, 2020 05:00 PM | August 02, 2020 05:00 PM | August 22, 2020 05:00 PM | September 20, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
160 | Yes | CMU1.6.3.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 159 |  | 157,162 | July 22, 2020 8:00 AM | August 20, 2020 5:00 PM | August 03, 2020 05:00 PM | September 01, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | Skilled carpenter
161 | Yes | CMU1.6.3.5 | Auto Scheduled | งานบันได | 30 days | 4 | 159 |  | 157,162 | July 22, 2020 8:00 AM | August 20, 2020 5:00 PM | August 03, 2020 05:00 PM | September 01, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
162 | Yes | CMU1.6.3.6 | Auto Scheduled | งานสี | 30 days | 4 | 158,160,161 |  |  | August 21, 2020 8:00 AM | September 19, 2020 5:00 PM | September 02, 2020 05:00 PM | October 01, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
163 | Yes | CMU1.6.3.7 | Auto Scheduled | งานสุขภัณฑ์ | 15 days | 4 |  |  |  | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | October 18, 2018 05:00 PM | November 01, 2018 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 395 days | 395 days | 395 days
164 | Yes | CMU1.6.3.7.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 135FS+135 days |  |  | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | August 24, 2019 05:00 PM | September 07, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 395 days | 395 days | 395 days | Sanitary-Plumber
165 | Yes | CMU1.6.4 | Auto Scheduled | งานระบบสุขาภิบาล ชั้นใต้ดิน | 501 days | 3 |  |  |  | April 6, 2019 8:00 AM | August 18, 2020 5:00 PM | October 17, 2018 05:00 PM | February 29, 2020 05:00 PM | May 24, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 44 days | 44 days
166 | Yes | CMU1.6.4.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 126 days | 4 |  |  |  | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | October 20, 2018 05:00 PM | February 22, 2019 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 419 days | 419 days | 419 days
167 | Yes | CMU1.6.4.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 140FS+15 days |  |  | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 10, 2019 05:00 PM | August 13, 2019 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 419 days | 419 days | 419 days | Sanitary-Plumber
168 | Yes | CMU1.6.4.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 126 days | 4 |  |  |  | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | October 21, 2018 05:00 PM | February 23, 2019 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 44 days | 44 days
169 | Yes | CMU1.6.4.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 144FS+15 days |  | 170FS+300 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 06, 2019 05:00 PM | August 09, 2019 05:00 PM | May 24, 2019 05:00 PM | September 26, 2019 05:00 PM | As Soon As Possible |  | No | 44 days | 44 days | 0 days | Sanitary-Plumber
170 | Yes | CMU1.6.4.3 | Auto Scheduled | งานระบบระบายน้ำฝน | 75 days | 4 | 169FS+300 days |  |  | June 5, 2020 8:00 AM | August 18, 2020 5:00 PM | June 05, 2020 05:00 PM | August 18, 2020 05:00 PM | July 23, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 44 days | 44 days | 44 days | Sanitary-Plumber
171 | Yes | CMU1.6.5 | Auto Scheduled | งานระบบไฟฟ้า ชั้นใต้ดิน | 147 days | 3 |  |  |  | April 8, 2020 8:00 AM | September 1, 2020 5:00 PM | October 21, 2018 05:00 PM | March 16, 2019 05:00 PM | May 12, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 30 days | 30 days | 30 days
172 | Yes | CMU1.6.5.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 60 days | 4 | 174FS+7 days |  |  | July 4, 2020 8:00 AM | September 1, 2020 5:00 PM | July 05, 2020 05:00 PM | September 02, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 30 days | 30 days | 30 days | Electrician
173 | Yes | CMU1.6.5.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 60 days | 4 | 174FS+7 days |  |  | July 4, 2020 8:00 AM | September 1, 2020 5:00 PM | July 05, 2020 05:00 PM | September 02, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 30 days | 30 days | 30 days | Electrician
174 | Yes | CMU1.6.5.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 154SS |  | 173FS+7 days,172FS+7 days | April 8, 2020 8:00 AM | June 26, 2020 5:00 PM | April 09, 2020 05:00 PM | June 27, 2020 05:00 PM | May 12, 2020 05:00 PM | July 30, 2020 05:00 PM | As Soon As Possible |  | No | 30 days | 30 days | 0 days | Electrician
175 | Yes | CMU1.6.5.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 154SS |  |  | April 8, 2020 8:00 AM | June 26, 2020 5:00 PM | April 11, 2020 05:00 PM | June 29, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 97 days | 97 days | 97 days | Electrician
176 | Yes | CMU1.6.5.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 154SS |  |  | April 8, 2020 8:00 AM | June 26, 2020 5:00 PM | April 11, 2020 05:00 PM | June 29, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 97 days | 97 days | 97 days | Electrician
177 | Yes | CMU1.6.6 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้นใต้ดิน | 165 days | 3 | 154SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 09, 2020 05:00 PM | September 20, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | Skilled carpenter
178 | Yes | CMU1.7 | Auto Scheduled | หมวดงานระบบคอมพิวเตอร์และแจ้งเหตุเพลิงไหม้ | 670 days | 2 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
179 | Yes | CMU1.7.1 | Auto Scheduled | งานระบบคอมพิวเตอร์ | 670 days | 3 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
180 | Yes | CMU1.7.1.1 | Auto Scheduled | ชั้นที่ 4 | 160 days | 4 | 36FS+14 days |  | 181 | November 30, 2018 8:00 AM | May 8, 2019 5:00 PM | November 30, 2018 05:00 PM | May 08, 2019 05:00 PM | April 24, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
181 | Yes | CMU1.7.1.2 | Auto Scheduled | ชั้นที่ 3 | 175 days | 4 | 180 | 182 | 182 | May 9, 2019 8:00 AM | October 30, 2019 5:00 PM | May 09, 2019 05:00 PM | October 30, 2019 05:00 PM | April 09, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
182 | Yes | CMU1.7.1.3 | Auto Scheduled | ชั้นที่ 2 | 175 days | 4 | 181 | 183 | 183,184 | October 31, 2019 8:00 AM | April 22, 2020 5:00 PM | October 31, 2019 05:00 PM | April 22, 2020 05:00 PM | April 09, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
183 | Yes | CMU1.7.1.4 | Auto Scheduled | ชั้นที่ 1 | 160 days | 4 | 182 | 180 |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 23, 2020 05:00 PM | September 29, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
184 | Yes | CMU1.7.1.5 | Auto Scheduled | ชั้นใต้ดิน | 160 days | 4 | 182 | 183SS |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 23, 2020 05:00 PM | September 29, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
185 | Yes | CMU1.7.2 | Auto Scheduled | ระบบแจ้งเหตุเพลิงไหม้ | 670 days | 3 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
186 | Yes | CMU1.7.2.1 | Auto Scheduled | ชั้นที่ 4 | 160 days | 4 | 36FS+14 days |  | 187 | November 30, 2018 8:00 AM | May 8, 2019 5:00 PM | November 30, 2018 05:00 PM | May 08, 2019 05:00 PM | April 24, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
187 | Yes | CMU1.7.2.2 | Auto Scheduled | ชั้นที่ 3 | 175 days | 4 | 186 | 188 | 188 | May 9, 2019 8:00 AM | October 30, 2019 5:00 PM | May 09, 2019 05:00 PM | October 30, 2019 05:00 PM | April 09, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
188 | Yes | CMU1.7.2.3 | Auto Scheduled | ชั้นที่ 2 | 175 days | 4 | 187 | 189 | 189,190 | October 31, 2019 8:00 AM | April 22, 2020 5:00 PM | October 31, 2019 05:00 PM | April 22, 2020 05:00 PM | April 09, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
189 | Yes | CMU1.7.2.4 | Auto Scheduled | ชั้นที่ 1 | 160 days | 4 | 188 | 186 |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 23, 2020 05:00 PM | September 29, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
190 | Yes | CMU1.7.2.5 | Auto Scheduled | ชั้นใต้ดิน | 160 days | 4 | 188 | 189SS |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 23, 2020 05:00 PM | September 29, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
191 | Yes | CMU1.8 | Auto Scheduled | หมวดงานสีภายนอก งานซ่อมแซมและตกแต่งภายนอกอาคาร | 660 days | 2 |  |  |  | November 30, 2018 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | August 06, 2020 05:00 PM | December 16, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 507 days | 12 days | 12 days
192 | Yes | CMU1.8.1 | Auto Scheduled | งานสีภายนอกและงานซ่อมแซมพื้นผิวภายนอกอาคาร | 660 days | 3 |  |  |  | November 30, 2018 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | August 06, 2020 05:00 PM | December 16, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 507 days | 12 days | 12 days
193 | Yes | CMU1.8.1.1 | Auto Scheduled | งานขัดลอกสีทาผนังเดิม | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 09, 2020 05:00 PM | September 20, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
194 | Yes | CMU1.8.1.2 | Auto Scheduled | น้ำยาทาปูนเก่า (สีรองพื้น) | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 09, 2020 05:00 PM | September 20, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
195 | Yes | CMU1.8.1.3 | Auto Scheduled | งานทาสีภายนอก (ทา 2 เที่ยว) ไม่รวมชั้นใต้ดิน | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 09, 2020 05:00 PM | September 20, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
196 | Yes | CMU1.8.1.4 | Auto Scheduled | งานทำความสะอาดและซ่อมแซมผนังกรุอิฐโชว์แนว (อ้างอิงราคางานขัดลอกสี) | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 09, 2020 05:00 PM | September 20, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
197 | Yes | CMU1.8.1.5 | Auto Scheduled | น้ำยาเคลือบผิวผนังอิฐโชว์แนว (อ้างอิงค่าทาน้ำยากันเชื้อรา) | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 09, 2020 05:00 PM | September 20, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
198 | Yes | CMU1.8.1.6 | Auto Scheduled | งานรื้อถอนแผ่นวัสดุกันซึมหลังคาดาดฟ้า (รื้อขนไป) | 90 days | 4 | 36FS+14 days |  |  | November 30, 2018 8:00 AM | February 27, 2019 5:00 PM | December 02, 2018 05:00 PM | March 01, 2019 05:00 PM | July 08, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 582 days | 582 days | 582 days | General worker
199 | Yes | CMU1.8.1.7 | Auto Scheduled | งานแผ่นวัสดุกันซึมแบบเป่าไฟผิวทราย | 90 days | 4 | 36FS+14 days |  |  | November 30, 2018 8:00 AM | February 27, 2019 5:00 PM | December 03, 2018 05:00 PM | March 02, 2019 05:00 PM | July 08, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 582 days | 582 days | 582 days | General worker
200 | Yes | CMU1.8.1.8 | Auto Scheduled | งานกันซึมชนิด Polyurethane สูตรน้ำมัน ชนิดยืดหยุ่นสูงเป็นพิเศษ | 90 days | 4 | 36FS+14 days |  |  | November 30, 2018 8:00 AM | February 27, 2019 5:00 PM | December 02, 2018 05:00 PM | March 01, 2019 05:00 PM | July 08, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 582 days | 582 days | 582 days | General worker
201 | Yes | CMU1.8.2 | Auto Scheduled | งานตกแต่งภายนอกอาคาร | 165 days | 3 |  |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | October 20, 2018 05:00 PM | April 02, 2019 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 12 days | 12 days | 12 days
202 | Yes | CMU1.8.2.1 | Auto Scheduled | ตะแกรงเหล็กฉีกกันนก XS-32 | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 09, 2020 05:00 PM | September 20, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
203 | Yes | CMU1.9 | Auto Scheduled | หมวดงานบริเวณ | 165 days | 2 |  |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | October 21, 2018 05:00 PM | April 03, 2019 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 12 days | 12 days | 12 days
204 | Yes | CMU1.9.1 | Auto Scheduled | งานรื้อถอน งานบริเวณ | 165 days | 3 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 09, 2020 05:00 PM | September 20, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
205 | Yes | CMU1.9.2 | Auto Scheduled | งานโครงสร้างวิศวกรรม งานบริเวณ | 165 days | 3 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 09, 2020 05:00 PM | September 20, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
206 | Yes | CMU1.9.3 | Auto Scheduled | งานสถาปัตยกรรม งานบริเวณ | 165 days | 3 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 09, 2020 05:00 PM | September 20, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
207 | Yes | CMU1.9.4 | Auto Scheduled | งานระบบไฟฟ้า งานบริเวณ | 165 days | 3 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 09, 2020 05:00 PM | September 20, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | Electrician
208 | Yes | CMU1.10 | Auto Scheduled | หมวดงานครุภัณฑ์จัดซื้อ | 670 days | 2 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
209 | Yes | CMU1.10.1 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัว | 510 days | 3 |  |  |  | April 14, 2019 8:00 AM | September 4, 2020 5:00 PM | October 17, 2018 05:00 PM | March 09, 2020 05:00 PM | May 15, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 522 days | 27 days | 27 days
210 | Yes | CMU1.10.1.1 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้นใต้ดิน | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | August 25, 2020 05:00 PM | September 08, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
211 | Yes | CMU1.10.1.2 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้น 1 | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | August 27, 2020 05:00 PM | September 10, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
212 | Yes | CMU1.10.1.3 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้น 2 | 15 days | 4 | 121FS-15 days |  |  | March 24, 2020 8:00 AM | April 7, 2020 5:00 PM | March 26, 2020 05:00 PM | April 09, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Skilled carpenter
213 | Yes | CMU1.10.1.4 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้น 3 | 15 days | 4 | 92FS-15 days |  |  | September 26, 2019 8:00 AM | October 10, 2019 5:00 PM | October 01, 2019 05:00 PM | October 15, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Skilled carpenter
214 | Yes | CMU1.10.1.5 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้น 4 | 15 days | 4 | 63 |  |  | April 14, 2019 8:00 AM | April 28, 2019 5:00 PM | April 19, 2019 05:00 PM | May 03, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 522 days | 522 days | 522 days | Skilled carpenter
215 | Yes | CMU1.10.2 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ | 525 days | 3 |  |  |  | March 30, 2019 8:00 AM | September 4, 2020 5:00 PM | October 17, 2018 05:00 PM | March 24, 2020 05:00 PM | April 30, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 522 days | 27 days | 27 days
216 | Yes | CMU1.10.2.1 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ ชั้น 1 | 30 days | 4 | 152FS-45 days |  |  | August 6, 2020 8:00 AM | September 4, 2020 5:00 PM | August 11, 2020 05:00 PM | September 09, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
217 | Yes | CMU1.10.2.2 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ ชั้น 2 | 30 days | 4 | 121FS-30 days |  |  | March 9, 2020 8:00 AM | April 7, 2020 5:00 PM | March 11, 2020 05:00 PM | April 09, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Skilled carpenter
218 | Yes | CMU1.10.2.3 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ ชั้น 3 | 30 days | 4 | 92FS-30 days |  |  | September 11, 2019 8:00 AM | October 10, 2019 5:00 PM | September 14, 2019 05:00 PM | October 13, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Skilled carpenter
219 | Yes | CMU1.10.2.4 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ ชั้น 4 | 30 days | 4 | 63FS-15 days |  |  | March 30, 2019 8:00 AM | April 28, 2019 5:00 PM | April 01, 2019 05:00 PM | April 30, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 522 days | 522 days | 522 days | Skilled carpenter
220 | Yes | CMU1.10.3 | Auto Scheduled | งานผ้าม่าน | 510 days | 3 |  |  |  | April 14, 2019 8:00 AM | September 4, 2020 5:00 PM | October 17, 2018 05:00 PM | March 09, 2020 05:00 PM | May 15, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 522 days | 27 days | 27 days
221 | Yes | CMU1.10.3.1 | Auto Scheduled | งานผ้าม่าน ชั้น 1 | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | August 25, 2020 05:00 PM | September 08, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
222 | Yes | CMU1.10.3.2 | Auto Scheduled | งานผ้าม่าน ชั้น 2 | 15 days | 4 | 121FS-15 days |  |  | March 24, 2020 8:00 AM | April 7, 2020 5:00 PM | March 27, 2020 05:00 PM | April 10, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Skilled carpenter
223 | Yes | CMU1.10.3.3 | Auto Scheduled | งานผ้าม่าน ชั้น 3 | 15 days | 4 | 92FS-15 days |  |  | September 26, 2019 8:00 AM | October 10, 2019 5:00 PM | September 30, 2019 05:00 PM | October 14, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Skilled carpenter
224 | Yes | CMU1.10.3.4 | Auto Scheduled | งานผ้าม่าน ชั้น 4 | 15 days | 4 | 63 |  |  | April 14, 2019 8:00 AM | April 28, 2019 5:00 PM | April 21, 2019 05:00 PM | May 05, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 522 days | 522 days | 522 days | Skilled carpenter
225 | Yes | CMU1.10.4 | Auto Scheduled | งานป้าย | 510 days | 3 |  |  |  | April 14, 2019 8:00 AM | September 4, 2020 5:00 PM | October 17, 2018 05:00 PM | March 09, 2020 05:00 PM | May 15, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 522 days | 27 days | 27 days
226 | Yes | CMU1.10.4.1 | Auto Scheduled | งานป้าย ชั้นใต้ดิน | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | August 26, 2020 05:00 PM | September 09, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
227 | Yes | CMU1.10.4.2 | Auto Scheduled | งานป้าย ชั้น 1 | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | August 27, 2020 05:00 PM | September 10, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
228 | Yes | CMU1.10.4.3 | Auto Scheduled | งานป้าย ชั้น 2 | 15 days | 4 | 121FS-15 days |  |  | March 24, 2020 8:00 AM | April 7, 2020 5:00 PM | March 27, 2020 05:00 PM | April 10, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Skilled carpenter
229 | Yes | CMU1.10.4.4 | Auto Scheduled | งานป้าย ชั้น 3 | 15 days | 4 | 92FS-15 days |  |  | September 26, 2019 8:00 AM | October 10, 2019 5:00 PM | October 01, 2019 05:00 PM | October 15, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Skilled carpenter
230 | Yes | CMU1.10.4.5 | Auto Scheduled | งานป้าย ชั้น 4 | 15 days | 4 | 63 |  |  | April 14, 2019 8:00 AM | April 28, 2019 5:00 PM | April 18, 2019 05:00 PM | May 02, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 522 days | 522 days | 522 days | Skilled carpenter
231 | Yes | CMU1.10.5 | Auto Scheduled | งานอื่นๆ | 15 days | 3 |  |  |  | August 6, 2020 8:00 AM | August 20, 2020 5:00 PM | October 19, 2018 05:00 PM | November 02, 2018 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 42 days | 42 days | 42 days
232 | Yes | CMU1.10.5.1 | Auto Scheduled | ตู้อลูมิเนียมพับขึ้นรูป พ่นสี ครอบตู้กดน้ำ | 15 days | 4 | 152FS-45 days |  |  | August 6, 2020 8:00 AM | August 20, 2020 5:00 PM | August 10, 2020 05:00 PM | August 24, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 42 days | 42 days | 42 days | General worker
233 | Yes | CMU1.10.6 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ | 670 days | 3 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
234 | Yes | CMU1.10.6.1 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้นใต้ดิน | 160 days | 4 | 236 |  |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 26, 2020 05:00 PM | October 02, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
235 | Yes | CMU1.10.6.2 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้น 1 | 160 days | 4 | 236 |  |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 26, 2020 05:00 PM | October 02, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
236 | Yes | CMU1.10.6.3 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้น 2 | 175 days | 4 | 237 |  | 235,234 | October 31, 2019 8:00 AM | April 22, 2020 5:00 PM | November 03, 2019 05:00 PM | April 25, 2020 05:00 PM | March 12, 2020 05:00 PM | September 02, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
237 | Yes | CMU1.10.6.4 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้น 3 | 175 days | 4 | 238 |  | 236 | May 9, 2019 8:00 AM | October 30, 2019 5:00 PM | May 12, 2019 05:00 PM | November 02, 2019 05:00 PM | March 12, 2020 05:00 PM | September 02, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
238 | Yes | CMU1.10.6.5 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้น 4 | 160 days | 4 | 36FS+14 days |  | 237 | November 30, 2018 8:00 AM | May 8, 2019 5:00 PM | December 01, 2018 05:00 PM | May 09, 2019 05:00 PM | March 27, 2020 05:00 PM | September 02, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
239 | Yes | CMU1.10.7 | Auto Scheduled | งานระบบเครื่องเสียงประกาศ (ใช้ลำโพงของเดิม) | 539 days | 3 |  |  |  | April 7, 2019 8:00 AM | September 26, 2020 5:00 PM | October 17, 2018 05:00 PM | April 07, 2020 05:00 PM | April 16, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 530 days | 5 days | 5 days
240 | Yes | CMU1.10.7.1 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้นใต้ดิน | 7 days | 4 | 241 |  |  | September 20, 2020 8:00 AM | September 26, 2020 5:00 PM | September 24, 2020 05:00 PM | September 30, 2020 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 5 days | 5 days | 5 days | Electrician
241 | Yes | CMU1.10.7.2 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้น 1 | 7 days | 4 | 152FS-7 days |  | 240 | September 13, 2020 8:00 AM | September 19, 2020 5:00 PM | September 14, 2020 05:00 PM | September 20, 2020 05:00 PM | September 09, 2020 05:00 PM | September 15, 2020 05:00 PM | As Soon As Possible |  | No | 5 days | 5 days | 0 days | Electrician
242 | Yes | CMU1.10.7.3 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้น 2 | 7 days | 4 | 121FS-7 days |  |  | April 1, 2020 8:00 AM | April 7, 2020 5:00 PM | April 02, 2020 05:00 PM | April 08, 2020 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Electrician
243 | Yes | CMU1.10.7.4 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้น 3 | 7 days | 4 | 92FS-7 days |  |  | October 4, 2019 8:00 AM | October 10, 2019 5:00 PM | October 07, 2019 05:00 PM | October 13, 2019 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Electrician
244 | Yes | CMU1.10.7.5 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้น 4 | 7 days | 4 | 63FS-7 days |  |  | April 7, 2019 8:00 AM | April 13, 2019 5:00 PM | April 14, 2019 05:00 PM | April 20, 2019 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 537 days | 537 days | 537 days | Electrician
245 | Yes | CMU1.10.8 | Auto Scheduled | งานระบบกล้องวงจรปิด (ใช้กล้องวงจรปิดของเดิม) | 539 days | 3 |  |  |  | April 7, 2019 8:00 AM | September 26, 2020 5:00 PM | October 17, 2018 05:00 PM | April 07, 2020 05:00 PM | April 16, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 530 days | 5 days | 5 days
246 | Yes | CMU1.10.8.1 | Auto Scheduled | งานกล้องวงจรปิด ชั้นใต้ดิน | 7 days | 4 | 247 |  |  | September 20, 2020 8:00 AM | September 26, 2020 5:00 PM | September 24, 2020 05:00 PM | September 30, 2020 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 5 days | 5 days | 5 days | Electrician
247 | Yes | CMU1.10.8.2 | Auto Scheduled | งานกล้องวงจรปิด ชั้น 1 | 7 days | 4 | 152FS-7 days |  | 246 | September 13, 2020 8:00 AM | September 19, 2020 5:00 PM | September 14, 2020 05:00 PM | September 20, 2020 05:00 PM | September 09, 2020 05:00 PM | September 15, 2020 05:00 PM | As Soon As Possible |  | No | 5 days | 5 days | 0 days | Electrician
248 | Yes | CMU1.10.8.3 | Auto Scheduled | งานกล้องวงจรปิด ชั้น 2 | 7 days | 4 | 121FS-7 days |  |  | April 1, 2020 8:00 AM | April 7, 2020 5:00 PM | April 05, 2020 05:00 PM | April 11, 2020 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Electrician
249 | Yes | CMU1.10.8.4 | Auto Scheduled | งานกล้องวงจรปิด ชั้น 3 | 7 days | 4 | 92FS-7 days |  |  | October 4, 2019 8:00 AM | October 10, 2019 5:00 PM | October 09, 2019 05:00 PM | October 15, 2019 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Electrician
250 | Yes | CMU1.10.8.5 | Auto Scheduled | งานกล้องวงจรปิด ชั้น 4 | 7 days | 4 | 63FS-7 days |  |  | April 7, 2019 8:00 AM | April 13, 2019 5:00 PM | April 10, 2019 05:00 PM | April 16, 2019 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 537 days | 537 days | 537 days | Electrician

## solutoion_3
ID | Active | WBS | Task_Mode | Name | Duration | Outline_Level | Predecessors | Predecessors2 | Successors | Start_Date | Finish_Date | Early_Start | Early_Finish | Late_Start | Late_Finish | Constraint_Type | Constraint_Date | Summary | Start_Slack | Finish_Slack | Free_Slack | Resource_Names
1 | Yes | CMU1 | Auto Scheduled | โครงการปรับปรุงสำนักหอสมุด มหาวิทยาลัยเชียงใหม่ | 716 days | 1 |  |  |  | October 17, 2018 8:00 AM | October 1, 2020 5:00 PM | October 17, 2018 05:00 PM | October 01, 2020 05:00 PM | October 21, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 0 days | 0 days | 0 days
2 | Yes | CMU1.1 | Auto Scheduled | หมวดเตรียมการ | 675 days | 2 |  |  |  | October 17, 2018 8:00 AM | August 21, 2020 5:00 PM | October 17, 2018 05:00 PM | August 21, 2020 05:00 PM | December 01, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 41 days | 41 days | 41 days
3 | Yes | CMU1.1.1 | Auto Scheduled | งานอาคารสนามและผังบริเวณโครงการ | 14 days | 3 | 4FS-7 days |  |  | October 26, 2018 8:00 AM | November 8, 2018 5:00 PM | October 30, 2018 05:00 PM | November 12, 2018 05:00 PM | September 22, 2020 05:00 PM | October 05, 2020 05:00 PM | Start No Earlier Than | Oct 24 '18 | No | 693 days | 693 days | 693 days | Engineer
4 | Yes | CMU1.1.2 | Auto Scheduled | งานเชื่อมต่อระบบสาธารณูปโภคโครงการ | 16 days | 3 |  |  | 3FS-7 days | October 17, 2018 8:00 AM | November 1, 2018 5:00 PM | October 18, 2018 05:00 PM | November 02, 2018 05:00 PM | September 13, 2020 05:00 PM | September 28, 2020 05:00 PM | As Soon As Possible |  | No | 693 days | 693 days | 0 days | Engineer
5 | Yes | CMU1.1.3 | Auto Scheduled | งานตรวจทดสอบระบบภายในอาคารก่อนดำเนินการปรับปรุง | 675 days | 3 |  |  |  | October 17, 2018 8:00 AM | August 21, 2020 5:00 PM | October 17, 2018 05:00 PM | August 21, 2020 05:00 PM | December 01, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 41 days | 41 days | 41 days
6 | Yes | CMU1.1.3.1 | Auto Scheduled | ชั้นที่ 4 | 15 days | 4 |  |  | 7FS+150 days | October 17, 2018 8:00 AM | October 31, 2018 5:00 PM | October 18, 2018 05:00 PM | November 01, 2018 05:00 PM | December 01, 2018 05:00 PM | December 15, 2018 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
7 | Yes | CMU1.1.3.2 | Auto Scheduled | ชั้นที่ 3 | 15 days | 4 | 6FS+150 days |  | 8FS+150 days | March 31, 2019 8:00 AM | April 14, 2019 5:00 PM | April 06, 2019 05:00 PM | April 20, 2019 05:00 PM | May 15, 2019 05:00 PM | May 29, 2019 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
8 | Yes | CMU1.1.3.3 | Auto Scheduled | ชั้นที่ 2 | 15 days | 4 | 7FS+150 days |  | 9FS+150 days | September 12, 2019 8:00 AM | September 26, 2019 5:00 PM | September 26, 2019 05:00 PM | October 10, 2019 05:00 PM | October 27, 2019 05:00 PM | November 10, 2019 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
9 | Yes | CMU1.1.3.4 | Auto Scheduled | ชั้นที่ 1 | 15 days | 4 | 8FS+150 days |  | 10FS+150 days | February 24, 2020 8:00 AM | March 9, 2020 5:00 PM | March 14, 2020 05:00 PM | March 28, 2020 05:00 PM | April 09, 2020 05:00 PM | April 23, 2020 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
10 | Yes | CMU1.1.3.5 | Auto Scheduled | ชั้นใต้ดินและภายนอก | 15 days | 4 | 9FS+150 days |  |  | August 7, 2020 8:00 AM | August 21, 2020 5:00 PM | September 04, 2020 05:00 PM | September 18, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 41 days | Engineer
11 | Yes | CMU1.1.4 | Auto Scheduled | งานสำรวจอุปกรณ์ไฟฟ้า, สุขภัณฑ์และครุภัณฑ์ (ของเดิม) ก่อนดำเนินการปรับปรุง | 675 days | 3 |  |  |  | October 17, 2018 8:00 AM | August 21, 2020 5:00 PM | October 17, 2018 05:00 PM | August 21, 2020 05:00 PM | December 01, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 41 days | 41 days | 41 days
12 | Yes | CMU1.1.4.1 | Auto Scheduled | ชั้นที่ 4 | 15 days | 4 |  |  | 13FS+150 days | October 17, 2018 8:00 AM | October 31, 2018 5:00 PM | October 19, 2018 05:00 PM | November 02, 2018 05:00 PM | December 01, 2018 05:00 PM | December 15, 2018 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
13 | Yes | CMU1.1.4.2 | Auto Scheduled | ชั้นที่ 3 | 15 days | 4 | 12FS+150 days |  | 14FS+150 days | March 31, 2019 8:00 AM | April 14, 2019 5:00 PM | April 05, 2019 05:00 PM | April 19, 2019 05:00 PM | May 15, 2019 05:00 PM | May 29, 2019 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
14 | Yes | CMU1.1.4.3 | Auto Scheduled | ชั้นที่ 2 | 15 days | 4 | 13FS+150 days |  | 15FS+150 days | September 12, 2019 8:00 AM | September 26, 2019 5:00 PM | September 23, 2019 05:00 PM | October 07, 2019 05:00 PM | October 27, 2019 05:00 PM | November 10, 2019 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
15 | Yes | CMU1.1.4.4 | Auto Scheduled | ชั้นที่ 1 | 15 days | 4 | 14FS+150 days |  | 16FS+150 days | February 24, 2020 8:00 AM | March 9, 2020 5:00 PM | March 09, 2020 05:00 PM | March 23, 2020 05:00 PM | April 09, 2020 05:00 PM | April 23, 2020 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
16 | Yes | CMU1.1.4.5 | Auto Scheduled | ชั้นใต้ดินและภายนอก | 15 days | 4 | 15FS+150 days |  |  | August 7, 2020 8:00 AM | August 21, 2020 5:00 PM | August 29, 2020 05:00 PM | September 12, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 41 days | Engineer
17 | Yes | CMU1.1.5 | Auto Scheduled | งานเอกสารขออนุมัติใช้วัสดุ, Shop Drawing และครุภัณฑ์ของโครงการ | 106 days | 3 |  |  |  | October 17, 2018 8:00 AM | January 30, 2019 5:00 PM | October 21, 2018 05:00 PM | February 03, 2019 05:00 PM | June 22, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 610 days | 610 days | 610 days
18 | Yes | CMU1.1.5.1 | Auto Scheduled | แบบ Shop Drawing ชั้นที่ 4 | 20 days | 4 |  |  | 19,25SS+14 days,26SS+14 days | October 17, 2018 8:00 AM | November 5, 2018 5:00 PM | October 17, 2018 05:00 PM | November 05, 2018 05:00 PM | October 01, 2018 05:00 PM | October 20, 2018 05:00 PM | As Soon As Possible |  | No | 610 days | 610 days | 0 days | Engineer
19 | Yes | CMU1.1.5.2 | Auto Scheduled | แบบ Shop Drawing ชั้นที่ 3 | 20 days | 4 | 18 |  | 20FS-7 days | November 6, 2018 8:00 AM | November 25, 2018 5:00 PM | November 12, 2018 05:00 PM | December 01, 2018 05:00 PM | July 13, 2020 05:00 PM | August 01, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
20 | Yes | CMU1.1.5.3 | Auto Scheduled | แบบ Shop Drawing ชั้นที่ 2 | 20 days | 4 | 19FS-7 days |  | 21FS-7 days | November 19, 2018 8:00 AM | December 8, 2018 5:00 PM | November 27, 2018 05:00 PM | December 16, 2018 05:00 PM | July 26, 2020 05:00 PM | August 14, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
21 | Yes | CMU1.1.5.4 | Auto Scheduled | แบบ Shop Drawing ชั้นที่ 1 | 20 days | 4 | 20FS-7 days |  | 22FS-7 days | December 2, 2018 8:00 AM | December 21, 2018 5:00 PM | December 15, 2018 05:00 PM | January 03, 2019 05:00 PM | August 08, 2020 05:00 PM | August 27, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
22 | Yes | CMU1.1.5.5 | Auto Scheduled | แบบ Shop Drawing ชั้นใต้ดิน | 20 days | 4 | 21FS-7 days |  | 23FS-7 days | December 15, 2018 8:00 AM | January 3, 2019 5:00 PM | January 02, 2019 05:00 PM | January 21, 2019 05:00 PM | August 21, 2020 05:00 PM | September 09, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
23 | Yes | CMU1.1.5.6 | Auto Scheduled | แบบ Shop Drawing ภายนอกอาคาร | 20 days | 4 | 22FS-7 days |  | 24FS-7 days | December 28, 2018 8:00 AM | January 16, 2019 5:00 PM | January 19, 2019 05:00 PM | February 07, 2019 05:00 PM | September 03, 2020 05:00 PM | September 22, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
24 | Yes | CMU1.1.5.7 | Auto Scheduled | แบบ Shop Drawing landscape | 20 days | 4 | 23FS-7 days |  |  | January 10, 2019 8:00 AM | January 29, 2019 5:00 PM | February 07, 2019 05:00 PM | February 26, 2019 05:00 PM | September 16, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 611 days | Engineer
25 | Yes | CMU1.1.5.8 | Auto Scheduled | แบบ Shop Drawing งานปรับปรุง ครุภัณฑ์ | 92 days | 4 | 18SS+14 days |  |  | October 31, 2018 8:00 AM | January 30, 2019 5:00 PM | November 06, 2018 05:00 PM | February 05, 2019 05:00 PM | July 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 610 days | 610 days | 610 days | Engineer
26 | Yes | CMU1.1.5.9 | Auto Scheduled | แบบ Shop Drawing งานจัดซื้อครุภัณฑ์ | 92 days | 4 | 18SS+14 days |  |  | October 31, 2018 8:00 AM | January 30, 2019 5:00 PM | November 08, 2018 05:00 PM | February 07, 2019 05:00 PM | July 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 610 days | 610 days | 610 days | Engineer
27 | Yes | CMU1.1.6 | Auto Scheduled | งานตรวจทดสอบระบบ, งานอบรมผู้ใช้อาคาร และ As-Built Drawing | 30 days | 3 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 21, 2018 05:00 PM | November 19, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 686 days | 686 days | 686 days
28 | Yes | CMU1.1.6.1 | Auto Scheduled | ชั้นที่ 4 | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 25, 2018 05:00 PM | November 23, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
29 | Yes | CMU1.1.6.2 | Auto Scheduled | ชั้นที่ 3 | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 27, 2018 05:00 PM | November 25, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
30 | Yes | CMU1.1.6.3 | Auto Scheduled | ชั้นที่ 2 | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 21, 2018 05:00 PM | November 19, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
31 | Yes | CMU1.1.6.4 | Auto Scheduled | ชั้นที่ 1 | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 26, 2018 05:00 PM | November 24, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
32 | Yes | CMU1.1.6.5 | Auto Scheduled | ชั้นใต้ดิน | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 23, 2018 05:00 PM | November 21, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
33 | Yes | CMU1.1.6.6 | Auto Scheduled | ทั้งอาคาร | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 22, 2018 05:00 PM | November 20, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
34 | Yes | CMU1.1.7 | Auto Scheduled | งานบริหารงานก่อสร้างและงานอื่น ๆ | 0 days | 3 |  |  |  | October 17, 2018 8:00 AM | October 17, 2018 8:00 AM | October 20, 2018 05:00 PM | October 19, 2018 05:00 PM | October 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 716 days | 716 days | 716 days | Engineer
35 | Yes | CMU1.2 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้น 4 | 471 days | 2 |  |  |  | October 17, 2018 8:00 AM | January 30, 2020 5:00 PM | October 17, 2018 05:00 PM | January 30, 2020 05:00 PM | June 23, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 0 days | 245 days | 0 days
36 | Yes | CMU1.2.1 | Auto Scheduled | งานรื้อถอน ชั้น 4 (รื้อขนไป) | 30 days | 3 |  |  | 39FS+45 days,40FS+45 days,51,63SS+14 days,80,109,140,180FS+14 days,186FS+14 days,198FS+14 days,199FS+14 days,200FS+14 days,238FS+14 days | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 17, 2018 05:00 PM | November 15, 2018 05:00 PM | March 11, 2018 05:00 PM | April 09, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | General worker
37 | Yes | CMU1.2.2 | Auto Scheduled | งานสถาปัตยกรรม ชั้น 4 | 396 days | 3 |  |  |  | December 31, 2018 8:00 AM | January 30, 2020 5:00 PM | October 17, 2018 05:00 PM | November 16, 2019 05:00 PM | September 06, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 326 days | 245 days | 245 days
38 | Yes | CMU1.2.2.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 39,41,42 |  |  | March 1, 2019 8:00 AM | March 30, 2019 5:00 PM | March 08, 2019 05:00 PM | April 06, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 551 days | Skilled carpenter
39 | Yes | CMU1.2.2.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 36FS+45 days |  | 38,43 | December 31, 2018 8:00 AM | February 28, 2019 5:00 PM | January 04, 2019 05:00 PM | March 04, 2019 05:00 PM | July 15, 2020 05:00 PM | September 12, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 0 days | General worker
40 | Yes | CMU1.2.2.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 36FS+45 days |  | 41,42 | December 31, 2018 8:00 AM | January 29, 2019 5:00 PM | January 02, 2019 05:00 PM | January 31, 2019 05:00 PM | August 14, 2020 05:00 PM | September 12, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 0 days | General worker
41 | Yes | CMU1.2.2.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 40 |  | 38,43 | January 30, 2019 8:00 AM | February 28, 2019 5:00 PM | February 03, 2019 05:00 PM | March 04, 2019 05:00 PM | August 14, 2020 05:00 PM | September 12, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 0 days | Skilled carpenter
42 | Yes | CMU1.2.2.5 | Auto Scheduled | งานบันได | 30 days | 4 | 40 |  | 38,43 | January 30, 2019 8:00 AM | February 28, 2019 5:00 PM | February 03, 2019 05:00 PM | March 04, 2019 05:00 PM | August 14, 2020 05:00 PM | September 12, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 0 days | General worker
43 | Yes | CMU1.2.2.6 | Auto Scheduled | งานสี | 30 days | 4 | 39,41,42 |  |  | March 1, 2019 8:00 AM | March 30, 2019 5:00 PM | March 07, 2019 05:00 PM | April 05, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 551 days | General worker
44 | Yes | CMU1.2.2.7 | Auto Scheduled | งานสุขภัณฑ์ | 315 days | 4 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 19, 2018 05:00 PM | August 29, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
45 | Yes | CMU1.2.2.7.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 46FS+135 days |  | 47FS+135 days | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | September 09, 2019 05:00 PM | September 23, 2019 05:00 PM | April 24, 2020 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
46 | Yes | CMU1.2.2.7.2 | Auto Scheduled | ZONE T-2 กลาง | 15 days | 5 | 51,55 |  | 45FS+135 days | March 22, 2019 8:00 AM | April 5, 2019 5:00 PM | April 05, 2019 05:00 PM | April 19, 2019 05:00 PM | November 26, 2019 05:00 PM | December 10, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
47 | Yes | CMU1.2.2.7.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 15 days | 5 | 45FS+135 days |  |  | January 16, 2020 8:00 AM | January 30, 2020 5:00 PM | February 12, 2020 05:00 PM | February 26, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 245 days | Sanitary-Plumber
48 | Yes | CMU1.2.3 | Auto Scheduled | งานระบบสุขาภิบาล ชั้น 4 | 408 days | 3 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
49 | Yes | CMU1.2.3.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
50 | Yes | CMU1.2.3.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 51FS+15 days |  | 52FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 16, 2019 05:00 PM | August 19, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
51 | Yes | CMU1.2.3.1.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 36 |  | 50FS+15 days,46,55SS | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 23, 2018 05:00 PM | March 28, 2019 05:00 PM | August 25, 2019 05:00 PM | December 28, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
52 | Yes | CMU1.2.3.1.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 50FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 07, 2019 05:00 PM | January 10, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
53 | Yes | CMU1.2.3.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
54 | Yes | CMU1.2.3.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 55FS+15 days |  | 56FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 21, 2019 05:00 PM | August 24, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
55 | Yes | CMU1.2.3.2.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 51SS |  | 54FS+15 days,46 | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 26, 2018 05:00 PM | March 31, 2019 05:00 PM | August 25, 2019 05:00 PM | December 28, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
56 | Yes | CMU1.2.3.2.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 54FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 15, 2019 05:00 PM | January 18, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
57 | Yes | CMU1.2.4 | Auto Scheduled | งานระบบไฟฟ้า ชั้น 4 | 117 days | 3 |  |  |  | November 30, 2018 8:00 AM | March 26, 2019 5:00 PM | October 20, 2018 05:00 PM | February 13, 2019 05:00 PM | June 11, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 555 days | 555 days | 555 days
58 | Yes | CMU1.2.4.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 30 days | 4 | 60FS+7 days |  |  | February 25, 2019 8:00 AM | March 26, 2019 5:00 PM | March 03, 2019 05:00 PM | April 01, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 555 days | 555 days | 555 days | Electrician
59 | Yes | CMU1.2.4.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 30 days | 4 | 60FS+7 days |  |  | February 25, 2019 8:00 AM | March 26, 2019 5:00 PM | March 03, 2019 05:00 PM | April 01, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 555 days | 555 days | 555 days | Electrician
60 | Yes | CMU1.2.4.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 63SS+30 days |  | 58FS+7 days,59FS+7 days | November 30, 2018 8:00 AM | February 17, 2019 5:00 PM | December 03, 2018 05:00 PM | February 20, 2019 05:00 PM | June 11, 2020 05:00 PM | August 29, 2020 05:00 PM | As Soon As Possible |  | No | 555 days | 555 days | 0 days | Electrician
61 | Yes | CMU1.2.4.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 63SS+30 days |  |  | November 30, 2018 8:00 AM | February 17, 2019 5:00 PM | December 02, 2018 05:00 PM | February 19, 2019 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 592 days | 592 days | 592 days | Electrician
62 | Yes | CMU1.2.4.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 63SS+30 days |  |  | November 30, 2018 8:00 AM | February 17, 2019 5:00 PM | December 06, 2018 05:00 PM | February 23, 2019 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 592 days | 592 days | 592 days | Electrician
63 | Yes | CMU1.2.5 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้น 4 | 165 days | 3 | 36SS+14 days |  | 62SS+30 days,60SS+30 days,61SS+30 days,65,214,219FS-15 days,224,230,244FS-7 days,250FS-7 days | October 31, 2018 8:00 AM | April 13, 2019 5:00 PM | October 31, 2018 05:00 PM | April 13, 2019 05:00 PM | June 19, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Skilled carpenter
64 | Yes | CMU1.3 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้น 3 | 441 days | 2 |  |  |  | November 16, 2018 8:00 AM | January 30, 2020 5:00 PM | October 17, 2018 05:00 PM | December 31, 2019 05:00 PM | July 23, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 149 days | 245 days | 149 days
65 | Yes | CMU1.3.1 | Auto Scheduled | งานรื้อถอน ชั้น 3 (รื้อขนไป) | 30 days | 3 | 63 | 121 | 68FS+45 days,69FS+45 days,92SS | April 14, 2019 8:00 AM | May 13, 2019 5:00 PM | April 14, 2019 05:00 PM | May 13, 2019 05:00 PM | July 19, 2018 05:00 PM | August 17, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | General worker
66 | Yes | CMU1.3.2 | Auto Scheduled | งานสถาปัตยกรรม ชั้น 3 | 315 days | 3 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 21, 2018 05:00 PM | August 31, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
67 | Yes | CMU1.3.2.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 68,70,71 |  |  | August 27, 2019 8:00 AM | September 25, 2019 5:00 PM | August 29, 2019 05:00 PM | September 27, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 372 days | Skilled carpenter
68 | Yes | CMU1.3.2.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 65FS+45 days |  | 67,72 | June 28, 2019 8:00 AM | August 26, 2019 5:00 PM | June 28, 2019 05:00 PM | August 26, 2019 05:00 PM | October 02, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 0 days | General worker
69 | Yes | CMU1.3.2.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 65FS+45 days |  | 70,71 | June 28, 2019 8:00 AM | July 27, 2019 5:00 PM | June 28, 2019 05:00 PM | July 27, 2019 05:00 PM | April 15, 2019 05:00 PM | May 14, 2019 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 0 days | General worker
70 | Yes | CMU1.3.2.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 69 |  | 67,72 | July 28, 2019 8:00 AM | August 26, 2019 5:00 PM | July 28, 2019 05:00 PM | August 26, 2019 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 0 days | Skilled carpenter
71 | Yes | CMU1.3.2.5 | Auto Scheduled | งานบันได | 30 days | 4 | 69 |  | 67,72 | July 28, 2019 8:00 AM | August 26, 2019 5:00 PM | July 28, 2019 05:00 PM | August 26, 2019 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 0 days | General worker
72 | Yes | CMU1.3.2.6 | Auto Scheduled | งานสี | 30 days | 4 | 68,70,71 |  |  | August 27, 2019 8:00 AM | September 25, 2019 5:00 PM | August 29, 2019 05:00 PM | September 27, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 372 days | General worker
73 | Yes | CMU1.3.2.7 | Auto Scheduled | งานสุขภัณฑ์ | 315 days | 4 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 21, 2018 05:00 PM | August 31, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
74 | Yes | CMU1.3.2.7.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 75FS+135 days |  | 76FS+135 days | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | August 22, 2019 05:00 PM | September 05, 2019 05:00 PM | April 24, 2020 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
75 | Yes | CMU1.3.2.7.2 | Auto Scheduled | ZONE T-2 กลาง | 15 days | 5 | 80,84 |  | 74FS+135 days | March 22, 2019 8:00 AM | April 5, 2019 5:00 PM | March 23, 2019 05:00 PM | April 06, 2019 05:00 PM | November 26, 2019 05:00 PM | December 10, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
76 | Yes | CMU1.3.2.7.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 15 days | 5 | 74FS+135 days |  |  | January 16, 2020 8:00 AM | January 30, 2020 5:00 PM | January 23, 2020 05:00 PM | February 06, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 245 days | Sanitary-Plumber
77 | Yes | CMU1.3.3 | Auto Scheduled | งานระบบสุขาภิบาล ชั้น 3 | 408 days | 3 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
78 | Yes | CMU1.3.3.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
79 | Yes | CMU1.3.3.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 80FS+15 days |  | 81FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 13, 2019 05:00 PM | August 16, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
80 | Yes | CMU1.3.3.1.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 36 |  | 79FS+15 days,84SS,75 | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 16, 2018 05:00 PM | March 21, 2019 05:00 PM | January 09, 2019 05:00 PM | May 14, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
81 | Yes | CMU1.3.3.1.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 79FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 08, 2019 05:00 PM | January 11, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
82 | Yes | CMU1.3.3.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
83 | Yes | CMU1.3.3.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 84FS+15 days |  | 85FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 11, 2019 05:00 PM | August 14, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
84 | Yes | CMU1.3.3.2.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 80SS |  | 83FS+15 days,75 | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 16, 2018 05:00 PM | March 21, 2019 05:00 PM | January 09, 2019 05:00 PM | May 14, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
85 | Yes | CMU1.3.3.2.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 83FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 05, 2019 05:00 PM | January 08, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
86 | Yes | CMU1.3.4 | Auto Scheduled | งานระบบไฟฟ้า ชั้น 3 | 147 days | 3 |  |  |  | May 14, 2019 8:00 AM | October 7, 2019 5:00 PM | October 21, 2018 05:00 PM | March 16, 2019 05:00 PM | May 12, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 360 days | 360 days | 360 days
87 | Yes | CMU1.3.4.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 60 days | 4 | 89FS+7 days |  |  | August 9, 2019 8:00 AM | October 7, 2019 5:00 PM | August 14, 2019 05:00 PM | October 12, 2019 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 360 days | 360 days | 360 days | Electrician
88 | Yes | CMU1.3.4.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 60 days | 4 | 89FS+7 days |  |  | August 9, 2019 8:00 AM | October 7, 2019 5:00 PM | August 17, 2019 05:00 PM | October 15, 2019 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 360 days | 360 days | 360 days | Electrician
89 | Yes | CMU1.3.4.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 92SS+30 days |  | 88FS+7 days,87FS+7 days | May 14, 2019 8:00 AM | August 1, 2019 5:00 PM | May 17, 2019 05:00 PM | August 04, 2019 05:00 PM | May 12, 2020 05:00 PM | July 30, 2020 05:00 PM | As Soon As Possible |  | No | 360 days | 360 days | 0 days | Electrician
90 | Yes | CMU1.3.4.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 92SS+30 days |  |  | May 14, 2019 8:00 AM | August 1, 2019 5:00 PM | May 21, 2019 05:00 PM | August 08, 2019 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 427 days | 427 days | 427 days | Electrician
91 | Yes | CMU1.3.4.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 92SS+30 days |  |  | May 14, 2019 8:00 AM | August 1, 2019 5:00 PM | May 22, 2019 05:00 PM | August 09, 2019 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 427 days | 427 days | 427 days | Electrician
92 | Yes | CMU1.3.5 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้น 3 | 180 days | 3 | 65SS |  | 91SS+30 days,90SS+30 days,89SS+30 days,94,213FS-15 days,218FS-30 days,223FS-15 days,229FS-15 days,243FS-7 days,249FS-7 days | April 14, 2019 8:00 AM | October 10, 2019 5:00 PM | April 16, 2019 05:00 PM | October 12, 2019 05:00 PM | October 12, 2019 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Skilled carpenter
93 | Yes | CMU1.4 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้น 2 | 509 days | 2 |  |  |  | November 16, 2018 8:00 AM | April 7, 2020 5:00 PM | October 17, 2018 05:00 PM | March 08, 2020 05:00 PM | May 16, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 177 days | 177 days
94 | Yes | CMU1.4.1 | Auto Scheduled | งานรื้อถอน ชั้น 2 (รื้อขนไป) | 30 days | 3 | 92 | 152 | 97FS+45 days,98FS+45 days,121SS | October 11, 2019 8:00 AM | November 9, 2019 5:00 PM | October 13, 2019 05:00 PM | November 11, 2019 05:00 PM | June 04, 2018 05:00 PM | July 03, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | General worker
95 | Yes | CMU1.4.2 | Auto Scheduled | งานสถาปัตยกรรม ชั้น 2 | 368 days | 3 |  |  |  | March 22, 2019 8:00 AM | March 23, 2020 5:00 PM | October 17, 2018 05:00 PM | October 19, 2019 05:00 PM | October 04, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 192 days | 192 days
96 | Yes | CMU1.4.2.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 97,99,100 |  |  | February 23, 2020 8:00 AM | March 23, 2020 5:00 PM | March 05, 2020 05:00 PM | April 03, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 192 days | Skilled carpenter
97 | Yes | CMU1.4.2.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 94FS+45 days |  | 96,101 | December 25, 2019 8:00 AM | February 22, 2020 5:00 PM | December 27, 2019 05:00 PM | February 24, 2020 05:00 PM | February 09, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 0 days | General worker
98 | Yes | CMU1.4.2.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 94FS+45 days |  | 99,100 | December 25, 2019 8:00 AM | January 23, 2020 5:00 PM | December 30, 2019 05:00 PM | January 28, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 0 days | General worker
99 | Yes | CMU1.4.2.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 98 |  | 96,101 | January 24, 2020 8:00 AM | February 22, 2020 5:00 PM | January 31, 2020 05:00 PM | February 29, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 0 days | Skilled carpenter
100 | Yes | CMU1.4.2.5 | Auto Scheduled | งานบันได | 30 days | 4 | 98 |  | 96,101 | January 24, 2020 8:00 AM | February 22, 2020 5:00 PM | February 01, 2020 05:00 PM | March 01, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 0 days | General worker
101 | Yes | CMU1.4.2.6 | Auto Scheduled | งานสี | 30 days | 4 | 97,99,100 |  |  | February 23, 2020 8:00 AM | March 23, 2020 5:00 PM | March 08, 2020 05:00 PM | April 06, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 192 days | General worker
102 | Yes | CMU1.4.2.7 | Auto Scheduled | งานสุขภัณฑ์ | 315 days | 4 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 20, 2018 05:00 PM | August 30, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
103 | Yes | CMU1.4.2.7.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 104FS+135 days |  | 105FS+135 days | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | September 04, 2019 05:00 PM | September 18, 2019 05:00 PM | April 24, 2020 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
104 | Yes | CMU1.4.2.7.2 | Auto Scheduled | ZONE T-2 กลาง | 15 days | 5 | 113,109 |  | 103FS+135 days | March 22, 2019 8:00 AM | April 5, 2019 5:00 PM | April 04, 2019 05:00 PM | April 18, 2019 05:00 PM | November 26, 2019 05:00 PM | December 10, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
105 | Yes | CMU1.4.2.7.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 15 days | 5 | 103FS+135 days |  |  | January 16, 2020 8:00 AM | January 30, 2020 5:00 PM | February 06, 2020 05:00 PM | February 20, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 245 days | Sanitary-Plumber
106 | Yes | CMU1.4.3 | Auto Scheduled | งานระบบสุขาภิบาล ชั้น 2 | 408 days | 3 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
107 | Yes | CMU1.4.3.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
108 | Yes | CMU1.4.3.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 109FS+15 days |  | 110FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 16, 2019 05:00 PM | August 19, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
109 | Yes | CMU1.4.3.1.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 36 |  | 113SS,104,108FS+15 days | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 22, 2018 05:00 PM | March 27, 2019 05:00 PM | August 25, 2019 05:00 PM | December 28, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
110 | Yes | CMU1.4.3.1.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 108FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 06, 2019 05:00 PM | January 09, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
111 | Yes | CMU1.4.3.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
112 | Yes | CMU1.4.3.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 113FS+15 days |  | 114FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 20, 2019 05:00 PM | August 23, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
113 | Yes | CMU1.4.3.2.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 109SS |  | 104,112FS+15 days | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 26, 2018 05:00 PM | March 31, 2019 05:00 PM | August 25, 2019 05:00 PM | December 28, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
114 | Yes | CMU1.4.3.2.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 112FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 11, 2019 05:00 PM | January 14, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
115 | Yes | CMU1.4.4 | Auto Scheduled | งานระบบไฟฟ้า ชั้น 2 | 147 days | 3 |  |  |  | November 10, 2019 8:00 AM | April 4, 2020 5:00 PM | October 19, 2018 05:00 PM | March 14, 2019 05:00 PM | May 12, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 180 days | 180 days | 180 days
116 | Yes | CMU1.4.4.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 60 days | 4 | 118FS+7 days |  |  | February 5, 2020 8:00 AM | April 4, 2020 5:00 PM | February 09, 2020 05:00 PM | April 08, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 180 days | 180 days | 180 days | Electrician
117 | Yes | CMU1.4.4.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 60 days | 4 | 118FS+7 days |  |  | February 5, 2020 8:00 AM | April 4, 2020 5:00 PM | February 11, 2020 05:00 PM | April 10, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 180 days | 180 days | 180 days | Electrician
118 | Yes | CMU1.4.4.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 121SS+30 days |  | 117FS+7 days,116FS+7 days | November 10, 2019 8:00 AM | January 28, 2020 5:00 PM | November 13, 2019 05:00 PM | January 31, 2020 05:00 PM | May 12, 2020 05:00 PM | July 30, 2020 05:00 PM | As Soon As Possible |  | No | 180 days | 180 days | 0 days | Electrician
119 | Yes | CMU1.4.4.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 121SS+30 days |  |  | November 10, 2019 8:00 AM | January 28, 2020 5:00 PM | November 16, 2019 05:00 PM | February 03, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 247 days | 247 days | 247 days | Electrician
120 | Yes | CMU1.4.4.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 121SS+30 days |  |  | November 10, 2019 8:00 AM | January 28, 2020 5:00 PM | November 17, 2019 05:00 PM | February 04, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 247 days | 247 days | 247 days | Electrician
121 | Yes | CMU1.4.5 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้น 2 | 180 days | 3 | 94SS |  | 120SS+30 days,119SS+30 days,118SS+30 days,123,212FS-15 days,217FS-30 days,222FS-15 days,228FS-15 days,242FS-7 days,248FS-7 days | October 11, 2019 8:00 AM | April 7, 2020 5:00 PM | October 13, 2019 05:00 PM | April 09, 2020 05:00 PM | June 04, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Skilled carpenter
122 | Yes | CMU1.5 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้น 1 | 686 days | 2 |  |  |  | November 16, 2018 8:00 AM | October 1, 2020 5:00 PM | October 17, 2018 05:00 PM | September 01, 2020 05:00 PM | November 20, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 0 days | 0 days
123 | Yes | CMU1.5.1 | Auto Scheduled | งานรื้อถอน ชั้น 1 (รื้อขนไป) | 30 days | 3 | 121 | 63 | 124,127FS+45 days,128FS+45 days,131FS+45 days,152SS,193SS,194SS,195SS,196SS,197SS,202SS,204SS,205SS,206SS,207SS | April 8, 2020 8:00 AM | May 7, 2020 5:00 PM | April 10, 2020 05:00 PM | May 09, 2020 05:00 PM | July 19, 2018 05:00 PM | August 17, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | General worker
124 | Yes | CMU1.5.2 | Auto Scheduled | งานโครงสร้างวิศวกรรม ชั้น 1 | 75 days | 3 | 123 |  |  | May 8, 2020 8:00 AM | July 21, 2020 5:00 PM | May 10, 2020 05:00 PM | July 23, 2020 05:00 PM | July 23, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 72 days | 72 days | 72 days | General worker
125 | Yes | CMU1.5.3 | Auto Scheduled | งานสถาปัตยกรรม ชั้น 1 | 548 days | 3 |  |  |  | March 22, 2019 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | April 16, 2020 05:00 PM | April 07, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 12 days | 12 days
126 | Yes | CMU1.5.3.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 127,129,130 |  |  | August 21, 2020 8:00 AM | September 19, 2020 5:00 PM | August 23, 2020 05:00 PM | September 21, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | Skilled carpenter
127 | Yes | CMU1.5.3.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 123FS+45 days |  | 126,132 | June 22, 2020 8:00 AM | August 20, 2020 5:00 PM | June 24, 2020 05:00 PM | August 22, 2020 05:00 PM | October 02, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
128 | Yes | CMU1.5.3.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 123FS+45 days |  | 129,130 | June 22, 2020 8:00 AM | July 21, 2020 5:00 PM | June 24, 2020 05:00 PM | July 23, 2020 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
129 | Yes | CMU1.5.3.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 128 |  | 126,132 | July 22, 2020 8:00 AM | August 20, 2020 5:00 PM | July 24, 2020 05:00 PM | August 22, 2020 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | Skilled carpenter
130 | Yes | CMU1.5.3.5 | Auto Scheduled | งานบันได | 30 days | 4 | 128 |  | 126,132 | July 22, 2020 8:00 AM | August 20, 2020 5:00 PM | July 24, 2020 05:00 PM | August 22, 2020 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
131 | Yes | CMU1.5.3.6 | Auto Scheduled | งานตกแต่งอื่น ๆ | 60 days | 4 | 123FS+45 days |  |  | June 22, 2020 8:00 AM | August 20, 2020 5:00 PM | June 24, 2020 05:00 PM | August 22, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 42 days | 42 days | 42 days | General worker
132 | Yes | CMU1.5.3.7 | Auto Scheduled | งานสี | 30 days | 4 | 127,129,130 |  |  | August 21, 2020 8:00 AM | September 19, 2020 5:00 PM | August 23, 2020 05:00 PM | September 21, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
133 | Yes | CMU1.5.3.8 | Auto Scheduled | งานสุขภัณฑ์ | 315 days | 4 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 22, 2018 05:00 PM | September 01, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
134 | Yes | CMU1.5.3.8.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 135FS+135 days |  | 136FS+135 days | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | August 23, 2019 05:00 PM | September 06, 2019 05:00 PM | April 24, 2020 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
135 | Yes | CMU1.5.3.8.2 | Auto Scheduled | ZONE T-2 กลาง | 15 days | 5 | 140,144 |  | 134FS+135 days,164FS+135 days | March 22, 2019 8:00 AM | April 5, 2019 5:00 PM | March 24, 2019 05:00 PM | April 07, 2019 05:00 PM | November 26, 2019 05:00 PM | December 10, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
136 | Yes | CMU1.5.3.8.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 15 days | 5 | 134FS+135 days |  |  | January 16, 2020 8:00 AM | January 30, 2020 5:00 PM | January 23, 2020 05:00 PM | February 06, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 245 days | Sanitary-Plumber
137 | Yes | CMU1.5.4 | Auto Scheduled | งานระบบสุขาภิบาล ชั้น 1 | 408 days | 3 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 278 days | 44 days
138 | Yes | CMU1.5.4.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 278 days | 44 days
139 | Yes | CMU1.5.4.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 140FS+15 days |  | 141FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 12, 2019 05:00 PM | August 15, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
140 | Yes | CMU1.5.4.1.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 36 |  | 139FS+15 days,144SS,135,167FS+15 days | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 16, 2018 05:00 PM | March 21, 2019 05:00 PM | January 03, 2019 05:00 PM | May 08, 2019 05:00 PM | As Soon As Possible |  | No | 44 days | 44 days | 0 days | Sanitary-Plumber
141 | Yes | CMU1.5.4.1.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 139FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 06, 2019 05:00 PM | January 09, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
142 | Yes | CMU1.5.4.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 278 days | 44 days
143 | Yes | CMU1.5.4.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 144FS+15 days |  | 145FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 12, 2019 05:00 PM | August 15, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
144 | Yes | CMU1.5.4.2.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 140SS |  | 143FS+15 days,135,169FS+15 days | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 16, 2018 05:00 PM | March 21, 2019 05:00 PM | January 03, 2019 05:00 PM | May 08, 2019 05:00 PM | As Soon As Possible |  | No | 44 days | 44 days | 0 days | Sanitary-Plumber
145 | Yes | CMU1.5.4.2.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 143FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 03, 2019 05:00 PM | January 06, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
146 | Yes | CMU1.5.5 | Auto Scheduled | งานระบบไฟฟ้า ชั้น 1 | 147 days | 3 |  |  |  | May 8, 2020 8:00 AM | October 1, 2020 5:00 PM | October 20, 2018 05:00 PM | March 15, 2019 05:00 PM | May 12, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 0 days | 0 days | 0 days
147 | Yes | CMU1.5.5.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 60 days | 4 | 149FS+7 days |  |  | August 3, 2020 8:00 AM | October 1, 2020 5:00 PM | August 05, 2020 05:00 PM | October 03, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Electrician
148 | Yes | CMU1.5.5.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 60 days | 4 | 149FS+7 days |  |  | August 3, 2020 8:00 AM | October 1, 2020 5:00 PM | August 05, 2020 05:00 PM | October 03, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Electrician
149 | Yes | CMU1.5.5.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 152SS+30 days |  | 148FS+7 days,147FS+7 days | May 8, 2020 8:00 AM | July 26, 2020 5:00 PM | May 10, 2020 05:00 PM | July 28, 2020 05:00 PM | May 12, 2020 05:00 PM | July 30, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Electrician
150 | Yes | CMU1.5.5.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 152SS+30 days |  |  | May 8, 2020 8:00 AM | July 26, 2020 5:00 PM | May 10, 2020 05:00 PM | July 28, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 67 days | 67 days | 67 days | Electrician
151 | Yes | CMU1.5.5.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 152SS+30 days |  |  | May 8, 2020 8:00 AM | July 26, 2020 5:00 PM | May 10, 2020 05:00 PM | July 28, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 67 days | 67 days | 67 days | Electrician
152 | Yes | CMU1.5.6 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้น 1 | 165 days | 3 | 123SS |  | 151SS+30 days,150SS+30 days,149SS+30 days,154SS,211FS-30 days,210FS-30 days,216FS-45 days,221FS-30 days,227FS-30 days,226FS-30 days,232FS-45 days,241FS-7 days,247FS-7 days | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 10, 2020 05:00 PM | September 21, 2020 05:00 PM | November 26, 2019 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Skilled carpenter
153 | Yes | CMU1.6 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้นใต้ดิน | 533 days | 2 |  |  |  | April 6, 2019 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | April 01, 2020 05:00 PM | April 22, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 12 days | 12 days
154 | Yes | CMU1.6.1 | Auto Scheduled | งานรื้อถอน ชั้นใต้ดิน (รื้อขนไป) | 30 days | 3 | 152SS |  | 155,158FS+45 days,159FS+45 days,177SS,176SS,175SS,174SS | April 8, 2020 8:00 AM | May 7, 2020 5:00 PM | April 10, 2020 05:00 PM | May 09, 2020 05:00 PM | November 26, 2019 05:00 PM | December 25, 2019 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
155 | Yes | CMU1.6.2 | Auto Scheduled | งานโครงสร้างวิศวกรรม ชั้นใต้ดิน | 75 days | 3 | 154 |  |  | May 8, 2020 8:00 AM | July 21, 2020 5:00 PM | May 10, 2020 05:00 PM | July 23, 2020 05:00 PM | July 23, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 72 days | 72 days | 72 days | General worker
156 | Yes | CMU1.6.3 | Auto Scheduled | งานสถาปัตยกรรม ชั้นใต้ดิน | 398 days | 3 |  |  |  | August 19, 2019 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | November 18, 2019 05:00 PM | September 04, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 320 days | 12 days | 12 days
157 | Yes | CMU1.6.3.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 158,160,161 |  |  | August 21, 2020 8:00 AM | September 19, 2020 5:00 PM | September 03, 2020 05:00 PM | October 02, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | Skilled carpenter
158 | Yes | CMU1.6.3.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 154FS+45 days |  | 157,162 | June 22, 2020 8:00 AM | August 20, 2020 5:00 PM | June 24, 2020 05:00 PM | August 22, 2020 05:00 PM | February 09, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
159 | Yes | CMU1.6.3.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 154FS+45 days |  | 160,161 | June 22, 2020 8:00 AM | July 21, 2020 5:00 PM | July 05, 2020 05:00 PM | August 03, 2020 05:00 PM | August 22, 2020 05:00 PM | September 20, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
160 | Yes | CMU1.6.3.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 159 |  | 157,162 | July 22, 2020 8:00 AM | August 20, 2020 5:00 PM | August 04, 2020 05:00 PM | September 02, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | Skilled carpenter
161 | Yes | CMU1.6.3.5 | Auto Scheduled | งานบันได | 30 days | 4 | 159 |  | 157,162 | July 22, 2020 8:00 AM | August 20, 2020 5:00 PM | August 04, 2020 05:00 PM | September 02, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
162 | Yes | CMU1.6.3.6 | Auto Scheduled | งานสี | 30 days | 4 | 158,160,161 |  |  | August 21, 2020 8:00 AM | September 19, 2020 5:00 PM | September 03, 2020 05:00 PM | October 02, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
163 | Yes | CMU1.6.3.7 | Auto Scheduled | งานสุขภัณฑ์ | 15 days | 4 |  |  |  | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | October 18, 2018 05:00 PM | November 01, 2018 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 395 days | 395 days | 395 days
164 | Yes | CMU1.6.3.7.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 135FS+135 days |  |  | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | August 26, 2019 05:00 PM | September 09, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 395 days | 395 days | 395 days | Sanitary-Plumber
165 | Yes | CMU1.6.4 | Auto Scheduled | งานระบบสุขาภิบาล ชั้นใต้ดิน | 501 days | 3 |  |  |  | April 6, 2019 8:00 AM | August 18, 2020 5:00 PM | October 17, 2018 05:00 PM | February 29, 2020 05:00 PM | May 24, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 44 days | 44 days
166 | Yes | CMU1.6.4.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 126 days | 4 |  |  |  | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | October 20, 2018 05:00 PM | February 22, 2019 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 419 days | 419 days | 419 days
167 | Yes | CMU1.6.4.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 140FS+15 days |  |  | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 11, 2019 05:00 PM | August 14, 2019 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 419 days | 419 days | 419 days | Sanitary-Plumber
168 | Yes | CMU1.6.4.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 126 days | 4 |  |  |  | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | October 20, 2018 05:00 PM | February 22, 2019 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 44 days | 44 days
169 | Yes | CMU1.6.4.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 144FS+15 days |  | 170FS+300 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 06, 2019 05:00 PM | August 09, 2019 05:00 PM | May 24, 2019 05:00 PM | September 26, 2019 05:00 PM | As Soon As Possible |  | No | 44 days | 44 days | 0 days | Sanitary-Plumber
170 | Yes | CMU1.6.4.3 | Auto Scheduled | งานระบบระบายน้ำฝน | 75 days | 4 | 169FS+300 days |  |  | June 5, 2020 8:00 AM | August 18, 2020 5:00 PM | June 05, 2020 05:00 PM | August 18, 2020 05:00 PM | July 23, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 44 days | 44 days | 44 days | Sanitary-Plumber
171 | Yes | CMU1.6.5 | Auto Scheduled | งานระบบไฟฟ้า ชั้นใต้ดิน | 147 days | 3 |  |  |  | April 8, 2020 8:00 AM | September 1, 2020 5:00 PM | October 22, 2018 05:00 PM | March 17, 2019 05:00 PM | May 12, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 30 days | 30 days | 30 days
172 | Yes | CMU1.6.5.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 60 days | 4 | 174FS+7 days |  |  | July 4, 2020 8:00 AM | September 1, 2020 5:00 PM | July 06, 2020 05:00 PM | September 03, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 30 days | 30 days | 30 days | Electrician
173 | Yes | CMU1.6.5.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 60 days | 4 | 174FS+7 days |  |  | July 4, 2020 8:00 AM | September 1, 2020 5:00 PM | July 06, 2020 05:00 PM | September 03, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 30 days | 30 days | 30 days | Electrician
174 | Yes | CMU1.6.5.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 154SS |  | 173FS+7 days,172FS+7 days | April 8, 2020 8:00 AM | June 26, 2020 5:00 PM | April 10, 2020 05:00 PM | June 28, 2020 05:00 PM | May 12, 2020 05:00 PM | July 30, 2020 05:00 PM | As Soon As Possible |  | No | 30 days | 30 days | 0 days | Electrician
175 | Yes | CMU1.6.5.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 154SS |  |  | April 8, 2020 8:00 AM | June 26, 2020 5:00 PM | April 12, 2020 05:00 PM | June 30, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 97 days | 97 days | 97 days | Electrician
176 | Yes | CMU1.6.5.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 154SS |  |  | April 8, 2020 8:00 AM | June 26, 2020 5:00 PM | April 12, 2020 05:00 PM | June 30, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 97 days | 97 days | 97 days | Electrician
177 | Yes | CMU1.6.6 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้นใต้ดิน | 165 days | 3 | 154SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 10, 2020 05:00 PM | September 21, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | Skilled carpenter
178 | Yes | CMU1.7 | Auto Scheduled | หมวดงานระบบคอมพิวเตอร์และแจ้งเหตุเพลิงไหม้ | 670 days | 2 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
179 | Yes | CMU1.7.1 | Auto Scheduled | งานระบบคอมพิวเตอร์ | 670 days | 3 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
180 | Yes | CMU1.7.1.1 | Auto Scheduled | ชั้นที่ 4 | 160 days | 4 | 36FS+14 days |  | 181 | November 30, 2018 8:00 AM | May 8, 2019 5:00 PM | November 30, 2018 05:00 PM | May 08, 2019 05:00 PM | April 24, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
181 | Yes | CMU1.7.1.2 | Auto Scheduled | ชั้นที่ 3 | 175 days | 4 | 180 | 182 | 182 | May 9, 2019 8:00 AM | October 30, 2019 5:00 PM | May 09, 2019 05:00 PM | October 30, 2019 05:00 PM | April 09, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
182 | Yes | CMU1.7.1.3 | Auto Scheduled | ชั้นที่ 2 | 175 days | 4 | 181 | 183 | 183,184 | October 31, 2019 8:00 AM | April 22, 2020 5:00 PM | October 31, 2019 05:00 PM | April 22, 2020 05:00 PM | April 09, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
183 | Yes | CMU1.7.1.4 | Auto Scheduled | ชั้นที่ 1 | 160 days | 4 | 182 | 180 |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 23, 2020 05:00 PM | September 29, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
184 | Yes | CMU1.7.1.5 | Auto Scheduled | ชั้นใต้ดิน | 160 days | 4 | 182 | 183SS |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 23, 2020 05:00 PM | September 29, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
185 | Yes | CMU1.7.2 | Auto Scheduled | ระบบแจ้งเหตุเพลิงไหม้ | 670 days | 3 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
186 | Yes | CMU1.7.2.1 | Auto Scheduled | ชั้นที่ 4 | 160 days | 4 | 36FS+14 days |  | 187 | November 30, 2018 8:00 AM | May 8, 2019 5:00 PM | November 30, 2018 05:00 PM | May 08, 2019 05:00 PM | April 24, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
187 | Yes | CMU1.7.2.2 | Auto Scheduled | ชั้นที่ 3 | 175 days | 4 | 186 | 188 | 188 | May 9, 2019 8:00 AM | October 30, 2019 5:00 PM | May 09, 2019 05:00 PM | October 30, 2019 05:00 PM | April 09, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
188 | Yes | CMU1.7.2.3 | Auto Scheduled | ชั้นที่ 2 | 175 days | 4 | 187 | 189 | 189,190 | October 31, 2019 8:00 AM | April 22, 2020 5:00 PM | October 31, 2019 05:00 PM | April 22, 2020 05:00 PM | April 09, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
189 | Yes | CMU1.7.2.4 | Auto Scheduled | ชั้นที่ 1 | 160 days | 4 | 188 | 186 |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 23, 2020 05:00 PM | September 29, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
190 | Yes | CMU1.7.2.5 | Auto Scheduled | ชั้นใต้ดิน | 160 days | 4 | 188 | 189SS |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 23, 2020 05:00 PM | September 29, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
191 | Yes | CMU1.8 | Auto Scheduled | หมวดงานสีภายนอก งานซ่อมแซมและตกแต่งภายนอกอาคาร | 660 days | 2 |  |  |  | November 30, 2018 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | August 06, 2020 05:00 PM | December 16, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 507 days | 12 days | 12 days
192 | Yes | CMU1.8.1 | Auto Scheduled | งานสีภายนอกและงานซ่อมแซมพื้นผิวภายนอกอาคาร | 660 days | 3 |  |  |  | November 30, 2018 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | August 06, 2020 05:00 PM | December 16, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 507 days | 12 days | 12 days
193 | Yes | CMU1.8.1.1 | Auto Scheduled | งานขัดลอกสีทาผนังเดิม | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 10, 2020 05:00 PM | September 21, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
194 | Yes | CMU1.8.1.2 | Auto Scheduled | น้ำยาทาปูนเก่า (สีรองพื้น) | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 10, 2020 05:00 PM | September 21, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
195 | Yes | CMU1.8.1.3 | Auto Scheduled | งานทาสีภายนอก (ทา 2 เที่ยว) ไม่รวมชั้นใต้ดิน | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 10, 2020 05:00 PM | September 21, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
196 | Yes | CMU1.8.1.4 | Auto Scheduled | งานทำความสะอาดและซ่อมแซมผนังกรุอิฐโชว์แนว (อ้างอิงราคางานขัดลอกสี) | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 10, 2020 05:00 PM | September 21, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
197 | Yes | CMU1.8.1.5 | Auto Scheduled | น้ำยาเคลือบผิวผนังอิฐโชว์แนว (อ้างอิงค่าทาน้ำยากันเชื้อรา) | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 10, 2020 05:00 PM | September 21, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
198 | Yes | CMU1.8.1.6 | Auto Scheduled | งานรื้อถอนแผ่นวัสดุกันซึมหลังคาดาดฟ้า (รื้อขนไป) | 90 days | 4 | 36FS+14 days |  |  | November 30, 2018 8:00 AM | February 27, 2019 5:00 PM | December 03, 2018 05:00 PM | March 02, 2019 05:00 PM | July 08, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 582 days | 582 days | 582 days | General worker
199 | Yes | CMU1.8.1.7 | Auto Scheduled | งานแผ่นวัสดุกันซึมแบบเป่าไฟผิวทราย | 90 days | 4 | 36FS+14 days |  |  | November 30, 2018 8:00 AM | February 27, 2019 5:00 PM | December 03, 2018 05:00 PM | March 02, 2019 05:00 PM | July 08, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 582 days | 582 days | 582 days | General worker
200 | Yes | CMU1.8.1.8 | Auto Scheduled | งานกันซึมชนิด Polyurethane สูตรน้ำมัน ชนิดยืดหยุ่นสูงเป็นพิเศษ | 90 days | 4 | 36FS+14 days |  |  | November 30, 2018 8:00 AM | February 27, 2019 5:00 PM | December 03, 2018 05:00 PM | March 02, 2019 05:00 PM | July 08, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 582 days | 582 days | 582 days | General worker
201 | Yes | CMU1.8.2 | Auto Scheduled | งานตกแต่งภายนอกอาคาร | 165 days | 3 |  |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | October 19, 2018 05:00 PM | April 01, 2019 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 12 days | 12 days | 12 days
202 | Yes | CMU1.8.2.1 | Auto Scheduled | ตะแกรงเหล็กฉีกกันนก XS-32 | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 10, 2020 05:00 PM | September 21, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
203 | Yes | CMU1.9 | Auto Scheduled | หมวดงานบริเวณ | 165 days | 2 |  |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | October 22, 2018 05:00 PM | April 04, 2019 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 12 days | 12 days | 12 days
204 | Yes | CMU1.9.1 | Auto Scheduled | งานรื้อถอน งานบริเวณ | 165 days | 3 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 10, 2020 05:00 PM | September 21, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
205 | Yes | CMU1.9.2 | Auto Scheduled | งานโครงสร้างวิศวกรรม งานบริเวณ | 165 days | 3 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 10, 2020 05:00 PM | September 21, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
206 | Yes | CMU1.9.3 | Auto Scheduled | งานสถาปัตยกรรม งานบริเวณ | 165 days | 3 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 10, 2020 05:00 PM | September 21, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
207 | Yes | CMU1.9.4 | Auto Scheduled | งานระบบไฟฟ้า งานบริเวณ | 165 days | 3 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 10, 2020 05:00 PM | September 21, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | Electrician
208 | Yes | CMU1.10 | Auto Scheduled | หมวดงานครุภัณฑ์จัดซื้อ | 670 days | 2 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
209 | Yes | CMU1.10.1 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัว | 510 days | 3 |  |  |  | April 14, 2019 8:00 AM | September 4, 2020 5:00 PM | October 17, 2018 05:00 PM | March 09, 2020 05:00 PM | May 15, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 522 days | 27 days | 27 days
210 | Yes | CMU1.10.1.1 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้นใต้ดิน | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | August 26, 2020 05:00 PM | September 09, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
211 | Yes | CMU1.10.1.2 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้น 1 | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | August 30, 2020 05:00 PM | September 13, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
212 | Yes | CMU1.10.1.3 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้น 2 | 15 days | 4 | 121FS-15 days |  |  | March 24, 2020 8:00 AM | April 7, 2020 5:00 PM | March 26, 2020 05:00 PM | April 09, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Skilled carpenter
213 | Yes | CMU1.10.1.4 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้น 3 | 15 days | 4 | 92FS-15 days |  |  | September 26, 2019 8:00 AM | October 10, 2019 5:00 PM | October 03, 2019 05:00 PM | October 17, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Skilled carpenter
214 | Yes | CMU1.10.1.5 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้น 4 | 15 days | 4 | 63 |  |  | April 14, 2019 8:00 AM | April 28, 2019 5:00 PM | April 19, 2019 05:00 PM | May 03, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 522 days | 522 days | 522 days | Skilled carpenter
215 | Yes | CMU1.10.2 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ | 525 days | 3 |  |  |  | March 30, 2019 8:00 AM | September 4, 2020 5:00 PM | October 17, 2018 05:00 PM | March 24, 2020 05:00 PM | April 30, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 522 days | 27 days | 27 days
216 | Yes | CMU1.10.2.1 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ ชั้น 1 | 30 days | 4 | 152FS-45 days |  |  | August 6, 2020 8:00 AM | September 4, 2020 5:00 PM | August 13, 2020 05:00 PM | September 11, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
217 | Yes | CMU1.10.2.2 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ ชั้น 2 | 30 days | 4 | 121FS-30 days |  |  | March 9, 2020 8:00 AM | April 7, 2020 5:00 PM | March 13, 2020 05:00 PM | April 11, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Skilled carpenter
218 | Yes | CMU1.10.2.3 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ ชั้น 3 | 30 days | 4 | 92FS-30 days |  |  | September 11, 2019 8:00 AM | October 10, 2019 5:00 PM | September 14, 2019 05:00 PM | October 13, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Skilled carpenter
219 | Yes | CMU1.10.2.4 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ ชั้น 4 | 30 days | 4 | 63FS-15 days |  |  | March 30, 2019 8:00 AM | April 28, 2019 5:00 PM | April 01, 2019 05:00 PM | April 30, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 522 days | 522 days | 522 days | Skilled carpenter
220 | Yes | CMU1.10.3 | Auto Scheduled | งานผ้าม่าน | 510 days | 3 |  |  |  | April 14, 2019 8:00 AM | September 4, 2020 5:00 PM | October 17, 2018 05:00 PM | March 09, 2020 05:00 PM | May 15, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 522 days | 27 days | 27 days
221 | Yes | CMU1.10.3.1 | Auto Scheduled | งานผ้าม่าน ชั้น 1 | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | August 27, 2020 05:00 PM | September 10, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
222 | Yes | CMU1.10.3.2 | Auto Scheduled | งานผ้าม่าน ชั้น 2 | 15 days | 4 | 121FS-15 days |  |  | March 24, 2020 8:00 AM | April 7, 2020 5:00 PM | March 28, 2020 05:00 PM | April 11, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Skilled carpenter
223 | Yes | CMU1.10.3.3 | Auto Scheduled | งานผ้าม่าน ชั้น 3 | 15 days | 4 | 92FS-15 days |  |  | September 26, 2019 8:00 AM | October 10, 2019 5:00 PM | September 30, 2019 05:00 PM | October 14, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Skilled carpenter
224 | Yes | CMU1.10.3.4 | Auto Scheduled | งานผ้าม่าน ชั้น 4 | 15 days | 4 | 63 |  |  | April 14, 2019 8:00 AM | April 28, 2019 5:00 PM | April 22, 2019 05:00 PM | May 06, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 522 days | 522 days | 522 days | Skilled carpenter
225 | Yes | CMU1.10.4 | Auto Scheduled | งานป้าย | 510 days | 3 |  |  |  | April 14, 2019 8:00 AM | September 4, 2020 5:00 PM | October 17, 2018 05:00 PM | March 09, 2020 05:00 PM | May 15, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 522 days | 27 days | 27 days
226 | Yes | CMU1.10.4.1 | Auto Scheduled | งานป้าย ชั้นใต้ดิน | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | August 26, 2020 05:00 PM | September 09, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
227 | Yes | CMU1.10.4.2 | Auto Scheduled | งานป้าย ชั้น 1 | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | August 29, 2020 05:00 PM | September 12, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
228 | Yes | CMU1.10.4.3 | Auto Scheduled | งานป้าย ชั้น 2 | 15 days | 4 | 121FS-15 days |  |  | March 24, 2020 8:00 AM | April 7, 2020 5:00 PM | March 28, 2020 05:00 PM | April 11, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Skilled carpenter
229 | Yes | CMU1.10.4.4 | Auto Scheduled | งานป้าย ชั้น 3 | 15 days | 4 | 92FS-15 days |  |  | September 26, 2019 8:00 AM | October 10, 2019 5:00 PM | October 02, 2019 05:00 PM | October 16, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Skilled carpenter
230 | Yes | CMU1.10.4.5 | Auto Scheduled | งานป้าย ชั้น 4 | 15 days | 4 | 63 |  |  | April 14, 2019 8:00 AM | April 28, 2019 5:00 PM | April 19, 2019 05:00 PM | May 03, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 522 days | 522 days | 522 days | Skilled carpenter
231 | Yes | CMU1.10.5 | Auto Scheduled | งานอื่นๆ | 15 days | 3 |  |  |  | August 6, 2020 8:00 AM | August 20, 2020 5:00 PM | October 19, 2018 05:00 PM | November 02, 2018 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 42 days | 42 days | 42 days
232 | Yes | CMU1.10.5.1 | Auto Scheduled | ตู้อลูมิเนียมพับขึ้นรูป พ่นสี ครอบตู้กดน้ำ | 15 days | 4 | 152FS-45 days |  |  | August 6, 2020 8:00 AM | August 20, 2020 5:00 PM | August 11, 2020 05:00 PM | August 25, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 42 days | 42 days | 42 days | General worker
233 | Yes | CMU1.10.6 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ | 670 days | 3 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
234 | Yes | CMU1.10.6.1 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้นใต้ดิน | 160 days | 4 | 236 |  |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 26, 2020 05:00 PM | October 02, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
235 | Yes | CMU1.10.6.2 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้น 1 | 160 days | 4 | 236 |  |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 26, 2020 05:00 PM | October 02, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
236 | Yes | CMU1.10.6.3 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้น 2 | 175 days | 4 | 237 |  | 235,234 | October 31, 2019 8:00 AM | April 22, 2020 5:00 PM | November 03, 2019 05:00 PM | April 25, 2020 05:00 PM | March 12, 2020 05:00 PM | September 02, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
237 | Yes | CMU1.10.6.4 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้น 3 | 175 days | 4 | 238 |  | 236 | May 9, 2019 8:00 AM | October 30, 2019 5:00 PM | May 12, 2019 05:00 PM | November 02, 2019 05:00 PM | March 12, 2020 05:00 PM | September 02, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
238 | Yes | CMU1.10.6.5 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้น 4 | 160 days | 4 | 36FS+14 days |  | 237 | November 30, 2018 8:00 AM | May 8, 2019 5:00 PM | December 01, 2018 05:00 PM | May 09, 2019 05:00 PM | March 27, 2020 05:00 PM | September 02, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
239 | Yes | CMU1.10.7 | Auto Scheduled | งานระบบเครื่องเสียงประกาศ (ใช้ลำโพงของเดิม) | 539 days | 3 |  |  |  | April 7, 2019 8:00 AM | September 26, 2020 5:00 PM | October 17, 2018 05:00 PM | April 07, 2020 05:00 PM | April 16, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 530 days | 5 days | 5 days
240 | Yes | CMU1.10.7.1 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้นใต้ดิน | 7 days | 4 | 241 |  |  | September 20, 2020 8:00 AM | September 26, 2020 5:00 PM | September 25, 2020 05:00 PM | October 01, 2020 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 5 days | 5 days | 5 days | Electrician
241 | Yes | CMU1.10.7.2 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้น 1 | 7 days | 4 | 152FS-7 days |  | 240 | September 13, 2020 8:00 AM | September 19, 2020 5:00 PM | September 15, 2020 05:00 PM | September 21, 2020 05:00 PM | September 09, 2020 05:00 PM | September 15, 2020 05:00 PM | As Soon As Possible |  | No | 5 days | 5 days | 0 days | Electrician
242 | Yes | CMU1.10.7.3 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้น 2 | 7 days | 4 | 121FS-7 days |  |  | April 1, 2020 8:00 AM | April 7, 2020 5:00 PM | April 04, 2020 05:00 PM | April 10, 2020 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Electrician
243 | Yes | CMU1.10.7.4 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้น 3 | 7 days | 4 | 92FS-7 days |  |  | October 4, 2019 8:00 AM | October 10, 2019 5:00 PM | October 13, 2019 05:00 PM | October 19, 2019 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Electrician
244 | Yes | CMU1.10.7.5 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้น 4 | 7 days | 4 | 63FS-7 days |  |  | April 7, 2019 8:00 AM | April 13, 2019 5:00 PM | April 12, 2019 05:00 PM | April 18, 2019 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 537 days | 537 days | 537 days | Electrician
245 | Yes | CMU1.10.8 | Auto Scheduled | งานระบบกล้องวงจรปิด (ใช้กล้องวงจรปิดของเดิม) | 539 days | 3 |  |  |  | April 7, 2019 8:00 AM | September 26, 2020 5:00 PM | October 17, 2018 05:00 PM | April 07, 2020 05:00 PM | April 16, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 530 days | 5 days | 5 days
246 | Yes | CMU1.10.8.1 | Auto Scheduled | งานกล้องวงจรปิด ชั้นใต้ดิน | 7 days | 4 | 247 |  |  | September 20, 2020 8:00 AM | September 26, 2020 5:00 PM | September 25, 2020 05:00 PM | October 01, 2020 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 5 days | 5 days | 5 days | Electrician
247 | Yes | CMU1.10.8.2 | Auto Scheduled | งานกล้องวงจรปิด ชั้น 1 | 7 days | 4 | 152FS-7 days |  | 246 | September 13, 2020 8:00 AM | September 19, 2020 5:00 PM | September 15, 2020 05:00 PM | September 21, 2020 05:00 PM | September 09, 2020 05:00 PM | September 15, 2020 05:00 PM | As Soon As Possible |  | No | 5 days | 5 days | 0 days | Electrician
248 | Yes | CMU1.10.8.3 | Auto Scheduled | งานกล้องวงจรปิด ชั้น 2 | 7 days | 4 | 121FS-7 days |  |  | April 1, 2020 8:00 AM | April 7, 2020 5:00 PM | April 06, 2020 05:00 PM | April 12, 2020 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Electrician
249 | Yes | CMU1.10.8.4 | Auto Scheduled | งานกล้องวงจรปิด ชั้น 3 | 7 days | 4 | 92FS-7 days |  |  | October 4, 2019 8:00 AM | October 10, 2019 5:00 PM | October 09, 2019 05:00 PM | October 15, 2019 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Electrician
250 | Yes | CMU1.10.8.5 | Auto Scheduled | งานกล้องวงจรปิด ชั้น 4 | 7 days | 4 | 63FS-7 days |  |  | April 7, 2019 8:00 AM | April 13, 2019 5:00 PM | April 10, 2019 05:00 PM | April 16, 2019 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 537 days | 537 days | 537 days | Electrician

## solutoion_4
ID | Active | WBS | Task_Mode | Name | Duration | Outline_Level | Predecessors | Predecessors2 | Successors | Start_Date | Finish_Date | Early_Start | Early_Finish | Late_Start | Late_Finish | Constraint_Type | Constraint_Date | Summary | Start_Slack | Finish_Slack | Free_Slack | Resource_Names
1 | Yes | CMU1 | Auto Scheduled | โครงการปรับปรุงสำนักหอสมุด มหาวิทยาลัยเชียงใหม่ | 716 days | 1 |  |  |  | October 17, 2018 8:00 AM | October 1, 2020 5:00 PM | October 17, 2018 05:00 PM | October 01, 2020 05:00 PM | October 21, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 0 days | 0 days | 0 days
2 | Yes | CMU1.1 | Auto Scheduled | หมวดเตรียมการ | 675 days | 2 |  |  |  | October 17, 2018 8:00 AM | August 21, 2020 5:00 PM | October 17, 2018 05:00 PM | August 21, 2020 05:00 PM | December 01, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 41 days | 41 days | 41 days
3 | Yes | CMU1.1.1 | Auto Scheduled | งานอาคารสนามและผังบริเวณโครงการ | 14 days | 3 | 4FS-7 days |  |  | October 26, 2018 8:00 AM | November 8, 2018 5:00 PM | November 01, 2018 05:00 PM | November 14, 2018 05:00 PM | September 22, 2020 05:00 PM | October 05, 2020 05:00 PM | Start No Earlier Than | Oct 24 '18 | No | 693 days | 693 days | 693 days | Engineer
4 | Yes | CMU1.1.2 | Auto Scheduled | งานเชื่อมต่อระบบสาธารณูปโภคโครงการ | 16 days | 3 |  |  | 3FS-7 days | October 17, 2018 8:00 AM | November 1, 2018 5:00 PM | October 19, 2018 05:00 PM | November 03, 2018 05:00 PM | September 13, 2020 05:00 PM | September 28, 2020 05:00 PM | As Soon As Possible |  | No | 693 days | 693 days | 0 days | Engineer
5 | Yes | CMU1.1.3 | Auto Scheduled | งานตรวจทดสอบระบบภายในอาคารก่อนดำเนินการปรับปรุง | 675 days | 3 |  |  |  | October 17, 2018 8:00 AM | August 21, 2020 5:00 PM | October 17, 2018 05:00 PM | August 21, 2020 05:00 PM | December 01, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 41 days | 41 days | 41 days
6 | Yes | CMU1.1.3.1 | Auto Scheduled | ชั้นที่ 4 | 15 days | 4 |  |  | 7FS+150 days | October 17, 2018 8:00 AM | October 31, 2018 5:00 PM | October 19, 2018 05:00 PM | November 02, 2018 05:00 PM | December 01, 2018 05:00 PM | December 15, 2018 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
7 | Yes | CMU1.1.3.2 | Auto Scheduled | ชั้นที่ 3 | 15 days | 4 | 6FS+150 days |  | 8FS+150 days | March 31, 2019 8:00 AM | April 14, 2019 5:00 PM | April 07, 2019 05:00 PM | April 21, 2019 05:00 PM | May 15, 2019 05:00 PM | May 29, 2019 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
8 | Yes | CMU1.1.3.3 | Auto Scheduled | ชั้นที่ 2 | 15 days | 4 | 7FS+150 days |  | 9FS+150 days | September 12, 2019 8:00 AM | September 26, 2019 5:00 PM | September 29, 2019 05:00 PM | October 13, 2019 05:00 PM | October 27, 2019 05:00 PM | November 10, 2019 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
9 | Yes | CMU1.1.3.4 | Auto Scheduled | ชั้นที่ 1 | 15 days | 4 | 8FS+150 days |  | 10FS+150 days | February 24, 2020 8:00 AM | March 9, 2020 5:00 PM | March 17, 2020 05:00 PM | March 31, 2020 05:00 PM | April 09, 2020 05:00 PM | April 23, 2020 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
10 | Yes | CMU1.1.3.5 | Auto Scheduled | ชั้นใต้ดินและภายนอก | 15 days | 4 | 9FS+150 days |  |  | August 7, 2020 8:00 AM | August 21, 2020 5:00 PM | September 08, 2020 05:00 PM | September 22, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 41 days | Engineer
11 | Yes | CMU1.1.4 | Auto Scheduled | งานสำรวจอุปกรณ์ไฟฟ้า, สุขภัณฑ์และครุภัณฑ์ (ของเดิม) ก่อนดำเนินการปรับปรุง | 675 days | 3 |  |  |  | October 17, 2018 8:00 AM | August 21, 2020 5:00 PM | October 17, 2018 05:00 PM | August 21, 2020 05:00 PM | December 01, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 41 days | 41 days | 41 days
12 | Yes | CMU1.1.4.1 | Auto Scheduled | ชั้นที่ 4 | 15 days | 4 |  |  | 13FS+150 days | October 17, 2018 8:00 AM | October 31, 2018 5:00 PM | October 18, 2018 05:00 PM | November 01, 2018 05:00 PM | December 01, 2018 05:00 PM | December 15, 2018 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
13 | Yes | CMU1.1.4.2 | Auto Scheduled | ชั้นที่ 3 | 15 days | 4 | 12FS+150 days |  | 14FS+150 days | March 31, 2019 8:00 AM | April 14, 2019 5:00 PM | April 04, 2019 05:00 PM | April 18, 2019 05:00 PM | May 15, 2019 05:00 PM | May 29, 2019 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
14 | Yes | CMU1.1.4.3 | Auto Scheduled | ชั้นที่ 2 | 15 days | 4 | 13FS+150 days |  | 15FS+150 days | September 12, 2019 8:00 AM | September 26, 2019 5:00 PM | September 22, 2019 05:00 PM | October 06, 2019 05:00 PM | October 27, 2019 05:00 PM | November 10, 2019 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
15 | Yes | CMU1.1.4.4 | Auto Scheduled | ชั้นที่ 1 | 15 days | 4 | 14FS+150 days |  | 16FS+150 days | February 24, 2020 8:00 AM | March 9, 2020 5:00 PM | March 22, 2020 05:00 PM | April 05, 2020 05:00 PM | April 09, 2020 05:00 PM | April 23, 2020 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
16 | Yes | CMU1.1.4.5 | Auto Scheduled | ชั้นใต้ดินและภายนอก | 15 days | 4 | 15FS+150 days |  |  | August 7, 2020 8:00 AM | August 21, 2020 5:00 PM | September 10, 2020 05:00 PM | September 24, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 41 days | Engineer
17 | Yes | CMU1.1.5 | Auto Scheduled | งานเอกสารขออนุมัติใช้วัสดุ, Shop Drawing และครุภัณฑ์ของโครงการ | 106 days | 3 |  |  |  | October 17, 2018 8:00 AM | January 30, 2019 5:00 PM | October 21, 2018 05:00 PM | February 03, 2019 05:00 PM | June 22, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 610 days | 610 days | 610 days
18 | Yes | CMU1.1.5.1 | Auto Scheduled | แบบ Shop Drawing ชั้นที่ 4 | 20 days | 4 |  |  | 19,25SS+14 days,26SS+14 days | October 17, 2018 8:00 AM | November 5, 2018 5:00 PM | October 17, 2018 05:00 PM | November 05, 2018 05:00 PM | October 01, 2018 05:00 PM | October 20, 2018 05:00 PM | As Soon As Possible |  | No | 610 days | 610 days | 0 days | Engineer
19 | Yes | CMU1.1.5.2 | Auto Scheduled | แบบ Shop Drawing ชั้นที่ 3 | 20 days | 4 | 18 |  | 20FS-7 days | November 6, 2018 8:00 AM | November 25, 2018 5:00 PM | November 13, 2018 05:00 PM | December 02, 2018 05:00 PM | July 13, 2020 05:00 PM | August 01, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
20 | Yes | CMU1.1.5.3 | Auto Scheduled | แบบ Shop Drawing ชั้นที่ 2 | 20 days | 4 | 19FS-7 days |  | 21FS-7 days | November 19, 2018 8:00 AM | December 8, 2018 5:00 PM | November 29, 2018 05:00 PM | December 18, 2018 05:00 PM | July 26, 2020 05:00 PM | August 14, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
21 | Yes | CMU1.1.5.4 | Auto Scheduled | แบบ Shop Drawing ชั้นที่ 1 | 20 days | 4 | 20FS-7 days |  | 22FS-7 days | December 2, 2018 8:00 AM | December 21, 2018 5:00 PM | December 18, 2018 05:00 PM | January 06, 2019 05:00 PM | August 08, 2020 05:00 PM | August 27, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
22 | Yes | CMU1.1.5.5 | Auto Scheduled | แบบ Shop Drawing ชั้นใต้ดิน | 20 days | 4 | 21FS-7 days |  | 23FS-7 days | December 15, 2018 8:00 AM | January 3, 2019 5:00 PM | January 06, 2019 05:00 PM | January 25, 2019 05:00 PM | August 21, 2020 05:00 PM | September 09, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
23 | Yes | CMU1.1.5.6 | Auto Scheduled | แบบ Shop Drawing ภายนอกอาคาร | 20 days | 4 | 22FS-7 days |  | 24FS-7 days | December 28, 2018 8:00 AM | January 16, 2019 5:00 PM | January 23, 2019 05:00 PM | February 11, 2019 05:00 PM | September 03, 2020 05:00 PM | September 22, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
24 | Yes | CMU1.1.5.7 | Auto Scheduled | แบบ Shop Drawing landscape | 20 days | 4 | 23FS-7 days |  |  | January 10, 2019 8:00 AM | January 29, 2019 5:00 PM | February 13, 2019 05:00 PM | March 04, 2019 05:00 PM | September 16, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 611 days | Engineer
25 | Yes | CMU1.1.5.8 | Auto Scheduled | แบบ Shop Drawing งานปรับปรุง ครุภัณฑ์ | 92 days | 4 | 18SS+14 days |  |  | October 31, 2018 8:00 AM | January 30, 2019 5:00 PM | November 15, 2018 05:00 PM | February 14, 2019 05:00 PM | July 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 610 days | 610 days | 610 days | Engineer
26 | Yes | CMU1.1.5.9 | Auto Scheduled | แบบ Shop Drawing งานจัดซื้อครุภัณฑ์ | 92 days | 4 | 18SS+14 days |  |  | October 31, 2018 8:00 AM | January 30, 2019 5:00 PM | November 07, 2018 05:00 PM | February 06, 2019 05:00 PM | July 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 610 days | 610 days | 610 days | Engineer
27 | Yes | CMU1.1.6 | Auto Scheduled | งานตรวจทดสอบระบบ, งานอบรมผู้ใช้อาคาร และ As-Built Drawing | 30 days | 3 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 22, 2018 05:00 PM | November 20, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 686 days | 686 days | 686 days
28 | Yes | CMU1.1.6.1 | Auto Scheduled | ชั้นที่ 4 | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 27, 2018 05:00 PM | November 25, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
29 | Yes | CMU1.1.6.2 | Auto Scheduled | ชั้นที่ 3 | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 29, 2018 05:00 PM | November 27, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
30 | Yes | CMU1.1.6.3 | Auto Scheduled | ชั้นที่ 2 | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 21, 2018 05:00 PM | November 19, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
31 | Yes | CMU1.1.6.4 | Auto Scheduled | ชั้นที่ 1 | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 29, 2018 05:00 PM | November 27, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
32 | Yes | CMU1.1.6.5 | Auto Scheduled | ชั้นใต้ดิน | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 24, 2018 05:00 PM | November 22, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
33 | Yes | CMU1.1.6.6 | Auto Scheduled | ทั้งอาคาร | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 23, 2018 05:00 PM | November 21, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
34 | Yes | CMU1.1.7 | Auto Scheduled | งานบริหารงานก่อสร้างและงานอื่น ๆ | 0 days | 3 |  |  |  | October 17, 2018 8:00 AM | October 17, 2018 8:00 AM | October 20, 2018 05:00 PM | October 19, 2018 05:00 PM | October 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 716 days | 716 days | 716 days | Engineer
35 | Yes | CMU1.2 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้น 4 | 471 days | 2 |  |  |  | October 17, 2018 8:00 AM | January 30, 2020 5:00 PM | October 17, 2018 05:00 PM | January 30, 2020 05:00 PM | June 23, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 0 days | 245 days | 0 days
36 | Yes | CMU1.2.1 | Auto Scheduled | งานรื้อถอน ชั้น 4 (รื้อขนไป) | 30 days | 3 |  |  | 39FS+45 days,40FS+45 days,51,63SS+14 days,80,109,140,180FS+14 days,186FS+14 days,198FS+14 days,199FS+14 days,200FS+14 days,238FS+14 days | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 17, 2018 05:00 PM | November 15, 2018 05:00 PM | March 11, 2018 05:00 PM | April 09, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | General worker
37 | Yes | CMU1.2.2 | Auto Scheduled | งานสถาปัตยกรรม ชั้น 4 | 396 days | 3 |  |  |  | December 31, 2018 8:00 AM | January 30, 2020 5:00 PM | October 17, 2018 05:00 PM | November 16, 2019 05:00 PM | September 06, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 326 days | 245 days | 245 days
38 | Yes | CMU1.2.2.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 39,41,42 |  |  | March 1, 2019 8:00 AM | March 30, 2019 5:00 PM | March 11, 2019 05:00 PM | April 09, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 551 days | Skilled carpenter
39 | Yes | CMU1.2.2.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 36FS+45 days |  | 38,43 | December 31, 2018 8:00 AM | February 28, 2019 5:00 PM | January 05, 2019 05:00 PM | March 05, 2019 05:00 PM | July 15, 2020 05:00 PM | September 12, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 0 days | General worker
40 | Yes | CMU1.2.2.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 36FS+45 days |  | 41,42 | December 31, 2018 8:00 AM | January 29, 2019 5:00 PM | January 03, 2019 05:00 PM | February 01, 2019 05:00 PM | August 14, 2020 05:00 PM | September 12, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 0 days | General worker
41 | Yes | CMU1.2.2.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 40 |  | 38,43 | January 30, 2019 8:00 AM | February 28, 2019 5:00 PM | February 05, 2019 05:00 PM | March 06, 2019 05:00 PM | August 14, 2020 05:00 PM | September 12, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 0 days | Skilled carpenter
42 | Yes | CMU1.2.2.5 | Auto Scheduled | งานบันได | 30 days | 4 | 40 |  | 38,43 | January 30, 2019 8:00 AM | February 28, 2019 5:00 PM | February 05, 2019 05:00 PM | March 06, 2019 05:00 PM | August 14, 2020 05:00 PM | September 12, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 0 days | General worker
43 | Yes | CMU1.2.2.6 | Auto Scheduled | งานสี | 30 days | 4 | 39,41,42 |  |  | March 1, 2019 8:00 AM | March 30, 2019 5:00 PM | March 10, 2019 05:00 PM | April 08, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 551 days | General worker
44 | Yes | CMU1.2.2.7 | Auto Scheduled | งานสุขภัณฑ์ | 315 days | 4 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 20, 2018 05:00 PM | August 30, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
45 | Yes | CMU1.2.2.7.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 46FS+135 days |  | 47FS+135 days | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | September 10, 2019 05:00 PM | September 24, 2019 05:00 PM | April 24, 2020 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
46 | Yes | CMU1.2.2.7.2 | Auto Scheduled | ZONE T-2 กลาง | 15 days | 5 | 51,55 |  | 45FS+135 days | March 22, 2019 8:00 AM | April 5, 2019 5:00 PM | April 07, 2019 05:00 PM | April 21, 2019 05:00 PM | November 26, 2019 05:00 PM | December 10, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
47 | Yes | CMU1.2.2.7.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 15 days | 5 | 45FS+135 days |  |  | January 16, 2020 8:00 AM | January 30, 2020 5:00 PM | February 14, 2020 05:00 PM | February 28, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 245 days | Sanitary-Plumber
48 | Yes | CMU1.2.3 | Auto Scheduled | งานระบบสุขาภิบาล ชั้น 4 | 408 days | 3 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
49 | Yes | CMU1.2.3.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
50 | Yes | CMU1.2.3.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 51FS+15 days |  | 52FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 17, 2019 05:00 PM | August 20, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
51 | Yes | CMU1.2.3.1.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 36 |  | 50FS+15 days,46,55SS | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 23, 2018 05:00 PM | March 28, 2019 05:00 PM | August 25, 2019 05:00 PM | December 28, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
52 | Yes | CMU1.2.3.1.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 50FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 09, 2019 05:00 PM | January 12, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
53 | Yes | CMU1.2.3.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
54 | Yes | CMU1.2.3.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 55FS+15 days |  | 56FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 23, 2019 05:00 PM | August 26, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
55 | Yes | CMU1.2.3.2.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 51SS |  | 54FS+15 days,46 | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 27, 2018 05:00 PM | April 01, 2019 05:00 PM | August 25, 2019 05:00 PM | December 28, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
56 | Yes | CMU1.2.3.2.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 54FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 17, 2019 05:00 PM | January 20, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
57 | Yes | CMU1.2.4 | Auto Scheduled | งานระบบไฟฟ้า ชั้น 4 | 117 days | 3 |  |  |  | November 30, 2018 8:00 AM | March 26, 2019 5:00 PM | October 21, 2018 05:00 PM | February 14, 2019 05:00 PM | June 11, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 555 days | 555 days | 555 days
58 | Yes | CMU1.2.4.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 30 days | 4 | 60FS+7 days |  |  | February 25, 2019 8:00 AM | March 26, 2019 5:00 PM | March 02, 2019 05:00 PM | March 31, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 555 days | 555 days | 555 days | Electrician
59 | Yes | CMU1.2.4.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 30 days | 4 | 60FS+7 days |  |  | February 25, 2019 8:00 AM | March 26, 2019 5:00 PM | March 04, 2019 05:00 PM | April 02, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 555 days | 555 days | 555 days | Electrician
60 | Yes | CMU1.2.4.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 63SS+30 days |  | 58FS+7 days,59FS+7 days | November 30, 2018 8:00 AM | February 17, 2019 5:00 PM | December 03, 2018 05:00 PM | February 20, 2019 05:00 PM | June 11, 2020 05:00 PM | August 29, 2020 05:00 PM | As Soon As Possible |  | No | 555 days | 555 days | 0 days | Electrician
61 | Yes | CMU1.2.4.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 63SS+30 days |  |  | November 30, 2018 8:00 AM | February 17, 2019 5:00 PM | December 04, 2018 05:00 PM | February 21, 2019 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 592 days | 592 days | 592 days | Electrician
62 | Yes | CMU1.2.4.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 63SS+30 days |  |  | November 30, 2018 8:00 AM | February 17, 2019 5:00 PM | December 05, 2018 05:00 PM | February 22, 2019 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 592 days | 592 days | 592 days | Electrician
63 | Yes | CMU1.2.5 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้น 4 | 165 days | 3 | 36SS+14 days |  | 62SS+30 days,60SS+30 days,61SS+30 days,65,214,219FS-15 days,224,230,244FS-7 days,250FS-7 days | October 31, 2018 8:00 AM | April 13, 2019 5:00 PM | October 31, 2018 05:00 PM | April 13, 2019 05:00 PM | June 19, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Skilled carpenter
64 | Yes | CMU1.3 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้น 3 | 441 days | 2 |  |  |  | November 16, 2018 8:00 AM | January 30, 2020 5:00 PM | October 17, 2018 05:00 PM | December 31, 2019 05:00 PM | July 23, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 149 days | 245 days | 149 days
65 | Yes | CMU1.3.1 | Auto Scheduled | งานรื้อถอน ชั้น 3 (รื้อขนไป) | 30 days | 3 | 63 | 121 | 68FS+45 days,69FS+45 days,92SS | April 14, 2019 8:00 AM | May 13, 2019 5:00 PM | April 14, 2019 05:00 PM | May 13, 2019 05:00 PM | July 19, 2018 05:00 PM | August 17, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | General worker
66 | Yes | CMU1.3.2 | Auto Scheduled | งานสถาปัตยกรรม ชั้น 3 | 315 days | 3 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 21, 2018 05:00 PM | August 31, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
67 | Yes | CMU1.3.2.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 68,70,71 |  |  | August 27, 2019 8:00 AM | September 25, 2019 5:00 PM | August 30, 2019 05:00 PM | September 28, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 372 days | Skilled carpenter
68 | Yes | CMU1.3.2.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 65FS+45 days |  | 67,72 | June 28, 2019 8:00 AM | August 26, 2019 5:00 PM | June 28, 2019 05:00 PM | August 26, 2019 05:00 PM | October 02, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 0 days | General worker
69 | Yes | CMU1.3.2.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 65FS+45 days |  | 70,71 | June 28, 2019 8:00 AM | July 27, 2019 5:00 PM | June 28, 2019 05:00 PM | July 27, 2019 05:00 PM | April 15, 2019 05:00 PM | May 14, 2019 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 0 days | General worker
70 | Yes | CMU1.3.2.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 69 |  | 67,72 | July 28, 2019 8:00 AM | August 26, 2019 5:00 PM | July 28, 2019 05:00 PM | August 26, 2019 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 0 days | Skilled carpenter
71 | Yes | CMU1.3.2.5 | Auto Scheduled | งานบันได | 30 days | 4 | 69 |  | 67,72 | July 28, 2019 8:00 AM | August 26, 2019 5:00 PM | July 28, 2019 05:00 PM | August 26, 2019 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 0 days | General worker
72 | Yes | CMU1.3.2.6 | Auto Scheduled | งานสี | 30 days | 4 | 68,70,71 |  |  | August 27, 2019 8:00 AM | September 25, 2019 5:00 PM | August 30, 2019 05:00 PM | September 28, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 372 days | General worker
73 | Yes | CMU1.3.2.7 | Auto Scheduled | งานสุขภัณฑ์ | 315 days | 4 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 21, 2018 05:00 PM | August 31, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
74 | Yes | CMU1.3.2.7.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 75FS+135 days |  | 76FS+135 days | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | August 25, 2019 05:00 PM | September 08, 2019 05:00 PM | April 24, 2020 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
75 | Yes | CMU1.3.2.7.2 | Auto Scheduled | ZONE T-2 กลาง | 15 days | 5 | 80,84 |  | 74FS+135 days | March 22, 2019 8:00 AM | April 5, 2019 5:00 PM | March 24, 2019 05:00 PM | April 07, 2019 05:00 PM | November 26, 2019 05:00 PM | December 10, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
76 | Yes | CMU1.3.2.7.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 15 days | 5 | 74FS+135 days |  |  | January 16, 2020 8:00 AM | January 30, 2020 5:00 PM | January 26, 2020 05:00 PM | February 09, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 245 days | Sanitary-Plumber
77 | Yes | CMU1.3.3 | Auto Scheduled | งานระบบสุขาภิบาล ชั้น 3 | 408 days | 3 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
78 | Yes | CMU1.3.3.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
79 | Yes | CMU1.3.3.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 80FS+15 days |  | 81FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 15, 2019 05:00 PM | August 18, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
80 | Yes | CMU1.3.3.1.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 36 |  | 79FS+15 days,84SS,75 | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 16, 2018 05:00 PM | March 21, 2019 05:00 PM | January 09, 2019 05:00 PM | May 14, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
81 | Yes | CMU1.3.3.1.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 79FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 08, 2019 05:00 PM | January 11, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
82 | Yes | CMU1.3.3.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
83 | Yes | CMU1.3.3.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 84FS+15 days |  | 85FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 11, 2019 05:00 PM | August 14, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
84 | Yes | CMU1.3.3.2.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 80SS |  | 83FS+15 days,75 | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 16, 2018 05:00 PM | March 21, 2019 05:00 PM | January 09, 2019 05:00 PM | May 14, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
85 | Yes | CMU1.3.3.2.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 83FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 06, 2019 05:00 PM | January 09, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
86 | Yes | CMU1.3.4 | Auto Scheduled | งานระบบไฟฟ้า ชั้น 3 | 147 days | 3 |  |  |  | May 14, 2019 8:00 AM | October 7, 2019 5:00 PM | October 21, 2018 05:00 PM | March 16, 2019 05:00 PM | May 12, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 360 days | 360 days | 360 days
87 | Yes | CMU1.3.4.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 60 days | 4 | 89FS+7 days |  |  | August 9, 2019 8:00 AM | October 7, 2019 5:00 PM | August 17, 2019 05:00 PM | October 15, 2019 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 360 days | 360 days | 360 days | Electrician
88 | Yes | CMU1.3.4.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 60 days | 4 | 89FS+7 days |  |  | August 9, 2019 8:00 AM | October 7, 2019 5:00 PM | August 20, 2019 05:00 PM | October 18, 2019 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 360 days | 360 days | 360 days | Electrician
89 | Yes | CMU1.3.4.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 92SS+30 days |  | 88FS+7 days,87FS+7 days | May 14, 2019 8:00 AM | August 1, 2019 5:00 PM | May 19, 2019 05:00 PM | August 06, 2019 05:00 PM | May 12, 2020 05:00 PM | July 30, 2020 05:00 PM | As Soon As Possible |  | No | 360 days | 360 days | 0 days | Electrician
90 | Yes | CMU1.3.4.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 92SS+30 days |  |  | May 14, 2019 8:00 AM | August 1, 2019 5:00 PM | May 22, 2019 05:00 PM | August 09, 2019 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 427 days | 427 days | 427 days | Electrician
91 | Yes | CMU1.3.4.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 92SS+30 days |  |  | May 14, 2019 8:00 AM | August 1, 2019 5:00 PM | May 23, 2019 05:00 PM | August 10, 2019 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 427 days | 427 days | 427 days | Electrician
92 | Yes | CMU1.3.5 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้น 3 | 180 days | 3 | 65SS |  | 91SS+30 days,90SS+30 days,89SS+30 days,94,213FS-15 days,218FS-30 days,223FS-15 days,229FS-15 days,243FS-7 days,249FS-7 days | April 14, 2019 8:00 AM | October 10, 2019 5:00 PM | April 17, 2019 05:00 PM | October 13, 2019 05:00 PM | October 12, 2019 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Skilled carpenter
93 | Yes | CMU1.4 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้น 2 | 509 days | 2 |  |  |  | November 16, 2018 8:00 AM | April 7, 2020 5:00 PM | October 17, 2018 05:00 PM | March 08, 2020 05:00 PM | May 16, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 177 days | 177 days
94 | Yes | CMU1.4.1 | Auto Scheduled | งานรื้อถอน ชั้น 2 (รื้อขนไป) | 30 days | 3 | 92 | 152 | 97FS+45 days,98FS+45 days,121SS | October 11, 2019 8:00 AM | November 9, 2019 5:00 PM | October 14, 2019 05:00 PM | November 12, 2019 05:00 PM | June 04, 2018 05:00 PM | July 03, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | General worker
95 | Yes | CMU1.4.2 | Auto Scheduled | งานสถาปัตยกรรม ชั้น 2 | 368 days | 3 |  |  |  | March 22, 2019 8:00 AM | March 23, 2020 5:00 PM | October 17, 2018 05:00 PM | October 19, 2019 05:00 PM | October 04, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 192 days | 192 days
96 | Yes | CMU1.4.2.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 97,99,100 |  |  | February 23, 2020 8:00 AM | March 23, 2020 5:00 PM | March 06, 2020 05:00 PM | April 04, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 192 days | Skilled carpenter
97 | Yes | CMU1.4.2.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 94FS+45 days |  | 96,101 | December 25, 2019 8:00 AM | February 22, 2020 5:00 PM | December 28, 2019 05:00 PM | February 25, 2020 05:00 PM | February 09, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 0 days | General worker
98 | Yes | CMU1.4.2.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 94FS+45 days |  | 99,100 | December 25, 2019 8:00 AM | January 23, 2020 5:00 PM | December 31, 2019 05:00 PM | January 29, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 0 days | General worker
99 | Yes | CMU1.4.2.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 98 |  | 96,101 | January 24, 2020 8:00 AM | February 22, 2020 5:00 PM | February 02, 2020 05:00 PM | March 02, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 0 days | Skilled carpenter
100 | Yes | CMU1.4.2.5 | Auto Scheduled | งานบันได | 30 days | 4 | 98 |  | 96,101 | January 24, 2020 8:00 AM | February 22, 2020 5:00 PM | February 02, 2020 05:00 PM | March 02, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 0 days | General worker
101 | Yes | CMU1.4.2.6 | Auto Scheduled | งานสี | 30 days | 4 | 97,99,100 |  |  | February 23, 2020 8:00 AM | March 23, 2020 5:00 PM | March 09, 2020 05:00 PM | April 07, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 192 days | General worker
102 | Yes | CMU1.4.2.7 | Auto Scheduled | งานสุขภัณฑ์ | 315 days | 4 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 21, 2018 05:00 PM | August 31, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
103 | Yes | CMU1.4.2.7.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 104FS+135 days |  | 105FS+135 days | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | September 05, 2019 05:00 PM | September 19, 2019 05:00 PM | April 24, 2020 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
104 | Yes | CMU1.4.2.7.2 | Auto Scheduled | ZONE T-2 กลาง | 15 days | 5 | 113,109 |  | 103FS+135 days | March 22, 2019 8:00 AM | April 5, 2019 5:00 PM | April 05, 2019 05:00 PM | April 19, 2019 05:00 PM | November 26, 2019 05:00 PM | December 10, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
105 | Yes | CMU1.4.2.7.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 15 days | 5 | 103FS+135 days |  |  | January 16, 2020 8:00 AM | January 30, 2020 5:00 PM | February 08, 2020 05:00 PM | February 22, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 245 days | Sanitary-Plumber
106 | Yes | CMU1.4.3 | Auto Scheduled | งานระบบสุขาภิบาล ชั้น 2 | 408 days | 3 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
107 | Yes | CMU1.4.3.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
108 | Yes | CMU1.4.3.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 109FS+15 days |  | 110FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 16, 2019 05:00 PM | August 19, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
109 | Yes | CMU1.4.3.1.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 36 |  | 113SS,104,108FS+15 days | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 22, 2018 05:00 PM | March 27, 2019 05:00 PM | August 25, 2019 05:00 PM | December 28, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
110 | Yes | CMU1.4.3.1.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 108FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 07, 2019 05:00 PM | January 10, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
111 | Yes | CMU1.4.3.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
112 | Yes | CMU1.4.3.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 113FS+15 days |  | 114FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 22, 2019 05:00 PM | August 25, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
113 | Yes | CMU1.4.3.2.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 109SS |  | 104,112FS+15 days | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 27, 2018 05:00 PM | April 01, 2019 05:00 PM | August 25, 2019 05:00 PM | December 28, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
114 | Yes | CMU1.4.3.2.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 112FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 14, 2019 05:00 PM | January 17, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
115 | Yes | CMU1.4.4 | Auto Scheduled | งานระบบไฟฟ้า ชั้น 2 | 147 days | 3 |  |  |  | November 10, 2019 8:00 AM | April 4, 2020 5:00 PM | October 20, 2018 05:00 PM | March 15, 2019 05:00 PM | May 12, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 180 days | 180 days | 180 days
116 | Yes | CMU1.4.4.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 60 days | 4 | 118FS+7 days |  |  | February 5, 2020 8:00 AM | April 4, 2020 5:00 PM | February 12, 2020 05:00 PM | April 11, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 180 days | 180 days | 180 days | Electrician
117 | Yes | CMU1.4.4.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 60 days | 4 | 118FS+7 days |  |  | February 5, 2020 8:00 AM | April 4, 2020 5:00 PM | February 13, 2020 05:00 PM | April 12, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 180 days | 180 days | 180 days | Electrician
118 | Yes | CMU1.4.4.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 121SS+30 days |  | 117FS+7 days,116FS+7 days | November 10, 2019 8:00 AM | January 28, 2020 5:00 PM | November 15, 2019 05:00 PM | February 02, 2020 05:00 PM | May 12, 2020 05:00 PM | July 30, 2020 05:00 PM | As Soon As Possible |  | No | 180 days | 180 days | 0 days | Electrician
119 | Yes | CMU1.4.4.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 121SS+30 days |  |  | November 10, 2019 8:00 AM | January 28, 2020 5:00 PM | November 17, 2019 05:00 PM | February 04, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 247 days | 247 days | 247 days | Electrician
120 | Yes | CMU1.4.4.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 121SS+30 days |  |  | November 10, 2019 8:00 AM | January 28, 2020 5:00 PM | November 19, 2019 05:00 PM | February 06, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 247 days | 247 days | 247 days | Electrician
121 | Yes | CMU1.4.5 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้น 2 | 180 days | 3 | 94SS |  | 120SS+30 days,119SS+30 days,118SS+30 days,123,212FS-15 days,217FS-30 days,222FS-15 days,228FS-15 days,242FS-7 days,248FS-7 days | October 11, 2019 8:00 AM | April 7, 2020 5:00 PM | October 14, 2019 05:00 PM | April 10, 2020 05:00 PM | June 04, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Skilled carpenter
122 | Yes | CMU1.5 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้น 1 | 686 days | 2 |  |  |  | November 16, 2018 8:00 AM | October 1, 2020 5:00 PM | October 17, 2018 05:00 PM | September 01, 2020 05:00 PM | November 20, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 0 days | 0 days
123 | Yes | CMU1.5.1 | Auto Scheduled | งานรื้อถอน ชั้น 1 (รื้อขนไป) | 30 days | 3 | 121 | 63 | 124,127FS+45 days,128FS+45 days,131FS+45 days,152SS,193SS,194SS,195SS,196SS,197SS,202SS,204SS,205SS,206SS,207SS | April 8, 2020 8:00 AM | May 7, 2020 5:00 PM | April 11, 2020 05:00 PM | May 10, 2020 05:00 PM | July 19, 2018 05:00 PM | August 17, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | General worker
124 | Yes | CMU1.5.2 | Auto Scheduled | งานโครงสร้างวิศวกรรม ชั้น 1 | 75 days | 3 | 123 |  |  | May 8, 2020 8:00 AM | July 21, 2020 5:00 PM | May 12, 2020 05:00 PM | July 25, 2020 05:00 PM | July 23, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 72 days | 72 days | 72 days | General worker
125 | Yes | CMU1.5.3 | Auto Scheduled | งานสถาปัตยกรรม ชั้น 1 | 548 days | 3 |  |  |  | March 22, 2019 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | April 16, 2020 05:00 PM | April 07, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 12 days | 12 days
126 | Yes | CMU1.5.3.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 127,129,130 |  |  | August 21, 2020 8:00 AM | September 19, 2020 5:00 PM | August 24, 2020 05:00 PM | September 22, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | Skilled carpenter
127 | Yes | CMU1.5.3.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 123FS+45 days |  | 126,132 | June 22, 2020 8:00 AM | August 20, 2020 5:00 PM | June 25, 2020 05:00 PM | August 23, 2020 05:00 PM | October 02, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
128 | Yes | CMU1.5.3.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 123FS+45 days |  | 129,130 | June 22, 2020 8:00 AM | July 21, 2020 5:00 PM | June 25, 2020 05:00 PM | July 24, 2020 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
129 | Yes | CMU1.5.3.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 128 |  | 126,132 | July 22, 2020 8:00 AM | August 20, 2020 5:00 PM | July 25, 2020 05:00 PM | August 23, 2020 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | Skilled carpenter
130 | Yes | CMU1.5.3.5 | Auto Scheduled | งานบันได | 30 days | 4 | 128 |  | 126,132 | July 22, 2020 8:00 AM | August 20, 2020 5:00 PM | July 25, 2020 05:00 PM | August 23, 2020 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
131 | Yes | CMU1.5.3.6 | Auto Scheduled | งานตกแต่งอื่น ๆ | 60 days | 4 | 123FS+45 days |  |  | June 22, 2020 8:00 AM | August 20, 2020 5:00 PM | June 25, 2020 05:00 PM | August 23, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 42 days | 42 days | 42 days | General worker
132 | Yes | CMU1.5.3.7 | Auto Scheduled | งานสี | 30 days | 4 | 127,129,130 |  |  | August 21, 2020 8:00 AM | September 19, 2020 5:00 PM | August 24, 2020 05:00 PM | September 22, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
133 | Yes | CMU1.5.3.8 | Auto Scheduled | งานสุขภัณฑ์ | 315 days | 4 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 22, 2018 05:00 PM | September 01, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
134 | Yes | CMU1.5.3.8.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 135FS+135 days |  | 136FS+135 days | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | August 24, 2019 05:00 PM | September 07, 2019 05:00 PM | April 24, 2020 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
135 | Yes | CMU1.5.3.8.2 | Auto Scheduled | ZONE T-2 กลาง | 15 days | 5 | 140,144 |  | 134FS+135 days,164FS+135 days | March 22, 2019 8:00 AM | April 5, 2019 5:00 PM | March 24, 2019 05:00 PM | April 07, 2019 05:00 PM | November 26, 2019 05:00 PM | December 10, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
136 | Yes | CMU1.5.3.8.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 15 days | 5 | 134FS+135 days |  |  | January 16, 2020 8:00 AM | January 30, 2020 5:00 PM | January 25, 2020 05:00 PM | February 08, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 245 days | Sanitary-Plumber
137 | Yes | CMU1.5.4 | Auto Scheduled | งานระบบสุขาภิบาล ชั้น 1 | 408 days | 3 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 278 days | 44 days
138 | Yes | CMU1.5.4.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 278 days | 44 days
139 | Yes | CMU1.5.4.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 140FS+15 days |  | 141FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 13, 2019 05:00 PM | August 16, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
140 | Yes | CMU1.5.4.1.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 36 |  | 139FS+15 days,144SS,135,167FS+15 days | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 16, 2018 05:00 PM | March 21, 2019 05:00 PM | January 03, 2019 05:00 PM | May 08, 2019 05:00 PM | As Soon As Possible |  | No | 44 days | 44 days | 0 days | Sanitary-Plumber
141 | Yes | CMU1.5.4.1.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 139FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 07, 2019 05:00 PM | January 10, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
142 | Yes | CMU1.5.4.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 278 days | 44 days
143 | Yes | CMU1.5.4.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 144FS+15 days |  | 145FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 11, 2019 05:00 PM | August 14, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
144 | Yes | CMU1.5.4.2.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 140SS |  | 143FS+15 days,135,169FS+15 days | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 16, 2018 05:00 PM | March 21, 2019 05:00 PM | January 03, 2019 05:00 PM | May 08, 2019 05:00 PM | As Soon As Possible |  | No | 44 days | 44 days | 0 days | Sanitary-Plumber
145 | Yes | CMU1.5.4.2.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 143FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 03, 2019 05:00 PM | January 06, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
146 | Yes | CMU1.5.5 | Auto Scheduled | งานระบบไฟฟ้า ชั้น 1 | 147 days | 3 |  |  |  | May 8, 2020 8:00 AM | October 1, 2020 5:00 PM | October 21, 2018 05:00 PM | March 16, 2019 05:00 PM | May 12, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 0 days | 0 days | 0 days
147 | Yes | CMU1.5.5.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 60 days | 4 | 149FS+7 days |  |  | August 3, 2020 8:00 AM | October 1, 2020 5:00 PM | August 06, 2020 05:00 PM | October 04, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Electrician
148 | Yes | CMU1.5.5.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 60 days | 4 | 149FS+7 days |  |  | August 3, 2020 8:00 AM | October 1, 2020 5:00 PM | August 06, 2020 05:00 PM | October 04, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Electrician
149 | Yes | CMU1.5.5.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 152SS+30 days |  | 148FS+7 days,147FS+7 days | May 8, 2020 8:00 AM | July 26, 2020 5:00 PM | May 11, 2020 05:00 PM | July 29, 2020 05:00 PM | May 12, 2020 05:00 PM | July 30, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Electrician
150 | Yes | CMU1.5.5.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 152SS+30 days |  |  | May 8, 2020 8:00 AM | July 26, 2020 5:00 PM | May 11, 2020 05:00 PM | July 29, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 67 days | 67 days | 67 days | Electrician
151 | Yes | CMU1.5.5.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 152SS+30 days |  |  | May 8, 2020 8:00 AM | July 26, 2020 5:00 PM | May 11, 2020 05:00 PM | July 29, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 67 days | 67 days | 67 days | Electrician
152 | Yes | CMU1.5.6 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้น 1 | 165 days | 3 | 123SS |  | 151SS+30 days,150SS+30 days,149SS+30 days,154SS,211FS-30 days,210FS-30 days,216FS-45 days,221FS-30 days,227FS-30 days,226FS-30 days,232FS-45 days,241FS-7 days,247FS-7 days | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 11, 2020 05:00 PM | September 22, 2020 05:00 PM | November 26, 2019 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Skilled carpenter
153 | Yes | CMU1.6 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้นใต้ดิน | 533 days | 2 |  |  |  | April 6, 2019 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | April 01, 2020 05:00 PM | April 22, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 12 days | 12 days
154 | Yes | CMU1.6.1 | Auto Scheduled | งานรื้อถอน ชั้นใต้ดิน (รื้อขนไป) | 30 days | 3 | 152SS |  | 155,158FS+45 days,159FS+45 days,177SS,176SS,175SS,174SS | April 8, 2020 8:00 AM | May 7, 2020 5:00 PM | April 11, 2020 05:00 PM | May 10, 2020 05:00 PM | November 26, 2019 05:00 PM | December 25, 2019 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
155 | Yes | CMU1.6.2 | Auto Scheduled | งานโครงสร้างวิศวกรรม ชั้นใต้ดิน | 75 days | 3 | 154 |  |  | May 8, 2020 8:00 AM | July 21, 2020 5:00 PM | May 12, 2020 05:00 PM | July 25, 2020 05:00 PM | July 23, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 72 days | 72 days | 72 days | General worker
156 | Yes | CMU1.6.3 | Auto Scheduled | งานสถาปัตยกรรม ชั้นใต้ดิน | 398 days | 3 |  |  |  | August 19, 2019 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | November 18, 2019 05:00 PM | September 04, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 320 days | 12 days | 12 days
157 | Yes | CMU1.6.3.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 158,160,161 |  |  | August 21, 2020 8:00 AM | September 19, 2020 5:00 PM | September 05, 2020 05:00 PM | October 04, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | Skilled carpenter
158 | Yes | CMU1.6.3.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 154FS+45 days |  | 157,162 | June 22, 2020 8:00 AM | August 20, 2020 5:00 PM | June 25, 2020 05:00 PM | August 23, 2020 05:00 PM | February 09, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
159 | Yes | CMU1.6.3.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 154FS+45 days |  | 160,161 | June 22, 2020 8:00 AM | July 21, 2020 5:00 PM | July 07, 2020 05:00 PM | August 05, 2020 05:00 PM | August 22, 2020 05:00 PM | September 20, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
160 | Yes | CMU1.6.3.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 159 |  | 157,162 | July 22, 2020 8:00 AM | August 20, 2020 5:00 PM | August 06, 2020 05:00 PM | September 04, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | Skilled carpenter
161 | Yes | CMU1.6.3.5 | Auto Scheduled | งานบันได | 30 days | 4 | 159 |  | 157,162 | July 22, 2020 8:00 AM | August 20, 2020 5:00 PM | August 06, 2020 05:00 PM | September 04, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
162 | Yes | CMU1.6.3.6 | Auto Scheduled | งานสี | 30 days | 4 | 158,160,161 |  |  | August 21, 2020 8:00 AM | September 19, 2020 5:00 PM | September 05, 2020 05:00 PM | October 04, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
163 | Yes | CMU1.6.3.7 | Auto Scheduled | งานสุขภัณฑ์ | 15 days | 4 |  |  |  | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | October 20, 2018 05:00 PM | November 03, 2018 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 395 days | 395 days | 395 days
164 | Yes | CMU1.6.3.7.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 135FS+135 days |  |  | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | August 27, 2019 05:00 PM | September 10, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 395 days | 395 days | 395 days | Sanitary-Plumber
165 | Yes | CMU1.6.4 | Auto Scheduled | งานระบบสุขาภิบาล ชั้นใต้ดิน | 501 days | 3 |  |  |  | April 6, 2019 8:00 AM | August 18, 2020 5:00 PM | October 17, 2018 05:00 PM | February 29, 2020 05:00 PM | May 24, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 44 days | 44 days
166 | Yes | CMU1.6.4.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 126 days | 4 |  |  |  | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | October 21, 2018 05:00 PM | February 23, 2019 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 419 days | 419 days | 419 days
167 | Yes | CMU1.6.4.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 140FS+15 days |  |  | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 12, 2019 05:00 PM | August 15, 2019 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 419 days | 419 days | 419 days | Sanitary-Plumber
168 | Yes | CMU1.6.4.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 126 days | 4 |  |  |  | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | October 21, 2018 05:00 PM | February 23, 2019 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 44 days | 44 days
169 | Yes | CMU1.6.4.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 144FS+15 days |  | 170FS+300 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 06, 2019 05:00 PM | August 09, 2019 05:00 PM | May 24, 2019 05:00 PM | September 26, 2019 05:00 PM | As Soon As Possible |  | No | 44 days | 44 days | 0 days | Sanitary-Plumber
170 | Yes | CMU1.6.4.3 | Auto Scheduled | งานระบบระบายน้ำฝน | 75 days | 4 | 169FS+300 days |  |  | June 5, 2020 8:00 AM | August 18, 2020 5:00 PM | June 05, 2020 05:00 PM | August 18, 2020 05:00 PM | July 23, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 44 days | 44 days | 44 days | Sanitary-Plumber
171 | Yes | CMU1.6.5 | Auto Scheduled | งานระบบไฟฟ้า ชั้นใต้ดิน | 147 days | 3 |  |  |  | April 8, 2020 8:00 AM | September 1, 2020 5:00 PM | October 23, 2018 05:00 PM | March 18, 2019 05:00 PM | May 12, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 30 days | 30 days | 30 days
172 | Yes | CMU1.6.5.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 60 days | 4 | 174FS+7 days |  |  | July 4, 2020 8:00 AM | September 1, 2020 5:00 PM | July 07, 2020 05:00 PM | September 04, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 30 days | 30 days | 30 days | Electrician
173 | Yes | CMU1.6.5.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 60 days | 4 | 174FS+7 days |  |  | July 4, 2020 8:00 AM | September 1, 2020 5:00 PM | July 07, 2020 05:00 PM | September 04, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 30 days | 30 days | 30 days | Electrician
174 | Yes | CMU1.6.5.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 154SS |  | 173FS+7 days,172FS+7 days | April 8, 2020 8:00 AM | June 26, 2020 5:00 PM | April 11, 2020 05:00 PM | June 29, 2020 05:00 PM | May 12, 2020 05:00 PM | July 30, 2020 05:00 PM | As Soon As Possible |  | No | 30 days | 30 days | 0 days | Electrician
175 | Yes | CMU1.6.5.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 154SS |  |  | April 8, 2020 8:00 AM | June 26, 2020 5:00 PM | April 14, 2020 05:00 PM | July 02, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 97 days | 97 days | 97 days | Electrician
176 | Yes | CMU1.6.5.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 154SS |  |  | April 8, 2020 8:00 AM | June 26, 2020 5:00 PM | April 13, 2020 05:00 PM | July 01, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 97 days | 97 days | 97 days | Electrician
177 | Yes | CMU1.6.6 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้นใต้ดิน | 165 days | 3 | 154SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 11, 2020 05:00 PM | September 22, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | Skilled carpenter
178 | Yes | CMU1.7 | Auto Scheduled | หมวดงานระบบคอมพิวเตอร์และแจ้งเหตุเพลิงไหม้ | 670 days | 2 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
179 | Yes | CMU1.7.1 | Auto Scheduled | งานระบบคอมพิวเตอร์ | 670 days | 3 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
180 | Yes | CMU1.7.1.1 | Auto Scheduled | ชั้นที่ 4 | 160 days | 4 | 36FS+14 days |  | 181 | November 30, 2018 8:00 AM | May 8, 2019 5:00 PM | November 30, 2018 05:00 PM | May 08, 2019 05:00 PM | April 24, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
181 | Yes | CMU1.7.1.2 | Auto Scheduled | ชั้นที่ 3 | 175 days | 4 | 180 | 182 | 182 | May 9, 2019 8:00 AM | October 30, 2019 5:00 PM | May 09, 2019 05:00 PM | October 30, 2019 05:00 PM | April 09, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
182 | Yes | CMU1.7.1.3 | Auto Scheduled | ชั้นที่ 2 | 175 days | 4 | 181 | 183 | 183,184 | October 31, 2019 8:00 AM | April 22, 2020 5:00 PM | October 31, 2019 05:00 PM | April 22, 2020 05:00 PM | April 09, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
183 | Yes | CMU1.7.1.4 | Auto Scheduled | ชั้นที่ 1 | 160 days | 4 | 182 | 180 |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 23, 2020 05:00 PM | September 29, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
184 | Yes | CMU1.7.1.5 | Auto Scheduled | ชั้นใต้ดิน | 160 days | 4 | 182 | 183SS |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 23, 2020 05:00 PM | September 29, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
185 | Yes | CMU1.7.2 | Auto Scheduled | ระบบแจ้งเหตุเพลิงไหม้ | 670 days | 3 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
186 | Yes | CMU1.7.2.1 | Auto Scheduled | ชั้นที่ 4 | 160 days | 4 | 36FS+14 days |  | 187 | November 30, 2018 8:00 AM | May 8, 2019 5:00 PM | November 30, 2018 05:00 PM | May 08, 2019 05:00 PM | April 24, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
187 | Yes | CMU1.7.2.2 | Auto Scheduled | ชั้นที่ 3 | 175 days | 4 | 186 | 188 | 188 | May 9, 2019 8:00 AM | October 30, 2019 5:00 PM | May 09, 2019 05:00 PM | October 30, 2019 05:00 PM | April 09, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
188 | Yes | CMU1.7.2.3 | Auto Scheduled | ชั้นที่ 2 | 175 days | 4 | 187 | 189 | 189,190 | October 31, 2019 8:00 AM | April 22, 2020 5:00 PM | October 31, 2019 05:00 PM | April 22, 2020 05:00 PM | April 09, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
189 | Yes | CMU1.7.2.4 | Auto Scheduled | ชั้นที่ 1 | 160 days | 4 | 188 | 186 |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 23, 2020 05:00 PM | September 29, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
190 | Yes | CMU1.7.2.5 | Auto Scheduled | ชั้นใต้ดิน | 160 days | 4 | 188 | 189SS |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 23, 2020 05:00 PM | September 29, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
191 | Yes | CMU1.8 | Auto Scheduled | หมวดงานสีภายนอก งานซ่อมแซมและตกแต่งภายนอกอาคาร | 660 days | 2 |  |  |  | November 30, 2018 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | August 06, 2020 05:00 PM | December 16, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 507 days | 12 days | 12 days
192 | Yes | CMU1.8.1 | Auto Scheduled | งานสีภายนอกและงานซ่อมแซมพื้นผิวภายนอกอาคาร | 660 days | 3 |  |  |  | November 30, 2018 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | August 06, 2020 05:00 PM | December 16, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 507 days | 12 days | 12 days
193 | Yes | CMU1.8.1.1 | Auto Scheduled | งานขัดลอกสีทาผนังเดิม | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 11, 2020 05:00 PM | September 22, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
194 | Yes | CMU1.8.1.2 | Auto Scheduled | น้ำยาทาปูนเก่า (สีรองพื้น) | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 11, 2020 05:00 PM | September 22, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
195 | Yes | CMU1.8.1.3 | Auto Scheduled | งานทาสีภายนอก (ทา 2 เที่ยว) ไม่รวมชั้นใต้ดิน | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 11, 2020 05:00 PM | September 22, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
196 | Yes | CMU1.8.1.4 | Auto Scheduled | งานทำความสะอาดและซ่อมแซมผนังกรุอิฐโชว์แนว (อ้างอิงราคางานขัดลอกสี) | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 11, 2020 05:00 PM | September 22, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
197 | Yes | CMU1.8.1.5 | Auto Scheduled | น้ำยาเคลือบผิวผนังอิฐโชว์แนว (อ้างอิงค่าทาน้ำยากันเชื้อรา) | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 11, 2020 05:00 PM | September 22, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
198 | Yes | CMU1.8.1.6 | Auto Scheduled | งานรื้อถอนแผ่นวัสดุกันซึมหลังคาดาดฟ้า (รื้อขนไป) | 90 days | 4 | 36FS+14 days |  |  | November 30, 2018 8:00 AM | February 27, 2019 5:00 PM | December 03, 2018 05:00 PM | March 02, 2019 05:00 PM | July 08, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 582 days | 582 days | 582 days | General worker
199 | Yes | CMU1.8.1.7 | Auto Scheduled | งานแผ่นวัสดุกันซึมแบบเป่าไฟผิวทราย | 90 days | 4 | 36FS+14 days |  |  | November 30, 2018 8:00 AM | February 27, 2019 5:00 PM | December 04, 2018 05:00 PM | March 03, 2019 05:00 PM | July 08, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 582 days | 582 days | 582 days | General worker
200 | Yes | CMU1.8.1.8 | Auto Scheduled | งานกันซึมชนิด Polyurethane สูตรน้ำมัน ชนิดยืดหยุ่นสูงเป็นพิเศษ | 90 days | 4 | 36FS+14 days |  |  | November 30, 2018 8:00 AM | February 27, 2019 5:00 PM | December 03, 2018 05:00 PM | March 02, 2019 05:00 PM | July 08, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 582 days | 582 days | 582 days | General worker
201 | Yes | CMU1.8.2 | Auto Scheduled | งานตกแต่งภายนอกอาคาร | 165 days | 3 |  |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | October 20, 2018 05:00 PM | April 02, 2019 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 12 days | 12 days | 12 days
202 | Yes | CMU1.8.2.1 | Auto Scheduled | ตะแกรงเหล็กฉีกกันนก XS-32 | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 11, 2020 05:00 PM | September 22, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
203 | Yes | CMU1.9 | Auto Scheduled | หมวดงานบริเวณ | 165 days | 2 |  |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | October 22, 2018 05:00 PM | April 04, 2019 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 12 days | 12 days | 12 days
204 | Yes | CMU1.9.1 | Auto Scheduled | งานรื้อถอน งานบริเวณ | 165 days | 3 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 11, 2020 05:00 PM | September 22, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
205 | Yes | CMU1.9.2 | Auto Scheduled | งานโครงสร้างวิศวกรรม งานบริเวณ | 165 days | 3 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 11, 2020 05:00 PM | September 22, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
206 | Yes | CMU1.9.3 | Auto Scheduled | งานสถาปัตยกรรม งานบริเวณ | 165 days | 3 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 11, 2020 05:00 PM | September 22, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
207 | Yes | CMU1.9.4 | Auto Scheduled | งานระบบไฟฟ้า งานบริเวณ | 165 days | 3 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 11, 2020 05:00 PM | September 22, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | Electrician
208 | Yes | CMU1.10 | Auto Scheduled | หมวดงานครุภัณฑ์จัดซื้อ | 670 days | 2 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
209 | Yes | CMU1.10.1 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัว | 510 days | 3 |  |  |  | April 14, 2019 8:00 AM | September 4, 2020 5:00 PM | October 17, 2018 05:00 PM | March 09, 2020 05:00 PM | May 15, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 522 days | 27 days | 27 days
210 | Yes | CMU1.10.1.1 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้นใต้ดิน | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | August 28, 2020 05:00 PM | September 11, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
211 | Yes | CMU1.10.1.2 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้น 1 | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | August 31, 2020 05:00 PM | September 14, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
212 | Yes | CMU1.10.1.3 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้น 2 | 15 days | 4 | 121FS-15 days |  |  | March 24, 2020 8:00 AM | April 7, 2020 5:00 PM | April 02, 2020 05:00 PM | April 16, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Skilled carpenter
213 | Yes | CMU1.10.1.4 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้น 3 | 15 days | 4 | 92FS-15 days |  |  | September 26, 2019 8:00 AM | October 10, 2019 5:00 PM | October 04, 2019 05:00 PM | October 18, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Skilled carpenter
214 | Yes | CMU1.10.1.5 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้น 4 | 15 days | 4 | 63 |  |  | April 14, 2019 8:00 AM | April 28, 2019 5:00 PM | April 21, 2019 05:00 PM | May 05, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 522 days | 522 days | 522 days | Skilled carpenter
215 | Yes | CMU1.10.2 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ | 525 days | 3 |  |  |  | March 30, 2019 8:00 AM | September 4, 2020 5:00 PM | October 17, 2018 05:00 PM | March 24, 2020 05:00 PM | April 30, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 522 days | 27 days | 27 days
216 | Yes | CMU1.10.2.1 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ ชั้น 1 | 30 days | 4 | 152FS-45 days |  |  | August 6, 2020 8:00 AM | September 4, 2020 5:00 PM | August 15, 2020 05:00 PM | September 13, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
217 | Yes | CMU1.10.2.2 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ ชั้น 2 | 30 days | 4 | 121FS-30 days |  |  | March 9, 2020 8:00 AM | April 7, 2020 5:00 PM | March 15, 2020 05:00 PM | April 13, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Skilled carpenter
218 | Yes | CMU1.10.2.3 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ ชั้น 3 | 30 days | 4 | 92FS-30 days |  |  | September 11, 2019 8:00 AM | October 10, 2019 5:00 PM | September 16, 2019 05:00 PM | October 15, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Skilled carpenter
219 | Yes | CMU1.10.2.4 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ ชั้น 4 | 30 days | 4 | 63FS-15 days |  |  | March 30, 2019 8:00 AM | April 28, 2019 5:00 PM | April 02, 2019 05:00 PM | May 01, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 522 days | 522 days | 522 days | Skilled carpenter
220 | Yes | CMU1.10.3 | Auto Scheduled | งานผ้าม่าน | 510 days | 3 |  |  |  | April 14, 2019 8:00 AM | September 4, 2020 5:00 PM | October 17, 2018 05:00 PM | March 09, 2020 05:00 PM | May 15, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 522 days | 27 days | 27 days
221 | Yes | CMU1.10.3.1 | Auto Scheduled | งานผ้าม่าน ชั้น 1 | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | August 28, 2020 05:00 PM | September 11, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
222 | Yes | CMU1.10.3.2 | Auto Scheduled | งานผ้าม่าน ชั้น 2 | 15 days | 4 | 121FS-15 days |  |  | March 24, 2020 8:00 AM | April 7, 2020 5:00 PM | March 30, 2020 05:00 PM | April 13, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Skilled carpenter
223 | Yes | CMU1.10.3.3 | Auto Scheduled | งานผ้าม่าน ชั้น 3 | 15 days | 4 | 92FS-15 days |  |  | September 26, 2019 8:00 AM | October 10, 2019 5:00 PM | October 02, 2019 05:00 PM | October 16, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Skilled carpenter
224 | Yes | CMU1.10.3.4 | Auto Scheduled | งานผ้าม่าน ชั้น 4 | 15 days | 4 | 63 |  |  | April 14, 2019 8:00 AM | April 28, 2019 5:00 PM | April 24, 2019 05:00 PM | May 08, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 522 days | 522 days | 522 days | Skilled carpenter
225 | Yes | CMU1.10.4 | Auto Scheduled | งานป้าย | 510 days | 3 |  |  |  | April 14, 2019 8:00 AM | September 4, 2020 5:00 PM | October 17, 2018 05:00 PM | March 09, 2020 05:00 PM | May 15, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 522 days | 27 days | 27 days
226 | Yes | CMU1.10.4.1 | Auto Scheduled | งานป้าย ชั้นใต้ดิน | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | August 28, 2020 05:00 PM | September 11, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
227 | Yes | CMU1.10.4.2 | Auto Scheduled | งานป้าย ชั้น 1 | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | August 31, 2020 05:00 PM | September 14, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
228 | Yes | CMU1.10.4.3 | Auto Scheduled | งานป้าย ชั้น 2 | 15 days | 4 | 121FS-15 days |  |  | March 24, 2020 8:00 AM | April 7, 2020 5:00 PM | March 30, 2020 05:00 PM | April 13, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Skilled carpenter
229 | Yes | CMU1.10.4.4 | Auto Scheduled | งานป้าย ชั้น 3 | 15 days | 4 | 92FS-15 days |  |  | September 26, 2019 8:00 AM | October 10, 2019 5:00 PM | October 03, 2019 05:00 PM | October 17, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Skilled carpenter
230 | Yes | CMU1.10.4.5 | Auto Scheduled | งานป้าย ชั้น 4 | 15 days | 4 | 63 |  |  | April 14, 2019 8:00 AM | April 28, 2019 5:00 PM | April 20, 2019 05:00 PM | May 04, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 522 days | 522 days | 522 days | Skilled carpenter
231 | Yes | CMU1.10.5 | Auto Scheduled | งานอื่นๆ | 15 days | 3 |  |  |  | August 6, 2020 8:00 AM | August 20, 2020 5:00 PM | October 20, 2018 05:00 PM | November 03, 2018 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 42 days | 42 days | 42 days
232 | Yes | CMU1.10.5.1 | Auto Scheduled | ตู้อลูมิเนียมพับขึ้นรูป พ่นสี ครอบตู้กดน้ำ | 15 days | 4 | 152FS-45 days |  |  | August 6, 2020 8:00 AM | August 20, 2020 5:00 PM | August 13, 2020 05:00 PM | August 27, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 42 days | 42 days | 42 days | General worker
233 | Yes | CMU1.10.6 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ | 670 days | 3 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
234 | Yes | CMU1.10.6.1 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้นใต้ดิน | 160 days | 4 | 236 |  |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 28, 2020 05:00 PM | October 04, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
235 | Yes | CMU1.10.6.2 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้น 1 | 160 days | 4 | 236 |  |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 28, 2020 05:00 PM | October 04, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
236 | Yes | CMU1.10.6.3 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้น 2 | 175 days | 4 | 237 |  | 235,234 | October 31, 2019 8:00 AM | April 22, 2020 5:00 PM | November 05, 2019 05:00 PM | April 27, 2020 05:00 PM | March 12, 2020 05:00 PM | September 02, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
237 | Yes | CMU1.10.6.4 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้น 3 | 175 days | 4 | 238 |  | 236 | May 9, 2019 8:00 AM | October 30, 2019 5:00 PM | May 14, 2019 05:00 PM | November 04, 2019 05:00 PM | March 12, 2020 05:00 PM | September 02, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
238 | Yes | CMU1.10.6.5 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้น 4 | 160 days | 4 | 36FS+14 days |  | 237 | November 30, 2018 8:00 AM | May 8, 2019 5:00 PM | December 02, 2018 05:00 PM | May 10, 2019 05:00 PM | March 27, 2020 05:00 PM | September 02, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
239 | Yes | CMU1.10.7 | Auto Scheduled | งานระบบเครื่องเสียงประกาศ (ใช้ลำโพงของเดิม) | 539 days | 3 |  |  |  | April 7, 2019 8:00 AM | September 26, 2020 5:00 PM | October 17, 2018 05:00 PM | April 07, 2020 05:00 PM | April 16, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 530 days | 5 days | 5 days
240 | Yes | CMU1.10.7.1 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้นใต้ดิน | 7 days | 4 | 241 |  |  | September 20, 2020 8:00 AM | September 26, 2020 5:00 PM | September 27, 2020 05:00 PM | October 03, 2020 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 5 days | 5 days | 5 days | Electrician
241 | Yes | CMU1.10.7.2 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้น 1 | 7 days | 4 | 152FS-7 days |  | 240 | September 13, 2020 8:00 AM | September 19, 2020 5:00 PM | September 16, 2020 05:00 PM | September 22, 2020 05:00 PM | September 09, 2020 05:00 PM | September 15, 2020 05:00 PM | As Soon As Possible |  | No | 5 days | 5 days | 0 days | Electrician
242 | Yes | CMU1.10.7.3 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้น 2 | 7 days | 4 | 121FS-7 days |  |  | April 1, 2020 8:00 AM | April 7, 2020 5:00 PM | April 06, 2020 05:00 PM | April 12, 2020 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Electrician
243 | Yes | CMU1.10.7.4 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้น 3 | 7 days | 4 | 92FS-7 days |  |  | October 4, 2019 8:00 AM | October 10, 2019 5:00 PM | October 11, 2019 05:00 PM | October 17, 2019 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Electrician
244 | Yes | CMU1.10.7.5 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้น 4 | 7 days | 4 | 63FS-7 days |  |  | April 7, 2019 8:00 AM | April 13, 2019 5:00 PM | April 11, 2019 05:00 PM | April 17, 2019 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 537 days | 537 days | 537 days | Electrician
245 | Yes | CMU1.10.8 | Auto Scheduled | งานระบบกล้องวงจรปิด (ใช้กล้องวงจรปิดของเดิม) | 539 days | 3 |  |  |  | April 7, 2019 8:00 AM | September 26, 2020 5:00 PM | October 17, 2018 05:00 PM | April 07, 2020 05:00 PM | April 16, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 530 days | 5 days | 5 days
246 | Yes | CMU1.10.8.1 | Auto Scheduled | งานกล้องวงจรปิด ชั้นใต้ดิน | 7 days | 4 | 247 |  |  | September 20, 2020 8:00 AM | September 26, 2020 5:00 PM | September 27, 2020 05:00 PM | October 03, 2020 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 5 days | 5 days | 5 days | Electrician
247 | Yes | CMU1.10.8.2 | Auto Scheduled | งานกล้องวงจรปิด ชั้น 1 | 7 days | 4 | 152FS-7 days |  | 246 | September 13, 2020 8:00 AM | September 19, 2020 5:00 PM | September 16, 2020 05:00 PM | September 22, 2020 05:00 PM | September 09, 2020 05:00 PM | September 15, 2020 05:00 PM | As Soon As Possible |  | No | 5 days | 5 days | 0 days | Electrician
248 | Yes | CMU1.10.8.3 | Auto Scheduled | งานกล้องวงจรปิด ชั้น 2 | 7 days | 4 | 121FS-7 days |  |  | April 1, 2020 8:00 AM | April 7, 2020 5:00 PM | April 07, 2020 05:00 PM | April 13, 2020 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Electrician
249 | Yes | CMU1.10.8.4 | Auto Scheduled | งานกล้องวงจรปิด ชั้น 3 | 7 days | 4 | 92FS-7 days |  |  | October 4, 2019 8:00 AM | October 10, 2019 5:00 PM | October 11, 2019 05:00 PM | October 17, 2019 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Electrician
250 | Yes | CMU1.10.8.5 | Auto Scheduled | งานกล้องวงจรปิด ชั้น 4 | 7 days | 4 | 63FS-7 days |  |  | April 7, 2019 8:00 AM | April 13, 2019 5:00 PM | April 11, 2019 05:00 PM | April 17, 2019 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 537 days | 537 days | 537 days | Electrician

## solutoion_5
ID | Active | WBS | Task_Mode | Name | Duration | Outline_Level | Predecessors | Predecessors2 | Successors | Start_Date | Finish_Date | Early_Start | Early_Finish | Late_Start | Late_Finish | Constraint_Type | Constraint_Date | Summary | Start_Slack | Finish_Slack | Free_Slack | Resource_Names
1 | Yes | CMU1 | Auto Scheduled | โครงการปรับปรุงสำนักหอสมุด มหาวิทยาลัยเชียงใหม่ | 716 days | 1 |  |  |  | October 17, 2018 8:00 AM | October 1, 2020 5:00 PM | October 17, 2018 05:00 PM | October 01, 2020 05:00 PM | October 21, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 0 days | 0 days | 0 days
2 | Yes | CMU1.1 | Auto Scheduled | หมวดเตรียมการ | 675 days | 2 |  |  |  | October 17, 2018 8:00 AM | August 21, 2020 5:00 PM | October 17, 2018 05:00 PM | August 21, 2020 05:00 PM | December 01, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 41 days | 41 days | 41 days
3 | Yes | CMU1.1.1 | Auto Scheduled | งานอาคารสนามและผังบริเวณโครงการ | 14 days | 3 | 4FS-7 days |  |  | October 26, 2018 8:00 AM | November 8, 2018 5:00 PM | November 01, 2018 05:00 PM | November 14, 2018 05:00 PM | September 22, 2020 05:00 PM | October 05, 2020 05:00 PM | Start No Earlier Than | Oct 24 '18 | No | 693 days | 693 days | 693 days | Engineer
4 | Yes | CMU1.1.2 | Auto Scheduled | งานเชื่อมต่อระบบสาธารณูปโภคโครงการ | 16 days | 3 |  |  | 3FS-7 days | October 17, 2018 8:00 AM | November 1, 2018 5:00 PM | October 19, 2018 05:00 PM | November 03, 2018 05:00 PM | September 13, 2020 05:00 PM | September 28, 2020 05:00 PM | As Soon As Possible |  | No | 693 days | 693 days | 0 days | Engineer
5 | Yes | CMU1.1.3 | Auto Scheduled | งานตรวจทดสอบระบบภายในอาคารก่อนดำเนินการปรับปรุง | 675 days | 3 |  |  |  | October 17, 2018 8:00 AM | August 21, 2020 5:00 PM | October 17, 2018 05:00 PM | August 21, 2020 05:00 PM | December 01, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 41 days | 41 days | 41 days
6 | Yes | CMU1.1.3.1 | Auto Scheduled | ชั้นที่ 4 | 15 days | 4 |  |  | 7FS+150 days | October 17, 2018 8:00 AM | October 31, 2018 5:00 PM | October 19, 2018 05:00 PM | November 02, 2018 05:00 PM | December 01, 2018 05:00 PM | December 15, 2018 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
7 | Yes | CMU1.1.3.2 | Auto Scheduled | ชั้นที่ 3 | 15 days | 4 | 6FS+150 days |  | 8FS+150 days | March 31, 2019 8:00 AM | April 14, 2019 5:00 PM | April 08, 2019 05:00 PM | April 22, 2019 05:00 PM | May 15, 2019 05:00 PM | May 29, 2019 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
8 | Yes | CMU1.1.3.3 | Auto Scheduled | ชั้นที่ 2 | 15 days | 4 | 7FS+150 days |  | 9FS+150 days | September 12, 2019 8:00 AM | September 26, 2019 5:00 PM | September 30, 2019 05:00 PM | October 14, 2019 05:00 PM | October 27, 2019 05:00 PM | November 10, 2019 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
9 | Yes | CMU1.1.3.4 | Auto Scheduled | ชั้นที่ 1 | 15 days | 4 | 8FS+150 days |  | 10FS+150 days | February 24, 2020 8:00 AM | March 9, 2020 5:00 PM | March 19, 2020 05:00 PM | April 02, 2020 05:00 PM | April 09, 2020 05:00 PM | April 23, 2020 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
10 | Yes | CMU1.1.3.5 | Auto Scheduled | ชั้นใต้ดินและภายนอก | 15 days | 4 | 9FS+150 days |  |  | August 7, 2020 8:00 AM | August 21, 2020 5:00 PM | September 10, 2020 05:00 PM | September 24, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 41 days | Engineer
11 | Yes | CMU1.1.4 | Auto Scheduled | งานสำรวจอุปกรณ์ไฟฟ้า, สุขภัณฑ์และครุภัณฑ์ (ของเดิม) ก่อนดำเนินการปรับปรุง | 675 days | 3 |  |  |  | October 17, 2018 8:00 AM | August 21, 2020 5:00 PM | October 17, 2018 05:00 PM | August 21, 2020 05:00 PM | December 01, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 41 days | 41 days | 41 days
12 | Yes | CMU1.1.4.1 | Auto Scheduled | ชั้นที่ 4 | 15 days | 4 |  |  | 13FS+150 days | October 17, 2018 8:00 AM | October 31, 2018 5:00 PM | October 19, 2018 05:00 PM | November 02, 2018 05:00 PM | December 01, 2018 05:00 PM | December 15, 2018 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
13 | Yes | CMU1.1.4.2 | Auto Scheduled | ชั้นที่ 3 | 15 days | 4 | 12FS+150 days |  | 14FS+150 days | March 31, 2019 8:00 AM | April 14, 2019 5:00 PM | April 05, 2019 05:00 PM | April 19, 2019 05:00 PM | May 15, 2019 05:00 PM | May 29, 2019 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
14 | Yes | CMU1.1.4.3 | Auto Scheduled | ชั้นที่ 2 | 15 days | 4 | 13FS+150 days |  | 15FS+150 days | September 12, 2019 8:00 AM | September 26, 2019 5:00 PM | September 23, 2019 05:00 PM | October 07, 2019 05:00 PM | October 27, 2019 05:00 PM | November 10, 2019 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
15 | Yes | CMU1.1.4.4 | Auto Scheduled | ชั้นที่ 1 | 15 days | 4 | 14FS+150 days |  | 16FS+150 days | February 24, 2020 8:00 AM | March 9, 2020 5:00 PM | March 10, 2020 05:00 PM | March 24, 2020 05:00 PM | April 09, 2020 05:00 PM | April 23, 2020 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
16 | Yes | CMU1.1.4.5 | Auto Scheduled | ชั้นใต้ดินและภายนอก | 15 days | 4 | 15FS+150 days |  |  | August 7, 2020 8:00 AM | August 21, 2020 5:00 PM | September 02, 2020 05:00 PM | September 16, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 41 days | Engineer
17 | Yes | CMU1.1.5 | Auto Scheduled | งานเอกสารขออนุมัติใช้วัสดุ, Shop Drawing และครุภัณฑ์ของโครงการ | 106 days | 3 |  |  |  | October 17, 2018 8:00 AM | January 30, 2019 5:00 PM | October 22, 2018 05:00 PM | February 04, 2019 05:00 PM | June 22, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 610 days | 610 days | 610 days
18 | Yes | CMU1.1.5.1 | Auto Scheduled | แบบ Shop Drawing ชั้นที่ 4 | 20 days | 4 |  |  | 19,25SS+14 days,26SS+14 days | October 17, 2018 8:00 AM | November 5, 2018 5:00 PM | October 17, 2018 05:00 PM | November 05, 2018 05:00 PM | October 01, 2018 05:00 PM | October 20, 2018 05:00 PM | As Soon As Possible |  | No | 610 days | 610 days | 0 days | Engineer
19 | Yes | CMU1.1.5.2 | Auto Scheduled | แบบ Shop Drawing ชั้นที่ 3 | 20 days | 4 | 18 |  | 20FS-7 days | November 6, 2018 8:00 AM | November 25, 2018 5:00 PM | November 13, 2018 05:00 PM | December 02, 2018 05:00 PM | July 13, 2020 05:00 PM | August 01, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
20 | Yes | CMU1.1.5.3 | Auto Scheduled | แบบ Shop Drawing ชั้นที่ 2 | 20 days | 4 | 19FS-7 days |  | 21FS-7 days | November 19, 2018 8:00 AM | December 8, 2018 5:00 PM | November 29, 2018 05:00 PM | December 18, 2018 05:00 PM | July 26, 2020 05:00 PM | August 14, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
21 | Yes | CMU1.1.5.4 | Auto Scheduled | แบบ Shop Drawing ชั้นที่ 1 | 20 days | 4 | 20FS-7 days |  | 22FS-7 days | December 2, 2018 8:00 AM | December 21, 2018 5:00 PM | December 18, 2018 05:00 PM | January 06, 2019 05:00 PM | August 08, 2020 05:00 PM | August 27, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
22 | Yes | CMU1.1.5.5 | Auto Scheduled | แบบ Shop Drawing ชั้นใต้ดิน | 20 days | 4 | 21FS-7 days |  | 23FS-7 days | December 15, 2018 8:00 AM | January 3, 2019 5:00 PM | January 06, 2019 05:00 PM | January 25, 2019 05:00 PM | August 21, 2020 05:00 PM | September 09, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
23 | Yes | CMU1.1.5.6 | Auto Scheduled | แบบ Shop Drawing ภายนอกอาคาร | 20 days | 4 | 22FS-7 days |  | 24FS-7 days | December 28, 2018 8:00 AM | January 16, 2019 5:00 PM | January 24, 2019 05:00 PM | February 12, 2019 05:00 PM | September 03, 2020 05:00 PM | September 22, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
24 | Yes | CMU1.1.5.7 | Auto Scheduled | แบบ Shop Drawing landscape | 20 days | 4 | 23FS-7 days |  |  | January 10, 2019 8:00 AM | January 29, 2019 5:00 PM | February 14, 2019 05:00 PM | March 05, 2019 05:00 PM | September 16, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 611 days | Engineer
25 | Yes | CMU1.1.5.8 | Auto Scheduled | แบบ Shop Drawing งานปรับปรุง ครุภัณฑ์ | 92 days | 4 | 18SS+14 days |  |  | October 31, 2018 8:00 AM | January 30, 2019 5:00 PM | November 07, 2018 05:00 PM | February 06, 2019 05:00 PM | July 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 610 days | 610 days | 610 days | Engineer
26 | Yes | CMU1.1.5.9 | Auto Scheduled | แบบ Shop Drawing งานจัดซื้อครุภัณฑ์ | 92 days | 4 | 18SS+14 days |  |  | October 31, 2018 8:00 AM | January 30, 2019 5:00 PM | November 10, 2018 05:00 PM | February 09, 2019 05:00 PM | July 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 610 days | 610 days | 610 days | Engineer
27 | Yes | CMU1.1.6 | Auto Scheduled | งานตรวจทดสอบระบบ, งานอบรมผู้ใช้อาคาร และ As-Built Drawing | 30 days | 3 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 22, 2018 05:00 PM | November 20, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 686 days | 686 days | 686 days
28 | Yes | CMU1.1.6.1 | Auto Scheduled | ชั้นที่ 4 | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 27, 2018 05:00 PM | November 25, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
29 | Yes | CMU1.1.6.2 | Auto Scheduled | ชั้นที่ 3 | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
30 | Yes | CMU1.1.6.3 | Auto Scheduled | ชั้นที่ 2 | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 22, 2018 05:00 PM | November 20, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
31 | Yes | CMU1.1.6.4 | Auto Scheduled | ชั้นที่ 1 | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 28, 2018 05:00 PM | November 26, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
32 | Yes | CMU1.1.6.5 | Auto Scheduled | ชั้นใต้ดิน | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 25, 2018 05:00 PM | November 23, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
33 | Yes | CMU1.1.6.6 | Auto Scheduled | ทั้งอาคาร | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 23, 2018 05:00 PM | November 21, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
34 | Yes | CMU1.1.7 | Auto Scheduled | งานบริหารงานก่อสร้างและงานอื่น ๆ | 0 days | 3 |  |  |  | October 17, 2018 8:00 AM | October 17, 2018 8:00 AM | October 20, 2018 05:00 PM | October 19, 2018 05:00 PM | October 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 716 days | 716 days | 716 days | Engineer
35 | Yes | CMU1.2 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้น 4 | 471 days | 2 |  |  |  | October 17, 2018 8:00 AM | January 30, 2020 5:00 PM | October 17, 2018 05:00 PM | January 30, 2020 05:00 PM | June 23, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 0 days | 245 days | 0 days
36 | Yes | CMU1.2.1 | Auto Scheduled | งานรื้อถอน ชั้น 4 (รื้อขนไป) | 30 days | 3 |  |  | 39FS+45 days,40FS+45 days,51,63SS+14 days,80,109,140,180FS+14 days,186FS+14 days,198FS+14 days,199FS+14 days,200FS+14 days,238FS+14 days | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 17, 2018 05:00 PM | November 15, 2018 05:00 PM | March 11, 2018 05:00 PM | April 09, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | General worker
37 | Yes | CMU1.2.2 | Auto Scheduled | งานสถาปัตยกรรม ชั้น 4 | 396 days | 3 |  |  |  | December 31, 2018 8:00 AM | January 30, 2020 5:00 PM | October 17, 2018 05:00 PM | November 16, 2019 05:00 PM | September 06, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 326 days | 245 days | 245 days
38 | Yes | CMU1.2.2.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 39,41,42 |  |  | March 1, 2019 8:00 AM | March 30, 2019 5:00 PM | March 11, 2019 05:00 PM | April 09, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 551 days | Skilled carpenter
39 | Yes | CMU1.2.2.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 36FS+45 days |  | 38,43 | December 31, 2018 8:00 AM | February 28, 2019 5:00 PM | January 05, 2019 05:00 PM | March 05, 2019 05:00 PM | July 15, 2020 05:00 PM | September 12, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 0 days | General worker
40 | Yes | CMU1.2.2.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 36FS+45 days |  | 41,42 | December 31, 2018 8:00 AM | January 29, 2019 5:00 PM | January 03, 2019 05:00 PM | February 01, 2019 05:00 PM | August 14, 2020 05:00 PM | September 12, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 0 days | General worker
41 | Yes | CMU1.2.2.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 40 |  | 38,43 | January 30, 2019 8:00 AM | February 28, 2019 5:00 PM | February 05, 2019 05:00 PM | March 06, 2019 05:00 PM | August 14, 2020 05:00 PM | September 12, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 0 days | Skilled carpenter
42 | Yes | CMU1.2.2.5 | Auto Scheduled | งานบันได | 30 days | 4 | 40 |  | 38,43 | January 30, 2019 8:00 AM | February 28, 2019 5:00 PM | February 05, 2019 05:00 PM | March 06, 2019 05:00 PM | August 14, 2020 05:00 PM | September 12, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 0 days | General worker
43 | Yes | CMU1.2.2.6 | Auto Scheduled | งานสี | 30 days | 4 | 39,41,42 |  |  | March 1, 2019 8:00 AM | March 30, 2019 5:00 PM | March 10, 2019 05:00 PM | April 08, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 551 days | General worker
44 | Yes | CMU1.2.2.7 | Auto Scheduled | งานสุขภัณฑ์ | 315 days | 4 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 20, 2018 05:00 PM | August 30, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
45 | Yes | CMU1.2.2.7.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 46FS+135 days |  | 47FS+135 days | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | September 14, 2019 05:00 PM | September 28, 2019 05:00 PM | April 24, 2020 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
46 | Yes | CMU1.2.2.7.2 | Auto Scheduled | ZONE T-2 กลาง | 15 days | 5 | 51,55 |  | 45FS+135 days | March 22, 2019 8:00 AM | April 5, 2019 5:00 PM | April 07, 2019 05:00 PM | April 21, 2019 05:00 PM | November 26, 2019 05:00 PM | December 10, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
47 | Yes | CMU1.2.2.7.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 15 days | 5 | 45FS+135 days |  |  | January 16, 2020 8:00 AM | January 30, 2020 5:00 PM | February 18, 2020 05:00 PM | March 03, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 245 days | Sanitary-Plumber
48 | Yes | CMU1.2.3 | Auto Scheduled | งานระบบสุขาภิบาล ชั้น 4 | 408 days | 3 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
49 | Yes | CMU1.2.3.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
50 | Yes | CMU1.2.3.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 51FS+15 days |  | 52FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 18, 2019 05:00 PM | August 21, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
51 | Yes | CMU1.2.3.1.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 36 |  | 50FS+15 days,46,55SS | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 23, 2018 05:00 PM | March 28, 2019 05:00 PM | August 25, 2019 05:00 PM | December 28, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
52 | Yes | CMU1.2.3.1.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 50FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 10, 2019 05:00 PM | January 13, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
53 | Yes | CMU1.2.3.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
54 | Yes | CMU1.2.3.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 55FS+15 days |  | 56FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 23, 2019 05:00 PM | August 26, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
55 | Yes | CMU1.2.3.2.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 51SS |  | 54FS+15 days,46 | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 27, 2018 05:00 PM | April 01, 2019 05:00 PM | August 25, 2019 05:00 PM | December 28, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
56 | Yes | CMU1.2.3.2.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 54FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 18, 2019 05:00 PM | January 21, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
57 | Yes | CMU1.2.4 | Auto Scheduled | งานระบบไฟฟ้า ชั้น 4 | 117 days | 3 |  |  |  | November 30, 2018 8:00 AM | March 26, 2019 5:00 PM | October 21, 2018 05:00 PM | February 14, 2019 05:00 PM | June 11, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 555 days | 555 days | 555 days
58 | Yes | CMU1.2.4.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 30 days | 4 | 60FS+7 days |  |  | February 25, 2019 8:00 AM | March 26, 2019 5:00 PM | March 04, 2019 05:00 PM | April 02, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 555 days | 555 days | 555 days | Electrician
59 | Yes | CMU1.2.4.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 30 days | 4 | 60FS+7 days |  |  | February 25, 2019 8:00 AM | March 26, 2019 5:00 PM | March 05, 2019 05:00 PM | April 03, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 555 days | 555 days | 555 days | Electrician
60 | Yes | CMU1.2.4.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 63SS+30 days |  | 58FS+7 days,59FS+7 days | November 30, 2018 8:00 AM | February 17, 2019 5:00 PM | December 04, 2018 05:00 PM | February 21, 2019 05:00 PM | June 11, 2020 05:00 PM | August 29, 2020 05:00 PM | As Soon As Possible |  | No | 555 days | 555 days | 0 days | Electrician
61 | Yes | CMU1.2.4.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 63SS+30 days |  |  | November 30, 2018 8:00 AM | February 17, 2019 5:00 PM | December 03, 2018 05:00 PM | February 20, 2019 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 592 days | 592 days | 592 days | Electrician
62 | Yes | CMU1.2.4.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 63SS+30 days |  |  | November 30, 2018 8:00 AM | February 17, 2019 5:00 PM | December 07, 2018 05:00 PM | February 24, 2019 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 592 days | 592 days | 592 days | Electrician
63 | Yes | CMU1.2.5 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้น 4 | 165 days | 3 | 36SS+14 days |  | 62SS+30 days,60SS+30 days,61SS+30 days,65,214,219FS-15 days,224,230,244FS-7 days,250FS-7 days | October 31, 2018 8:00 AM | April 13, 2019 5:00 PM | October 31, 2018 05:00 PM | April 13, 2019 05:00 PM | June 19, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Skilled carpenter
64 | Yes | CMU1.3 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้น 3 | 441 days | 2 |  |  |  | November 16, 2018 8:00 AM | January 30, 2020 5:00 PM | October 17, 2018 05:00 PM | December 31, 2019 05:00 PM | July 23, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 149 days | 245 days | 149 days
65 | Yes | CMU1.3.1 | Auto Scheduled | งานรื้อถอน ชั้น 3 (รื้อขนไป) | 30 days | 3 | 63 | 121 | 68FS+45 days,69FS+45 days,92SS | April 14, 2019 8:00 AM | May 13, 2019 5:00 PM | April 14, 2019 05:00 PM | May 13, 2019 05:00 PM | July 19, 2018 05:00 PM | August 17, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | General worker
66 | Yes | CMU1.3.2 | Auto Scheduled | งานสถาปัตยกรรม ชั้น 3 | 315 days | 3 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 22, 2018 05:00 PM | September 01, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
67 | Yes | CMU1.3.2.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 68,70,71 |  |  | August 27, 2019 8:00 AM | September 25, 2019 5:00 PM | August 30, 2019 05:00 PM | September 28, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 372 days | Skilled carpenter
68 | Yes | CMU1.3.2.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 65FS+45 days |  | 67,72 | June 28, 2019 8:00 AM | August 26, 2019 5:00 PM | June 28, 2019 05:00 PM | August 26, 2019 05:00 PM | October 02, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 0 days | General worker
69 | Yes | CMU1.3.2.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 65FS+45 days |  | 70,71 | June 28, 2019 8:00 AM | July 27, 2019 5:00 PM | June 28, 2019 05:00 PM | July 27, 2019 05:00 PM | April 15, 2019 05:00 PM | May 14, 2019 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 0 days | General worker
70 | Yes | CMU1.3.2.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 69 |  | 67,72 | July 28, 2019 8:00 AM | August 26, 2019 5:00 PM | July 28, 2019 05:00 PM | August 26, 2019 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 0 days | Skilled carpenter
71 | Yes | CMU1.3.2.5 | Auto Scheduled | งานบันได | 30 days | 4 | 69 |  | 67,72 | July 28, 2019 8:00 AM | August 26, 2019 5:00 PM | July 28, 2019 05:00 PM | August 26, 2019 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 0 days | General worker
72 | Yes | CMU1.3.2.6 | Auto Scheduled | งานสี | 30 days | 4 | 68,70,71 |  |  | August 27, 2019 8:00 AM | September 25, 2019 5:00 PM | August 30, 2019 05:00 PM | September 28, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 372 days | General worker
73 | Yes | CMU1.3.2.7 | Auto Scheduled | งานสุขภัณฑ์ | 315 days | 4 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 22, 2018 05:00 PM | September 01, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
74 | Yes | CMU1.3.2.7.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 75FS+135 days |  | 76FS+135 days | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | August 24, 2019 05:00 PM | September 07, 2019 05:00 PM | April 24, 2020 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
75 | Yes | CMU1.3.2.7.2 | Auto Scheduled | ZONE T-2 กลาง | 15 days | 5 | 80,84 |  | 74FS+135 days | March 22, 2019 8:00 AM | April 5, 2019 5:00 PM | March 24, 2019 05:00 PM | April 07, 2019 05:00 PM | November 26, 2019 05:00 PM | December 10, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
76 | Yes | CMU1.3.2.7.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 15 days | 5 | 74FS+135 days |  |  | January 16, 2020 8:00 AM | January 30, 2020 5:00 PM | January 26, 2020 05:00 PM | February 09, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 245 days | Sanitary-Plumber
77 | Yes | CMU1.3.3 | Auto Scheduled | งานระบบสุขาภิบาล ชั้น 3 | 408 days | 3 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
78 | Yes | CMU1.3.3.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
79 | Yes | CMU1.3.3.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 80FS+15 days |  | 81FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 15, 2019 05:00 PM | August 18, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
80 | Yes | CMU1.3.3.1.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 36 |  | 79FS+15 days,84SS,75 | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 16, 2018 05:00 PM | March 21, 2019 05:00 PM | January 09, 2019 05:00 PM | May 14, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
81 | Yes | CMU1.3.3.1.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 79FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 12, 2019 05:00 PM | January 15, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
82 | Yes | CMU1.3.3.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
83 | Yes | CMU1.3.3.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 84FS+15 days |  | 85FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 11, 2019 05:00 PM | August 14, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
84 | Yes | CMU1.3.3.2.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 80SS |  | 83FS+15 days,75 | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 16, 2018 05:00 PM | March 21, 2019 05:00 PM | January 09, 2019 05:00 PM | May 14, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
85 | Yes | CMU1.3.3.2.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 83FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 07, 2019 05:00 PM | January 10, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
86 | Yes | CMU1.3.4 | Auto Scheduled | งานระบบไฟฟ้า ชั้น 3 | 147 days | 3 |  |  |  | May 14, 2019 8:00 AM | October 7, 2019 5:00 PM | October 21, 2018 05:00 PM | March 16, 2019 05:00 PM | May 12, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 360 days | 360 days | 360 days
87 | Yes | CMU1.3.4.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 60 days | 4 | 89FS+7 days |  |  | August 9, 2019 8:00 AM | October 7, 2019 5:00 PM | August 16, 2019 05:00 PM | October 14, 2019 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 360 days | 360 days | 360 days | Electrician
88 | Yes | CMU1.3.4.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 60 days | 4 | 89FS+7 days |  |  | August 9, 2019 8:00 AM | October 7, 2019 5:00 PM | August 21, 2019 05:00 PM | October 19, 2019 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 360 days | 360 days | 360 days | Electrician
89 | Yes | CMU1.3.4.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 92SS+30 days |  | 88FS+7 days,87FS+7 days | May 14, 2019 8:00 AM | August 1, 2019 5:00 PM | May 18, 2019 05:00 PM | August 05, 2019 05:00 PM | May 12, 2020 05:00 PM | July 30, 2020 05:00 PM | As Soon As Possible |  | No | 360 days | 360 days | 0 days | Electrician
90 | Yes | CMU1.3.4.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 92SS+30 days |  |  | May 14, 2019 8:00 AM | August 1, 2019 5:00 PM | May 22, 2019 05:00 PM | August 09, 2019 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 427 days | 427 days | 427 days | Electrician
91 | Yes | CMU1.3.4.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 92SS+30 days |  |  | May 14, 2019 8:00 AM | August 1, 2019 5:00 PM | May 23, 2019 05:00 PM | August 10, 2019 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 427 days | 427 days | 427 days | Electrician
92 | Yes | CMU1.3.5 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้น 3 | 180 days | 3 | 65SS |  | 91SS+30 days,90SS+30 days,89SS+30 days,94,213FS-15 days,218FS-30 days,223FS-15 days,229FS-15 days,243FS-7 days,249FS-7 days | April 14, 2019 8:00 AM | October 10, 2019 5:00 PM | April 16, 2019 05:00 PM | October 12, 2019 05:00 PM | October 12, 2019 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Skilled carpenter
93 | Yes | CMU1.4 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้น 2 | 509 days | 2 |  |  |  | November 16, 2018 8:00 AM | April 7, 2020 5:00 PM | October 17, 2018 05:00 PM | March 08, 2020 05:00 PM | May 16, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 177 days | 177 days
94 | Yes | CMU1.4.1 | Auto Scheduled | งานรื้อถอน ชั้น 2 (รื้อขนไป) | 30 days | 3 | 92 | 152 | 97FS+45 days,98FS+45 days,121SS | October 11, 2019 8:00 AM | November 9, 2019 5:00 PM | October 13, 2019 05:00 PM | November 11, 2019 05:00 PM | June 04, 2018 05:00 PM | July 03, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | General worker
95 | Yes | CMU1.4.2 | Auto Scheduled | งานสถาปัตยกรรม ชั้น 2 | 368 days | 3 |  |  |  | March 22, 2019 8:00 AM | March 23, 2020 5:00 PM | October 17, 2018 05:00 PM | October 19, 2019 05:00 PM | October 04, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 192 days | 192 days
96 | Yes | CMU1.4.2.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 97,99,100 |  |  | February 23, 2020 8:00 AM | March 23, 2020 5:00 PM | March 06, 2020 05:00 PM | April 04, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 192 days | Skilled carpenter
97 | Yes | CMU1.4.2.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 94FS+45 days |  | 96,101 | December 25, 2019 8:00 AM | February 22, 2020 5:00 PM | December 27, 2019 05:00 PM | February 24, 2020 05:00 PM | February 09, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 0 days | General worker
98 | Yes | CMU1.4.2.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 94FS+45 days |  | 99,100 | December 25, 2019 8:00 AM | January 23, 2020 5:00 PM | December 31, 2019 05:00 PM | January 29, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 0 days | General worker
99 | Yes | CMU1.4.2.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 98 |  | 96,101 | January 24, 2020 8:00 AM | February 22, 2020 5:00 PM | February 02, 2020 05:00 PM | March 02, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 0 days | Skilled carpenter
100 | Yes | CMU1.4.2.5 | Auto Scheduled | งานบันได | 30 days | 4 | 98 |  | 96,101 | January 24, 2020 8:00 AM | February 22, 2020 5:00 PM | February 02, 2020 05:00 PM | March 02, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 0 days | General worker
101 | Yes | CMU1.4.2.6 | Auto Scheduled | งานสี | 30 days | 4 | 97,99,100 |  |  | February 23, 2020 8:00 AM | March 23, 2020 5:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 192 days | General worker
102 | Yes | CMU1.4.2.7 | Auto Scheduled | งานสุขภัณฑ์ | 315 days | 4 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 21, 2018 05:00 PM | August 31, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
103 | Yes | CMU1.4.2.7.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 104FS+135 days |  | 105FS+135 days | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | September 08, 2019 05:00 PM | September 22, 2019 05:00 PM | April 24, 2020 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
104 | Yes | CMU1.4.2.7.2 | Auto Scheduled | ZONE T-2 กลาง | 15 days | 5 | 113,109 |  | 103FS+135 days | March 22, 2019 8:00 AM | April 5, 2019 5:00 PM | April 07, 2019 05:00 PM | April 21, 2019 05:00 PM | November 26, 2019 05:00 PM | December 10, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
105 | Yes | CMU1.4.2.7.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 15 days | 5 | 103FS+135 days |  |  | January 16, 2020 8:00 AM | January 30, 2020 5:00 PM | February 11, 2020 05:00 PM | February 25, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 245 days | Sanitary-Plumber
106 | Yes | CMU1.4.3 | Auto Scheduled | งานระบบสุขาภิบาล ชั้น 2 | 408 days | 3 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
107 | Yes | CMU1.4.3.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
108 | Yes | CMU1.4.3.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 109FS+15 days |  | 110FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 18, 2019 05:00 PM | August 21, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
109 | Yes | CMU1.4.3.1.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 36 |  | 113SS,104,108FS+15 days | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 23, 2018 05:00 PM | March 28, 2019 05:00 PM | August 25, 2019 05:00 PM | December 28, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
110 | Yes | CMU1.4.3.1.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 108FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 09, 2019 05:00 PM | January 12, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
111 | Yes | CMU1.4.3.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
112 | Yes | CMU1.4.3.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 113FS+15 days |  | 114FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 25, 2019 05:00 PM | August 28, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
113 | Yes | CMU1.4.3.2.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 109SS |  | 104,112FS+15 days | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 29, 2018 05:00 PM | April 03, 2019 05:00 PM | August 25, 2019 05:00 PM | December 28, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
114 | Yes | CMU1.4.3.2.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 112FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 17, 2019 05:00 PM | January 20, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
115 | Yes | CMU1.4.4 | Auto Scheduled | งานระบบไฟฟ้า ชั้น 2 | 147 days | 3 |  |  |  | November 10, 2019 8:00 AM | April 4, 2020 5:00 PM | October 20, 2018 05:00 PM | March 15, 2019 05:00 PM | May 12, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 180 days | 180 days | 180 days
116 | Yes | CMU1.4.4.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 60 days | 4 | 118FS+7 days |  |  | February 5, 2020 8:00 AM | April 4, 2020 5:00 PM | February 11, 2020 05:00 PM | April 10, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 180 days | 180 days | 180 days | Electrician
117 | Yes | CMU1.4.4.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 60 days | 4 | 118FS+7 days |  |  | February 5, 2020 8:00 AM | April 4, 2020 5:00 PM | February 12, 2020 05:00 PM | April 11, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 180 days | 180 days | 180 days | Electrician
118 | Yes | CMU1.4.4.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 121SS+30 days |  | 117FS+7 days,116FS+7 days | November 10, 2019 8:00 AM | January 28, 2020 5:00 PM | November 14, 2019 05:00 PM | February 01, 2020 05:00 PM | May 12, 2020 05:00 PM | July 30, 2020 05:00 PM | As Soon As Possible |  | No | 180 days | 180 days | 0 days | Electrician
119 | Yes | CMU1.4.4.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 121SS+30 days |  |  | November 10, 2019 8:00 AM | January 28, 2020 5:00 PM | November 17, 2019 05:00 PM | February 04, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 247 days | 247 days | 247 days | Electrician
120 | Yes | CMU1.4.4.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 121SS+30 days |  |  | November 10, 2019 8:00 AM | January 28, 2020 5:00 PM | November 18, 2019 05:00 PM | February 05, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 247 days | 247 days | 247 days | Electrician
121 | Yes | CMU1.4.5 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้น 2 | 180 days | 3 | 94SS |  | 120SS+30 days,119SS+30 days,118SS+30 days,123,212FS-15 days,217FS-30 days,222FS-15 days,228FS-15 days,242FS-7 days,248FS-7 days | October 11, 2019 8:00 AM | April 7, 2020 5:00 PM | October 13, 2019 05:00 PM | April 09, 2020 05:00 PM | June 04, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Skilled carpenter
122 | Yes | CMU1.5 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้น 1 | 686 days | 2 |  |  |  | November 16, 2018 8:00 AM | October 1, 2020 5:00 PM | October 17, 2018 05:00 PM | September 01, 2020 05:00 PM | November 20, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 0 days | 0 days
123 | Yes | CMU1.5.1 | Auto Scheduled | งานรื้อถอน ชั้น 1 (รื้อขนไป) | 30 days | 3 | 121 | 63 | 124,127FS+45 days,128FS+45 days,131FS+45 days,152SS,193SS,194SS,195SS,196SS,197SS,202SS,204SS,205SS,206SS,207SS | April 8, 2020 8:00 AM | May 7, 2020 5:00 PM | April 10, 2020 05:00 PM | May 09, 2020 05:00 PM | July 19, 2018 05:00 PM | August 17, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | General worker
124 | Yes | CMU1.5.2 | Auto Scheduled | งานโครงสร้างวิศวกรรม ชั้น 1 | 75 days | 3 | 123 |  |  | May 8, 2020 8:00 AM | July 21, 2020 5:00 PM | May 11, 2020 05:00 PM | July 24, 2020 05:00 PM | July 23, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 72 days | 72 days | 72 days | General worker
125 | Yes | CMU1.5.3 | Auto Scheduled | งานสถาปัตยกรรม ชั้น 1 | 548 days | 3 |  |  |  | March 22, 2019 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | April 16, 2020 05:00 PM | April 07, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 12 days | 12 days
126 | Yes | CMU1.5.3.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 127,129,130 |  |  | August 21, 2020 8:00 AM | September 19, 2020 5:00 PM | August 23, 2020 05:00 PM | September 21, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | Skilled carpenter
127 | Yes | CMU1.5.3.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 123FS+45 days |  | 126,132 | June 22, 2020 8:00 AM | August 20, 2020 5:00 PM | June 24, 2020 05:00 PM | August 22, 2020 05:00 PM | October 02, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
128 | Yes | CMU1.5.3.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 123FS+45 days |  | 129,130 | June 22, 2020 8:00 AM | July 21, 2020 5:00 PM | June 24, 2020 05:00 PM | July 23, 2020 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
129 | Yes | CMU1.5.3.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 128 |  | 126,132 | July 22, 2020 8:00 AM | August 20, 2020 5:00 PM | July 24, 2020 05:00 PM | August 22, 2020 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | Skilled carpenter
130 | Yes | CMU1.5.3.5 | Auto Scheduled | งานบันได | 30 days | 4 | 128 |  | 126,132 | July 22, 2020 8:00 AM | August 20, 2020 5:00 PM | July 24, 2020 05:00 PM | August 22, 2020 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
131 | Yes | CMU1.5.3.6 | Auto Scheduled | งานตกแต่งอื่น ๆ | 60 days | 4 | 123FS+45 days |  |  | June 22, 2020 8:00 AM | August 20, 2020 5:00 PM | June 24, 2020 05:00 PM | August 22, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 42 days | 42 days | 42 days | General worker
132 | Yes | CMU1.5.3.7 | Auto Scheduled | งานสี | 30 days | 4 | 127,129,130 |  |  | August 21, 2020 8:00 AM | September 19, 2020 5:00 PM | August 23, 2020 05:00 PM | September 21, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
133 | Yes | CMU1.5.3.8 | Auto Scheduled | งานสุขภัณฑ์ | 315 days | 4 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 23, 2018 05:00 PM | September 02, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
134 | Yes | CMU1.5.3.8.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 135FS+135 days |  | 136FS+135 days | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | August 24, 2019 05:00 PM | September 07, 2019 05:00 PM | April 24, 2020 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
135 | Yes | CMU1.5.3.8.2 | Auto Scheduled | ZONE T-2 กลาง | 15 days | 5 | 140,144 |  | 134FS+135 days,164FS+135 days | March 22, 2019 8:00 AM | April 5, 2019 5:00 PM | March 24, 2019 05:00 PM | April 07, 2019 05:00 PM | November 26, 2019 05:00 PM | December 10, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
136 | Yes | CMU1.5.3.8.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 15 days | 5 | 134FS+135 days |  |  | January 16, 2020 8:00 AM | January 30, 2020 5:00 PM | January 24, 2020 05:00 PM | February 07, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 245 days | Sanitary-Plumber
137 | Yes | CMU1.5.4 | Auto Scheduled | งานระบบสุขาภิบาล ชั้น 1 | 408 days | 3 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 278 days | 44 days
138 | Yes | CMU1.5.4.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 278 days | 44 days
139 | Yes | CMU1.5.4.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 140FS+15 days |  | 141FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 13, 2019 05:00 PM | August 16, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
140 | Yes | CMU1.5.4.1.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 36 |  | 139FS+15 days,144SS,135,167FS+15 days | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 16, 2018 05:00 PM | March 21, 2019 05:00 PM | January 03, 2019 05:00 PM | May 08, 2019 05:00 PM | As Soon As Possible |  | No | 44 days | 44 days | 0 days | Sanitary-Plumber
141 | Yes | CMU1.5.4.1.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 139FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 08, 2019 05:00 PM | January 11, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
142 | Yes | CMU1.5.4.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 278 days | 44 days
143 | Yes | CMU1.5.4.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 144FS+15 days |  | 145FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 12, 2019 05:00 PM | August 15, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
144 | Yes | CMU1.5.4.2.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 140SS |  | 143FS+15 days,135,169FS+15 days | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 16, 2018 05:00 PM | March 21, 2019 05:00 PM | January 03, 2019 05:00 PM | May 08, 2019 05:00 PM | As Soon As Possible |  | No | 44 days | 44 days | 0 days | Sanitary-Plumber
145 | Yes | CMU1.5.4.2.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 143FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 04, 2019 05:00 PM | January 07, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
146 | Yes | CMU1.5.5 | Auto Scheduled | งานระบบไฟฟ้า ชั้น 1 | 147 days | 3 |  |  |  | May 8, 2020 8:00 AM | October 1, 2020 5:00 PM | October 21, 2018 05:00 PM | March 16, 2019 05:00 PM | May 12, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 0 days | 0 days | 0 days
147 | Yes | CMU1.5.5.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 60 days | 4 | 149FS+7 days |  |  | August 3, 2020 8:00 AM | October 1, 2020 5:00 PM | August 05, 2020 05:00 PM | October 03, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Electrician
148 | Yes | CMU1.5.5.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 60 days | 4 | 149FS+7 days |  |  | August 3, 2020 8:00 AM | October 1, 2020 5:00 PM | August 05, 2020 05:00 PM | October 03, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Electrician
149 | Yes | CMU1.5.5.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 152SS+30 days |  | 148FS+7 days,147FS+7 days | May 8, 2020 8:00 AM | July 26, 2020 5:00 PM | May 10, 2020 05:00 PM | July 28, 2020 05:00 PM | May 12, 2020 05:00 PM | July 30, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Electrician
150 | Yes | CMU1.5.5.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 152SS+30 days |  |  | May 8, 2020 8:00 AM | July 26, 2020 5:00 PM | May 10, 2020 05:00 PM | July 28, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 67 days | 67 days | 67 days | Electrician
151 | Yes | CMU1.5.5.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 152SS+30 days |  |  | May 8, 2020 8:00 AM | July 26, 2020 5:00 PM | May 10, 2020 05:00 PM | July 28, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 67 days | 67 days | 67 days | Electrician
152 | Yes | CMU1.5.6 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้น 1 | 165 days | 3 | 123SS |  | 151SS+30 days,150SS+30 days,149SS+30 days,154SS,211FS-30 days,210FS-30 days,216FS-45 days,221FS-30 days,227FS-30 days,226FS-30 days,232FS-45 days,241FS-7 days,247FS-7 days | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 10, 2020 05:00 PM | September 21, 2020 05:00 PM | November 26, 2019 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Skilled carpenter
153 | Yes | CMU1.6 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้นใต้ดิน | 533 days | 2 |  |  |  | April 6, 2019 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | April 01, 2020 05:00 PM | April 22, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 12 days | 12 days
154 | Yes | CMU1.6.1 | Auto Scheduled | งานรื้อถอน ชั้นใต้ดิน (รื้อขนไป) | 30 days | 3 | 152SS |  | 155,158FS+45 days,159FS+45 days,177SS,176SS,175SS,174SS | April 8, 2020 8:00 AM | May 7, 2020 5:00 PM | April 10, 2020 05:00 PM | May 09, 2020 05:00 PM | November 26, 2019 05:00 PM | December 25, 2019 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
155 | Yes | CMU1.6.2 | Auto Scheduled | งานโครงสร้างวิศวกรรม ชั้นใต้ดิน | 75 days | 3 | 154 |  |  | May 8, 2020 8:00 AM | July 21, 2020 5:00 PM | May 11, 2020 05:00 PM | July 24, 2020 05:00 PM | July 23, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 72 days | 72 days | 72 days | General worker
156 | Yes | CMU1.6.3 | Auto Scheduled | งานสถาปัตยกรรม ชั้นใต้ดิน | 398 days | 3 |  |  |  | August 19, 2019 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | November 18, 2019 05:00 PM | September 04, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 320 days | 12 days | 12 days
157 | Yes | CMU1.6.3.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 158,160,161 |  |  | August 21, 2020 8:00 AM | September 19, 2020 5:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | Skilled carpenter
158 | Yes | CMU1.6.3.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 154FS+45 days |  | 157,162 | June 22, 2020 8:00 AM | August 20, 2020 5:00 PM | June 24, 2020 05:00 PM | August 22, 2020 05:00 PM | February 09, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
159 | Yes | CMU1.6.3.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 154FS+45 days |  | 160,161 | June 22, 2020 8:00 AM | July 21, 2020 5:00 PM | July 08, 2020 05:00 PM | August 06, 2020 05:00 PM | August 22, 2020 05:00 PM | September 20, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
160 | Yes | CMU1.6.3.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 159 |  | 157,162 | July 22, 2020 8:00 AM | August 20, 2020 5:00 PM | August 07, 2020 05:00 PM | September 05, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | Skilled carpenter
161 | Yes | CMU1.6.3.5 | Auto Scheduled | งานบันได | 30 days | 4 | 159 |  | 157,162 | July 22, 2020 8:00 AM | August 20, 2020 5:00 PM | August 07, 2020 05:00 PM | September 05, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
162 | Yes | CMU1.6.3.6 | Auto Scheduled | งานสี | 30 days | 4 | 158,160,161 |  |  | August 21, 2020 8:00 AM | September 19, 2020 5:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
163 | Yes | CMU1.6.3.7 | Auto Scheduled | งานสุขภัณฑ์ | 15 days | 4 |  |  |  | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | October 19, 2018 05:00 PM | November 02, 2018 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 395 days | 395 days | 395 days
164 | Yes | CMU1.6.3.7.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 135FS+135 days |  |  | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | August 27, 2019 05:00 PM | September 10, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 395 days | 395 days | 395 days | Sanitary-Plumber
165 | Yes | CMU1.6.4 | Auto Scheduled | งานระบบสุขาภิบาล ชั้นใต้ดิน | 501 days | 3 |  |  |  | April 6, 2019 8:00 AM | August 18, 2020 5:00 PM | October 17, 2018 05:00 PM | February 29, 2020 05:00 PM | May 24, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 44 days | 44 days
166 | Yes | CMU1.6.4.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 126 days | 4 |  |  |  | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | October 21, 2018 05:00 PM | February 23, 2019 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 419 days | 419 days | 419 days
167 | Yes | CMU1.6.4.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 140FS+15 days |  |  | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 13, 2019 05:00 PM | August 16, 2019 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 419 days | 419 days | 419 days | Sanitary-Plumber
168 | Yes | CMU1.6.4.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 126 days | 4 |  |  |  | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | October 21, 2018 05:00 PM | February 23, 2019 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 44 days | 44 days
169 | Yes | CMU1.6.4.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 144FS+15 days |  | 170FS+300 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 06, 2019 05:00 PM | August 09, 2019 05:00 PM | May 24, 2019 05:00 PM | September 26, 2019 05:00 PM | As Soon As Possible |  | No | 44 days | 44 days | 0 days | Sanitary-Plumber
170 | Yes | CMU1.6.4.3 | Auto Scheduled | งานระบบระบายน้ำฝน | 75 days | 4 | 169FS+300 days |  |  | June 5, 2020 8:00 AM | August 18, 2020 5:00 PM | June 05, 2020 05:00 PM | August 18, 2020 05:00 PM | July 23, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 44 days | 44 days | 44 days | Sanitary-Plumber
171 | Yes | CMU1.6.5 | Auto Scheduled | งานระบบไฟฟ้า ชั้นใต้ดิน | 147 days | 3 |  |  |  | April 8, 2020 8:00 AM | September 1, 2020 5:00 PM | October 23, 2018 05:00 PM | March 18, 2019 05:00 PM | May 12, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 30 days | 30 days | 30 days
172 | Yes | CMU1.6.5.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 60 days | 4 | 174FS+7 days |  |  | July 4, 2020 8:00 AM | September 1, 2020 5:00 PM | July 06, 2020 05:00 PM | September 03, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 30 days | 30 days | 30 days | Electrician
173 | Yes | CMU1.6.5.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 60 days | 4 | 174FS+7 days |  |  | July 4, 2020 8:00 AM | September 1, 2020 5:00 PM | July 06, 2020 05:00 PM | September 03, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 30 days | 30 days | 30 days | Electrician
174 | Yes | CMU1.6.5.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 154SS |  | 173FS+7 days,172FS+7 days | April 8, 2020 8:00 AM | June 26, 2020 5:00 PM | April 10, 2020 05:00 PM | June 28, 2020 05:00 PM | May 12, 2020 05:00 PM | July 30, 2020 05:00 PM | As Soon As Possible |  | No | 30 days | 30 days | 0 days | Electrician
175 | Yes | CMU1.6.5.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 154SS |  |  | April 8, 2020 8:00 AM | June 26, 2020 5:00 PM | April 13, 2020 05:00 PM | July 01, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 97 days | 97 days | 97 days | Electrician
176 | Yes | CMU1.6.5.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 154SS |  |  | April 8, 2020 8:00 AM | June 26, 2020 5:00 PM | April 13, 2020 05:00 PM | July 01, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 97 days | 97 days | 97 days | Electrician
177 | Yes | CMU1.6.6 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้นใต้ดิน | 165 days | 3 | 154SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 10, 2020 05:00 PM | September 21, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | Skilled carpenter
178 | Yes | CMU1.7 | Auto Scheduled | หมวดงานระบบคอมพิวเตอร์และแจ้งเหตุเพลิงไหม้ | 670 days | 2 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
179 | Yes | CMU1.7.1 | Auto Scheduled | งานระบบคอมพิวเตอร์ | 670 days | 3 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
180 | Yes | CMU1.7.1.1 | Auto Scheduled | ชั้นที่ 4 | 160 days | 4 | 36FS+14 days |  | 181 | November 30, 2018 8:00 AM | May 8, 2019 5:00 PM | November 30, 2018 05:00 PM | May 08, 2019 05:00 PM | April 24, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
181 | Yes | CMU1.7.1.2 | Auto Scheduled | ชั้นที่ 3 | 175 days | 4 | 180 | 182 | 182 | May 9, 2019 8:00 AM | October 30, 2019 5:00 PM | May 09, 2019 05:00 PM | October 30, 2019 05:00 PM | April 09, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
182 | Yes | CMU1.7.1.3 | Auto Scheduled | ชั้นที่ 2 | 175 days | 4 | 181 | 183 | 183,184 | October 31, 2019 8:00 AM | April 22, 2020 5:00 PM | October 31, 2019 05:00 PM | April 22, 2020 05:00 PM | April 09, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
183 | Yes | CMU1.7.1.4 | Auto Scheduled | ชั้นที่ 1 | 160 days | 4 | 182 | 180 |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 23, 2020 05:00 PM | September 29, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
184 | Yes | CMU1.7.1.5 | Auto Scheduled | ชั้นใต้ดิน | 160 days | 4 | 182 | 183SS |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 23, 2020 05:00 PM | September 29, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
185 | Yes | CMU1.7.2 | Auto Scheduled | ระบบแจ้งเหตุเพลิงไหม้ | 670 days | 3 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
186 | Yes | CMU1.7.2.1 | Auto Scheduled | ชั้นที่ 4 | 160 days | 4 | 36FS+14 days |  | 187 | November 30, 2018 8:00 AM | May 8, 2019 5:00 PM | November 30, 2018 05:00 PM | May 08, 2019 05:00 PM | April 24, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
187 | Yes | CMU1.7.2.2 | Auto Scheduled | ชั้นที่ 3 | 175 days | 4 | 186 | 188 | 188 | May 9, 2019 8:00 AM | October 30, 2019 5:00 PM | May 09, 2019 05:00 PM | October 30, 2019 05:00 PM | April 09, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
188 | Yes | CMU1.7.2.3 | Auto Scheduled | ชั้นที่ 2 | 175 days | 4 | 187 | 189 | 189,190 | October 31, 2019 8:00 AM | April 22, 2020 5:00 PM | October 31, 2019 05:00 PM | April 22, 2020 05:00 PM | April 09, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
189 | Yes | CMU1.7.2.4 | Auto Scheduled | ชั้นที่ 1 | 160 days | 4 | 188 | 186 |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 23, 2020 05:00 PM | September 29, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
190 | Yes | CMU1.7.2.5 | Auto Scheduled | ชั้นใต้ดิน | 160 days | 4 | 188 | 189SS |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 23, 2020 05:00 PM | September 29, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
191 | Yes | CMU1.8 | Auto Scheduled | หมวดงานสีภายนอก งานซ่อมแซมและตกแต่งภายนอกอาคาร | 660 days | 2 |  |  |  | November 30, 2018 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | August 06, 2020 05:00 PM | December 16, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 507 days | 12 days | 12 days
192 | Yes | CMU1.8.1 | Auto Scheduled | งานสีภายนอกและงานซ่อมแซมพื้นผิวภายนอกอาคาร | 660 days | 3 |  |  |  | November 30, 2018 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | August 06, 2020 05:00 PM | December 16, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 507 days | 12 days | 12 days
193 | Yes | CMU1.8.1.1 | Auto Scheduled | งานขัดลอกสีทาผนังเดิม | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 10, 2020 05:00 PM | September 21, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
194 | Yes | CMU1.8.1.2 | Auto Scheduled | น้ำยาทาปูนเก่า (สีรองพื้น) | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 10, 2020 05:00 PM | September 21, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
195 | Yes | CMU1.8.1.3 | Auto Scheduled | งานทาสีภายนอก (ทา 2 เที่ยว) ไม่รวมชั้นใต้ดิน | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 10, 2020 05:00 PM | September 21, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
196 | Yes | CMU1.8.1.4 | Auto Scheduled | งานทำความสะอาดและซ่อมแซมผนังกรุอิฐโชว์แนว (อ้างอิงราคางานขัดลอกสี) | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 10, 2020 05:00 PM | September 21, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
197 | Yes | CMU1.8.1.5 | Auto Scheduled | น้ำยาเคลือบผิวผนังอิฐโชว์แนว (อ้างอิงค่าทาน้ำยากันเชื้อรา) | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 10, 2020 05:00 PM | September 21, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
198 | Yes | CMU1.8.1.6 | Auto Scheduled | งานรื้อถอนแผ่นวัสดุกันซึมหลังคาดาดฟ้า (รื้อขนไป) | 90 days | 4 | 36FS+14 days |  |  | November 30, 2018 8:00 AM | February 27, 2019 5:00 PM | December 03, 2018 05:00 PM | March 02, 2019 05:00 PM | July 08, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 582 days | 582 days | 582 days | General worker
199 | Yes | CMU1.8.1.7 | Auto Scheduled | งานแผ่นวัสดุกันซึมแบบเป่าไฟผิวทราย | 90 days | 4 | 36FS+14 days |  |  | November 30, 2018 8:00 AM | February 27, 2019 5:00 PM | December 04, 2018 05:00 PM | March 03, 2019 05:00 PM | July 08, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 582 days | 582 days | 582 days | General worker
200 | Yes | CMU1.8.1.8 | Auto Scheduled | งานกันซึมชนิด Polyurethane สูตรน้ำมัน ชนิดยืดหยุ่นสูงเป็นพิเศษ | 90 days | 4 | 36FS+14 days |  |  | November 30, 2018 8:00 AM | February 27, 2019 5:00 PM | December 04, 2018 05:00 PM | March 03, 2019 05:00 PM | July 08, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 582 days | 582 days | 582 days | General worker
201 | Yes | CMU1.8.2 | Auto Scheduled | งานตกแต่งภายนอกอาคาร | 165 days | 3 |  |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | October 20, 2018 05:00 PM | April 02, 2019 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 12 days | 12 days | 12 days
202 | Yes | CMU1.8.2.1 | Auto Scheduled | ตะแกรงเหล็กฉีกกันนก XS-32 | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 10, 2020 05:00 PM | September 21, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
203 | Yes | CMU1.9 | Auto Scheduled | หมวดงานบริเวณ | 165 days | 2 |  |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | October 23, 2018 05:00 PM | April 05, 2019 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 12 days | 12 days | 12 days
204 | Yes | CMU1.9.1 | Auto Scheduled | งานรื้อถอน งานบริเวณ | 165 days | 3 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 10, 2020 05:00 PM | September 21, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
205 | Yes | CMU1.9.2 | Auto Scheduled | งานโครงสร้างวิศวกรรม งานบริเวณ | 165 days | 3 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 10, 2020 05:00 PM | September 21, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
206 | Yes | CMU1.9.3 | Auto Scheduled | งานสถาปัตยกรรม งานบริเวณ | 165 days | 3 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 10, 2020 05:00 PM | September 21, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
207 | Yes | CMU1.9.4 | Auto Scheduled | งานระบบไฟฟ้า งานบริเวณ | 165 days | 3 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 10, 2020 05:00 PM | September 21, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | Electrician
208 | Yes | CMU1.10 | Auto Scheduled | หมวดงานครุภัณฑ์จัดซื้อ | 670 days | 2 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
209 | Yes | CMU1.10.1 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัว | 510 days | 3 |  |  |  | April 14, 2019 8:00 AM | September 4, 2020 5:00 PM | October 17, 2018 05:00 PM | March 09, 2020 05:00 PM | May 15, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 522 days | 27 days | 27 days
210 | Yes | CMU1.10.1.1 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้นใต้ดิน | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | August 27, 2020 05:00 PM | September 10, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
211 | Yes | CMU1.10.1.2 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้น 1 | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | August 30, 2020 05:00 PM | September 13, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
212 | Yes | CMU1.10.1.3 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้น 2 | 15 days | 4 | 121FS-15 days |  |  | March 24, 2020 8:00 AM | April 7, 2020 5:00 PM | March 27, 2020 05:00 PM | April 10, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Skilled carpenter
213 | Yes | CMU1.10.1.4 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้น 3 | 15 days | 4 | 92FS-15 days |  |  | September 26, 2019 8:00 AM | October 10, 2019 5:00 PM | October 04, 2019 05:00 PM | October 18, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Skilled carpenter
214 | Yes | CMU1.10.1.5 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้น 4 | 15 days | 4 | 63 |  |  | April 14, 2019 8:00 AM | April 28, 2019 5:00 PM | April 21, 2019 05:00 PM | May 05, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 522 days | 522 days | 522 days | Skilled carpenter
215 | Yes | CMU1.10.2 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ | 525 days | 3 |  |  |  | March 30, 2019 8:00 AM | September 4, 2020 5:00 PM | October 17, 2018 05:00 PM | March 24, 2020 05:00 PM | April 30, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 522 days | 27 days | 27 days
216 | Yes | CMU1.10.2.1 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ ชั้น 1 | 30 days | 4 | 152FS-45 days |  |  | August 6, 2020 8:00 AM | September 4, 2020 5:00 PM | August 14, 2020 05:00 PM | September 12, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
217 | Yes | CMU1.10.2.2 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ ชั้น 2 | 30 days | 4 | 121FS-30 days |  |  | March 9, 2020 8:00 AM | April 7, 2020 5:00 PM | March 14, 2020 05:00 PM | April 12, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Skilled carpenter
218 | Yes | CMU1.10.2.3 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ ชั้น 3 | 30 days | 4 | 92FS-30 days |  |  | September 11, 2019 8:00 AM | October 10, 2019 5:00 PM | September 15, 2019 05:00 PM | October 14, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Skilled carpenter
219 | Yes | CMU1.10.2.4 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ ชั้น 4 | 30 days | 4 | 63FS-15 days |  |  | March 30, 2019 8:00 AM | April 28, 2019 5:00 PM | April 02, 2019 05:00 PM | May 01, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 522 days | 522 days | 522 days | Skilled carpenter
220 | Yes | CMU1.10.3 | Auto Scheduled | งานผ้าม่าน | 510 days | 3 |  |  |  | April 14, 2019 8:00 AM | September 4, 2020 5:00 PM | October 17, 2018 05:00 PM | March 09, 2020 05:00 PM | May 15, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 522 days | 27 days | 27 days
221 | Yes | CMU1.10.3.1 | Auto Scheduled | งานผ้าม่าน ชั้น 1 | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | August 28, 2020 05:00 PM | September 11, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
222 | Yes | CMU1.10.3.2 | Auto Scheduled | งานผ้าม่าน ชั้น 2 | 15 days | 4 | 121FS-15 days |  |  | March 24, 2020 8:00 AM | April 7, 2020 5:00 PM | March 29, 2020 05:00 PM | April 12, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Skilled carpenter
223 | Yes | CMU1.10.3.3 | Auto Scheduled | งานผ้าม่าน ชั้น 3 | 15 days | 4 | 92FS-15 days |  |  | September 26, 2019 8:00 AM | October 10, 2019 5:00 PM | October 01, 2019 05:00 PM | October 15, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Skilled carpenter
224 | Yes | CMU1.10.3.4 | Auto Scheduled | งานผ้าม่าน ชั้น 4 | 15 days | 4 | 63 |  |  | April 14, 2019 8:00 AM | April 28, 2019 5:00 PM | April 25, 2019 05:00 PM | May 09, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 522 days | 522 days | 522 days | Skilled carpenter
225 | Yes | CMU1.10.4 | Auto Scheduled | งานป้าย | 510 days | 3 |  |  |  | April 14, 2019 8:00 AM | September 4, 2020 5:00 PM | October 17, 2018 05:00 PM | March 09, 2020 05:00 PM | May 15, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 522 days | 27 days | 27 days
226 | Yes | CMU1.10.4.1 | Auto Scheduled | งานป้าย ชั้นใต้ดิน | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | August 27, 2020 05:00 PM | September 10, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
227 | Yes | CMU1.10.4.2 | Auto Scheduled | งานป้าย ชั้น 1 | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | August 30, 2020 05:00 PM | September 13, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
228 | Yes | CMU1.10.4.3 | Auto Scheduled | งานป้าย ชั้น 2 | 15 days | 4 | 121FS-15 days |  |  | March 24, 2020 8:00 AM | April 7, 2020 5:00 PM | March 29, 2020 05:00 PM | April 12, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Skilled carpenter
229 | Yes | CMU1.10.4.4 | Auto Scheduled | งานป้าย ชั้น 3 | 15 days | 4 | 92FS-15 days |  |  | September 26, 2019 8:00 AM | October 10, 2019 5:00 PM | October 02, 2019 05:00 PM | October 16, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Skilled carpenter
230 | Yes | CMU1.10.4.5 | Auto Scheduled | งานป้าย ชั้น 4 | 15 days | 4 | 63 |  |  | April 14, 2019 8:00 AM | April 28, 2019 5:00 PM | April 20, 2019 05:00 PM | May 04, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 522 days | 522 days | 522 days | Skilled carpenter
231 | Yes | CMU1.10.5 | Auto Scheduled | งานอื่นๆ | 15 days | 3 |  |  |  | August 6, 2020 8:00 AM | August 20, 2020 5:00 PM | October 20, 2018 05:00 PM | November 03, 2018 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 42 days | 42 days | 42 days
232 | Yes | CMU1.10.5.1 | Auto Scheduled | ตู้อลูมิเนียมพับขึ้นรูป พ่นสี ครอบตู้กดน้ำ | 15 days | 4 | 152FS-45 days |  |  | August 6, 2020 8:00 AM | August 20, 2020 5:00 PM | August 12, 2020 05:00 PM | August 26, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 42 days | 42 days | 42 days | General worker
233 | Yes | CMU1.10.6 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ | 670 days | 3 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
234 | Yes | CMU1.10.6.1 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้นใต้ดิน | 160 days | 4 | 236 |  |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 28, 2020 05:00 PM | October 04, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
235 | Yes | CMU1.10.6.2 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้น 1 | 160 days | 4 | 236 |  |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 28, 2020 05:00 PM | October 04, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
236 | Yes | CMU1.10.6.3 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้น 2 | 175 days | 4 | 237 |  | 235,234 | October 31, 2019 8:00 AM | April 22, 2020 5:00 PM | November 05, 2019 05:00 PM | April 27, 2020 05:00 PM | March 12, 2020 05:00 PM | September 02, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
237 | Yes | CMU1.10.6.4 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้น 3 | 175 days | 4 | 238 |  | 236 | May 9, 2019 8:00 AM | October 30, 2019 5:00 PM | May 14, 2019 05:00 PM | November 04, 2019 05:00 PM | March 12, 2020 05:00 PM | September 02, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
238 | Yes | CMU1.10.6.5 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้น 4 | 160 days | 4 | 36FS+14 days |  | 237 | November 30, 2018 8:00 AM | May 8, 2019 5:00 PM | December 02, 2018 05:00 PM | May 10, 2019 05:00 PM | March 27, 2020 05:00 PM | September 02, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
239 | Yes | CMU1.10.7 | Auto Scheduled | งานระบบเครื่องเสียงประกาศ (ใช้ลำโพงของเดิม) | 539 days | 3 |  |  |  | April 7, 2019 8:00 AM | September 26, 2020 5:00 PM | October 17, 2018 05:00 PM | April 07, 2020 05:00 PM | April 16, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 530 days | 5 days | 5 days
240 | Yes | CMU1.10.7.1 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้นใต้ดิน | 7 days | 4 | 241 |  |  | September 20, 2020 8:00 AM | September 26, 2020 5:00 PM | September 26, 2020 05:00 PM | October 02, 2020 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 5 days | 5 days | 5 days | Electrician
241 | Yes | CMU1.10.7.2 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้น 1 | 7 days | 4 | 152FS-7 days |  | 240 | September 13, 2020 8:00 AM | September 19, 2020 5:00 PM | September 15, 2020 05:00 PM | September 21, 2020 05:00 PM | September 09, 2020 05:00 PM | September 15, 2020 05:00 PM | As Soon As Possible |  | No | 5 days | 5 days | 0 days | Electrician
242 | Yes | CMU1.10.7.3 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้น 2 | 7 days | 4 | 121FS-7 days |  |  | April 1, 2020 8:00 AM | April 7, 2020 5:00 PM | April 05, 2020 05:00 PM | April 11, 2020 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Electrician
243 | Yes | CMU1.10.7.4 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้น 3 | 7 days | 4 | 92FS-7 days |  |  | October 4, 2019 8:00 AM | October 10, 2019 5:00 PM | October 16, 2019 05:00 PM | October 22, 2019 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Electrician
244 | Yes | CMU1.10.7.5 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้น 4 | 7 days | 4 | 63FS-7 days |  |  | April 7, 2019 8:00 AM | April 13, 2019 5:00 PM | April 15, 2019 05:00 PM | April 21, 2019 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 537 days | 537 days | 537 days | Electrician
245 | Yes | CMU1.10.8 | Auto Scheduled | งานระบบกล้องวงจรปิด (ใช้กล้องวงจรปิดของเดิม) | 539 days | 3 |  |  |  | April 7, 2019 8:00 AM | September 26, 2020 5:00 PM | October 17, 2018 05:00 PM | April 07, 2020 05:00 PM | April 16, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 530 days | 5 days | 5 days
246 | Yes | CMU1.10.8.1 | Auto Scheduled | งานกล้องวงจรปิด ชั้นใต้ดิน | 7 days | 4 | 247 |  |  | September 20, 2020 8:00 AM | September 26, 2020 5:00 PM | September 26, 2020 05:00 PM | October 02, 2020 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 5 days | 5 days | 5 days | Electrician
247 | Yes | CMU1.10.8.2 | Auto Scheduled | งานกล้องวงจรปิด ชั้น 1 | 7 days | 4 | 152FS-7 days |  | 246 | September 13, 2020 8:00 AM | September 19, 2020 5:00 PM | September 15, 2020 05:00 PM | September 21, 2020 05:00 PM | September 09, 2020 05:00 PM | September 15, 2020 05:00 PM | As Soon As Possible |  | No | 5 days | 5 days | 0 days | Electrician
248 | Yes | CMU1.10.8.3 | Auto Scheduled | งานกล้องวงจรปิด ชั้น 2 | 7 days | 4 | 121FS-7 days |  |  | April 1, 2020 8:00 AM | April 7, 2020 5:00 PM | April 06, 2020 05:00 PM | April 12, 2020 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Electrician
249 | Yes | CMU1.10.8.4 | Auto Scheduled | งานกล้องวงจรปิด ชั้น 3 | 7 days | 4 | 92FS-7 days |  |  | October 4, 2019 8:00 AM | October 10, 2019 5:00 PM | October 10, 2019 05:00 PM | October 16, 2019 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Electrician
250 | Yes | CMU1.10.8.5 | Auto Scheduled | งานกล้องวงจรปิด ชั้น 4 | 7 days | 4 | 63FS-7 days |  |  | April 7, 2019 8:00 AM | April 13, 2019 5:00 PM | April 11, 2019 05:00 PM | April 17, 2019 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 537 days | 537 days | 537 days | Electrician

## solutoion_6
ID | Active | WBS | Task_Mode | Name | Duration | Outline_Level | Predecessors | Predecessors2 | Successors | Start_Date | Finish_Date | Early_Start | Early_Finish | Late_Start | Late_Finish | Constraint_Type | Constraint_Date | Summary | Start_Slack | Finish_Slack | Free_Slack | Resource_Names
1 | Yes | CMU1 | Auto Scheduled | โครงการปรับปรุงสำนักหอสมุด มหาวิทยาลัยเชียงใหม่ | 716 days | 1 |  |  |  | October 17, 2018 8:00 AM | October 1, 2020 5:00 PM | October 17, 2018 05:00 PM | October 01, 2020 05:00 PM | October 21, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 0 days | 0 days | 0 days
2 | Yes | CMU1.1 | Auto Scheduled | หมวดเตรียมการ | 675 days | 2 |  |  |  | October 17, 2018 8:00 AM | August 21, 2020 5:00 PM | October 17, 2018 05:00 PM | August 21, 2020 05:00 PM | December 01, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 41 days | 41 days | 41 days
3 | Yes | CMU1.1.1 | Auto Scheduled | งานอาคารสนามและผังบริเวณโครงการ | 14 days | 3 | 4FS-7 days |  |  | October 26, 2018 8:00 AM | November 8, 2018 5:00 PM | November 01, 2018 05:00 PM | November 14, 2018 05:00 PM | September 22, 2020 05:00 PM | October 05, 2020 05:00 PM | Start No Earlier Than | Oct 24 '18 | No | 693 days | 693 days | 693 days | Engineer
4 | Yes | CMU1.1.2 | Auto Scheduled | งานเชื่อมต่อระบบสาธารณูปโภคโครงการ | 16 days | 3 |  |  | 3FS-7 days | October 17, 2018 8:00 AM | November 1, 2018 5:00 PM | October 19, 2018 05:00 PM | November 03, 2018 05:00 PM | September 13, 2020 05:00 PM | September 28, 2020 05:00 PM | As Soon As Possible |  | No | 693 days | 693 days | 0 days | Engineer
5 | Yes | CMU1.1.3 | Auto Scheduled | งานตรวจทดสอบระบบภายในอาคารก่อนดำเนินการปรับปรุง | 675 days | 3 |  |  |  | October 17, 2018 8:00 AM | August 21, 2020 5:00 PM | October 17, 2018 05:00 PM | August 21, 2020 05:00 PM | December 01, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 41 days | 41 days | 41 days
6 | Yes | CMU1.1.3.1 | Auto Scheduled | ชั้นที่ 4 | 15 days | 4 |  |  | 7FS+150 days | October 17, 2018 8:00 AM | October 31, 2018 5:00 PM | October 19, 2018 05:00 PM | November 02, 2018 05:00 PM | December 01, 2018 05:00 PM | December 15, 2018 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
7 | Yes | CMU1.1.3.2 | Auto Scheduled | ชั้นที่ 3 | 15 days | 4 | 6FS+150 days |  | 8FS+150 days | March 31, 2019 8:00 AM | April 14, 2019 5:00 PM | April 08, 2019 05:00 PM | April 22, 2019 05:00 PM | May 15, 2019 05:00 PM | May 29, 2019 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
8 | Yes | CMU1.1.3.3 | Auto Scheduled | ชั้นที่ 2 | 15 days | 4 | 7FS+150 days |  | 9FS+150 days | September 12, 2019 8:00 AM | September 26, 2019 5:00 PM | October 02, 2019 05:00 PM | October 16, 2019 05:00 PM | October 27, 2019 05:00 PM | November 10, 2019 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
9 | Yes | CMU1.1.3.4 | Auto Scheduled | ชั้นที่ 1 | 15 days | 4 | 8FS+150 days |  | 10FS+150 days | February 24, 2020 8:00 AM | March 9, 2020 5:00 PM | March 31, 2020 05:00 PM | April 14, 2020 05:00 PM | April 09, 2020 05:00 PM | April 23, 2020 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
10 | Yes | CMU1.1.3.5 | Auto Scheduled | ชั้นใต้ดินและภายนอก | 15 days | 4 | 9FS+150 days |  |  | August 7, 2020 8:00 AM | August 21, 2020 5:00 PM | September 22, 2020 05:00 PM | October 06, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 41 days | Engineer
11 | Yes | CMU1.1.4 | Auto Scheduled | งานสำรวจอุปกรณ์ไฟฟ้า, สุขภัณฑ์และครุภัณฑ์ (ของเดิม) ก่อนดำเนินการปรับปรุง | 675 days | 3 |  |  |  | October 17, 2018 8:00 AM | August 21, 2020 5:00 PM | October 17, 2018 05:00 PM | August 21, 2020 05:00 PM | December 01, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 41 days | 41 days | 41 days
12 | Yes | CMU1.1.4.1 | Auto Scheduled | ชั้นที่ 4 | 15 days | 4 |  |  | 13FS+150 days | October 17, 2018 8:00 AM | October 31, 2018 5:00 PM | October 19, 2018 05:00 PM | November 02, 2018 05:00 PM | December 01, 2018 05:00 PM | December 15, 2018 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
13 | Yes | CMU1.1.4.2 | Auto Scheduled | ชั้นที่ 3 | 15 days | 4 | 12FS+150 days |  | 14FS+150 days | March 31, 2019 8:00 AM | April 14, 2019 5:00 PM | April 05, 2019 05:00 PM | April 19, 2019 05:00 PM | May 15, 2019 05:00 PM | May 29, 2019 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
14 | Yes | CMU1.1.4.3 | Auto Scheduled | ชั้นที่ 2 | 15 days | 4 | 13FS+150 days |  | 15FS+150 days | September 12, 2019 8:00 AM | September 26, 2019 5:00 PM | September 23, 2019 05:00 PM | October 07, 2019 05:00 PM | October 27, 2019 05:00 PM | November 10, 2019 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
15 | Yes | CMU1.1.4.4 | Auto Scheduled | ชั้นที่ 1 | 15 days | 4 | 14FS+150 days |  | 16FS+150 days | February 24, 2020 8:00 AM | March 9, 2020 5:00 PM | March 17, 2020 05:00 PM | March 31, 2020 05:00 PM | April 09, 2020 05:00 PM | April 23, 2020 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
16 | Yes | CMU1.1.4.5 | Auto Scheduled | ชั้นใต้ดินและภายนอก | 15 days | 4 | 15FS+150 days |  |  | August 7, 2020 8:00 AM | August 21, 2020 5:00 PM | September 06, 2020 05:00 PM | September 20, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 41 days | Engineer
17 | Yes | CMU1.1.5 | Auto Scheduled | งานเอกสารขออนุมัติใช้วัสดุ, Shop Drawing และครุภัณฑ์ของโครงการ | 106 days | 3 |  |  |  | October 17, 2018 8:00 AM | January 30, 2019 5:00 PM | October 21, 2018 05:00 PM | February 03, 2019 05:00 PM | June 22, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 610 days | 610 days | 610 days
18 | Yes | CMU1.1.5.1 | Auto Scheduled | แบบ Shop Drawing ชั้นที่ 4 | 20 days | 4 |  |  | 19,25SS+14 days,26SS+14 days | October 17, 2018 8:00 AM | November 5, 2018 5:00 PM | October 17, 2018 05:00 PM | November 05, 2018 05:00 PM | October 01, 2018 05:00 PM | October 20, 2018 05:00 PM | As Soon As Possible |  | No | 610 days | 610 days | 0 days | Engineer
19 | Yes | CMU1.1.5.2 | Auto Scheduled | แบบ Shop Drawing ชั้นที่ 3 | 20 days | 4 | 18 |  | 20FS-7 days | November 6, 2018 8:00 AM | November 25, 2018 5:00 PM | November 13, 2018 05:00 PM | December 02, 2018 05:00 PM | July 13, 2020 05:00 PM | August 01, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
20 | Yes | CMU1.1.5.3 | Auto Scheduled | แบบ Shop Drawing ชั้นที่ 2 | 20 days | 4 | 19FS-7 days |  | 21FS-7 days | November 19, 2018 8:00 AM | December 8, 2018 5:00 PM | November 29, 2018 05:00 PM | December 18, 2018 05:00 PM | July 26, 2020 05:00 PM | August 14, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
21 | Yes | CMU1.1.5.4 | Auto Scheduled | แบบ Shop Drawing ชั้นที่ 1 | 20 days | 4 | 20FS-7 days |  | 22FS-7 days | December 2, 2018 8:00 AM | December 21, 2018 5:00 PM | December 19, 2018 05:00 PM | January 07, 2019 05:00 PM | August 08, 2020 05:00 PM | August 27, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
22 | Yes | CMU1.1.5.5 | Auto Scheduled | แบบ Shop Drawing ชั้นใต้ดิน | 20 days | 4 | 21FS-7 days |  | 23FS-7 days | December 15, 2018 8:00 AM | January 3, 2019 5:00 PM | January 07, 2019 05:00 PM | January 26, 2019 05:00 PM | August 21, 2020 05:00 PM | September 09, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
23 | Yes | CMU1.1.5.6 | Auto Scheduled | แบบ Shop Drawing ภายนอกอาคาร | 20 days | 4 | 22FS-7 days |  | 24FS-7 days | December 28, 2018 8:00 AM | January 16, 2019 5:00 PM | January 24, 2019 05:00 PM | February 12, 2019 05:00 PM | September 03, 2020 05:00 PM | September 22, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
24 | Yes | CMU1.1.5.7 | Auto Scheduled | แบบ Shop Drawing landscape | 20 days | 4 | 23FS-7 days |  |  | January 10, 2019 8:00 AM | January 29, 2019 5:00 PM | February 13, 2019 05:00 PM | March 04, 2019 05:00 PM | September 16, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 611 days | Engineer
25 | Yes | CMU1.1.5.8 | Auto Scheduled | แบบ Shop Drawing งานปรับปรุง ครุภัณฑ์ | 92 days | 4 | 18SS+14 days |  |  | October 31, 2018 8:00 AM | January 30, 2019 5:00 PM | November 08, 2018 05:00 PM | February 07, 2019 05:00 PM | July 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 610 days | 610 days | 610 days | Engineer
26 | Yes | CMU1.1.5.9 | Auto Scheduled | แบบ Shop Drawing งานจัดซื้อครุภัณฑ์ | 92 days | 4 | 18SS+14 days |  |  | October 31, 2018 8:00 AM | January 30, 2019 5:00 PM | November 06, 2018 05:00 PM | February 05, 2019 05:00 PM | July 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 610 days | 610 days | 610 days | Engineer
27 | Yes | CMU1.1.6 | Auto Scheduled | งานตรวจทดสอบระบบ, งานอบรมผู้ใช้อาคาร และ As-Built Drawing | 30 days | 3 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 22, 2018 05:00 PM | November 20, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 686 days | 686 days | 686 days
28 | Yes | CMU1.1.6.1 | Auto Scheduled | ชั้นที่ 4 | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 26, 2018 05:00 PM | November 24, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
29 | Yes | CMU1.1.6.2 | Auto Scheduled | ชั้นที่ 3 | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 29, 2018 05:00 PM | November 27, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
30 | Yes | CMU1.1.6.3 | Auto Scheduled | ชั้นที่ 2 | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 21, 2018 05:00 PM | November 19, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
31 | Yes | CMU1.1.6.4 | Auto Scheduled | ชั้นที่ 1 | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 28, 2018 05:00 PM | November 26, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
32 | Yes | CMU1.1.6.5 | Auto Scheduled | ชั้นใต้ดิน | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 24, 2018 05:00 PM | November 22, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
33 | Yes | CMU1.1.6.6 | Auto Scheduled | ทั้งอาคาร | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 23, 2018 05:00 PM | November 21, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
34 | Yes | CMU1.1.7 | Auto Scheduled | งานบริหารงานก่อสร้างและงานอื่น ๆ | 0 days | 3 |  |  |  | October 17, 2018 8:00 AM | October 17, 2018 8:00 AM | October 20, 2018 05:00 PM | October 19, 2018 05:00 PM | October 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 716 days | 716 days | 716 days | Engineer
35 | Yes | CMU1.2 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้น 4 | 471 days | 2 |  |  |  | October 17, 2018 8:00 AM | January 30, 2020 5:00 PM | October 17, 2018 05:00 PM | January 30, 2020 05:00 PM | June 23, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 0 days | 245 days | 0 days
36 | Yes | CMU1.2.1 | Auto Scheduled | งานรื้อถอน ชั้น 4 (รื้อขนไป) | 30 days | 3 |  |  | 39FS+45 days,40FS+45 days,51,63SS+14 days,80,109,140,180FS+14 days,186FS+14 days,198FS+14 days,199FS+14 days,200FS+14 days,238FS+14 days | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 17, 2018 05:00 PM | November 15, 2018 05:00 PM | March 11, 2018 05:00 PM | April 09, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | General worker
37 | Yes | CMU1.2.2 | Auto Scheduled | งานสถาปัตยกรรม ชั้น 4 | 396 days | 3 |  |  |  | December 31, 2018 8:00 AM | January 30, 2020 5:00 PM | October 17, 2018 05:00 PM | November 16, 2019 05:00 PM | September 06, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 326 days | 245 days | 245 days
38 | Yes | CMU1.2.2.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 39,41,42 |  |  | March 1, 2019 8:00 AM | March 30, 2019 5:00 PM | March 11, 2019 05:00 PM | April 09, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 551 days | Skilled carpenter
39 | Yes | CMU1.2.2.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 36FS+45 days |  | 38,43 | December 31, 2018 8:00 AM | February 28, 2019 5:00 PM | January 05, 2019 05:00 PM | March 05, 2019 05:00 PM | July 15, 2020 05:00 PM | September 12, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 0 days | General worker
40 | Yes | CMU1.2.2.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 36FS+45 days |  | 41,42 | December 31, 2018 8:00 AM | January 29, 2019 5:00 PM | January 03, 2019 05:00 PM | February 01, 2019 05:00 PM | August 14, 2020 05:00 PM | September 12, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 0 days | General worker
41 | Yes | CMU1.2.2.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 40 |  | 38,43 | January 30, 2019 8:00 AM | February 28, 2019 5:00 PM | February 05, 2019 05:00 PM | March 06, 2019 05:00 PM | August 14, 2020 05:00 PM | September 12, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 0 days | Skilled carpenter
42 | Yes | CMU1.2.2.5 | Auto Scheduled | งานบันได | 30 days | 4 | 40 |  | 38,43 | January 30, 2019 8:00 AM | February 28, 2019 5:00 PM | February 05, 2019 05:00 PM | March 06, 2019 05:00 PM | August 14, 2020 05:00 PM | September 12, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 0 days | General worker
43 | Yes | CMU1.2.2.6 | Auto Scheduled | งานสี | 30 days | 4 | 39,41,42 |  |  | March 1, 2019 8:00 AM | March 30, 2019 5:00 PM | March 10, 2019 05:00 PM | April 08, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 551 days | General worker
44 | Yes | CMU1.2.2.7 | Auto Scheduled | งานสุขภัณฑ์ | 315 days | 4 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 20, 2018 05:00 PM | August 30, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
45 | Yes | CMU1.2.2.7.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 46FS+135 days |  | 47FS+135 days | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | September 11, 2019 05:00 PM | September 25, 2019 05:00 PM | April 24, 2020 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
46 | Yes | CMU1.2.2.7.2 | Auto Scheduled | ZONE T-2 กลาง | 15 days | 5 | 51,55 |  | 45FS+135 days | March 22, 2019 8:00 AM | April 5, 2019 5:00 PM | April 07, 2019 05:00 PM | April 21, 2019 05:00 PM | November 26, 2019 05:00 PM | December 10, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
47 | Yes | CMU1.2.2.7.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 15 days | 5 | 45FS+135 days |  |  | January 16, 2020 8:00 AM | January 30, 2020 5:00 PM | February 15, 2020 05:00 PM | February 29, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 245 days | Sanitary-Plumber
48 | Yes | CMU1.2.3 | Auto Scheduled | งานระบบสุขาภิบาล ชั้น 4 | 408 days | 3 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
49 | Yes | CMU1.2.3.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
50 | Yes | CMU1.2.3.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 51FS+15 days |  | 52FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 17, 2019 05:00 PM | August 20, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
51 | Yes | CMU1.2.3.1.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 36 |  | 50FS+15 days,46,55SS | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 23, 2018 05:00 PM | March 28, 2019 05:00 PM | August 25, 2019 05:00 PM | December 28, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
52 | Yes | CMU1.2.3.1.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 50FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 09, 2019 05:00 PM | January 12, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
53 | Yes | CMU1.2.3.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
54 | Yes | CMU1.2.3.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 55FS+15 days |  | 56FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 23, 2019 05:00 PM | August 26, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
55 | Yes | CMU1.2.3.2.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 51SS |  | 54FS+15 days,46 | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 27, 2018 05:00 PM | April 01, 2019 05:00 PM | August 25, 2019 05:00 PM | December 28, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
56 | Yes | CMU1.2.3.2.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 54FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 18, 2019 05:00 PM | January 21, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
57 | Yes | CMU1.2.4 | Auto Scheduled | งานระบบไฟฟ้า ชั้น 4 | 117 days | 3 |  |  |  | November 30, 2018 8:00 AM | March 26, 2019 5:00 PM | October 21, 2018 05:00 PM | February 14, 2019 05:00 PM | June 11, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 555 days | 555 days | 555 days
58 | Yes | CMU1.2.4.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 30 days | 4 | 60FS+7 days |  |  | February 25, 2019 8:00 AM | March 26, 2019 5:00 PM | March 03, 2019 05:00 PM | April 01, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 555 days | 555 days | 555 days | Electrician
59 | Yes | CMU1.2.4.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 30 days | 4 | 60FS+7 days |  |  | February 25, 2019 8:00 AM | March 26, 2019 5:00 PM | March 03, 2019 05:00 PM | April 01, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 555 days | 555 days | 555 days | Electrician
60 | Yes | CMU1.2.4.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 63SS+30 days |  | 58FS+7 days,59FS+7 days | November 30, 2018 8:00 AM | February 17, 2019 5:00 PM | December 03, 2018 05:00 PM | February 20, 2019 05:00 PM | June 11, 2020 05:00 PM | August 29, 2020 05:00 PM | As Soon As Possible |  | No | 555 days | 555 days | 0 days | Electrician
61 | Yes | CMU1.2.4.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 63SS+30 days |  |  | November 30, 2018 8:00 AM | February 17, 2019 5:00 PM | December 04, 2018 05:00 PM | February 21, 2019 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 592 days | 592 days | 592 days | Electrician
62 | Yes | CMU1.2.4.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 63SS+30 days |  |  | November 30, 2018 8:00 AM | February 17, 2019 5:00 PM | December 05, 2018 05:00 PM | February 22, 2019 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 592 days | 592 days | 592 days | Electrician
63 | Yes | CMU1.2.5 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้น 4 | 165 days | 3 | 36SS+14 days |  | 62SS+30 days,60SS+30 days,61SS+30 days,65,214,219FS-15 days,224,230,244FS-7 days,250FS-7 days | October 31, 2018 8:00 AM | April 13, 2019 5:00 PM | October 31, 2018 05:00 PM | April 13, 2019 05:00 PM | June 19, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Skilled carpenter
64 | Yes | CMU1.3 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้น 3 | 441 days | 2 |  |  |  | November 16, 2018 8:00 AM | January 30, 2020 5:00 PM | October 17, 2018 05:00 PM | December 31, 2019 05:00 PM | July 23, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 149 days | 245 days | 149 days
65 | Yes | CMU1.3.1 | Auto Scheduled | งานรื้อถอน ชั้น 3 (รื้อขนไป) | 30 days | 3 | 63 | 121 | 68FS+45 days,69FS+45 days,92SS | April 14, 2019 8:00 AM | May 13, 2019 5:00 PM | April 14, 2019 05:00 PM | May 13, 2019 05:00 PM | July 19, 2018 05:00 PM | August 17, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | General worker
66 | Yes | CMU1.3.2 | Auto Scheduled | งานสถาปัตยกรรม ชั้น 3 | 315 days | 3 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 22, 2018 05:00 PM | September 01, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
67 | Yes | CMU1.3.2.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 68,70,71 |  |  | August 27, 2019 8:00 AM | September 25, 2019 5:00 PM | August 30, 2019 05:00 PM | September 28, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 372 days | Skilled carpenter
68 | Yes | CMU1.3.2.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 65FS+45 days |  | 67,72 | June 28, 2019 8:00 AM | August 26, 2019 5:00 PM | June 28, 2019 05:00 PM | August 26, 2019 05:00 PM | October 02, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 0 days | General worker
69 | Yes | CMU1.3.2.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 65FS+45 days |  | 70,71 | June 28, 2019 8:00 AM | July 27, 2019 5:00 PM | June 28, 2019 05:00 PM | July 27, 2019 05:00 PM | April 15, 2019 05:00 PM | May 14, 2019 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 0 days | General worker
70 | Yes | CMU1.3.2.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 69 |  | 67,72 | July 28, 2019 8:00 AM | August 26, 2019 5:00 PM | July 28, 2019 05:00 PM | August 26, 2019 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 0 days | Skilled carpenter
71 | Yes | CMU1.3.2.5 | Auto Scheduled | งานบันได | 30 days | 4 | 69 |  | 67,72 | July 28, 2019 8:00 AM | August 26, 2019 5:00 PM | July 28, 2019 05:00 PM | August 26, 2019 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 0 days | General worker
72 | Yes | CMU1.3.2.6 | Auto Scheduled | งานสี | 30 days | 4 | 68,70,71 |  |  | August 27, 2019 8:00 AM | September 25, 2019 5:00 PM | August 30, 2019 05:00 PM | September 28, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 372 days | General worker
73 | Yes | CMU1.3.2.7 | Auto Scheduled | งานสุขภัณฑ์ | 315 days | 4 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 21, 2018 05:00 PM | August 31, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
74 | Yes | CMU1.3.2.7.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 75FS+135 days |  | 76FS+135 days | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | August 25, 2019 05:00 PM | September 08, 2019 05:00 PM | April 24, 2020 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
75 | Yes | CMU1.3.2.7.2 | Auto Scheduled | ZONE T-2 กลาง | 15 days | 5 | 80,84 |  | 74FS+135 days | March 22, 2019 8:00 AM | April 5, 2019 5:00 PM | March 24, 2019 05:00 PM | April 07, 2019 05:00 PM | November 26, 2019 05:00 PM | December 10, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
76 | Yes | CMU1.3.2.7.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 15 days | 5 | 74FS+135 days |  |  | January 16, 2020 8:00 AM | January 30, 2020 5:00 PM | January 27, 2020 05:00 PM | February 10, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 245 days | Sanitary-Plumber
77 | Yes | CMU1.3.3 | Auto Scheduled | งานระบบสุขาภิบาล ชั้น 3 | 408 days | 3 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
78 | Yes | CMU1.3.3.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
79 | Yes | CMU1.3.3.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 80FS+15 days |  | 81FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 14, 2019 05:00 PM | August 17, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
80 | Yes | CMU1.3.3.1.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 36 |  | 79FS+15 days,84SS,75 | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 16, 2018 05:00 PM | March 21, 2019 05:00 PM | January 09, 2019 05:00 PM | May 14, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
81 | Yes | CMU1.3.3.1.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 79FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 08, 2019 05:00 PM | January 11, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
82 | Yes | CMU1.3.3.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
83 | Yes | CMU1.3.3.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 84FS+15 days |  | 85FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 11, 2019 05:00 PM | August 14, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
84 | Yes | CMU1.3.3.2.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 80SS |  | 83FS+15 days,75 | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 16, 2018 05:00 PM | March 21, 2019 05:00 PM | January 09, 2019 05:00 PM | May 14, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
85 | Yes | CMU1.3.3.2.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 83FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 07, 2019 05:00 PM | January 10, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
86 | Yes | CMU1.3.4 | Auto Scheduled | งานระบบไฟฟ้า ชั้น 3 | 147 days | 3 |  |  |  | May 14, 2019 8:00 AM | October 7, 2019 5:00 PM | October 21, 2018 05:00 PM | March 16, 2019 05:00 PM | May 12, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 360 days | 360 days | 360 days
87 | Yes | CMU1.3.4.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 60 days | 4 | 89FS+7 days |  |  | August 9, 2019 8:00 AM | October 7, 2019 5:00 PM | August 17, 2019 05:00 PM | October 15, 2019 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 360 days | 360 days | 360 days | Electrician
88 | Yes | CMU1.3.4.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 60 days | 4 | 89FS+7 days |  |  | August 9, 2019 8:00 AM | October 7, 2019 5:00 PM | August 21, 2019 05:00 PM | October 19, 2019 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 360 days | 360 days | 360 days | Electrician
89 | Yes | CMU1.3.4.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 92SS+30 days |  | 88FS+7 days,87FS+7 days | May 14, 2019 8:00 AM | August 1, 2019 5:00 PM | May 19, 2019 05:00 PM | August 06, 2019 05:00 PM | May 12, 2020 05:00 PM | July 30, 2020 05:00 PM | As Soon As Possible |  | No | 360 days | 360 days | 0 days | Electrician
90 | Yes | CMU1.3.4.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 92SS+30 days |  |  | May 14, 2019 8:00 AM | August 1, 2019 5:00 PM | May 22, 2019 05:00 PM | August 09, 2019 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 427 days | 427 days | 427 days | Electrician
91 | Yes | CMU1.3.4.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 92SS+30 days |  |  | May 14, 2019 8:00 AM | August 1, 2019 5:00 PM | May 23, 2019 05:00 PM | August 10, 2019 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 427 days | 427 days | 427 days | Electrician
92 | Yes | CMU1.3.5 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้น 3 | 180 days | 3 | 65SS |  | 91SS+30 days,90SS+30 days,89SS+30 days,94,213FS-15 days,218FS-30 days,223FS-15 days,229FS-15 days,243FS-7 days,249FS-7 days | April 14, 2019 8:00 AM | October 10, 2019 5:00 PM | April 17, 2019 05:00 PM | October 13, 2019 05:00 PM | October 12, 2019 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Skilled carpenter
93 | Yes | CMU1.4 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้น 2 | 509 days | 2 |  |  |  | November 16, 2018 8:00 AM | April 7, 2020 5:00 PM | October 17, 2018 05:00 PM | March 08, 2020 05:00 PM | May 16, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 177 days | 177 days
94 | Yes | CMU1.4.1 | Auto Scheduled | งานรื้อถอน ชั้น 2 (รื้อขนไป) | 30 days | 3 | 92 | 152 | 97FS+45 days,98FS+45 days,121SS | October 11, 2019 8:00 AM | November 9, 2019 5:00 PM | October 14, 2019 05:00 PM | November 12, 2019 05:00 PM | June 04, 2018 05:00 PM | July 03, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | General worker
95 | Yes | CMU1.4.2 | Auto Scheduled | งานสถาปัตยกรรม ชั้น 2 | 368 days | 3 |  |  |  | March 22, 2019 8:00 AM | March 23, 2020 5:00 PM | October 17, 2018 05:00 PM | October 19, 2019 05:00 PM | October 04, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 192 days | 192 days
96 | Yes | CMU1.4.2.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 97,99,100 |  |  | February 23, 2020 8:00 AM | March 23, 2020 5:00 PM | March 06, 2020 05:00 PM | April 04, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 192 days | Skilled carpenter
97 | Yes | CMU1.4.2.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 94FS+45 days |  | 96,101 | December 25, 2019 8:00 AM | February 22, 2020 5:00 PM | December 28, 2019 05:00 PM | February 25, 2020 05:00 PM | February 09, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 0 days | General worker
98 | Yes | CMU1.4.2.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 94FS+45 days |  | 99,100 | December 25, 2019 8:00 AM | January 23, 2020 5:00 PM | December 31, 2019 05:00 PM | January 29, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 0 days | General worker
99 | Yes | CMU1.4.2.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 98 |  | 96,101 | January 24, 2020 8:00 AM | February 22, 2020 5:00 PM | February 02, 2020 05:00 PM | March 02, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 0 days | Skilled carpenter
100 | Yes | CMU1.4.2.5 | Auto Scheduled | งานบันได | 30 days | 4 | 98 |  | 96,101 | January 24, 2020 8:00 AM | February 22, 2020 5:00 PM | February 02, 2020 05:00 PM | March 02, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 0 days | General worker
101 | Yes | CMU1.4.2.6 | Auto Scheduled | งานสี | 30 days | 4 | 97,99,100 |  |  | February 23, 2020 8:00 AM | March 23, 2020 5:00 PM | March 09, 2020 05:00 PM | April 07, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 192 days | General worker
102 | Yes | CMU1.4.2.7 | Auto Scheduled | งานสุขภัณฑ์ | 315 days | 4 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 21, 2018 05:00 PM | August 31, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
103 | Yes | CMU1.4.2.7.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 104FS+135 days |  | 105FS+135 days | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | September 05, 2019 05:00 PM | September 19, 2019 05:00 PM | April 24, 2020 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
104 | Yes | CMU1.4.2.7.2 | Auto Scheduled | ZONE T-2 กลาง | 15 days | 5 | 113,109 |  | 103FS+135 days | March 22, 2019 8:00 AM | April 5, 2019 5:00 PM | April 05, 2019 05:00 PM | April 19, 2019 05:00 PM | November 26, 2019 05:00 PM | December 10, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
105 | Yes | CMU1.4.2.7.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 15 days | 5 | 103FS+135 days |  |  | January 16, 2020 8:00 AM | January 30, 2020 5:00 PM | February 07, 2020 05:00 PM | February 21, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 245 days | Sanitary-Plumber
106 | Yes | CMU1.4.3 | Auto Scheduled | งานระบบสุขาภิบาล ชั้น 2 | 408 days | 3 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
107 | Yes | CMU1.4.3.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
108 | Yes | CMU1.4.3.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 109FS+15 days |  | 110FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 16, 2019 05:00 PM | August 19, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
109 | Yes | CMU1.4.3.1.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 36 |  | 113SS,104,108FS+15 days | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 22, 2018 05:00 PM | March 27, 2019 05:00 PM | August 25, 2019 05:00 PM | December 28, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
110 | Yes | CMU1.4.3.1.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 108FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 07, 2019 05:00 PM | January 10, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
111 | Yes | CMU1.4.3.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
112 | Yes | CMU1.4.3.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 113FS+15 days |  | 114FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 24, 2019 05:00 PM | August 27, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
113 | Yes | CMU1.4.3.2.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 109SS |  | 104,112FS+15 days | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 27, 2018 05:00 PM | April 01, 2019 05:00 PM | August 25, 2019 05:00 PM | December 28, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
114 | Yes | CMU1.4.3.2.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 112FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 16, 2019 05:00 PM | January 19, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
115 | Yes | CMU1.4.4 | Auto Scheduled | งานระบบไฟฟ้า ชั้น 2 | 147 days | 3 |  |  |  | November 10, 2019 8:00 AM | April 4, 2020 5:00 PM | October 20, 2018 05:00 PM | March 15, 2019 05:00 PM | May 12, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 180 days | 180 days | 180 days
116 | Yes | CMU1.4.4.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 60 days | 4 | 118FS+7 days |  |  | February 5, 2020 8:00 AM | April 4, 2020 5:00 PM | February 12, 2020 05:00 PM | April 11, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 180 days | 180 days | 180 days | Electrician
117 | Yes | CMU1.4.4.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 60 days | 4 | 118FS+7 days |  |  | February 5, 2020 8:00 AM | April 4, 2020 5:00 PM | February 13, 2020 05:00 PM | April 12, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 180 days | 180 days | 180 days | Electrician
118 | Yes | CMU1.4.4.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 121SS+30 days |  | 117FS+7 days,116FS+7 days | November 10, 2019 8:00 AM | January 28, 2020 5:00 PM | November 15, 2019 05:00 PM | February 02, 2020 05:00 PM | May 12, 2020 05:00 PM | July 30, 2020 05:00 PM | As Soon As Possible |  | No | 180 days | 180 days | 0 days | Electrician
119 | Yes | CMU1.4.4.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 121SS+30 days |  |  | November 10, 2019 8:00 AM | January 28, 2020 5:00 PM | November 17, 2019 05:00 PM | February 04, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 247 days | 247 days | 247 days | Electrician
120 | Yes | CMU1.4.4.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 121SS+30 days |  |  | November 10, 2019 8:00 AM | January 28, 2020 5:00 PM | November 19, 2019 05:00 PM | February 06, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 247 days | 247 days | 247 days | Electrician
121 | Yes | CMU1.4.5 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้น 2 | 180 days | 3 | 94SS |  | 120SS+30 days,119SS+30 days,118SS+30 days,123,212FS-15 days,217FS-30 days,222FS-15 days,228FS-15 days,242FS-7 days,248FS-7 days | October 11, 2019 8:00 AM | April 7, 2020 5:00 PM | October 14, 2019 05:00 PM | April 10, 2020 05:00 PM | June 04, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Skilled carpenter
122 | Yes | CMU1.5 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้น 1 | 686 days | 2 |  |  |  | November 16, 2018 8:00 AM | October 1, 2020 5:00 PM | October 17, 2018 05:00 PM | September 01, 2020 05:00 PM | November 20, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 0 days | 0 days
123 | Yes | CMU1.5.1 | Auto Scheduled | งานรื้อถอน ชั้น 1 (รื้อขนไป) | 30 days | 3 | 121 | 63 | 124,127FS+45 days,128FS+45 days,131FS+45 days,152SS,193SS,194SS,195SS,196SS,197SS,202SS,204SS,205SS,206SS,207SS | April 8, 2020 8:00 AM | May 7, 2020 5:00 PM | April 11, 2020 05:00 PM | May 10, 2020 05:00 PM | July 19, 2018 05:00 PM | August 17, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | General worker
124 | Yes | CMU1.5.2 | Auto Scheduled | งานโครงสร้างวิศวกรรม ชั้น 1 | 75 days | 3 | 123 |  |  | May 8, 2020 8:00 AM | July 21, 2020 5:00 PM | May 12, 2020 05:00 PM | July 25, 2020 05:00 PM | July 23, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 72 days | 72 days | 72 days | General worker
125 | Yes | CMU1.5.3 | Auto Scheduled | งานสถาปัตยกรรม ชั้น 1 | 548 days | 3 |  |  |  | March 22, 2019 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | April 16, 2020 05:00 PM | April 07, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 12 days | 12 days
126 | Yes | CMU1.5.3.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 127,129,130 |  |  | August 21, 2020 8:00 AM | September 19, 2020 5:00 PM | August 24, 2020 05:00 PM | September 22, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | Skilled carpenter
127 | Yes | CMU1.5.3.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 123FS+45 days |  | 126,132 | June 22, 2020 8:00 AM | August 20, 2020 5:00 PM | June 25, 2020 05:00 PM | August 23, 2020 05:00 PM | October 02, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
128 | Yes | CMU1.5.3.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 123FS+45 days |  | 129,130 | June 22, 2020 8:00 AM | July 21, 2020 5:00 PM | June 25, 2020 05:00 PM | July 24, 2020 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
129 | Yes | CMU1.5.3.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 128 |  | 126,132 | July 22, 2020 8:00 AM | August 20, 2020 5:00 PM | July 25, 2020 05:00 PM | August 23, 2020 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | Skilled carpenter
130 | Yes | CMU1.5.3.5 | Auto Scheduled | งานบันได | 30 days | 4 | 128 |  | 126,132 | July 22, 2020 8:00 AM | August 20, 2020 5:00 PM | July 25, 2020 05:00 PM | August 23, 2020 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
131 | Yes | CMU1.5.3.6 | Auto Scheduled | งานตกแต่งอื่น ๆ | 60 days | 4 | 123FS+45 days |  |  | June 22, 2020 8:00 AM | August 20, 2020 5:00 PM | June 25, 2020 05:00 PM | August 23, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 42 days | 42 days | 42 days | General worker
132 | Yes | CMU1.5.3.7 | Auto Scheduled | งานสี | 30 days | 4 | 127,129,130 |  |  | August 21, 2020 8:00 AM | September 19, 2020 5:00 PM | August 24, 2020 05:00 PM | September 22, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
133 | Yes | CMU1.5.3.8 | Auto Scheduled | งานสุขภัณฑ์ | 315 days | 4 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 22, 2018 05:00 PM | September 01, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
134 | Yes | CMU1.5.3.8.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 135FS+135 days |  | 136FS+135 days | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | August 24, 2019 05:00 PM | September 07, 2019 05:00 PM | April 24, 2020 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
135 | Yes | CMU1.5.3.8.2 | Auto Scheduled | ZONE T-2 กลาง | 15 days | 5 | 140,144 |  | 134FS+135 days,164FS+135 days | March 22, 2019 8:00 AM | April 5, 2019 5:00 PM | March 24, 2019 05:00 PM | April 07, 2019 05:00 PM | November 26, 2019 05:00 PM | December 10, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
136 | Yes | CMU1.5.3.8.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 15 days | 5 | 134FS+135 days |  |  | January 16, 2020 8:00 AM | January 30, 2020 5:00 PM | January 25, 2020 05:00 PM | February 08, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 245 days | Sanitary-Plumber
137 | Yes | CMU1.5.4 | Auto Scheduled | งานระบบสุขาภิบาล ชั้น 1 | 408 days | 3 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 278 days | 44 days
138 | Yes | CMU1.5.4.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 278 days | 44 days
139 | Yes | CMU1.5.4.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 140FS+15 days |  | 141FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 13, 2019 05:00 PM | August 16, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
140 | Yes | CMU1.5.4.1.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 36 |  | 139FS+15 days,144SS,135,167FS+15 days | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 16, 2018 05:00 PM | March 21, 2019 05:00 PM | January 03, 2019 05:00 PM | May 08, 2019 05:00 PM | As Soon As Possible |  | No | 44 days | 44 days | 0 days | Sanitary-Plumber
141 | Yes | CMU1.5.4.1.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 139FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 07, 2019 05:00 PM | January 10, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
142 | Yes | CMU1.5.4.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 278 days | 44 days
143 | Yes | CMU1.5.4.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 144FS+15 days |  | 145FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 12, 2019 05:00 PM | August 15, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
144 | Yes | CMU1.5.4.2.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 140SS |  | 143FS+15 days,135,169FS+15 days | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 16, 2018 05:00 PM | March 21, 2019 05:00 PM | January 03, 2019 05:00 PM | May 08, 2019 05:00 PM | As Soon As Possible |  | No | 44 days | 44 days | 0 days | Sanitary-Plumber
145 | Yes | CMU1.5.4.2.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 143FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 04, 2019 05:00 PM | January 07, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
146 | Yes | CMU1.5.5 | Auto Scheduled | งานระบบไฟฟ้า ชั้น 1 | 147 days | 3 |  |  |  | May 8, 2020 8:00 AM | October 1, 2020 5:00 PM | October 21, 2018 05:00 PM | March 16, 2019 05:00 PM | May 12, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 0 days | 0 days | 0 days
147 | Yes | CMU1.5.5.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 60 days | 4 | 149FS+7 days |  |  | August 3, 2020 8:00 AM | October 1, 2020 5:00 PM | August 06, 2020 05:00 PM | October 04, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Electrician
148 | Yes | CMU1.5.5.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 60 days | 4 | 149FS+7 days |  |  | August 3, 2020 8:00 AM | October 1, 2020 5:00 PM | August 06, 2020 05:00 PM | October 04, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Electrician
149 | Yes | CMU1.5.5.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 152SS+30 days |  | 148FS+7 days,147FS+7 days | May 8, 2020 8:00 AM | July 26, 2020 5:00 PM | May 11, 2020 05:00 PM | July 29, 2020 05:00 PM | May 12, 2020 05:00 PM | July 30, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Electrician
150 | Yes | CMU1.5.5.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 152SS+30 days |  |  | May 8, 2020 8:00 AM | July 26, 2020 5:00 PM | May 11, 2020 05:00 PM | July 29, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 67 days | 67 days | 67 days | Electrician
151 | Yes | CMU1.5.5.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 152SS+30 days |  |  | May 8, 2020 8:00 AM | July 26, 2020 5:00 PM | May 11, 2020 05:00 PM | July 29, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 67 days | 67 days | 67 days | Electrician
152 | Yes | CMU1.5.6 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้น 1 | 165 days | 3 | 123SS |  | 151SS+30 days,150SS+30 days,149SS+30 days,154SS,211FS-30 days,210FS-30 days,216FS-45 days,221FS-30 days,227FS-30 days,226FS-30 days,232FS-45 days,241FS-7 days,247FS-7 days | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 11, 2020 05:00 PM | September 22, 2020 05:00 PM | November 26, 2019 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Skilled carpenter
153 | Yes | CMU1.6 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้นใต้ดิน | 533 days | 2 |  |  |  | April 6, 2019 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | April 01, 2020 05:00 PM | April 22, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 12 days | 12 days
154 | Yes | CMU1.6.1 | Auto Scheduled | งานรื้อถอน ชั้นใต้ดิน (รื้อขนไป) | 30 days | 3 | 152SS |  | 155,158FS+45 days,159FS+45 days,177SS,176SS,175SS,174SS | April 8, 2020 8:00 AM | May 7, 2020 5:00 PM | April 11, 2020 05:00 PM | May 10, 2020 05:00 PM | November 26, 2019 05:00 PM | December 25, 2019 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
155 | Yes | CMU1.6.2 | Auto Scheduled | งานโครงสร้างวิศวกรรม ชั้นใต้ดิน | 75 days | 3 | 154 |  |  | May 8, 2020 8:00 AM | July 21, 2020 5:00 PM | May 12, 2020 05:00 PM | July 25, 2020 05:00 PM | July 23, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 72 days | 72 days | 72 days | General worker
156 | Yes | CMU1.6.3 | Auto Scheduled | งานสถาปัตยกรรม ชั้นใต้ดิน | 398 days | 3 |  |  |  | August 19, 2019 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | November 18, 2019 05:00 PM | September 04, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 320 days | 12 days | 12 days
157 | Yes | CMU1.6.3.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 158,160,161 |  |  | August 21, 2020 8:00 AM | September 19, 2020 5:00 PM | September 07, 2020 05:00 PM | October 06, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | Skilled carpenter
158 | Yes | CMU1.6.3.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 154FS+45 days |  | 157,162 | June 22, 2020 8:00 AM | August 20, 2020 5:00 PM | June 25, 2020 05:00 PM | August 23, 2020 05:00 PM | February 09, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
159 | Yes | CMU1.6.3.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 154FS+45 days |  | 160,161 | June 22, 2020 8:00 AM | July 21, 2020 5:00 PM | July 09, 2020 05:00 PM | August 07, 2020 05:00 PM | August 22, 2020 05:00 PM | September 20, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
160 | Yes | CMU1.6.3.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 159 |  | 157,162 | July 22, 2020 8:00 AM | August 20, 2020 5:00 PM | August 08, 2020 05:00 PM | September 06, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | Skilled carpenter
161 | Yes | CMU1.6.3.5 | Auto Scheduled | งานบันได | 30 days | 4 | 159 |  | 157,162 | July 22, 2020 8:00 AM | August 20, 2020 5:00 PM | August 08, 2020 05:00 PM | September 06, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
162 | Yes | CMU1.6.3.6 | Auto Scheduled | งานสี | 30 days | 4 | 158,160,161 |  |  | August 21, 2020 8:00 AM | September 19, 2020 5:00 PM | September 07, 2020 05:00 PM | October 06, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
163 | Yes | CMU1.6.3.7 | Auto Scheduled | งานสุขภัณฑ์ | 15 days | 4 |  |  |  | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | October 20, 2018 05:00 PM | November 03, 2018 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 395 days | 395 days | 395 days
164 | Yes | CMU1.6.3.7.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 135FS+135 days |  |  | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | August 27, 2019 05:00 PM | September 10, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 395 days | 395 days | 395 days | Sanitary-Plumber
165 | Yes | CMU1.6.4 | Auto Scheduled | งานระบบสุขาภิบาล ชั้นใต้ดิน | 501 days | 3 |  |  |  | April 6, 2019 8:00 AM | August 18, 2020 5:00 PM | October 17, 2018 05:00 PM | February 29, 2020 05:00 PM | May 24, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 44 days | 44 days
166 | Yes | CMU1.6.4.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 126 days | 4 |  |  |  | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | October 21, 2018 05:00 PM | February 23, 2019 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 419 days | 419 days | 419 days
167 | Yes | CMU1.6.4.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 140FS+15 days |  |  | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 13, 2019 05:00 PM | August 16, 2019 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 419 days | 419 days | 419 days | Sanitary-Plumber
168 | Yes | CMU1.6.4.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 126 days | 4 |  |  |  | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | October 21, 2018 05:00 PM | February 23, 2019 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 44 days | 44 days
169 | Yes | CMU1.6.4.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 144FS+15 days |  | 170FS+300 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 06, 2019 05:00 PM | August 09, 2019 05:00 PM | May 24, 2019 05:00 PM | September 26, 2019 05:00 PM | As Soon As Possible |  | No | 44 days | 44 days | 0 days | Sanitary-Plumber
170 | Yes | CMU1.6.4.3 | Auto Scheduled | งานระบบระบายน้ำฝน | 75 days | 4 | 169FS+300 days |  |  | June 5, 2020 8:00 AM | August 18, 2020 5:00 PM | June 05, 2020 05:00 PM | August 18, 2020 05:00 PM | July 23, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 44 days | 44 days | 44 days | Sanitary-Plumber
171 | Yes | CMU1.6.5 | Auto Scheduled | งานระบบไฟฟ้า ชั้นใต้ดิน | 147 days | 3 |  |  |  | April 8, 2020 8:00 AM | September 1, 2020 5:00 PM | October 23, 2018 05:00 PM | March 18, 2019 05:00 PM | May 12, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 30 days | 30 days | 30 days
172 | Yes | CMU1.6.5.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 60 days | 4 | 174FS+7 days |  |  | July 4, 2020 8:00 AM | September 1, 2020 5:00 PM | July 07, 2020 05:00 PM | September 04, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 30 days | 30 days | 30 days | Electrician
173 | Yes | CMU1.6.5.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 60 days | 4 | 174FS+7 days |  |  | July 4, 2020 8:00 AM | September 1, 2020 5:00 PM | July 07, 2020 05:00 PM | September 04, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 30 days | 30 days | 30 days | Electrician
174 | Yes | CMU1.6.5.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 154SS |  | 173FS+7 days,172FS+7 days | April 8, 2020 8:00 AM | June 26, 2020 5:00 PM | April 11, 2020 05:00 PM | June 29, 2020 05:00 PM | May 12, 2020 05:00 PM | July 30, 2020 05:00 PM | As Soon As Possible |  | No | 30 days | 30 days | 0 days | Electrician
175 | Yes | CMU1.6.5.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 154SS |  |  | April 8, 2020 8:00 AM | June 26, 2020 5:00 PM | April 14, 2020 05:00 PM | July 02, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 97 days | 97 days | 97 days | Electrician
176 | Yes | CMU1.6.5.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 154SS |  |  | April 8, 2020 8:00 AM | June 26, 2020 5:00 PM | April 13, 2020 05:00 PM | July 01, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 97 days | 97 days | 97 days | Electrician
177 | Yes | CMU1.6.6 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้นใต้ดิน | 165 days | 3 | 154SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 11, 2020 05:00 PM | September 22, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | Skilled carpenter
178 | Yes | CMU1.7 | Auto Scheduled | หมวดงานระบบคอมพิวเตอร์และแจ้งเหตุเพลิงไหม้ | 670 days | 2 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
179 | Yes | CMU1.7.1 | Auto Scheduled | งานระบบคอมพิวเตอร์ | 670 days | 3 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
180 | Yes | CMU1.7.1.1 | Auto Scheduled | ชั้นที่ 4 | 160 days | 4 | 36FS+14 days |  | 181 | November 30, 2018 8:00 AM | May 8, 2019 5:00 PM | November 30, 2018 05:00 PM | May 08, 2019 05:00 PM | April 24, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
181 | Yes | CMU1.7.1.2 | Auto Scheduled | ชั้นที่ 3 | 175 days | 4 | 180 | 182 | 182 | May 9, 2019 8:00 AM | October 30, 2019 5:00 PM | May 09, 2019 05:00 PM | October 30, 2019 05:00 PM | April 09, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
182 | Yes | CMU1.7.1.3 | Auto Scheduled | ชั้นที่ 2 | 175 days | 4 | 181 | 183 | 183,184 | October 31, 2019 8:00 AM | April 22, 2020 5:00 PM | October 31, 2019 05:00 PM | April 22, 2020 05:00 PM | April 09, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
183 | Yes | CMU1.7.1.4 | Auto Scheduled | ชั้นที่ 1 | 160 days | 4 | 182 | 180 |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 23, 2020 05:00 PM | September 29, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
184 | Yes | CMU1.7.1.5 | Auto Scheduled | ชั้นใต้ดิน | 160 days | 4 | 182 | 183SS |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 23, 2020 05:00 PM | September 29, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
185 | Yes | CMU1.7.2 | Auto Scheduled | ระบบแจ้งเหตุเพลิงไหม้ | 670 days | 3 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
186 | Yes | CMU1.7.2.1 | Auto Scheduled | ชั้นที่ 4 | 160 days | 4 | 36FS+14 days |  | 187 | November 30, 2018 8:00 AM | May 8, 2019 5:00 PM | November 30, 2018 05:00 PM | May 08, 2019 05:00 PM | April 24, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
187 | Yes | CMU1.7.2.2 | Auto Scheduled | ชั้นที่ 3 | 175 days | 4 | 186 | 188 | 188 | May 9, 2019 8:00 AM | October 30, 2019 5:00 PM | May 09, 2019 05:00 PM | October 30, 2019 05:00 PM | April 09, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
188 | Yes | CMU1.7.2.3 | Auto Scheduled | ชั้นที่ 2 | 175 days | 4 | 187 | 189 | 189,190 | October 31, 2019 8:00 AM | April 22, 2020 5:00 PM | October 31, 2019 05:00 PM | April 22, 2020 05:00 PM | April 09, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
189 | Yes | CMU1.7.2.4 | Auto Scheduled | ชั้นที่ 1 | 160 days | 4 | 188 | 186 |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 23, 2020 05:00 PM | September 29, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
190 | Yes | CMU1.7.2.5 | Auto Scheduled | ชั้นใต้ดิน | 160 days | 4 | 188 | 189SS |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 23, 2020 05:00 PM | September 29, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
191 | Yes | CMU1.8 | Auto Scheduled | หมวดงานสีภายนอก งานซ่อมแซมและตกแต่งภายนอกอาคาร | 660 days | 2 |  |  |  | November 30, 2018 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | August 06, 2020 05:00 PM | December 16, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 507 days | 12 days | 12 days
192 | Yes | CMU1.8.1 | Auto Scheduled | งานสีภายนอกและงานซ่อมแซมพื้นผิวภายนอกอาคาร | 660 days | 3 |  |  |  | November 30, 2018 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | August 06, 2020 05:00 PM | December 16, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 507 days | 12 days | 12 days
193 | Yes | CMU1.8.1.1 | Auto Scheduled | งานขัดลอกสีทาผนังเดิม | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 11, 2020 05:00 PM | September 22, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
194 | Yes | CMU1.8.1.2 | Auto Scheduled | น้ำยาทาปูนเก่า (สีรองพื้น) | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 11, 2020 05:00 PM | September 22, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
195 | Yes | CMU1.8.1.3 | Auto Scheduled | งานทาสีภายนอก (ทา 2 เที่ยว) ไม่รวมชั้นใต้ดิน | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 11, 2020 05:00 PM | September 22, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
196 | Yes | CMU1.8.1.4 | Auto Scheduled | งานทำความสะอาดและซ่อมแซมผนังกรุอิฐโชว์แนว (อ้างอิงราคางานขัดลอกสี) | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 11, 2020 05:00 PM | September 22, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
197 | Yes | CMU1.8.1.5 | Auto Scheduled | น้ำยาเคลือบผิวผนังอิฐโชว์แนว (อ้างอิงค่าทาน้ำยากันเชื้อรา) | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 11, 2020 05:00 PM | September 22, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
198 | Yes | CMU1.8.1.6 | Auto Scheduled | งานรื้อถอนแผ่นวัสดุกันซึมหลังคาดาดฟ้า (รื้อขนไป) | 90 days | 4 | 36FS+14 days |  |  | November 30, 2018 8:00 AM | February 27, 2019 5:00 PM | December 03, 2018 05:00 PM | March 02, 2019 05:00 PM | July 08, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 582 days | 582 days | 582 days | General worker
199 | Yes | CMU1.8.1.7 | Auto Scheduled | งานแผ่นวัสดุกันซึมแบบเป่าไฟผิวทราย | 90 days | 4 | 36FS+14 days |  |  | November 30, 2018 8:00 AM | February 27, 2019 5:00 PM | December 04, 2018 05:00 PM | March 03, 2019 05:00 PM | July 08, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 582 days | 582 days | 582 days | General worker
200 | Yes | CMU1.8.1.8 | Auto Scheduled | งานกันซึมชนิด Polyurethane สูตรน้ำมัน ชนิดยืดหยุ่นสูงเป็นพิเศษ | 90 days | 4 | 36FS+14 days |  |  | November 30, 2018 8:00 AM | February 27, 2019 5:00 PM | December 03, 2018 05:00 PM | March 02, 2019 05:00 PM | July 08, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 582 days | 582 days | 582 days | General worker
201 | Yes | CMU1.8.2 | Auto Scheduled | งานตกแต่งภายนอกอาคาร | 165 days | 3 |  |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | October 20, 2018 05:00 PM | April 02, 2019 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 12 days | 12 days | 12 days
202 | Yes | CMU1.8.2.1 | Auto Scheduled | ตะแกรงเหล็กฉีกกันนก XS-32 | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 11, 2020 05:00 PM | September 22, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
203 | Yes | CMU1.9 | Auto Scheduled | หมวดงานบริเวณ | 165 days | 2 |  |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | October 22, 2018 05:00 PM | April 04, 2019 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 12 days | 12 days | 12 days
204 | Yes | CMU1.9.1 | Auto Scheduled | งานรื้อถอน งานบริเวณ | 165 days | 3 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 11, 2020 05:00 PM | September 22, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
205 | Yes | CMU1.9.2 | Auto Scheduled | งานโครงสร้างวิศวกรรม งานบริเวณ | 165 days | 3 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 11, 2020 05:00 PM | September 22, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
206 | Yes | CMU1.9.3 | Auto Scheduled | งานสถาปัตยกรรม งานบริเวณ | 165 days | 3 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 11, 2020 05:00 PM | September 22, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
207 | Yes | CMU1.9.4 | Auto Scheduled | งานระบบไฟฟ้า งานบริเวณ | 165 days | 3 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 11, 2020 05:00 PM | September 22, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | Electrician
208 | Yes | CMU1.10 | Auto Scheduled | หมวดงานครุภัณฑ์จัดซื้อ | 670 days | 2 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
209 | Yes | CMU1.10.1 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัว | 510 days | 3 |  |  |  | April 14, 2019 8:00 AM | September 4, 2020 5:00 PM | October 17, 2018 05:00 PM | March 09, 2020 05:00 PM | May 15, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 522 days | 27 days | 27 days
210 | Yes | CMU1.10.1.1 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้นใต้ดิน | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | August 29, 2020 05:00 PM | September 12, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
211 | Yes | CMU1.10.1.2 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้น 1 | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | August 31, 2020 05:00 PM | September 14, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
212 | Yes | CMU1.10.1.3 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้น 2 | 15 days | 4 | 121FS-15 days |  |  | March 24, 2020 8:00 AM | April 7, 2020 5:00 PM | March 31, 2020 05:00 PM | April 14, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Skilled carpenter
213 | Yes | CMU1.10.1.4 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้น 3 | 15 days | 4 | 92FS-15 days |  |  | September 26, 2019 8:00 AM | October 10, 2019 5:00 PM | October 04, 2019 05:00 PM | October 18, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Skilled carpenter
214 | Yes | CMU1.10.1.5 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้น 4 | 15 days | 4 | 63 |  |  | April 14, 2019 8:00 AM | April 28, 2019 5:00 PM | April 21, 2019 05:00 PM | May 05, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 522 days | 522 days | 522 days | Skilled carpenter
215 | Yes | CMU1.10.2 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ | 525 days | 3 |  |  |  | March 30, 2019 8:00 AM | September 4, 2020 5:00 PM | October 17, 2018 05:00 PM | March 24, 2020 05:00 PM | April 30, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 522 days | 27 days | 27 days
216 | Yes | CMU1.10.2.1 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ ชั้น 1 | 30 days | 4 | 152FS-45 days |  |  | August 6, 2020 8:00 AM | September 4, 2020 5:00 PM | August 15, 2020 05:00 PM | September 13, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
217 | Yes | CMU1.10.2.2 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ ชั้น 2 | 30 days | 4 | 121FS-30 days |  |  | March 9, 2020 8:00 AM | April 7, 2020 5:00 PM | March 15, 2020 05:00 PM | April 13, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Skilled carpenter
218 | Yes | CMU1.10.2.3 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ ชั้น 3 | 30 days | 4 | 92FS-30 days |  |  | September 11, 2019 8:00 AM | October 10, 2019 5:00 PM | September 16, 2019 05:00 PM | October 15, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Skilled carpenter
219 | Yes | CMU1.10.2.4 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ ชั้น 4 | 30 days | 4 | 63FS-15 days |  |  | March 30, 2019 8:00 AM | April 28, 2019 5:00 PM | April 02, 2019 05:00 PM | May 01, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 522 days | 522 days | 522 days | Skilled carpenter
220 | Yes | CMU1.10.3 | Auto Scheduled | งานผ้าม่าน | 510 days | 3 |  |  |  | April 14, 2019 8:00 AM | September 4, 2020 5:00 PM | October 17, 2018 05:00 PM | March 09, 2020 05:00 PM | May 15, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 522 days | 27 days | 27 days
221 | Yes | CMU1.10.3.1 | Auto Scheduled | งานผ้าม่าน ชั้น 1 | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | August 28, 2020 05:00 PM | September 11, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
222 | Yes | CMU1.10.3.2 | Auto Scheduled | งานผ้าม่าน ชั้น 2 | 15 days | 4 | 121FS-15 days |  |  | March 24, 2020 8:00 AM | April 7, 2020 5:00 PM | March 30, 2020 05:00 PM | April 13, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Skilled carpenter
223 | Yes | CMU1.10.3.3 | Auto Scheduled | งานผ้าม่าน ชั้น 3 | 15 days | 4 | 92FS-15 days |  |  | September 26, 2019 8:00 AM | October 10, 2019 5:00 PM | October 03, 2019 05:00 PM | October 17, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Skilled carpenter
224 | Yes | CMU1.10.3.4 | Auto Scheduled | งานผ้าม่าน ชั้น 4 | 15 days | 4 | 63 |  |  | April 14, 2019 8:00 AM | April 28, 2019 5:00 PM | April 24, 2019 05:00 PM | May 08, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 522 days | 522 days | 522 days | Skilled carpenter
225 | Yes | CMU1.10.4 | Auto Scheduled | งานป้าย | 510 days | 3 |  |  |  | April 14, 2019 8:00 AM | September 4, 2020 5:00 PM | October 17, 2018 05:00 PM | March 09, 2020 05:00 PM | May 15, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 522 days | 27 days | 27 days
226 | Yes | CMU1.10.4.1 | Auto Scheduled | งานป้าย ชั้นใต้ดิน | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | August 28, 2020 05:00 PM | September 11, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
227 | Yes | CMU1.10.4.2 | Auto Scheduled | งานป้าย ชั้น 1 | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | August 31, 2020 05:00 PM | September 14, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
228 | Yes | CMU1.10.4.3 | Auto Scheduled | งานป้าย ชั้น 2 | 15 days | 4 | 121FS-15 days |  |  | March 24, 2020 8:00 AM | April 7, 2020 5:00 PM | March 30, 2020 05:00 PM | April 13, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Skilled carpenter
229 | Yes | CMU1.10.4.4 | Auto Scheduled | งานป้าย ชั้น 3 | 15 days | 4 | 92FS-15 days |  |  | September 26, 2019 8:00 AM | October 10, 2019 5:00 PM | October 03, 2019 05:00 PM | October 17, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Skilled carpenter
230 | Yes | CMU1.10.4.5 | Auto Scheduled | งานป้าย ชั้น 4 | 15 days | 4 | 63 |  |  | April 14, 2019 8:00 AM | April 28, 2019 5:00 PM | April 19, 2019 05:00 PM | May 03, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 522 days | 522 days | 522 days | Skilled carpenter
231 | Yes | CMU1.10.5 | Auto Scheduled | งานอื่นๆ | 15 days | 3 |  |  |  | August 6, 2020 8:00 AM | August 20, 2020 5:00 PM | October 20, 2018 05:00 PM | November 03, 2018 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 42 days | 42 days | 42 days
232 | Yes | CMU1.10.5.1 | Auto Scheduled | ตู้อลูมิเนียมพับขึ้นรูป พ่นสี ครอบตู้กดน้ำ | 15 days | 4 | 152FS-45 days |  |  | August 6, 2020 8:00 AM | August 20, 2020 5:00 PM | August 15, 2020 05:00 PM | August 29, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 42 days | 42 days | 42 days | General worker
233 | Yes | CMU1.10.6 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ | 670 days | 3 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
234 | Yes | CMU1.10.6.1 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้นใต้ดิน | 160 days | 4 | 236 |  |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 28, 2020 05:00 PM | October 04, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
235 | Yes | CMU1.10.6.2 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้น 1 | 160 days | 4 | 236 |  |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 28, 2020 05:00 PM | October 04, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
236 | Yes | CMU1.10.6.3 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้น 2 | 175 days | 4 | 237 |  | 235,234 | October 31, 2019 8:00 AM | April 22, 2020 5:00 PM | November 05, 2019 05:00 PM | April 27, 2020 05:00 PM | March 12, 2020 05:00 PM | September 02, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
237 | Yes | CMU1.10.6.4 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้น 3 | 175 days | 4 | 238 |  | 236 | May 9, 2019 8:00 AM | October 30, 2019 5:00 PM | May 14, 2019 05:00 PM | November 04, 2019 05:00 PM | March 12, 2020 05:00 PM | September 02, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
238 | Yes | CMU1.10.6.5 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้น 4 | 160 days | 4 | 36FS+14 days |  | 237 | November 30, 2018 8:00 AM | May 8, 2019 5:00 PM | December 02, 2018 05:00 PM | May 10, 2019 05:00 PM | March 27, 2020 05:00 PM | September 02, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
239 | Yes | CMU1.10.7 | Auto Scheduled | งานระบบเครื่องเสียงประกาศ (ใช้ลำโพงของเดิม) | 539 days | 3 |  |  |  | April 7, 2019 8:00 AM | September 26, 2020 5:00 PM | October 17, 2018 05:00 PM | April 07, 2020 05:00 PM | April 16, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 530 days | 5 days | 5 days
240 | Yes | CMU1.10.7.1 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้นใต้ดิน | 7 days | 4 | 241 |  |  | September 20, 2020 8:00 AM | September 26, 2020 5:00 PM | September 27, 2020 05:00 PM | October 03, 2020 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 5 days | 5 days | 5 days | Electrician
241 | Yes | CMU1.10.7.2 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้น 1 | 7 days | 4 | 152FS-7 days |  | 240 | September 13, 2020 8:00 AM | September 19, 2020 5:00 PM | September 16, 2020 05:00 PM | September 22, 2020 05:00 PM | September 09, 2020 05:00 PM | September 15, 2020 05:00 PM | As Soon As Possible |  | No | 5 days | 5 days | 0 days | Electrician
242 | Yes | CMU1.10.7.3 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้น 2 | 7 days | 4 | 121FS-7 days |  |  | April 1, 2020 8:00 AM | April 7, 2020 5:00 PM | April 06, 2020 05:00 PM | April 12, 2020 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Electrician
243 | Yes | CMU1.10.7.4 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้น 3 | 7 days | 4 | 92FS-7 days |  |  | October 4, 2019 8:00 AM | October 10, 2019 5:00 PM | October 11, 2019 05:00 PM | October 17, 2019 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Electrician
244 | Yes | CMU1.10.7.5 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้น 4 | 7 days | 4 | 63FS-7 days |  |  | April 7, 2019 8:00 AM | April 13, 2019 5:00 PM | April 12, 2019 05:00 PM | April 18, 2019 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 537 days | 537 days | 537 days | Electrician
245 | Yes | CMU1.10.8 | Auto Scheduled | งานระบบกล้องวงจรปิด (ใช้กล้องวงจรปิดของเดิม) | 539 days | 3 |  |  |  | April 7, 2019 8:00 AM | September 26, 2020 5:00 PM | October 17, 2018 05:00 PM | April 07, 2020 05:00 PM | April 16, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 530 days | 5 days | 5 days
246 | Yes | CMU1.10.8.1 | Auto Scheduled | งานกล้องวงจรปิด ชั้นใต้ดิน | 7 days | 4 | 247 |  |  | September 20, 2020 8:00 AM | September 26, 2020 5:00 PM | September 28, 2020 05:00 PM | October 04, 2020 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 5 days | 5 days | 5 days | Electrician
247 | Yes | CMU1.10.8.2 | Auto Scheduled | งานกล้องวงจรปิด ชั้น 1 | 7 days | 4 | 152FS-7 days |  | 246 | September 13, 2020 8:00 AM | September 19, 2020 5:00 PM | September 16, 2020 05:00 PM | September 22, 2020 05:00 PM | September 09, 2020 05:00 PM | September 15, 2020 05:00 PM | As Soon As Possible |  | No | 5 days | 5 days | 0 days | Electrician
248 | Yes | CMU1.10.8.3 | Auto Scheduled | งานกล้องวงจรปิด ชั้น 2 | 7 days | 4 | 121FS-7 days |  |  | April 1, 2020 8:00 AM | April 7, 2020 5:00 PM | April 07, 2020 05:00 PM | April 13, 2020 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Electrician
249 | Yes | CMU1.10.8.4 | Auto Scheduled | งานกล้องวงจรปิด ชั้น 3 | 7 days | 4 | 92FS-7 days |  |  | October 4, 2019 8:00 AM | October 10, 2019 5:00 PM | October 11, 2019 05:00 PM | October 17, 2019 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Electrician
250 | Yes | CMU1.10.8.5 | Auto Scheduled | งานกล้องวงจรปิด ชั้น 4 | 7 days | 4 | 63FS-7 days |  |  | April 7, 2019 8:00 AM | April 13, 2019 5:00 PM | April 11, 2019 05:00 PM | April 17, 2019 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 537 days | 537 days | 537 days | Electrician

## solutoion_7
ID | Active | WBS | Task_Mode | Name | Duration | Outline_Level | Predecessors | Predecessors2 | Successors | Start_Date | Finish_Date | Early_Start | Early_Finish | Late_Start | Late_Finish | Constraint_Type | Constraint_Date | Summary | Start_Slack | Finish_Slack | Free_Slack | Resource_Names
1 | Yes | CMU1 | Auto Scheduled | โครงการปรับปรุงสำนักหอสมุด มหาวิทยาลัยเชียงใหม่ | 716 days | 1 |  |  |  | October 17, 2018 8:00 AM | October 1, 2020 5:00 PM | October 17, 2018 05:00 PM | October 01, 2020 05:00 PM | October 21, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 0 days | 0 days | 0 days
2 | Yes | CMU1.1 | Auto Scheduled | หมวดเตรียมการ | 675 days | 2 |  |  |  | October 17, 2018 8:00 AM | August 21, 2020 5:00 PM | October 17, 2018 05:00 PM | August 21, 2020 05:00 PM | December 01, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 41 days | 41 days | 41 days
3 | Yes | CMU1.1.1 | Auto Scheduled | งานอาคารสนามและผังบริเวณโครงการ | 14 days | 3 | 4FS-7 days |  |  | October 26, 2018 8:00 AM | November 8, 2018 5:00 PM | November 03, 2018 05:00 PM | November 16, 2018 05:00 PM | September 22, 2020 05:00 PM | October 05, 2020 05:00 PM | Start No Earlier Than | Oct 24 '18 | No | 693 days | 693 days | 693 days | Engineer
4 | Yes | CMU1.1.2 | Auto Scheduled | งานเชื่อมต่อระบบสาธารณูปโภคโครงการ | 16 days | 3 |  |  | 3FS-7 days | October 17, 2018 8:00 AM | November 1, 2018 5:00 PM | October 20, 2018 05:00 PM | November 04, 2018 05:00 PM | September 13, 2020 05:00 PM | September 28, 2020 05:00 PM | As Soon As Possible |  | No | 693 days | 693 days | 0 days | Engineer
5 | Yes | CMU1.1.3 | Auto Scheduled | งานตรวจทดสอบระบบภายในอาคารก่อนดำเนินการปรับปรุง | 675 days | 3 |  |  |  | October 17, 2018 8:00 AM | August 21, 2020 5:00 PM | October 17, 2018 05:00 PM | August 21, 2020 05:00 PM | December 01, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 41 days | 41 days | 41 days
6 | Yes | CMU1.1.3.1 | Auto Scheduled | ชั้นที่ 4 | 15 days | 4 |  |  | 7FS+150 days | October 17, 2018 8:00 AM | October 31, 2018 5:00 PM | October 19, 2018 05:00 PM | November 02, 2018 05:00 PM | December 01, 2018 05:00 PM | December 15, 2018 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
7 | Yes | CMU1.1.3.2 | Auto Scheduled | ชั้นที่ 3 | 15 days | 4 | 6FS+150 days |  | 8FS+150 days | March 31, 2019 8:00 AM | April 14, 2019 5:00 PM | April 08, 2019 05:00 PM | April 22, 2019 05:00 PM | May 15, 2019 05:00 PM | May 29, 2019 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
8 | Yes | CMU1.1.3.3 | Auto Scheduled | ชั้นที่ 2 | 15 days | 4 | 7FS+150 days |  | 9FS+150 days | September 12, 2019 8:00 AM | September 26, 2019 5:00 PM | October 03, 2019 05:00 PM | October 17, 2019 05:00 PM | October 27, 2019 05:00 PM | November 10, 2019 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
9 | Yes | CMU1.1.3.4 | Auto Scheduled | ชั้นที่ 1 | 15 days | 4 | 8FS+150 days |  | 10FS+150 days | February 24, 2020 8:00 AM | March 9, 2020 5:00 PM | March 23, 2020 05:00 PM | April 06, 2020 05:00 PM | April 09, 2020 05:00 PM | April 23, 2020 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
10 | Yes | CMU1.1.3.5 | Auto Scheduled | ชั้นใต้ดินและภายนอก | 15 days | 4 | 9FS+150 days |  |  | August 7, 2020 8:00 AM | August 21, 2020 5:00 PM | September 18, 2020 05:00 PM | October 02, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 41 days | Engineer
11 | Yes | CMU1.1.4 | Auto Scheduled | งานสำรวจอุปกรณ์ไฟฟ้า, สุขภัณฑ์และครุภัณฑ์ (ของเดิม) ก่อนดำเนินการปรับปรุง | 675 days | 3 |  |  |  | October 17, 2018 8:00 AM | August 21, 2020 5:00 PM | October 17, 2018 05:00 PM | August 21, 2020 05:00 PM | December 01, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 41 days | 41 days | 41 days
12 | Yes | CMU1.1.4.1 | Auto Scheduled | ชั้นที่ 4 | 15 days | 4 |  |  | 13FS+150 days | October 17, 2018 8:00 AM | October 31, 2018 5:00 PM | October 19, 2018 05:00 PM | November 02, 2018 05:00 PM | December 01, 2018 05:00 PM | December 15, 2018 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
13 | Yes | CMU1.1.4.2 | Auto Scheduled | ชั้นที่ 3 | 15 days | 4 | 12FS+150 days |  | 14FS+150 days | March 31, 2019 8:00 AM | April 14, 2019 5:00 PM | April 06, 2019 05:00 PM | April 20, 2019 05:00 PM | May 15, 2019 05:00 PM | May 29, 2019 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
14 | Yes | CMU1.1.4.3 | Auto Scheduled | ชั้นที่ 2 | 15 days | 4 | 13FS+150 days |  | 15FS+150 days | September 12, 2019 8:00 AM | September 26, 2019 5:00 PM | September 23, 2019 05:00 PM | October 07, 2019 05:00 PM | October 27, 2019 05:00 PM | November 10, 2019 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
15 | Yes | CMU1.1.4.4 | Auto Scheduled | ชั้นที่ 1 | 15 days | 4 | 14FS+150 days |  | 16FS+150 days | February 24, 2020 8:00 AM | March 9, 2020 5:00 PM | March 15, 2020 05:00 PM | March 29, 2020 05:00 PM | April 09, 2020 05:00 PM | April 23, 2020 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
16 | Yes | CMU1.1.4.5 | Auto Scheduled | ชั้นใต้ดินและภายนอก | 15 days | 4 | 15FS+150 days |  |  | August 7, 2020 8:00 AM | August 21, 2020 5:00 PM | September 03, 2020 05:00 PM | September 17, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 41 days | Engineer
17 | Yes | CMU1.1.5 | Auto Scheduled | งานเอกสารขออนุมัติใช้วัสดุ, Shop Drawing และครุภัณฑ์ของโครงการ | 106 days | 3 |  |  |  | October 17, 2018 8:00 AM | January 30, 2019 5:00 PM | October 22, 2018 05:00 PM | February 04, 2019 05:00 PM | June 22, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 610 days | 610 days | 610 days
18 | Yes | CMU1.1.5.1 | Auto Scheduled | แบบ Shop Drawing ชั้นที่ 4 | 20 days | 4 |  |  | 19,25SS+14 days,26SS+14 days | October 17, 2018 8:00 AM | November 5, 2018 5:00 PM | October 17, 2018 05:00 PM | November 05, 2018 05:00 PM | October 01, 2018 05:00 PM | October 20, 2018 05:00 PM | As Soon As Possible |  | No | 610 days | 610 days | 0 days | Engineer
19 | Yes | CMU1.1.5.2 | Auto Scheduled | แบบ Shop Drawing ชั้นที่ 3 | 20 days | 4 | 18 |  | 20FS-7 days | November 6, 2018 8:00 AM | November 25, 2018 5:00 PM | November 13, 2018 05:00 PM | December 02, 2018 05:00 PM | July 13, 2020 05:00 PM | August 01, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
20 | Yes | CMU1.1.5.3 | Auto Scheduled | แบบ Shop Drawing ชั้นที่ 2 | 20 days | 4 | 19FS-7 days |  | 21FS-7 days | November 19, 2018 8:00 AM | December 8, 2018 5:00 PM | November 30, 2018 05:00 PM | December 19, 2018 05:00 PM | July 26, 2020 05:00 PM | August 14, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
21 | Yes | CMU1.1.5.4 | Auto Scheduled | แบบ Shop Drawing ชั้นที่ 1 | 20 days | 4 | 20FS-7 days |  | 22FS-7 days | December 2, 2018 8:00 AM | December 21, 2018 5:00 PM | December 20, 2018 05:00 PM | January 08, 2019 05:00 PM | August 08, 2020 05:00 PM | August 27, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
22 | Yes | CMU1.1.5.5 | Auto Scheduled | แบบ Shop Drawing ชั้นใต้ดิน | 20 days | 4 | 21FS-7 days |  | 23FS-7 days | December 15, 2018 8:00 AM | January 3, 2019 5:00 PM | January 08, 2019 05:00 PM | January 27, 2019 05:00 PM | August 21, 2020 05:00 PM | September 09, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
23 | Yes | CMU1.1.5.6 | Auto Scheduled | แบบ Shop Drawing ภายนอกอาคาร | 20 days | 4 | 22FS-7 days |  | 24FS-7 days | December 28, 2018 8:00 AM | January 16, 2019 5:00 PM | January 27, 2019 05:00 PM | February 15, 2019 05:00 PM | September 03, 2020 05:00 PM | September 22, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
24 | Yes | CMU1.1.5.7 | Auto Scheduled | แบบ Shop Drawing landscape | 20 days | 4 | 23FS-7 days |  |  | January 10, 2019 8:00 AM | January 29, 2019 5:00 PM | February 18, 2019 05:00 PM | March 09, 2019 05:00 PM | September 16, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 611 days | Engineer
25 | Yes | CMU1.1.5.8 | Auto Scheduled | แบบ Shop Drawing งานปรับปรุง ครุภัณฑ์ | 92 days | 4 | 18SS+14 days |  |  | October 31, 2018 8:00 AM | January 30, 2019 5:00 PM | November 16, 2018 05:00 PM | February 15, 2019 05:00 PM | July 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 610 days | 610 days | 610 days | Engineer
26 | Yes | CMU1.1.5.9 | Auto Scheduled | แบบ Shop Drawing งานจัดซื้อครุภัณฑ์ | 92 days | 4 | 18SS+14 days |  |  | October 31, 2018 8:00 AM | January 30, 2019 5:00 PM | November 07, 2018 05:00 PM | February 06, 2019 05:00 PM | July 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 610 days | 610 days | 610 days | Engineer
27 | Yes | CMU1.1.6 | Auto Scheduled | งานตรวจทดสอบระบบ, งานอบรมผู้ใช้อาคาร และ As-Built Drawing | 30 days | 3 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 22, 2018 05:00 PM | November 20, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 686 days | 686 days | 686 days
28 | Yes | CMU1.1.6.1 | Auto Scheduled | ชั้นที่ 4 | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 27, 2018 05:00 PM | November 25, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
29 | Yes | CMU1.1.6.2 | Auto Scheduled | ชั้นที่ 3 | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 28, 2018 05:00 PM | November 26, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
30 | Yes | CMU1.1.6.3 | Auto Scheduled | ชั้นที่ 2 | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 22, 2018 05:00 PM | November 20, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
31 | Yes | CMU1.1.6.4 | Auto Scheduled | ชั้นที่ 1 | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 29, 2018 05:00 PM | November 27, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
32 | Yes | CMU1.1.6.5 | Auto Scheduled | ชั้นใต้ดิน | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 24, 2018 05:00 PM | November 22, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
33 | Yes | CMU1.1.6.6 | Auto Scheduled | ทั้งอาคาร | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 24, 2018 05:00 PM | November 22, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
34 | Yes | CMU1.1.7 | Auto Scheduled | งานบริหารงานก่อสร้างและงานอื่น ๆ | 0 days | 3 |  |  |  | October 17, 2018 8:00 AM | October 17, 2018 8:00 AM | October 20, 2018 05:00 PM | October 19, 2018 05:00 PM | October 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 716 days | 716 days | 716 days | Engineer
35 | Yes | CMU1.2 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้น 4 | 471 days | 2 |  |  |  | October 17, 2018 8:00 AM | January 30, 2020 5:00 PM | October 17, 2018 05:00 PM | January 30, 2020 05:00 PM | June 23, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 0 days | 245 days | 0 days
36 | Yes | CMU1.2.1 | Auto Scheduled | งานรื้อถอน ชั้น 4 (รื้อขนไป) | 30 days | 3 |  |  | 39FS+45 days,40FS+45 days,51,63SS+14 days,80,109,140,180FS+14 days,186FS+14 days,198FS+14 days,199FS+14 days,200FS+14 days,238FS+14 days | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 17, 2018 05:00 PM | November 15, 2018 05:00 PM | March 11, 2018 05:00 PM | April 09, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | General worker
37 | Yes | CMU1.2.2 | Auto Scheduled | งานสถาปัตยกรรม ชั้น 4 | 396 days | 3 |  |  |  | December 31, 2018 8:00 AM | January 30, 2020 5:00 PM | October 17, 2018 05:00 PM | November 16, 2019 05:00 PM | September 06, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 326 days | 245 days | 245 days
38 | Yes | CMU1.2.2.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 39,41,42 |  |  | March 1, 2019 8:00 AM | March 30, 2019 5:00 PM | March 11, 2019 05:00 PM | April 09, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 551 days | Skilled carpenter
39 | Yes | CMU1.2.2.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 36FS+45 days |  | 38,43 | December 31, 2018 8:00 AM | February 28, 2019 5:00 PM | January 05, 2019 05:00 PM | March 05, 2019 05:00 PM | July 15, 2020 05:00 PM | September 12, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 0 days | General worker
40 | Yes | CMU1.2.2.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 36FS+45 days |  | 41,42 | December 31, 2018 8:00 AM | January 29, 2019 5:00 PM | January 03, 2019 05:00 PM | February 01, 2019 05:00 PM | August 14, 2020 05:00 PM | September 12, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 0 days | General worker
41 | Yes | CMU1.2.2.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 40 |  | 38,43 | January 30, 2019 8:00 AM | February 28, 2019 5:00 PM | February 05, 2019 05:00 PM | March 06, 2019 05:00 PM | August 14, 2020 05:00 PM | September 12, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 0 days | Skilled carpenter
42 | Yes | CMU1.2.2.5 | Auto Scheduled | งานบันได | 30 days | 4 | 40 |  | 38,43 | January 30, 2019 8:00 AM | February 28, 2019 5:00 PM | February 06, 2019 05:00 PM | March 07, 2019 05:00 PM | August 14, 2020 05:00 PM | September 12, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 0 days | General worker
43 | Yes | CMU1.2.2.6 | Auto Scheduled | งานสี | 30 days | 4 | 39,41,42 |  |  | March 1, 2019 8:00 AM | March 30, 2019 5:00 PM | March 11, 2019 05:00 PM | April 09, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 551 days | General worker
44 | Yes | CMU1.2.2.7 | Auto Scheduled | งานสุขภัณฑ์ | 315 days | 4 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 20, 2018 05:00 PM | August 30, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
45 | Yes | CMU1.2.2.7.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 46FS+135 days |  | 47FS+135 days | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | September 12, 2019 05:00 PM | September 26, 2019 05:00 PM | April 24, 2020 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
46 | Yes | CMU1.2.2.7.2 | Auto Scheduled | ZONE T-2 กลาง | 15 days | 5 | 51,55 |  | 45FS+135 days | March 22, 2019 8:00 AM | April 5, 2019 5:00 PM | April 09, 2019 05:00 PM | April 23, 2019 05:00 PM | November 26, 2019 05:00 PM | December 10, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
47 | Yes | CMU1.2.2.7.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 15 days | 5 | 45FS+135 days |  |  | January 16, 2020 8:00 AM | January 30, 2020 5:00 PM | February 16, 2020 05:00 PM | March 01, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 245 days | Sanitary-Plumber
48 | Yes | CMU1.2.3 | Auto Scheduled | งานระบบสุขาภิบาล ชั้น 4 | 408 days | 3 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
49 | Yes | CMU1.2.3.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
50 | Yes | CMU1.2.3.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 51FS+15 days |  | 52FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 17, 2019 05:00 PM | August 20, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
51 | Yes | CMU1.2.3.1.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 36 |  | 50FS+15 days,46,55SS | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 23, 2018 05:00 PM | March 28, 2019 05:00 PM | August 25, 2019 05:00 PM | December 28, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
52 | Yes | CMU1.2.3.1.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 50FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 09, 2019 05:00 PM | January 12, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
53 | Yes | CMU1.2.3.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
54 | Yes | CMU1.2.3.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 55FS+15 days |  | 56FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 25, 2019 05:00 PM | August 28, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
55 | Yes | CMU1.2.3.2.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 51SS |  | 54FS+15 days,46 | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 29, 2018 05:00 PM | April 03, 2019 05:00 PM | August 25, 2019 05:00 PM | December 28, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
56 | Yes | CMU1.2.3.2.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 54FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 20, 2019 05:00 PM | January 23, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
57 | Yes | CMU1.2.4 | Auto Scheduled | งานระบบไฟฟ้า ชั้น 4 | 117 days | 3 |  |  |  | November 30, 2018 8:00 AM | March 26, 2019 5:00 PM | October 21, 2018 05:00 PM | February 14, 2019 05:00 PM | June 11, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 555 days | 555 days | 555 days
58 | Yes | CMU1.2.4.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 30 days | 4 | 60FS+7 days |  |  | February 25, 2019 8:00 AM | March 26, 2019 5:00 PM | March 04, 2019 05:00 PM | April 02, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 555 days | 555 days | 555 days | Electrician
59 | Yes | CMU1.2.4.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 30 days | 4 | 60FS+7 days |  |  | February 25, 2019 8:00 AM | March 26, 2019 5:00 PM | March 04, 2019 05:00 PM | April 02, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 555 days | 555 days | 555 days | Electrician
60 | Yes | CMU1.2.4.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 63SS+30 days |  | 58FS+7 days,59FS+7 days | November 30, 2018 8:00 AM | February 17, 2019 5:00 PM | December 04, 2018 05:00 PM | February 21, 2019 05:00 PM | June 11, 2020 05:00 PM | August 29, 2020 05:00 PM | As Soon As Possible |  | No | 555 days | 555 days | 0 days | Electrician
61 | Yes | CMU1.2.4.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 63SS+30 days |  |  | November 30, 2018 8:00 AM | February 17, 2019 5:00 PM | December 04, 2018 05:00 PM | February 21, 2019 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 592 days | 592 days | 592 days | Electrician
62 | Yes | CMU1.2.4.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 63SS+30 days |  |  | November 30, 2018 8:00 AM | February 17, 2019 5:00 PM | December 04, 2018 05:00 PM | February 21, 2019 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 592 days | 592 days | 592 days | Electrician
63 | Yes | CMU1.2.5 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้น 4 | 165 days | 3 | 36SS+14 days |  | 62SS+30 days,60SS+30 days,61SS+30 days,65,214,219FS-15 days,224,230,244FS-7 days,250FS-7 days | October 31, 2018 8:00 AM | April 13, 2019 5:00 PM | October 31, 2018 05:00 PM | April 13, 2019 05:00 PM | June 19, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Skilled carpenter
64 | Yes | CMU1.3 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้น 3 | 441 days | 2 |  |  |  | November 16, 2018 8:00 AM | January 30, 2020 5:00 PM | October 17, 2018 05:00 PM | December 31, 2019 05:00 PM | July 23, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 149 days | 245 days | 149 days
65 | Yes | CMU1.3.1 | Auto Scheduled | งานรื้อถอน ชั้น 3 (รื้อขนไป) | 30 days | 3 | 63 | 121 | 68FS+45 days,69FS+45 days,92SS | April 14, 2019 8:00 AM | May 13, 2019 5:00 PM | April 14, 2019 05:00 PM | May 13, 2019 05:00 PM | July 19, 2018 05:00 PM | August 17, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | General worker
66 | Yes | CMU1.3.2 | Auto Scheduled | งานสถาปัตยกรรม ชั้น 3 | 315 days | 3 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 21, 2018 05:00 PM | August 31, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
67 | Yes | CMU1.3.2.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 68,70,71 |  |  | August 27, 2019 8:00 AM | September 25, 2019 5:00 PM | August 31, 2019 05:00 PM | September 29, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 372 days | Skilled carpenter
68 | Yes | CMU1.3.2.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 65FS+45 days |  | 67,72 | June 28, 2019 8:00 AM | August 26, 2019 5:00 PM | June 28, 2019 05:00 PM | August 26, 2019 05:00 PM | October 02, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 0 days | General worker
69 | Yes | CMU1.3.2.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 65FS+45 days |  | 70,71 | June 28, 2019 8:00 AM | July 27, 2019 5:00 PM | June 28, 2019 05:00 PM | July 27, 2019 05:00 PM | April 15, 2019 05:00 PM | May 14, 2019 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 0 days | General worker
70 | Yes | CMU1.3.2.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 69 |  | 67,72 | July 28, 2019 8:00 AM | August 26, 2019 5:00 PM | July 28, 2019 05:00 PM | August 26, 2019 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 0 days | Skilled carpenter
71 | Yes | CMU1.3.2.5 | Auto Scheduled | งานบันได | 30 days | 4 | 69 |  | 67,72 | July 28, 2019 8:00 AM | August 26, 2019 5:00 PM | July 28, 2019 05:00 PM | August 26, 2019 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 0 days | General worker
72 | Yes | CMU1.3.2.6 | Auto Scheduled | งานสี | 30 days | 4 | 68,70,71 |  |  | August 27, 2019 8:00 AM | September 25, 2019 5:00 PM | August 30, 2019 05:00 PM | September 28, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 372 days | General worker
73 | Yes | CMU1.3.2.7 | Auto Scheduled | งานสุขภัณฑ์ | 315 days | 4 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 21, 2018 05:00 PM | August 31, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
74 | Yes | CMU1.3.2.7.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 75FS+135 days |  | 76FS+135 days | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | August 25, 2019 05:00 PM | September 08, 2019 05:00 PM | April 24, 2020 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
75 | Yes | CMU1.3.2.7.2 | Auto Scheduled | ZONE T-2 กลาง | 15 days | 5 | 80,84 |  | 74FS+135 days | March 22, 2019 8:00 AM | April 5, 2019 5:00 PM | March 24, 2019 05:00 PM | April 07, 2019 05:00 PM | November 26, 2019 05:00 PM | December 10, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
76 | Yes | CMU1.3.2.7.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 15 days | 5 | 74FS+135 days |  |  | January 16, 2020 8:00 AM | January 30, 2020 5:00 PM | January 28, 2020 05:00 PM | February 11, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 245 days | Sanitary-Plumber
77 | Yes | CMU1.3.3 | Auto Scheduled | งานระบบสุขาภิบาล ชั้น 3 | 408 days | 3 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
78 | Yes | CMU1.3.3.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
79 | Yes | CMU1.3.3.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 80FS+15 days |  | 81FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 16, 2019 05:00 PM | August 19, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
80 | Yes | CMU1.3.3.1.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 36 |  | 79FS+15 days,84SS,75 | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 16, 2018 05:00 PM | March 21, 2019 05:00 PM | January 09, 2019 05:00 PM | May 14, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
81 | Yes | CMU1.3.3.1.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 79FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 09, 2019 05:00 PM | January 12, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
82 | Yes | CMU1.3.3.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
83 | Yes | CMU1.3.3.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 84FS+15 days |  | 85FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 12, 2019 05:00 PM | August 15, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
84 | Yes | CMU1.3.3.2.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 80SS |  | 83FS+15 days,75 | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 16, 2018 05:00 PM | March 21, 2019 05:00 PM | January 09, 2019 05:00 PM | May 14, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
85 | Yes | CMU1.3.3.2.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 83FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 08, 2019 05:00 PM | January 11, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
86 | Yes | CMU1.3.4 | Auto Scheduled | งานระบบไฟฟ้า ชั้น 3 | 147 days | 3 |  |  |  | May 14, 2019 8:00 AM | October 7, 2019 5:00 PM | October 21, 2018 05:00 PM | March 16, 2019 05:00 PM | May 12, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 360 days | 360 days | 360 days
87 | Yes | CMU1.3.4.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 60 days | 4 | 89FS+7 days |  |  | August 9, 2019 8:00 AM | October 7, 2019 5:00 PM | August 19, 2019 05:00 PM | October 17, 2019 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 360 days | 360 days | 360 days | Electrician
88 | Yes | CMU1.3.4.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 60 days | 4 | 89FS+7 days |  |  | August 9, 2019 8:00 AM | October 7, 2019 5:00 PM | August 24, 2019 05:00 PM | October 22, 2019 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 360 days | 360 days | 360 days | Electrician
89 | Yes | CMU1.3.4.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 92SS+30 days |  | 88FS+7 days,87FS+7 days | May 14, 2019 8:00 AM | August 1, 2019 5:00 PM | May 21, 2019 05:00 PM | August 08, 2019 05:00 PM | May 12, 2020 05:00 PM | July 30, 2020 05:00 PM | As Soon As Possible |  | No | 360 days | 360 days | 0 days | Electrician
90 | Yes | CMU1.3.4.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 92SS+30 days |  |  | May 14, 2019 8:00 AM | August 1, 2019 5:00 PM | May 24, 2019 05:00 PM | August 11, 2019 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 427 days | 427 days | 427 days | Electrician
91 | Yes | CMU1.3.4.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 92SS+30 days |  |  | May 14, 2019 8:00 AM | August 1, 2019 5:00 PM | May 26, 2019 05:00 PM | August 13, 2019 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 427 days | 427 days | 427 days | Electrician
92 | Yes | CMU1.3.5 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้น 3 | 180 days | 3 | 65SS |  | 91SS+30 days,90SS+30 days,89SS+30 days,94,213FS-15 days,218FS-30 days,223FS-15 days,229FS-15 days,243FS-7 days,249FS-7 days | April 14, 2019 8:00 AM | October 10, 2019 5:00 PM | April 19, 2019 05:00 PM | October 15, 2019 05:00 PM | October 12, 2019 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Skilled carpenter
93 | Yes | CMU1.4 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้น 2 | 509 days | 2 |  |  |  | November 16, 2018 8:00 AM | April 7, 2020 5:00 PM | October 17, 2018 05:00 PM | March 08, 2020 05:00 PM | May 16, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 177 days | 177 days
94 | Yes | CMU1.4.1 | Auto Scheduled | งานรื้อถอน ชั้น 2 (รื้อขนไป) | 30 days | 3 | 92 | 152 | 97FS+45 days,98FS+45 days,121SS | October 11, 2019 8:00 AM | November 9, 2019 5:00 PM | October 16, 2019 05:00 PM | November 14, 2019 05:00 PM | June 04, 2018 05:00 PM | July 03, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | General worker
95 | Yes | CMU1.4.2 | Auto Scheduled | งานสถาปัตยกรรม ชั้น 2 | 368 days | 3 |  |  |  | March 22, 2019 8:00 AM | March 23, 2020 5:00 PM | October 17, 2018 05:00 PM | October 19, 2019 05:00 PM | October 04, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 192 days | 192 days
96 | Yes | CMU1.4.2.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 97,99,100 |  |  | February 23, 2020 8:00 AM | March 23, 2020 5:00 PM | March 09, 2020 05:00 PM | April 07, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 192 days | Skilled carpenter
97 | Yes | CMU1.4.2.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 94FS+45 days |  | 96,101 | December 25, 2019 8:00 AM | February 22, 2020 5:00 PM | December 30, 2019 05:00 PM | February 27, 2020 05:00 PM | February 09, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 0 days | General worker
98 | Yes | CMU1.4.2.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 94FS+45 days |  | 99,100 | December 25, 2019 8:00 AM | January 23, 2020 5:00 PM | January 02, 2020 05:00 PM | January 31, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 0 days | General worker
99 | Yes | CMU1.4.2.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 98 |  | 96,101 | January 24, 2020 8:00 AM | February 22, 2020 5:00 PM | February 05, 2020 05:00 PM | March 05, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 0 days | Skilled carpenter
100 | Yes | CMU1.4.2.5 | Auto Scheduled | งานบันได | 30 days | 4 | 98 |  | 96,101 | January 24, 2020 8:00 AM | February 22, 2020 5:00 PM | February 04, 2020 05:00 PM | March 04, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 0 days | General worker
101 | Yes | CMU1.4.2.6 | Auto Scheduled | งานสี | 30 days | 4 | 97,99,100 |  |  | February 23, 2020 8:00 AM | March 23, 2020 5:00 PM | March 13, 2020 05:00 PM | April 11, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 192 days | General worker
102 | Yes | CMU1.4.2.7 | Auto Scheduled | งานสุขภัณฑ์ | 315 days | 4 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 22, 2018 05:00 PM | September 01, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
103 | Yes | CMU1.4.2.7.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 104FS+135 days |  | 105FS+135 days | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | September 07, 2019 05:00 PM | September 21, 2019 05:00 PM | April 24, 2020 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
104 | Yes | CMU1.4.2.7.2 | Auto Scheduled | ZONE T-2 กลาง | 15 days | 5 | 113,109 |  | 103FS+135 days | March 22, 2019 8:00 AM | April 5, 2019 5:00 PM | April 06, 2019 05:00 PM | April 20, 2019 05:00 PM | November 26, 2019 05:00 PM | December 10, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
105 | Yes | CMU1.4.2.7.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 15 days | 5 | 103FS+135 days |  |  | January 16, 2020 8:00 AM | January 30, 2020 5:00 PM | February 09, 2020 05:00 PM | February 23, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 245 days | Sanitary-Plumber
106 | Yes | CMU1.4.3 | Auto Scheduled | งานระบบสุขาภิบาล ชั้น 2 | 408 days | 3 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
107 | Yes | CMU1.4.3.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
108 | Yes | CMU1.4.3.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 109FS+15 days |  | 110FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 18, 2019 05:00 PM | August 21, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
109 | Yes | CMU1.4.3.1.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 36 |  | 113SS,104,108FS+15 days | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 23, 2018 05:00 PM | March 28, 2019 05:00 PM | August 25, 2019 05:00 PM | December 28, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
110 | Yes | CMU1.4.3.1.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 108FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 09, 2019 05:00 PM | January 12, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
111 | Yes | CMU1.4.3.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
112 | Yes | CMU1.4.3.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 113FS+15 days |  | 114FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 24, 2019 05:00 PM | August 27, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
113 | Yes | CMU1.4.3.2.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 109SS |  | 104,112FS+15 days | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 28, 2018 05:00 PM | April 02, 2019 05:00 PM | August 25, 2019 05:00 PM | December 28, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
114 | Yes | CMU1.4.3.2.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 112FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 16, 2019 05:00 PM | January 19, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
115 | Yes | CMU1.4.4 | Auto Scheduled | งานระบบไฟฟ้า ชั้น 2 | 147 days | 3 |  |  |  | November 10, 2019 8:00 AM | April 4, 2020 5:00 PM | October 20, 2018 05:00 PM | March 15, 2019 05:00 PM | May 12, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 180 days | 180 days | 180 days
116 | Yes | CMU1.4.4.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 60 days | 4 | 118FS+7 days |  |  | February 5, 2020 8:00 AM | April 4, 2020 5:00 PM | February 14, 2020 05:00 PM | April 13, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 180 days | 180 days | 180 days | Electrician
117 | Yes | CMU1.4.4.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 60 days | 4 | 118FS+7 days |  |  | February 5, 2020 8:00 AM | April 4, 2020 5:00 PM | February 16, 2020 05:00 PM | April 15, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 180 days | 180 days | 180 days | Electrician
118 | Yes | CMU1.4.4.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 121SS+30 days |  | 117FS+7 days,116FS+7 days | November 10, 2019 8:00 AM | January 28, 2020 5:00 PM | November 17, 2019 05:00 PM | February 04, 2020 05:00 PM | May 12, 2020 05:00 PM | July 30, 2020 05:00 PM | As Soon As Possible |  | No | 180 days | 180 days | 0 days | Electrician
119 | Yes | CMU1.4.4.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 121SS+30 days |  |  | November 10, 2019 8:00 AM | January 28, 2020 5:00 PM | November 20, 2019 05:00 PM | February 07, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 247 days | 247 days | 247 days | Electrician
120 | Yes | CMU1.4.4.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 121SS+30 days |  |  | November 10, 2019 8:00 AM | January 28, 2020 5:00 PM | November 22, 2019 05:00 PM | February 09, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 247 days | 247 days | 247 days | Electrician
121 | Yes | CMU1.4.5 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้น 2 | 180 days | 3 | 94SS |  | 120SS+30 days,119SS+30 days,118SS+30 days,123,212FS-15 days,217FS-30 days,222FS-15 days,228FS-15 days,242FS-7 days,248FS-7 days | October 11, 2019 8:00 AM | April 7, 2020 5:00 PM | October 16, 2019 05:00 PM | April 12, 2020 05:00 PM | June 04, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Skilled carpenter
122 | Yes | CMU1.5 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้น 1 | 686 days | 2 |  |  |  | November 16, 2018 8:00 AM | October 1, 2020 5:00 PM | October 17, 2018 05:00 PM | September 01, 2020 05:00 PM | November 20, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 0 days | 0 days
123 | Yes | CMU1.5.1 | Auto Scheduled | งานรื้อถอน ชั้น 1 (รื้อขนไป) | 30 days | 3 | 121 | 63 | 124,127FS+45 days,128FS+45 days,131FS+45 days,152SS,193SS,194SS,195SS,196SS,197SS,202SS,204SS,205SS,206SS,207SS | April 8, 2020 8:00 AM | May 7, 2020 5:00 PM | April 13, 2020 05:00 PM | May 12, 2020 05:00 PM | July 19, 2018 05:00 PM | August 17, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | General worker
124 | Yes | CMU1.5.2 | Auto Scheduled | งานโครงสร้างวิศวกรรม ชั้น 1 | 75 days | 3 | 123 |  |  | May 8, 2020 8:00 AM | July 21, 2020 5:00 PM | May 14, 2020 05:00 PM | July 27, 2020 05:00 PM | July 23, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 72 days | 72 days | 72 days | General worker
125 | Yes | CMU1.5.3 | Auto Scheduled | งานสถาปัตยกรรม ชั้น 1 | 548 days | 3 |  |  |  | March 22, 2019 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | April 16, 2020 05:00 PM | April 07, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 12 days | 12 days
126 | Yes | CMU1.5.3.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 127,129,130 |  |  | August 21, 2020 8:00 AM | September 19, 2020 5:00 PM | August 26, 2020 05:00 PM | September 24, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | Skilled carpenter
127 | Yes | CMU1.5.3.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 123FS+45 days |  | 126,132 | June 22, 2020 8:00 AM | August 20, 2020 5:00 PM | June 27, 2020 05:00 PM | August 25, 2020 05:00 PM | October 02, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
128 | Yes | CMU1.5.3.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 123FS+45 days |  | 129,130 | June 22, 2020 8:00 AM | July 21, 2020 5:00 PM | June 27, 2020 05:00 PM | July 26, 2020 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
129 | Yes | CMU1.5.3.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 128 |  | 126,132 | July 22, 2020 8:00 AM | August 20, 2020 5:00 PM | July 27, 2020 05:00 PM | August 25, 2020 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | Skilled carpenter
130 | Yes | CMU1.5.3.5 | Auto Scheduled | งานบันได | 30 days | 4 | 128 |  | 126,132 | July 22, 2020 8:00 AM | August 20, 2020 5:00 PM | July 27, 2020 05:00 PM | August 25, 2020 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
131 | Yes | CMU1.5.3.6 | Auto Scheduled | งานตกแต่งอื่น ๆ | 60 days | 4 | 123FS+45 days |  |  | June 22, 2020 8:00 AM | August 20, 2020 5:00 PM | June 27, 2020 05:00 PM | August 25, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 42 days | 42 days | 42 days | General worker
132 | Yes | CMU1.5.3.7 | Auto Scheduled | งานสี | 30 days | 4 | 127,129,130 |  |  | August 21, 2020 8:00 AM | September 19, 2020 5:00 PM | August 26, 2020 05:00 PM | September 24, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
133 | Yes | CMU1.5.3.8 | Auto Scheduled | งานสุขภัณฑ์ | 315 days | 4 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 23, 2018 05:00 PM | September 02, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
134 | Yes | CMU1.5.3.8.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 135FS+135 days |  | 136FS+135 days | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | August 24, 2019 05:00 PM | September 07, 2019 05:00 PM | April 24, 2020 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
135 | Yes | CMU1.5.3.8.2 | Auto Scheduled | ZONE T-2 กลาง | 15 days | 5 | 140,144 |  | 134FS+135 days,164FS+135 days | March 22, 2019 8:00 AM | April 5, 2019 5:00 PM | March 24, 2019 05:00 PM | April 07, 2019 05:00 PM | November 26, 2019 05:00 PM | December 10, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
136 | Yes | CMU1.5.3.8.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 15 days | 5 | 134FS+135 days |  |  | January 16, 2020 8:00 AM | January 30, 2020 5:00 PM | January 24, 2020 05:00 PM | February 07, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 245 days | Sanitary-Plumber
137 | Yes | CMU1.5.4 | Auto Scheduled | งานระบบสุขาภิบาล ชั้น 1 | 408 days | 3 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 278 days | 44 days
138 | Yes | CMU1.5.4.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 278 days | 44 days
139 | Yes | CMU1.5.4.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 140FS+15 days |  | 141FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 13, 2019 05:00 PM | August 16, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
140 | Yes | CMU1.5.4.1.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 36 |  | 139FS+15 days,144SS,135,167FS+15 days | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 16, 2018 05:00 PM | March 21, 2019 05:00 PM | January 03, 2019 05:00 PM | May 08, 2019 05:00 PM | As Soon As Possible |  | No | 44 days | 44 days | 0 days | Sanitary-Plumber
141 | Yes | CMU1.5.4.1.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 139FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 08, 2019 05:00 PM | January 11, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
142 | Yes | CMU1.5.4.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 278 days | 44 days
143 | Yes | CMU1.5.4.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 144FS+15 days |  | 145FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 12, 2019 05:00 PM | August 15, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
144 | Yes | CMU1.5.4.2.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 140SS |  | 143FS+15 days,135,169FS+15 days | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 16, 2018 05:00 PM | March 21, 2019 05:00 PM | January 03, 2019 05:00 PM | May 08, 2019 05:00 PM | As Soon As Possible |  | No | 44 days | 44 days | 0 days | Sanitary-Plumber
145 | Yes | CMU1.5.4.2.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 143FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 04, 2019 05:00 PM | January 07, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
146 | Yes | CMU1.5.5 | Auto Scheduled | งานระบบไฟฟ้า ชั้น 1 | 147 days | 3 |  |  |  | May 8, 2020 8:00 AM | October 1, 2020 5:00 PM | October 20, 2018 05:00 PM | March 15, 2019 05:00 PM | May 12, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 0 days | 0 days | 0 days
147 | Yes | CMU1.5.5.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 60 days | 4 | 149FS+7 days |  |  | August 3, 2020 8:00 AM | October 1, 2020 5:00 PM | August 08, 2020 05:00 PM | October 06, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Electrician
148 | Yes | CMU1.5.5.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 60 days | 4 | 149FS+7 days |  |  | August 3, 2020 8:00 AM | October 1, 2020 5:00 PM | August 08, 2020 05:00 PM | October 06, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Electrician
149 | Yes | CMU1.5.5.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 152SS+30 days |  | 148FS+7 days,147FS+7 days | May 8, 2020 8:00 AM | July 26, 2020 5:00 PM | May 13, 2020 05:00 PM | July 31, 2020 05:00 PM | May 12, 2020 05:00 PM | July 30, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Electrician
150 | Yes | CMU1.5.5.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 152SS+30 days |  |  | May 8, 2020 8:00 AM | July 26, 2020 5:00 PM | May 13, 2020 05:00 PM | July 31, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 67 days | 67 days | 67 days | Electrician
151 | Yes | CMU1.5.5.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 152SS+30 days |  |  | May 8, 2020 8:00 AM | July 26, 2020 5:00 PM | May 13, 2020 05:00 PM | July 31, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 67 days | 67 days | 67 days | Electrician
152 | Yes | CMU1.5.6 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้น 1 | 165 days | 3 | 123SS |  | 151SS+30 days,150SS+30 days,149SS+30 days,154SS,211FS-30 days,210FS-30 days,216FS-45 days,221FS-30 days,227FS-30 days,226FS-30 days,232FS-45 days,241FS-7 days,247FS-7 days | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 13, 2020 05:00 PM | September 24, 2020 05:00 PM | November 26, 2019 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Skilled carpenter
153 | Yes | CMU1.6 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้นใต้ดิน | 533 days | 2 |  |  |  | April 6, 2019 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | April 01, 2020 05:00 PM | April 22, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 12 days | 12 days
154 | Yes | CMU1.6.1 | Auto Scheduled | งานรื้อถอน ชั้นใต้ดิน (รื้อขนไป) | 30 days | 3 | 152SS |  | 155,158FS+45 days,159FS+45 days,177SS,176SS,175SS,174SS | April 8, 2020 8:00 AM | May 7, 2020 5:00 PM | April 13, 2020 05:00 PM | May 12, 2020 05:00 PM | November 26, 2019 05:00 PM | December 25, 2019 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
155 | Yes | CMU1.6.2 | Auto Scheduled | งานโครงสร้างวิศวกรรม ชั้นใต้ดิน | 75 days | 3 | 154 |  |  | May 8, 2020 8:00 AM | July 21, 2020 5:00 PM | May 14, 2020 05:00 PM | July 27, 2020 05:00 PM | July 23, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 72 days | 72 days | 72 days | General worker
156 | Yes | CMU1.6.3 | Auto Scheduled | งานสถาปัตยกรรม ชั้นใต้ดิน | 398 days | 3 |  |  |  | August 19, 2019 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | November 18, 2019 05:00 PM | September 04, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 320 days | 12 days | 12 days
157 | Yes | CMU1.6.3.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 158,160,161 |  |  | August 21, 2020 8:00 AM | September 19, 2020 5:00 PM | September 09, 2020 05:00 PM | October 08, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | Skilled carpenter
158 | Yes | CMU1.6.3.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 154FS+45 days |  | 157,162 | June 22, 2020 8:00 AM | August 20, 2020 5:00 PM | June 27, 2020 05:00 PM | August 25, 2020 05:00 PM | February 09, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
159 | Yes | CMU1.6.3.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 154FS+45 days |  | 160,161 | June 22, 2020 8:00 AM | July 21, 2020 5:00 PM | July 11, 2020 05:00 PM | August 09, 2020 05:00 PM | August 22, 2020 05:00 PM | September 20, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
160 | Yes | CMU1.6.3.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 159 |  | 157,162 | July 22, 2020 8:00 AM | August 20, 2020 5:00 PM | August 10, 2020 05:00 PM | September 08, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | Skilled carpenter
161 | Yes | CMU1.6.3.5 | Auto Scheduled | งานบันได | 30 days | 4 | 159 |  | 157,162 | July 22, 2020 8:00 AM | August 20, 2020 5:00 PM | August 10, 2020 05:00 PM | September 08, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
162 | Yes | CMU1.6.3.6 | Auto Scheduled | งานสี | 30 days | 4 | 158,160,161 |  |  | August 21, 2020 8:00 AM | September 19, 2020 5:00 PM | September 09, 2020 05:00 PM | October 08, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
163 | Yes | CMU1.6.3.7 | Auto Scheduled | งานสุขภัณฑ์ | 15 days | 4 |  |  |  | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | October 20, 2018 05:00 PM | November 03, 2018 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 395 days | 395 days | 395 days
164 | Yes | CMU1.6.3.7.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 135FS+135 days |  |  | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | August 27, 2019 05:00 PM | September 10, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 395 days | 395 days | 395 days | Sanitary-Plumber
165 | Yes | CMU1.6.4 | Auto Scheduled | งานระบบสุขาภิบาล ชั้นใต้ดิน | 501 days | 3 |  |  |  | April 6, 2019 8:00 AM | August 18, 2020 5:00 PM | October 17, 2018 05:00 PM | February 29, 2020 05:00 PM | May 24, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 44 days | 44 days
166 | Yes | CMU1.6.4.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 126 days | 4 |  |  |  | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | October 22, 2018 05:00 PM | February 24, 2019 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 419 days | 419 days | 419 days
167 | Yes | CMU1.6.4.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 140FS+15 days |  |  | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 12, 2019 05:00 PM | August 15, 2019 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 419 days | 419 days | 419 days | Sanitary-Plumber
168 | Yes | CMU1.6.4.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 126 days | 4 |  |  |  | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | October 22, 2018 05:00 PM | February 24, 2019 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 44 days | 44 days
169 | Yes | CMU1.6.4.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 144FS+15 days |  | 170FS+300 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 06, 2019 05:00 PM | August 09, 2019 05:00 PM | May 24, 2019 05:00 PM | September 26, 2019 05:00 PM | As Soon As Possible |  | No | 44 days | 44 days | 0 days | Sanitary-Plumber
170 | Yes | CMU1.6.4.3 | Auto Scheduled | งานระบบระบายน้ำฝน | 75 days | 4 | 169FS+300 days |  |  | June 5, 2020 8:00 AM | August 18, 2020 5:00 PM | June 05, 2020 05:00 PM | August 18, 2020 05:00 PM | July 23, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 44 days | 44 days | 44 days | Sanitary-Plumber
171 | Yes | CMU1.6.5 | Auto Scheduled | งานระบบไฟฟ้า ชั้นใต้ดิน | 147 days | 3 |  |  |  | April 8, 2020 8:00 AM | September 1, 2020 5:00 PM | October 24, 2018 05:00 PM | March 19, 2019 05:00 PM | May 12, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 30 days | 30 days | 30 days
172 | Yes | CMU1.6.5.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 60 days | 4 | 174FS+7 days |  |  | July 4, 2020 8:00 AM | September 1, 2020 5:00 PM | July 09, 2020 05:00 PM | September 06, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 30 days | 30 days | 30 days | Electrician
173 | Yes | CMU1.6.5.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 60 days | 4 | 174FS+7 days |  |  | July 4, 2020 8:00 AM | September 1, 2020 5:00 PM | July 09, 2020 05:00 PM | September 06, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 30 days | 30 days | 30 days | Electrician
174 | Yes | CMU1.6.5.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 154SS |  | 173FS+7 days,172FS+7 days | April 8, 2020 8:00 AM | June 26, 2020 5:00 PM | April 13, 2020 05:00 PM | July 01, 2020 05:00 PM | May 12, 2020 05:00 PM | July 30, 2020 05:00 PM | As Soon As Possible |  | No | 30 days | 30 days | 0 days | Electrician
175 | Yes | CMU1.6.5.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 154SS |  |  | April 8, 2020 8:00 AM | June 26, 2020 5:00 PM | April 16, 2020 05:00 PM | July 04, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 97 days | 97 days | 97 days | Electrician
176 | Yes | CMU1.6.5.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 154SS |  |  | April 8, 2020 8:00 AM | June 26, 2020 5:00 PM | April 16, 2020 05:00 PM | July 04, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 97 days | 97 days | 97 days | Electrician
177 | Yes | CMU1.6.6 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้นใต้ดิน | 165 days | 3 | 154SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 13, 2020 05:00 PM | September 24, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | Skilled carpenter
178 | Yes | CMU1.7 | Auto Scheduled | หมวดงานระบบคอมพิวเตอร์และแจ้งเหตุเพลิงไหม้ | 670 days | 2 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
179 | Yes | CMU1.7.1 | Auto Scheduled | งานระบบคอมพิวเตอร์ | 670 days | 3 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
180 | Yes | CMU1.7.1.1 | Auto Scheduled | ชั้นที่ 4 | 160 days | 4 | 36FS+14 days |  | 181 | November 30, 2018 8:00 AM | May 8, 2019 5:00 PM | November 30, 2018 05:00 PM | May 08, 2019 05:00 PM | April 24, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
181 | Yes | CMU1.7.1.2 | Auto Scheduled | ชั้นที่ 3 | 175 days | 4 | 180 | 182 | 182 | May 9, 2019 8:00 AM | October 30, 2019 5:00 PM | May 09, 2019 05:00 PM | October 30, 2019 05:00 PM | April 09, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
182 | Yes | CMU1.7.1.3 | Auto Scheduled | ชั้นที่ 2 | 175 days | 4 | 181 | 183 | 183,184 | October 31, 2019 8:00 AM | April 22, 2020 5:00 PM | October 31, 2019 05:00 PM | April 22, 2020 05:00 PM | April 09, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
183 | Yes | CMU1.7.1.4 | Auto Scheduled | ชั้นที่ 1 | 160 days | 4 | 182 | 180 |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 23, 2020 05:00 PM | September 29, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
184 | Yes | CMU1.7.1.5 | Auto Scheduled | ชั้นใต้ดิน | 160 days | 4 | 182 | 183SS |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 23, 2020 05:00 PM | September 29, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
185 | Yes | CMU1.7.2 | Auto Scheduled | ระบบแจ้งเหตุเพลิงไหม้ | 670 days | 3 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
186 | Yes | CMU1.7.2.1 | Auto Scheduled | ชั้นที่ 4 | 160 days | 4 | 36FS+14 days |  | 187 | November 30, 2018 8:00 AM | May 8, 2019 5:00 PM | November 30, 2018 05:00 PM | May 08, 2019 05:00 PM | April 24, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
187 | Yes | CMU1.7.2.2 | Auto Scheduled | ชั้นที่ 3 | 175 days | 4 | 186 | 188 | 188 | May 9, 2019 8:00 AM | October 30, 2019 5:00 PM | May 09, 2019 05:00 PM | October 30, 2019 05:00 PM | April 09, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
188 | Yes | CMU1.7.2.3 | Auto Scheduled | ชั้นที่ 2 | 175 days | 4 | 187 | 189 | 189,190 | October 31, 2019 8:00 AM | April 22, 2020 5:00 PM | October 31, 2019 05:00 PM | April 22, 2020 05:00 PM | April 09, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
189 | Yes | CMU1.7.2.4 | Auto Scheduled | ชั้นที่ 1 | 160 days | 4 | 188 | 186 |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 23, 2020 05:00 PM | September 29, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
190 | Yes | CMU1.7.2.5 | Auto Scheduled | ชั้นใต้ดิน | 160 days | 4 | 188 | 189SS |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 23, 2020 05:00 PM | September 29, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
191 | Yes | CMU1.8 | Auto Scheduled | หมวดงานสีภายนอก งานซ่อมแซมและตกแต่งภายนอกอาคาร | 660 days | 2 |  |  |  | November 30, 2018 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | August 06, 2020 05:00 PM | December 16, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 507 days | 12 days | 12 days
192 | Yes | CMU1.8.1 | Auto Scheduled | งานสีภายนอกและงานซ่อมแซมพื้นผิวภายนอกอาคาร | 660 days | 3 |  |  |  | November 30, 2018 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | August 06, 2020 05:00 PM | December 16, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 507 days | 12 days | 12 days
193 | Yes | CMU1.8.1.1 | Auto Scheduled | งานขัดลอกสีทาผนังเดิม | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 13, 2020 05:00 PM | September 24, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
194 | Yes | CMU1.8.1.2 | Auto Scheduled | น้ำยาทาปูนเก่า (สีรองพื้น) | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 13, 2020 05:00 PM | September 24, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
195 | Yes | CMU1.8.1.3 | Auto Scheduled | งานทาสีภายนอก (ทา 2 เที่ยว) ไม่รวมชั้นใต้ดิน | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 13, 2020 05:00 PM | September 24, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
196 | Yes | CMU1.8.1.4 | Auto Scheduled | งานทำความสะอาดและซ่อมแซมผนังกรุอิฐโชว์แนว (อ้างอิงราคางานขัดลอกสี) | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 13, 2020 05:00 PM | September 24, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
197 | Yes | CMU1.8.1.5 | Auto Scheduled | น้ำยาเคลือบผิวผนังอิฐโชว์แนว (อ้างอิงค่าทาน้ำยากันเชื้อรา) | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 13, 2020 05:00 PM | September 24, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
198 | Yes | CMU1.8.1.6 | Auto Scheduled | งานรื้อถอนแผ่นวัสดุกันซึมหลังคาดาดฟ้า (รื้อขนไป) | 90 days | 4 | 36FS+14 days |  |  | November 30, 2018 8:00 AM | February 27, 2019 5:00 PM | December 03, 2018 05:00 PM | March 02, 2019 05:00 PM | July 08, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 582 days | 582 days | 582 days | General worker
199 | Yes | CMU1.8.1.7 | Auto Scheduled | งานแผ่นวัสดุกันซึมแบบเป่าไฟผิวทราย | 90 days | 4 | 36FS+14 days |  |  | November 30, 2018 8:00 AM | February 27, 2019 5:00 PM | December 04, 2018 05:00 PM | March 03, 2019 05:00 PM | July 08, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 582 days | 582 days | 582 days | General worker
200 | Yes | CMU1.8.1.8 | Auto Scheduled | งานกันซึมชนิด Polyurethane สูตรน้ำมัน ชนิดยืดหยุ่นสูงเป็นพิเศษ | 90 days | 4 | 36FS+14 days |  |  | November 30, 2018 8:00 AM | February 27, 2019 5:00 PM | December 03, 2018 05:00 PM | March 02, 2019 05:00 PM | July 08, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 582 days | 582 days | 582 days | General worker
201 | Yes | CMU1.8.2 | Auto Scheduled | งานตกแต่งภายนอกอาคาร | 165 days | 3 |  |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | October 20, 2018 05:00 PM | April 02, 2019 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 12 days | 12 days | 12 days
202 | Yes | CMU1.8.2.1 | Auto Scheduled | ตะแกรงเหล็กฉีกกันนก XS-32 | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 13, 2020 05:00 PM | September 24, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
203 | Yes | CMU1.9 | Auto Scheduled | หมวดงานบริเวณ | 165 days | 2 |  |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | October 23, 2018 05:00 PM | April 05, 2019 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 12 days | 12 days | 12 days
204 | Yes | CMU1.9.1 | Auto Scheduled | งานรื้อถอน งานบริเวณ | 165 days | 3 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 13, 2020 05:00 PM | September 24, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
205 | Yes | CMU1.9.2 | Auto Scheduled | งานโครงสร้างวิศวกรรม งานบริเวณ | 165 days | 3 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 13, 2020 05:00 PM | September 24, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
206 | Yes | CMU1.9.3 | Auto Scheduled | งานสถาปัตยกรรม งานบริเวณ | 165 days | 3 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 13, 2020 05:00 PM | September 24, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
207 | Yes | CMU1.9.4 | Auto Scheduled | งานระบบไฟฟ้า งานบริเวณ | 165 days | 3 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 13, 2020 05:00 PM | September 24, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | Electrician
208 | Yes | CMU1.10 | Auto Scheduled | หมวดงานครุภัณฑ์จัดซื้อ | 670 days | 2 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
209 | Yes | CMU1.10.1 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัว | 510 days | 3 |  |  |  | April 14, 2019 8:00 AM | September 4, 2020 5:00 PM | October 17, 2018 05:00 PM | March 09, 2020 05:00 PM | May 15, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 522 days | 27 days | 27 days
210 | Yes | CMU1.10.1.1 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้นใต้ดิน | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | August 30, 2020 05:00 PM | September 13, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
211 | Yes | CMU1.10.1.2 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้น 1 | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | September 02, 2020 05:00 PM | September 16, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
212 | Yes | CMU1.10.1.3 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้น 2 | 15 days | 4 | 121FS-15 days |  |  | March 24, 2020 8:00 AM | April 7, 2020 5:00 PM | April 01, 2020 05:00 PM | April 15, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Skilled carpenter
213 | Yes | CMU1.10.1.4 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้น 3 | 15 days | 4 | 92FS-15 days |  |  | September 26, 2019 8:00 AM | October 10, 2019 5:00 PM | October 07, 2019 05:00 PM | October 21, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Skilled carpenter
214 | Yes | CMU1.10.1.5 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้น 4 | 15 days | 4 | 63 |  |  | April 14, 2019 8:00 AM | April 28, 2019 5:00 PM | April 21, 2019 05:00 PM | May 05, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 522 days | 522 days | 522 days | Skilled carpenter
215 | Yes | CMU1.10.2 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ | 525 days | 3 |  |  |  | March 30, 2019 8:00 AM | September 4, 2020 5:00 PM | October 17, 2018 05:00 PM | March 24, 2020 05:00 PM | April 30, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 522 days | 27 days | 27 days
216 | Yes | CMU1.10.2.1 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ ชั้น 1 | 30 days | 4 | 152FS-45 days |  |  | August 6, 2020 8:00 AM | September 4, 2020 5:00 PM | August 17, 2020 05:00 PM | September 15, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
217 | Yes | CMU1.10.2.2 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ ชั้น 2 | 30 days | 4 | 121FS-30 days |  |  | March 9, 2020 8:00 AM | April 7, 2020 5:00 PM | March 18, 2020 05:00 PM | April 16, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Skilled carpenter
218 | Yes | CMU1.10.2.3 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ ชั้น 3 | 30 days | 4 | 92FS-30 days |  |  | September 11, 2019 8:00 AM | October 10, 2019 5:00 PM | September 18, 2019 05:00 PM | October 17, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Skilled carpenter
219 | Yes | CMU1.10.2.4 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ ชั้น 4 | 30 days | 4 | 63FS-15 days |  |  | March 30, 2019 8:00 AM | April 28, 2019 5:00 PM | April 02, 2019 05:00 PM | May 01, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 522 days | 522 days | 522 days | Skilled carpenter
220 | Yes | CMU1.10.3 | Auto Scheduled | งานผ้าม่าน | 510 days | 3 |  |  |  | April 14, 2019 8:00 AM | September 4, 2020 5:00 PM | October 17, 2018 05:00 PM | March 09, 2020 05:00 PM | May 15, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 522 days | 27 days | 27 days
221 | Yes | CMU1.10.3.1 | Auto Scheduled | งานผ้าม่าน ชั้น 1 | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | August 31, 2020 05:00 PM | September 14, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
222 | Yes | CMU1.10.3.2 | Auto Scheduled | งานผ้าม่าน ชั้น 2 | 15 days | 4 | 121FS-15 days |  |  | March 24, 2020 8:00 AM | April 7, 2020 5:00 PM | April 02, 2020 05:00 PM | April 16, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Skilled carpenter
223 | Yes | CMU1.10.3.3 | Auto Scheduled | งานผ้าม่าน ชั้น 3 | 15 days | 4 | 92FS-15 days |  |  | September 26, 2019 8:00 AM | October 10, 2019 5:00 PM | October 05, 2019 05:00 PM | October 19, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Skilled carpenter
224 | Yes | CMU1.10.3.4 | Auto Scheduled | งานผ้าม่าน ชั้น 4 | 15 days | 4 | 63 |  |  | April 14, 2019 8:00 AM | April 28, 2019 5:00 PM | April 23, 2019 05:00 PM | May 07, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 522 days | 522 days | 522 days | Skilled carpenter
225 | Yes | CMU1.10.4 | Auto Scheduled | งานป้าย | 510 days | 3 |  |  |  | April 14, 2019 8:00 AM | September 4, 2020 5:00 PM | October 17, 2018 05:00 PM | March 09, 2020 05:00 PM | May 15, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 522 days | 27 days | 27 days
226 | Yes | CMU1.10.4.1 | Auto Scheduled | งานป้าย ชั้นใต้ดิน | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | August 30, 2020 05:00 PM | September 13, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
227 | Yes | CMU1.10.4.2 | Auto Scheduled | งานป้าย ชั้น 1 | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | September 04, 2020 05:00 PM | September 18, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
228 | Yes | CMU1.10.4.3 | Auto Scheduled | งานป้าย ชั้น 2 | 15 days | 4 | 121FS-15 days |  |  | March 24, 2020 8:00 AM | April 7, 2020 5:00 PM | April 01, 2020 05:00 PM | April 15, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Skilled carpenter
229 | Yes | CMU1.10.4.4 | Auto Scheduled | งานป้าย ชั้น 3 | 15 days | 4 | 92FS-15 days |  |  | September 26, 2019 8:00 AM | October 10, 2019 5:00 PM | October 05, 2019 05:00 PM | October 19, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Skilled carpenter
230 | Yes | CMU1.10.4.5 | Auto Scheduled | งานป้าย ชั้น 4 | 15 days | 4 | 63 |  |  | April 14, 2019 8:00 AM | April 28, 2019 5:00 PM | April 19, 2019 05:00 PM | May 03, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 522 days | 522 days | 522 days | Skilled carpenter
231 | Yes | CMU1.10.5 | Auto Scheduled | งานอื่นๆ | 15 days | 3 |  |  |  | August 6, 2020 8:00 AM | August 20, 2020 5:00 PM | October 20, 2018 05:00 PM | November 03, 2018 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 42 days | 42 days | 42 days
232 | Yes | CMU1.10.5.1 | Auto Scheduled | ตู้อลูมิเนียมพับขึ้นรูป พ่นสี ครอบตู้กดน้ำ | 15 days | 4 | 152FS-45 days |  |  | August 6, 2020 8:00 AM | August 20, 2020 5:00 PM | August 17, 2020 05:00 PM | August 31, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 42 days | 42 days | 42 days | General worker
233 | Yes | CMU1.10.6 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ | 670 days | 3 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
234 | Yes | CMU1.10.6.1 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้นใต้ดิน | 160 days | 4 | 236 |  |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 30, 2020 05:00 PM | October 06, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
235 | Yes | CMU1.10.6.2 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้น 1 | 160 days | 4 | 236 |  |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 30, 2020 05:00 PM | October 06, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
236 | Yes | CMU1.10.6.3 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้น 2 | 175 days | 4 | 237 |  | 235,234 | October 31, 2019 8:00 AM | April 22, 2020 5:00 PM | November 07, 2019 05:00 PM | April 29, 2020 05:00 PM | March 12, 2020 05:00 PM | September 02, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
237 | Yes | CMU1.10.6.4 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้น 3 | 175 days | 4 | 238 |  | 236 | May 9, 2019 8:00 AM | October 30, 2019 5:00 PM | May 16, 2019 05:00 PM | November 06, 2019 05:00 PM | March 12, 2020 05:00 PM | September 02, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
238 | Yes | CMU1.10.6.5 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้น 4 | 160 days | 4 | 36FS+14 days |  | 237 | November 30, 2018 8:00 AM | May 8, 2019 5:00 PM | December 03, 2018 05:00 PM | May 11, 2019 05:00 PM | March 27, 2020 05:00 PM | September 02, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
239 | Yes | CMU1.10.7 | Auto Scheduled | งานระบบเครื่องเสียงประกาศ (ใช้ลำโพงของเดิม) | 539 days | 3 |  |  |  | April 7, 2019 8:00 AM | September 26, 2020 5:00 PM | October 17, 2018 05:00 PM | April 07, 2020 05:00 PM | April 16, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 530 days | 5 days | 5 days
240 | Yes | CMU1.10.7.1 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้นใต้ดิน | 7 days | 4 | 241 |  |  | September 20, 2020 8:00 AM | September 26, 2020 5:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 5 days | 5 days | 5 days | Electrician
241 | Yes | CMU1.10.7.2 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้น 1 | 7 days | 4 | 152FS-7 days |  | 240 | September 13, 2020 8:00 AM | September 19, 2020 5:00 PM | September 18, 2020 05:00 PM | September 24, 2020 05:00 PM | September 09, 2020 05:00 PM | September 15, 2020 05:00 PM | As Soon As Possible |  | No | 5 days | 5 days | 0 days | Electrician
242 | Yes | CMU1.10.7.3 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้น 2 | 7 days | 4 | 121FS-7 days |  |  | April 1, 2020 8:00 AM | April 7, 2020 5:00 PM | April 08, 2020 05:00 PM | April 14, 2020 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Electrician
243 | Yes | CMU1.10.7.4 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้น 3 | 7 days | 4 | 92FS-7 days |  |  | October 4, 2019 8:00 AM | October 10, 2019 5:00 PM | October 13, 2019 05:00 PM | October 19, 2019 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Electrician
244 | Yes | CMU1.10.7.5 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้น 4 | 7 days | 4 | 63FS-7 days |  |  | April 7, 2019 8:00 AM | April 13, 2019 5:00 PM | April 15, 2019 05:00 PM | April 21, 2019 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 537 days | 537 days | 537 days | Electrician
245 | Yes | CMU1.10.8 | Auto Scheduled | งานระบบกล้องวงจรปิด (ใช้กล้องวงจรปิดของเดิม) | 539 days | 3 |  |  |  | April 7, 2019 8:00 AM | September 26, 2020 5:00 PM | October 17, 2018 05:00 PM | April 07, 2020 05:00 PM | April 16, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 530 days | 5 days | 5 days
246 | Yes | CMU1.10.8.1 | Auto Scheduled | งานกล้องวงจรปิด ชั้นใต้ดิน | 7 days | 4 | 247 |  |  | September 20, 2020 8:00 AM | September 26, 2020 5:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 5 days | 5 days | 5 days | Electrician
247 | Yes | CMU1.10.8.2 | Auto Scheduled | งานกล้องวงจรปิด ชั้น 1 | 7 days | 4 | 152FS-7 days |  | 246 | September 13, 2020 8:00 AM | September 19, 2020 5:00 PM | September 18, 2020 05:00 PM | September 24, 2020 05:00 PM | September 09, 2020 05:00 PM | September 15, 2020 05:00 PM | As Soon As Possible |  | No | 5 days | 5 days | 0 days | Electrician
248 | Yes | CMU1.10.8.3 | Auto Scheduled | งานกล้องวงจรปิด ชั้น 2 | 7 days | 4 | 121FS-7 days |  |  | April 1, 2020 8:00 AM | April 7, 2020 5:00 PM | April 10, 2020 05:00 PM | April 16, 2020 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Electrician
249 | Yes | CMU1.10.8.4 | Auto Scheduled | งานกล้องวงจรปิด ชั้น 3 | 7 days | 4 | 92FS-7 days |  |  | October 4, 2019 8:00 AM | October 10, 2019 5:00 PM | October 13, 2019 05:00 PM | October 19, 2019 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Electrician
250 | Yes | CMU1.10.8.5 | Auto Scheduled | งานกล้องวงจรปิด ชั้น 4 | 7 days | 4 | 63FS-7 days |  |  | April 7, 2019 8:00 AM | April 13, 2019 5:00 PM | April 14, 2019 05:00 PM | April 20, 2019 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 537 days | 537 days | 537 days | Electrician

## solutoion_8
ID | Active | WBS | Task_Mode | Name | Duration | Outline_Level | Predecessors | Predecessors2 | Successors | Start_Date | Finish_Date | Early_Start | Early_Finish | Late_Start | Late_Finish | Constraint_Type | Constraint_Date | Summary | Start_Slack | Finish_Slack | Free_Slack | Resource_Names
1 | Yes | CMU1 | Auto Scheduled | โครงการปรับปรุงสำนักหอสมุด มหาวิทยาลัยเชียงใหม่ | 716 days | 1 |  |  |  | October 17, 2018 8:00 AM | October 1, 2020 5:00 PM | October 17, 2018 05:00 PM | October 01, 2020 05:00 PM | October 21, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 0 days | 0 days | 0 days
2 | Yes | CMU1.1 | Auto Scheduled | หมวดเตรียมการ | 675 days | 2 |  |  |  | October 17, 2018 8:00 AM | August 21, 2020 5:00 PM | October 17, 2018 05:00 PM | August 21, 2020 05:00 PM | December 01, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 41 days | 41 days | 41 days
3 | Yes | CMU1.1.1 | Auto Scheduled | งานอาคารสนามและผังบริเวณโครงการ | 14 days | 3 | 4FS-7 days |  |  | October 26, 2018 8:00 AM | November 8, 2018 5:00 PM | November 01, 2018 05:00 PM | November 14, 2018 05:00 PM | September 22, 2020 05:00 PM | October 05, 2020 05:00 PM | Start No Earlier Than | Oct 24 '18 | No | 693 days | 693 days | 693 days | Engineer
4 | Yes | CMU1.1.2 | Auto Scheduled | งานเชื่อมต่อระบบสาธารณูปโภคโครงการ | 16 days | 3 |  |  | 3FS-7 days | October 17, 2018 8:00 AM | November 1, 2018 5:00 PM | October 19, 2018 05:00 PM | November 03, 2018 05:00 PM | September 13, 2020 05:00 PM | September 28, 2020 05:00 PM | As Soon As Possible |  | No | 693 days | 693 days | 0 days | Engineer
5 | Yes | CMU1.1.3 | Auto Scheduled | งานตรวจทดสอบระบบภายในอาคารก่อนดำเนินการปรับปรุง | 675 days | 3 |  |  |  | October 17, 2018 8:00 AM | August 21, 2020 5:00 PM | October 17, 2018 05:00 PM | August 21, 2020 05:00 PM | December 01, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 41 days | 41 days | 41 days
6 | Yes | CMU1.1.3.1 | Auto Scheduled | ชั้นที่ 4 | 15 days | 4 |  |  | 7FS+150 days | October 17, 2018 8:00 AM | October 31, 2018 5:00 PM | October 19, 2018 05:00 PM | November 02, 2018 05:00 PM | December 01, 2018 05:00 PM | December 15, 2018 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
7 | Yes | CMU1.1.3.2 | Auto Scheduled | ชั้นที่ 3 | 15 days | 4 | 6FS+150 days |  | 8FS+150 days | March 31, 2019 8:00 AM | April 14, 2019 5:00 PM | April 07, 2019 05:00 PM | April 21, 2019 05:00 PM | May 15, 2019 05:00 PM | May 29, 2019 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
8 | Yes | CMU1.1.3.3 | Auto Scheduled | ชั้นที่ 2 | 15 days | 4 | 7FS+150 days |  | 9FS+150 days | September 12, 2019 8:00 AM | September 26, 2019 5:00 PM | September 30, 2019 05:00 PM | October 14, 2019 05:00 PM | October 27, 2019 05:00 PM | November 10, 2019 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
9 | Yes | CMU1.1.3.4 | Auto Scheduled | ชั้นที่ 1 | 15 days | 4 | 8FS+150 days |  | 10FS+150 days | February 24, 2020 8:00 AM | March 9, 2020 5:00 PM | March 19, 2020 05:00 PM | April 02, 2020 05:00 PM | April 09, 2020 05:00 PM | April 23, 2020 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
10 | Yes | CMU1.1.3.5 | Auto Scheduled | ชั้นใต้ดินและภายนอก | 15 days | 4 | 9FS+150 days |  |  | August 7, 2020 8:00 AM | August 21, 2020 5:00 PM | September 17, 2020 05:00 PM | October 01, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 41 days | Engineer
11 | Yes | CMU1.1.4 | Auto Scheduled | งานสำรวจอุปกรณ์ไฟฟ้า, สุขภัณฑ์และครุภัณฑ์ (ของเดิม) ก่อนดำเนินการปรับปรุง | 675 days | 3 |  |  |  | October 17, 2018 8:00 AM | August 21, 2020 5:00 PM | October 17, 2018 05:00 PM | August 21, 2020 05:00 PM | December 01, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 41 days | 41 days | 41 days
12 | Yes | CMU1.1.4.1 | Auto Scheduled | ชั้นที่ 4 | 15 days | 4 |  |  | 13FS+150 days | October 17, 2018 8:00 AM | October 31, 2018 5:00 PM | October 20, 2018 05:00 PM | November 03, 2018 05:00 PM | December 01, 2018 05:00 PM | December 15, 2018 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
13 | Yes | CMU1.1.4.2 | Auto Scheduled | ชั้นที่ 3 | 15 days | 4 | 12FS+150 days |  | 14FS+150 days | March 31, 2019 8:00 AM | April 14, 2019 5:00 PM | April 06, 2019 05:00 PM | April 20, 2019 05:00 PM | May 15, 2019 05:00 PM | May 29, 2019 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
14 | Yes | CMU1.1.4.3 | Auto Scheduled | ชั้นที่ 2 | 15 days | 4 | 13FS+150 days |  | 15FS+150 days | September 12, 2019 8:00 AM | September 26, 2019 5:00 PM | September 24, 2019 05:00 PM | October 08, 2019 05:00 PM | October 27, 2019 05:00 PM | November 10, 2019 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
15 | Yes | CMU1.1.4.4 | Auto Scheduled | ชั้นที่ 1 | 15 days | 4 | 14FS+150 days |  | 16FS+150 days | February 24, 2020 8:00 AM | March 9, 2020 5:00 PM | March 13, 2020 05:00 PM | March 27, 2020 05:00 PM | April 09, 2020 05:00 PM | April 23, 2020 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
16 | Yes | CMU1.1.4.5 | Auto Scheduled | ชั้นใต้ดินและภายนอก | 15 days | 4 | 15FS+150 days |  |  | August 7, 2020 8:00 AM | August 21, 2020 5:00 PM | September 05, 2020 05:00 PM | September 19, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 41 days | Engineer
17 | Yes | CMU1.1.5 | Auto Scheduled | งานเอกสารขออนุมัติใช้วัสดุ, Shop Drawing และครุภัณฑ์ของโครงการ | 106 days | 3 |  |  |  | October 17, 2018 8:00 AM | January 30, 2019 5:00 PM | October 21, 2018 05:00 PM | February 03, 2019 05:00 PM | June 22, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 610 days | 610 days | 610 days
18 | Yes | CMU1.1.5.1 | Auto Scheduled | แบบ Shop Drawing ชั้นที่ 4 | 20 days | 4 |  |  | 19,25SS+14 days,26SS+14 days | October 17, 2018 8:00 AM | November 5, 2018 5:00 PM | October 17, 2018 05:00 PM | November 05, 2018 05:00 PM | October 01, 2018 05:00 PM | October 20, 2018 05:00 PM | As Soon As Possible |  | No | 610 days | 610 days | 0 days | Engineer
19 | Yes | CMU1.1.5.2 | Auto Scheduled | แบบ Shop Drawing ชั้นที่ 3 | 20 days | 4 | 18 |  | 20FS-7 days | November 6, 2018 8:00 AM | November 25, 2018 5:00 PM | November 13, 2018 05:00 PM | December 02, 2018 05:00 PM | July 13, 2020 05:00 PM | August 01, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
20 | Yes | CMU1.1.5.3 | Auto Scheduled | แบบ Shop Drawing ชั้นที่ 2 | 20 days | 4 | 19FS-7 days |  | 21FS-7 days | November 19, 2018 8:00 AM | December 8, 2018 5:00 PM | November 29, 2018 05:00 PM | December 18, 2018 05:00 PM | July 26, 2020 05:00 PM | August 14, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
21 | Yes | CMU1.1.5.4 | Auto Scheduled | แบบ Shop Drawing ชั้นที่ 1 | 20 days | 4 | 20FS-7 days |  | 22FS-7 days | December 2, 2018 8:00 AM | December 21, 2018 5:00 PM | December 18, 2018 05:00 PM | January 06, 2019 05:00 PM | August 08, 2020 05:00 PM | August 27, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
22 | Yes | CMU1.1.5.5 | Auto Scheduled | แบบ Shop Drawing ชั้นใต้ดิน | 20 days | 4 | 21FS-7 days |  | 23FS-7 days | December 15, 2018 8:00 AM | January 3, 2019 5:00 PM | January 06, 2019 05:00 PM | January 25, 2019 05:00 PM | August 21, 2020 05:00 PM | September 09, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
23 | Yes | CMU1.1.5.6 | Auto Scheduled | แบบ Shop Drawing ภายนอกอาคาร | 20 days | 4 | 22FS-7 days |  | 24FS-7 days | December 28, 2018 8:00 AM | January 16, 2019 5:00 PM | January 26, 2019 05:00 PM | February 14, 2019 05:00 PM | September 03, 2020 05:00 PM | September 22, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
24 | Yes | CMU1.1.5.7 | Auto Scheduled | แบบ Shop Drawing landscape | 20 days | 4 | 23FS-7 days |  |  | January 10, 2019 8:00 AM | January 29, 2019 5:00 PM | February 15, 2019 05:00 PM | March 06, 2019 05:00 PM | September 16, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 611 days | Engineer
25 | Yes | CMU1.1.5.8 | Auto Scheduled | แบบ Shop Drawing งานปรับปรุง ครุภัณฑ์ | 92 days | 4 | 18SS+14 days |  |  | October 31, 2018 8:00 AM | January 30, 2019 5:00 PM | November 06, 2018 05:00 PM | February 05, 2019 05:00 PM | July 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 610 days | 610 days | 610 days | Engineer
26 | Yes | CMU1.1.5.9 | Auto Scheduled | แบบ Shop Drawing งานจัดซื้อครุภัณฑ์ | 92 days | 4 | 18SS+14 days |  |  | October 31, 2018 8:00 AM | January 30, 2019 5:00 PM | November 06, 2018 05:00 PM | February 05, 2019 05:00 PM | July 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 610 days | 610 days | 610 days | Engineer
27 | Yes | CMU1.1.6 | Auto Scheduled | งานตรวจทดสอบระบบ, งานอบรมผู้ใช้อาคาร และ As-Built Drawing | 30 days | 3 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 22, 2018 05:00 PM | November 20, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 686 days | 686 days | 686 days
28 | Yes | CMU1.1.6.1 | Auto Scheduled | ชั้นที่ 4 | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 27, 2018 05:00 PM | November 25, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
29 | Yes | CMU1.1.6.2 | Auto Scheduled | ชั้นที่ 3 | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 29, 2018 05:00 PM | November 27, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
30 | Yes | CMU1.1.6.3 | Auto Scheduled | ชั้นที่ 2 | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 21, 2018 05:00 PM | November 19, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
31 | Yes | CMU1.1.6.4 | Auto Scheduled | ชั้นที่ 1 | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 28, 2018 05:00 PM | November 26, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
32 | Yes | CMU1.1.6.5 | Auto Scheduled | ชั้นใต้ดิน | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 25, 2018 05:00 PM | November 23, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
33 | Yes | CMU1.1.6.6 | Auto Scheduled | ทั้งอาคาร | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 23, 2018 05:00 PM | November 21, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
34 | Yes | CMU1.1.7 | Auto Scheduled | งานบริหารงานก่อสร้างและงานอื่น ๆ | 0 days | 3 |  |  |  | October 17, 2018 8:00 AM | October 17, 2018 8:00 AM | October 20, 2018 05:00 PM | October 19, 2018 05:00 PM | October 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 716 days | 716 days | 716 days | Engineer
35 | Yes | CMU1.2 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้น 4 | 471 days | 2 |  |  |  | October 17, 2018 8:00 AM | January 30, 2020 5:00 PM | October 17, 2018 05:00 PM | January 30, 2020 05:00 PM | June 23, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 0 days | 245 days | 0 days
36 | Yes | CMU1.2.1 | Auto Scheduled | งานรื้อถอน ชั้น 4 (รื้อขนไป) | 30 days | 3 |  |  | 39FS+45 days,40FS+45 days,51,63SS+14 days,80,109,140,180FS+14 days,186FS+14 days,198FS+14 days,199FS+14 days,200FS+14 days,238FS+14 days | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 17, 2018 05:00 PM | November 15, 2018 05:00 PM | March 11, 2018 05:00 PM | April 09, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | General worker
37 | Yes | CMU1.2.2 | Auto Scheduled | งานสถาปัตยกรรม ชั้น 4 | 396 days | 3 |  |  |  | December 31, 2018 8:00 AM | January 30, 2020 5:00 PM | October 17, 2018 05:00 PM | November 16, 2019 05:00 PM | September 06, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 326 days | 245 days | 245 days
38 | Yes | CMU1.2.2.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 39,41,42 |  |  | March 1, 2019 8:00 AM | March 30, 2019 5:00 PM | March 14, 2019 05:00 PM | April 12, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 551 days | Skilled carpenter
39 | Yes | CMU1.2.2.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 36FS+45 days |  | 38,43 | December 31, 2018 8:00 AM | February 28, 2019 5:00 PM | January 05, 2019 05:00 PM | March 05, 2019 05:00 PM | July 15, 2020 05:00 PM | September 12, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 0 days | General worker
40 | Yes | CMU1.2.2.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 36FS+45 days |  | 41,42 | December 31, 2018 8:00 AM | January 29, 2019 5:00 PM | January 03, 2019 05:00 PM | February 01, 2019 05:00 PM | August 14, 2020 05:00 PM | September 12, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 0 days | General worker
41 | Yes | CMU1.2.2.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 40 |  | 38,43 | January 30, 2019 8:00 AM | February 28, 2019 5:00 PM | February 05, 2019 05:00 PM | March 06, 2019 05:00 PM | August 14, 2020 05:00 PM | September 12, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 0 days | Skilled carpenter
42 | Yes | CMU1.2.2.5 | Auto Scheduled | งานบันได | 30 days | 4 | 40 |  | 38,43 | January 30, 2019 8:00 AM | February 28, 2019 5:00 PM | February 05, 2019 05:00 PM | March 06, 2019 05:00 PM | August 14, 2020 05:00 PM | September 12, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 0 days | General worker
43 | Yes | CMU1.2.2.6 | Auto Scheduled | งานสี | 30 days | 4 | 39,41,42 |  |  | March 1, 2019 8:00 AM | March 30, 2019 5:00 PM | March 10, 2019 05:00 PM | April 08, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 551 days | General worker
44 | Yes | CMU1.2.2.7 | Auto Scheduled | งานสุขภัณฑ์ | 315 days | 4 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 20, 2018 05:00 PM | August 30, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
45 | Yes | CMU1.2.2.7.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 46FS+135 days |  | 47FS+135 days | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | September 14, 2019 05:00 PM | September 28, 2019 05:00 PM | April 24, 2020 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
46 | Yes | CMU1.2.2.7.2 | Auto Scheduled | ZONE T-2 กลาง | 15 days | 5 | 51,55 |  | 45FS+135 days | March 22, 2019 8:00 AM | April 5, 2019 5:00 PM | April 10, 2019 05:00 PM | April 24, 2019 05:00 PM | November 26, 2019 05:00 PM | December 10, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
47 | Yes | CMU1.2.2.7.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 15 days | 5 | 45FS+135 days |  |  | January 16, 2020 8:00 AM | January 30, 2020 5:00 PM | February 17, 2020 05:00 PM | March 02, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 245 days | Sanitary-Plumber
48 | Yes | CMU1.2.3 | Auto Scheduled | งานระบบสุขาภิบาล ชั้น 4 | 408 days | 3 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
49 | Yes | CMU1.2.3.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
50 | Yes | CMU1.2.3.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 51FS+15 days |  | 52FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 20, 2019 05:00 PM | August 23, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
51 | Yes | CMU1.2.3.1.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 36 |  | 50FS+15 days,46,55SS | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 23, 2018 05:00 PM | March 28, 2019 05:00 PM | August 25, 2019 05:00 PM | December 28, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
52 | Yes | CMU1.2.3.1.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 50FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 12, 2019 05:00 PM | January 15, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
53 | Yes | CMU1.2.3.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
54 | Yes | CMU1.2.3.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 55FS+15 days |  | 56FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 26, 2019 05:00 PM | August 29, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
55 | Yes | CMU1.2.3.2.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 51SS |  | 54FS+15 days,46 | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 30, 2018 05:00 PM | April 04, 2019 05:00 PM | August 25, 2019 05:00 PM | December 28, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
56 | Yes | CMU1.2.3.2.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 54FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 23, 2019 05:00 PM | January 26, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
57 | Yes | CMU1.2.4 | Auto Scheduled | งานระบบไฟฟ้า ชั้น 4 | 117 days | 3 |  |  |  | November 30, 2018 8:00 AM | March 26, 2019 5:00 PM | October 21, 2018 05:00 PM | February 14, 2019 05:00 PM | June 11, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 555 days | 555 days | 555 days
58 | Yes | CMU1.2.4.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 30 days | 4 | 60FS+7 days |  |  | February 25, 2019 8:00 AM | March 26, 2019 5:00 PM | March 04, 2019 05:00 PM | April 02, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 555 days | 555 days | 555 days | Electrician
59 | Yes | CMU1.2.4.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 30 days | 4 | 60FS+7 days |  |  | February 25, 2019 8:00 AM | March 26, 2019 5:00 PM | March 04, 2019 05:00 PM | April 02, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 555 days | 555 days | 555 days | Electrician
60 | Yes | CMU1.2.4.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 63SS+30 days |  | 58FS+7 days,59FS+7 days | November 30, 2018 8:00 AM | February 17, 2019 5:00 PM | December 04, 2018 05:00 PM | February 21, 2019 05:00 PM | June 11, 2020 05:00 PM | August 29, 2020 05:00 PM | As Soon As Possible |  | No | 555 days | 555 days | 0 days | Electrician
61 | Yes | CMU1.2.4.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 63SS+30 days |  |  | November 30, 2018 8:00 AM | February 17, 2019 5:00 PM | December 03, 2018 05:00 PM | February 20, 2019 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 592 days | 592 days | 592 days | Electrician
62 | Yes | CMU1.2.4.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 63SS+30 days |  |  | November 30, 2018 8:00 AM | February 17, 2019 5:00 PM | December 05, 2018 05:00 PM | February 22, 2019 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 592 days | 592 days | 592 days | Electrician
63 | Yes | CMU1.2.5 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้น 4 | 165 days | 3 | 36SS+14 days |  | 62SS+30 days,60SS+30 days,61SS+30 days,65,214,219FS-15 days,224,230,244FS-7 days,250FS-7 days | October 31, 2018 8:00 AM | April 13, 2019 5:00 PM | October 31, 2018 05:00 PM | April 13, 2019 05:00 PM | June 19, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Skilled carpenter
64 | Yes | CMU1.3 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้น 3 | 441 days | 2 |  |  |  | November 16, 2018 8:00 AM | January 30, 2020 5:00 PM | October 17, 2018 05:00 PM | December 31, 2019 05:00 PM | July 23, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 149 days | 245 days | 149 days
65 | Yes | CMU1.3.1 | Auto Scheduled | งานรื้อถอน ชั้น 3 (รื้อขนไป) | 30 days | 3 | 63 | 121 | 68FS+45 days,69FS+45 days,92SS | April 14, 2019 8:00 AM | May 13, 2019 5:00 PM | April 14, 2019 05:00 PM | May 13, 2019 05:00 PM | July 19, 2018 05:00 PM | August 17, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | General worker
66 | Yes | CMU1.3.2 | Auto Scheduled | งานสถาปัตยกรรม ชั้น 3 | 315 days | 3 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 22, 2018 05:00 PM | September 01, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
67 | Yes | CMU1.3.2.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 68,70,71 |  |  | August 27, 2019 8:00 AM | September 25, 2019 5:00 PM | August 30, 2019 05:00 PM | September 28, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 372 days | Skilled carpenter
68 | Yes | CMU1.3.2.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 65FS+45 days |  | 67,72 | June 28, 2019 8:00 AM | August 26, 2019 5:00 PM | June 28, 2019 05:00 PM | August 26, 2019 05:00 PM | October 02, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 0 days | General worker
69 | Yes | CMU1.3.2.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 65FS+45 days |  | 70,71 | June 28, 2019 8:00 AM | July 27, 2019 5:00 PM | June 28, 2019 05:00 PM | July 27, 2019 05:00 PM | April 15, 2019 05:00 PM | May 14, 2019 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 0 days | General worker
70 | Yes | CMU1.3.2.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 69 |  | 67,72 | July 28, 2019 8:00 AM | August 26, 2019 5:00 PM | July 28, 2019 05:00 PM | August 26, 2019 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 0 days | Skilled carpenter
71 | Yes | CMU1.3.2.5 | Auto Scheduled | งานบันได | 30 days | 4 | 69 |  | 67,72 | July 28, 2019 8:00 AM | August 26, 2019 5:00 PM | July 28, 2019 05:00 PM | August 26, 2019 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 0 days | General worker
72 | Yes | CMU1.3.2.6 | Auto Scheduled | งานสี | 30 days | 4 | 68,70,71 |  |  | August 27, 2019 8:00 AM | September 25, 2019 5:00 PM | August 30, 2019 05:00 PM | September 28, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 372 days | General worker
73 | Yes | CMU1.3.2.7 | Auto Scheduled | งานสุขภัณฑ์ | 315 days | 4 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 23, 2018 05:00 PM | September 02, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
74 | Yes | CMU1.3.2.7.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 75FS+135 days |  | 76FS+135 days | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | August 25, 2019 05:00 PM | September 08, 2019 05:00 PM | April 24, 2020 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
75 | Yes | CMU1.3.2.7.2 | Auto Scheduled | ZONE T-2 กลาง | 15 days | 5 | 80,84 |  | 74FS+135 days | March 22, 2019 8:00 AM | April 5, 2019 5:00 PM | March 24, 2019 05:00 PM | April 07, 2019 05:00 PM | November 26, 2019 05:00 PM | December 10, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
76 | Yes | CMU1.3.2.7.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 15 days | 5 | 74FS+135 days |  |  | January 16, 2020 8:00 AM | January 30, 2020 5:00 PM | January 27, 2020 05:00 PM | February 10, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 245 days | Sanitary-Plumber
77 | Yes | CMU1.3.3 | Auto Scheduled | งานระบบสุขาภิบาล ชั้น 3 | 408 days | 3 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
78 | Yes | CMU1.3.3.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
79 | Yes | CMU1.3.3.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 80FS+15 days |  | 81FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 18, 2019 05:00 PM | August 21, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
80 | Yes | CMU1.3.3.1.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 36 |  | 79FS+15 days,84SS,75 | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 16, 2018 05:00 PM | March 21, 2019 05:00 PM | January 09, 2019 05:00 PM | May 14, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
81 | Yes | CMU1.3.3.1.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 79FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 11, 2019 05:00 PM | January 14, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
82 | Yes | CMU1.3.3.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
83 | Yes | CMU1.3.3.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 84FS+15 days |  | 85FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 11, 2019 05:00 PM | August 14, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
84 | Yes | CMU1.3.3.2.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 80SS |  | 83FS+15 days,75 | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 16, 2018 05:00 PM | March 21, 2019 05:00 PM | January 09, 2019 05:00 PM | May 14, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
85 | Yes | CMU1.3.3.2.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 83FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 08, 2019 05:00 PM | January 11, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
86 | Yes | CMU1.3.4 | Auto Scheduled | งานระบบไฟฟ้า ชั้น 3 | 147 days | 3 |  |  |  | May 14, 2019 8:00 AM | October 7, 2019 5:00 PM | October 21, 2018 05:00 PM | March 16, 2019 05:00 PM | May 12, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 360 days | 360 days | 360 days
87 | Yes | CMU1.3.4.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 60 days | 4 | 89FS+7 days |  |  | August 9, 2019 8:00 AM | October 7, 2019 5:00 PM | August 18, 2019 05:00 PM | October 16, 2019 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 360 days | 360 days | 360 days | Electrician
88 | Yes | CMU1.3.4.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 60 days | 4 | 89FS+7 days |  |  | August 9, 2019 8:00 AM | October 7, 2019 5:00 PM | August 24, 2019 05:00 PM | October 22, 2019 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 360 days | 360 days | 360 days | Electrician
89 | Yes | CMU1.3.4.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 92SS+30 days |  | 88FS+7 days,87FS+7 days | May 14, 2019 8:00 AM | August 1, 2019 5:00 PM | May 20, 2019 05:00 PM | August 07, 2019 05:00 PM | May 12, 2020 05:00 PM | July 30, 2020 05:00 PM | As Soon As Possible |  | No | 360 days | 360 days | 0 days | Electrician
90 | Yes | CMU1.3.4.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 92SS+30 days |  |  | May 14, 2019 8:00 AM | August 1, 2019 5:00 PM | May 23, 2019 05:00 PM | August 10, 2019 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 427 days | 427 days | 427 days | Electrician
91 | Yes | CMU1.3.4.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 92SS+30 days |  |  | May 14, 2019 8:00 AM | August 1, 2019 5:00 PM | May 24, 2019 05:00 PM | August 11, 2019 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 427 days | 427 days | 427 days | Electrician
92 | Yes | CMU1.3.5 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้น 3 | 180 days | 3 | 65SS |  | 91SS+30 days,90SS+30 days,89SS+30 days,94,213FS-15 days,218FS-30 days,223FS-15 days,229FS-15 days,243FS-7 days,249FS-7 days | April 14, 2019 8:00 AM | October 10, 2019 5:00 PM | April 18, 2019 05:00 PM | October 14, 2019 05:00 PM | October 12, 2019 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Skilled carpenter
93 | Yes | CMU1.4 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้น 2 | 509 days | 2 |  |  |  | November 16, 2018 8:00 AM | April 7, 2020 5:00 PM | October 17, 2018 05:00 PM | March 08, 2020 05:00 PM | May 16, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 177 days | 177 days
94 | Yes | CMU1.4.1 | Auto Scheduled | งานรื้อถอน ชั้น 2 (รื้อขนไป) | 30 days | 3 | 92 | 152 | 97FS+45 days,98FS+45 days,121SS | October 11, 2019 8:00 AM | November 9, 2019 5:00 PM | October 15, 2019 05:00 PM | November 13, 2019 05:00 PM | June 04, 2018 05:00 PM | July 03, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | General worker
95 | Yes | CMU1.4.2 | Auto Scheduled | งานสถาปัตยกรรม ชั้น 2 | 368 days | 3 |  |  |  | March 22, 2019 8:00 AM | March 23, 2020 5:00 PM | October 17, 2018 05:00 PM | October 19, 2019 05:00 PM | October 04, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 192 days | 192 days
96 | Yes | CMU1.4.2.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 97,99,100 |  |  | February 23, 2020 8:00 AM | March 23, 2020 5:00 PM | March 07, 2020 05:00 PM | April 05, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 192 days | Skilled carpenter
97 | Yes | CMU1.4.2.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 94FS+45 days |  | 96,101 | December 25, 2019 8:00 AM | February 22, 2020 5:00 PM | December 29, 2019 05:00 PM | February 26, 2020 05:00 PM | February 09, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 0 days | General worker
98 | Yes | CMU1.4.2.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 94FS+45 days |  | 99,100 | December 25, 2019 8:00 AM | January 23, 2020 5:00 PM | January 01, 2020 05:00 PM | January 30, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 0 days | General worker
99 | Yes | CMU1.4.2.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 98 |  | 96,101 | January 24, 2020 8:00 AM | February 22, 2020 5:00 PM | February 03, 2020 05:00 PM | March 03, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 0 days | Skilled carpenter
100 | Yes | CMU1.4.2.5 | Auto Scheduled | งานบันได | 30 days | 4 | 98 |  | 96,101 | January 24, 2020 8:00 AM | February 22, 2020 5:00 PM | February 03, 2020 05:00 PM | March 03, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 0 days | General worker
101 | Yes | CMU1.4.2.6 | Auto Scheduled | งานสี | 30 days | 4 | 97,99,100 |  |  | February 23, 2020 8:00 AM | March 23, 2020 5:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 192 days | General worker
102 | Yes | CMU1.4.2.7 | Auto Scheduled | งานสุขภัณฑ์ | 315 days | 4 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 21, 2018 05:00 PM | August 31, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
103 | Yes | CMU1.4.2.7.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 104FS+135 days |  | 105FS+135 days | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | September 14, 2019 05:00 PM | September 28, 2019 05:00 PM | April 24, 2020 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
104 | Yes | CMU1.4.2.7.2 | Auto Scheduled | ZONE T-2 กลาง | 15 days | 5 | 113,109 |  | 103FS+135 days | March 22, 2019 8:00 AM | April 5, 2019 5:00 PM | April 13, 2019 05:00 PM | April 27, 2019 05:00 PM | November 26, 2019 05:00 PM | December 10, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
105 | Yes | CMU1.4.2.7.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 15 days | 5 | 103FS+135 days |  |  | January 16, 2020 8:00 AM | January 30, 2020 5:00 PM | February 17, 2020 05:00 PM | March 02, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 245 days | Sanitary-Plumber
106 | Yes | CMU1.4.3 | Auto Scheduled | งานระบบสุขาภิบาล ชั้น 2 | 408 days | 3 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
107 | Yes | CMU1.4.3.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
108 | Yes | CMU1.4.3.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 109FS+15 days |  | 110FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 19, 2019 05:00 PM | August 22, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
109 | Yes | CMU1.4.3.1.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 36 |  | 113SS,104,108FS+15 days | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 25, 2018 05:00 PM | March 30, 2019 05:00 PM | August 25, 2019 05:00 PM | December 28, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
110 | Yes | CMU1.4.3.1.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 108FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 10, 2019 05:00 PM | January 13, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
111 | Yes | CMU1.4.3.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
112 | Yes | CMU1.4.3.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 113FS+15 days |  | 114FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 30, 2019 05:00 PM | September 02, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
113 | Yes | CMU1.4.3.2.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 109SS |  | 104,112FS+15 days | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | December 01, 2018 05:00 PM | April 05, 2019 05:00 PM | August 25, 2019 05:00 PM | December 28, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
114 | Yes | CMU1.4.3.2.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 112FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 22, 2019 05:00 PM | January 25, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
115 | Yes | CMU1.4.4 | Auto Scheduled | งานระบบไฟฟ้า ชั้น 2 | 147 days | 3 |  |  |  | November 10, 2019 8:00 AM | April 4, 2020 5:00 PM | October 20, 2018 05:00 PM | March 15, 2019 05:00 PM | May 12, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 180 days | 180 days | 180 days
116 | Yes | CMU1.4.4.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 60 days | 4 | 118FS+7 days |  |  | February 5, 2020 8:00 AM | April 4, 2020 5:00 PM | February 12, 2020 05:00 PM | April 11, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 180 days | 180 days | 180 days | Electrician
117 | Yes | CMU1.4.4.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 60 days | 4 | 118FS+7 days |  |  | February 5, 2020 8:00 AM | April 4, 2020 5:00 PM | February 14, 2020 05:00 PM | April 13, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 180 days | 180 days | 180 days | Electrician
118 | Yes | CMU1.4.4.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 121SS+30 days |  | 117FS+7 days,116FS+7 days | November 10, 2019 8:00 AM | January 28, 2020 5:00 PM | November 16, 2019 05:00 PM | February 03, 2020 05:00 PM | May 12, 2020 05:00 PM | July 30, 2020 05:00 PM | As Soon As Possible |  | No | 180 days | 180 days | 0 days | Electrician
119 | Yes | CMU1.4.4.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 121SS+30 days |  |  | November 10, 2019 8:00 AM | January 28, 2020 5:00 PM | November 18, 2019 05:00 PM | February 05, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 247 days | 247 days | 247 days | Electrician
120 | Yes | CMU1.4.4.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 121SS+30 days |  |  | November 10, 2019 8:00 AM | January 28, 2020 5:00 PM | November 21, 2019 05:00 PM | February 08, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 247 days | 247 days | 247 days | Electrician
121 | Yes | CMU1.4.5 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้น 2 | 180 days | 3 | 94SS |  | 120SS+30 days,119SS+30 days,118SS+30 days,123,212FS-15 days,217FS-30 days,222FS-15 days,228FS-15 days,242FS-7 days,248FS-7 days | October 11, 2019 8:00 AM | April 7, 2020 5:00 PM | October 15, 2019 05:00 PM | April 11, 2020 05:00 PM | June 04, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Skilled carpenter
122 | Yes | CMU1.5 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้น 1 | 686 days | 2 |  |  |  | November 16, 2018 8:00 AM | October 1, 2020 5:00 PM | October 17, 2018 05:00 PM | September 01, 2020 05:00 PM | November 20, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 0 days | 0 days
123 | Yes | CMU1.5.1 | Auto Scheduled | งานรื้อถอน ชั้น 1 (รื้อขนไป) | 30 days | 3 | 121 | 63 | 124,127FS+45 days,128FS+45 days,131FS+45 days,152SS,193SS,194SS,195SS,196SS,197SS,202SS,204SS,205SS,206SS,207SS | April 8, 2020 8:00 AM | May 7, 2020 5:00 PM | April 12, 2020 05:00 PM | May 11, 2020 05:00 PM | July 19, 2018 05:00 PM | August 17, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | General worker
124 | Yes | CMU1.5.2 | Auto Scheduled | งานโครงสร้างวิศวกรรม ชั้น 1 | 75 days | 3 | 123 |  |  | May 8, 2020 8:00 AM | July 21, 2020 5:00 PM | May 13, 2020 05:00 PM | July 26, 2020 05:00 PM | July 23, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 72 days | 72 days | 72 days | General worker
125 | Yes | CMU1.5.3 | Auto Scheduled | งานสถาปัตยกรรม ชั้น 1 | 548 days | 3 |  |  |  | March 22, 2019 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | April 16, 2020 05:00 PM | April 07, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 12 days | 12 days
126 | Yes | CMU1.5.3.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 127,129,130 |  |  | August 21, 2020 8:00 AM | September 19, 2020 5:00 PM | August 25, 2020 05:00 PM | September 23, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | Skilled carpenter
127 | Yes | CMU1.5.3.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 123FS+45 days |  | 126,132 | June 22, 2020 8:00 AM | August 20, 2020 5:00 PM | June 26, 2020 05:00 PM | August 24, 2020 05:00 PM | October 02, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
128 | Yes | CMU1.5.3.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 123FS+45 days |  | 129,130 | June 22, 2020 8:00 AM | July 21, 2020 5:00 PM | June 26, 2020 05:00 PM | July 25, 2020 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
129 | Yes | CMU1.5.3.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 128 |  | 126,132 | July 22, 2020 8:00 AM | August 20, 2020 5:00 PM | July 26, 2020 05:00 PM | August 24, 2020 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | Skilled carpenter
130 | Yes | CMU1.5.3.5 | Auto Scheduled | งานบันได | 30 days | 4 | 128 |  | 126,132 | July 22, 2020 8:00 AM | August 20, 2020 5:00 PM | July 26, 2020 05:00 PM | August 24, 2020 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
131 | Yes | CMU1.5.3.6 | Auto Scheduled | งานตกแต่งอื่น ๆ | 60 days | 4 | 123FS+45 days |  |  | June 22, 2020 8:00 AM | August 20, 2020 5:00 PM | June 26, 2020 05:00 PM | August 24, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 42 days | 42 days | 42 days | General worker
132 | Yes | CMU1.5.3.7 | Auto Scheduled | งานสี | 30 days | 4 | 127,129,130 |  |  | August 21, 2020 8:00 AM | September 19, 2020 5:00 PM | August 25, 2020 05:00 PM | September 23, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
133 | Yes | CMU1.5.3.8 | Auto Scheduled | งานสุขภัณฑ์ | 315 days | 4 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 24, 2018 05:00 PM | September 03, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
134 | Yes | CMU1.5.3.8.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 135FS+135 days |  | 136FS+135 days | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | August 24, 2019 05:00 PM | September 07, 2019 05:00 PM | April 24, 2020 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
135 | Yes | CMU1.5.3.8.2 | Auto Scheduled | ZONE T-2 กลาง | 15 days | 5 | 140,144 |  | 134FS+135 days,164FS+135 days | March 22, 2019 8:00 AM | April 5, 2019 5:00 PM | March 24, 2019 05:00 PM | April 07, 2019 05:00 PM | November 26, 2019 05:00 PM | December 10, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
136 | Yes | CMU1.5.3.8.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 15 days | 5 | 134FS+135 days |  |  | January 16, 2020 8:00 AM | January 30, 2020 5:00 PM | January 25, 2020 05:00 PM | February 08, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 245 days | Sanitary-Plumber
137 | Yes | CMU1.5.4 | Auto Scheduled | งานระบบสุขาภิบาล ชั้น 1 | 408 days | 3 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 278 days | 44 days
138 | Yes | CMU1.5.4.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 278 days | 44 days
139 | Yes | CMU1.5.4.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 140FS+15 days |  | 141FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 13, 2019 05:00 PM | August 16, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
140 | Yes | CMU1.5.4.1.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 36 |  | 139FS+15 days,144SS,135,167FS+15 days | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 16, 2018 05:00 PM | March 21, 2019 05:00 PM | January 03, 2019 05:00 PM | May 08, 2019 05:00 PM | As Soon As Possible |  | No | 44 days | 44 days | 0 days | Sanitary-Plumber
141 | Yes | CMU1.5.4.1.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 139FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 07, 2019 05:00 PM | January 10, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
142 | Yes | CMU1.5.4.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 278 days | 44 days
143 | Yes | CMU1.5.4.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 144FS+15 days |  | 145FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 12, 2019 05:00 PM | August 15, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
144 | Yes | CMU1.5.4.2.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 140SS |  | 143FS+15 days,135,169FS+15 days | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 16, 2018 05:00 PM | March 21, 2019 05:00 PM | January 03, 2019 05:00 PM | May 08, 2019 05:00 PM | As Soon As Possible |  | No | 44 days | 44 days | 0 days | Sanitary-Plumber
145 | Yes | CMU1.5.4.2.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 143FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 04, 2019 05:00 PM | January 07, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
146 | Yes | CMU1.5.5 | Auto Scheduled | งานระบบไฟฟ้า ชั้น 1 | 147 days | 3 |  |  |  | May 8, 2020 8:00 AM | October 1, 2020 5:00 PM | October 21, 2018 05:00 PM | March 16, 2019 05:00 PM | May 12, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 0 days | 0 days | 0 days
147 | Yes | CMU1.5.5.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 60 days | 4 | 149FS+7 days |  |  | August 3, 2020 8:00 AM | October 1, 2020 5:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Electrician
148 | Yes | CMU1.5.5.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 60 days | 4 | 149FS+7 days |  |  | August 3, 2020 8:00 AM | October 1, 2020 5:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Electrician
149 | Yes | CMU1.5.5.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 152SS+30 days |  | 148FS+7 days,147FS+7 days | May 8, 2020 8:00 AM | July 26, 2020 5:00 PM | May 12, 2020 05:00 PM | July 30, 2020 05:00 PM | May 12, 2020 05:00 PM | July 30, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Electrician
150 | Yes | CMU1.5.5.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 152SS+30 days |  |  | May 8, 2020 8:00 AM | July 26, 2020 5:00 PM | May 12, 2020 05:00 PM | July 30, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 67 days | 67 days | 67 days | Electrician
151 | Yes | CMU1.5.5.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 152SS+30 days |  |  | May 8, 2020 8:00 AM | July 26, 2020 5:00 PM | May 12, 2020 05:00 PM | July 30, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 67 days | 67 days | 67 days | Electrician
152 | Yes | CMU1.5.6 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้น 1 | 165 days | 3 | 123SS |  | 151SS+30 days,150SS+30 days,149SS+30 days,154SS,211FS-30 days,210FS-30 days,216FS-45 days,221FS-30 days,227FS-30 days,226FS-30 days,232FS-45 days,241FS-7 days,247FS-7 days | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 12, 2020 05:00 PM | September 23, 2020 05:00 PM | November 26, 2019 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Skilled carpenter
153 | Yes | CMU1.6 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้นใต้ดิน | 533 days | 2 |  |  |  | April 6, 2019 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | April 01, 2020 05:00 PM | April 22, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 12 days | 12 days
154 | Yes | CMU1.6.1 | Auto Scheduled | งานรื้อถอน ชั้นใต้ดิน (รื้อขนไป) | 30 days | 3 | 152SS |  | 155,158FS+45 days,159FS+45 days,177SS,176SS,175SS,174SS | April 8, 2020 8:00 AM | May 7, 2020 5:00 PM | April 12, 2020 05:00 PM | May 11, 2020 05:00 PM | November 26, 2019 05:00 PM | December 25, 2019 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
155 | Yes | CMU1.6.2 | Auto Scheduled | งานโครงสร้างวิศวกรรม ชั้นใต้ดิน | 75 days | 3 | 154 |  |  | May 8, 2020 8:00 AM | July 21, 2020 5:00 PM | May 13, 2020 05:00 PM | July 26, 2020 05:00 PM | July 23, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 72 days | 72 days | 72 days | General worker
156 | Yes | CMU1.6.3 | Auto Scheduled | งานสถาปัตยกรรม ชั้นใต้ดิน | 398 days | 3 |  |  |  | August 19, 2019 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | November 18, 2019 05:00 PM | September 04, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 320 days | 12 days | 12 days
157 | Yes | CMU1.6.3.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 158,160,161 |  |  | August 21, 2020 8:00 AM | September 19, 2020 5:00 PM | September 10, 2020 05:00 PM | October 09, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | Skilled carpenter
158 | Yes | CMU1.6.3.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 154FS+45 days |  | 157,162 | June 22, 2020 8:00 AM | August 20, 2020 5:00 PM | June 26, 2020 05:00 PM | August 24, 2020 05:00 PM | February 09, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
159 | Yes | CMU1.6.3.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 154FS+45 days |  | 160,161 | June 22, 2020 8:00 AM | July 21, 2020 5:00 PM | July 12, 2020 05:00 PM | August 10, 2020 05:00 PM | August 22, 2020 05:00 PM | September 20, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
160 | Yes | CMU1.6.3.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 159 |  | 157,162 | July 22, 2020 8:00 AM | August 20, 2020 5:00 PM | August 11, 2020 05:00 PM | September 09, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | Skilled carpenter
161 | Yes | CMU1.6.3.5 | Auto Scheduled | งานบันได | 30 days | 4 | 159 |  | 157,162 | July 22, 2020 8:00 AM | August 20, 2020 5:00 PM | August 11, 2020 05:00 PM | September 09, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
162 | Yes | CMU1.6.3.6 | Auto Scheduled | งานสี | 30 days | 4 | 158,160,161 |  |  | August 21, 2020 8:00 AM | September 19, 2020 5:00 PM | September 10, 2020 05:00 PM | October 09, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
163 | Yes | CMU1.6.3.7 | Auto Scheduled | งานสุขภัณฑ์ | 15 days | 4 |  |  |  | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | October 20, 2018 05:00 PM | November 03, 2018 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 395 days | 395 days | 395 days
164 | Yes | CMU1.6.3.7.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 135FS+135 days |  |  | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | August 27, 2019 05:00 PM | September 10, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 395 days | 395 days | 395 days | Sanitary-Plumber
165 | Yes | CMU1.6.4 | Auto Scheduled | งานระบบสุขาภิบาล ชั้นใต้ดิน | 501 days | 3 |  |  |  | April 6, 2019 8:00 AM | August 18, 2020 5:00 PM | October 17, 2018 05:00 PM | February 29, 2020 05:00 PM | May 24, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 44 days | 44 days
166 | Yes | CMU1.6.4.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 126 days | 4 |  |  |  | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | October 23, 2018 05:00 PM | February 25, 2019 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 419 days | 419 days | 419 days
167 | Yes | CMU1.6.4.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 140FS+15 days |  |  | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 12, 2019 05:00 PM | August 15, 2019 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 419 days | 419 days | 419 days | Sanitary-Plumber
168 | Yes | CMU1.6.4.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 126 days | 4 |  |  |  | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | October 21, 2018 05:00 PM | February 23, 2019 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 44 days | 44 days
169 | Yes | CMU1.6.4.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 144FS+15 days |  | 170FS+300 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 06, 2019 05:00 PM | August 09, 2019 05:00 PM | May 24, 2019 05:00 PM | September 26, 2019 05:00 PM | As Soon As Possible |  | No | 44 days | 44 days | 0 days | Sanitary-Plumber
170 | Yes | CMU1.6.4.3 | Auto Scheduled | งานระบบระบายน้ำฝน | 75 days | 4 | 169FS+300 days |  |  | June 5, 2020 8:00 AM | August 18, 2020 5:00 PM | June 05, 2020 05:00 PM | August 18, 2020 05:00 PM | July 23, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 44 days | 44 days | 44 days | Sanitary-Plumber
171 | Yes | CMU1.6.5 | Auto Scheduled | งานระบบไฟฟ้า ชั้นใต้ดิน | 147 days | 3 |  |  |  | April 8, 2020 8:00 AM | September 1, 2020 5:00 PM | October 23, 2018 05:00 PM | March 18, 2019 05:00 PM | May 12, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 30 days | 30 days | 30 days
172 | Yes | CMU1.6.5.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 60 days | 4 | 174FS+7 days |  |  | July 4, 2020 8:00 AM | September 1, 2020 5:00 PM | July 08, 2020 05:00 PM | September 05, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 30 days | 30 days | 30 days | Electrician
173 | Yes | CMU1.6.5.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 60 days | 4 | 174FS+7 days |  |  | July 4, 2020 8:00 AM | September 1, 2020 5:00 PM | July 08, 2020 05:00 PM | September 05, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 30 days | 30 days | 30 days | Electrician
174 | Yes | CMU1.6.5.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 154SS |  | 173FS+7 days,172FS+7 days | April 8, 2020 8:00 AM | June 26, 2020 5:00 PM | April 12, 2020 05:00 PM | June 30, 2020 05:00 PM | May 12, 2020 05:00 PM | July 30, 2020 05:00 PM | As Soon As Possible |  | No | 30 days | 30 days | 0 days | Electrician
175 | Yes | CMU1.6.5.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 154SS |  |  | April 8, 2020 8:00 AM | June 26, 2020 5:00 PM | April 15, 2020 05:00 PM | July 03, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 97 days | 97 days | 97 days | Electrician
176 | Yes | CMU1.6.5.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 154SS |  |  | April 8, 2020 8:00 AM | June 26, 2020 5:00 PM | April 16, 2020 05:00 PM | July 04, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 97 days | 97 days | 97 days | Electrician
177 | Yes | CMU1.6.6 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้นใต้ดิน | 165 days | 3 | 154SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 12, 2020 05:00 PM | September 23, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | Skilled carpenter
178 | Yes | CMU1.7 | Auto Scheduled | หมวดงานระบบคอมพิวเตอร์และแจ้งเหตุเพลิงไหม้ | 670 days | 2 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
179 | Yes | CMU1.7.1 | Auto Scheduled | งานระบบคอมพิวเตอร์ | 670 days | 3 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
180 | Yes | CMU1.7.1.1 | Auto Scheduled | ชั้นที่ 4 | 160 days | 4 | 36FS+14 days |  | 181 | November 30, 2018 8:00 AM | May 8, 2019 5:00 PM | November 30, 2018 05:00 PM | May 08, 2019 05:00 PM | April 24, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
181 | Yes | CMU1.7.1.2 | Auto Scheduled | ชั้นที่ 3 | 175 days | 4 | 180 | 182 | 182 | May 9, 2019 8:00 AM | October 30, 2019 5:00 PM | May 09, 2019 05:00 PM | October 30, 2019 05:00 PM | April 09, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
182 | Yes | CMU1.7.1.3 | Auto Scheduled | ชั้นที่ 2 | 175 days | 4 | 181 | 183 | 183,184 | October 31, 2019 8:00 AM | April 22, 2020 5:00 PM | October 31, 2019 05:00 PM | April 22, 2020 05:00 PM | April 09, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
183 | Yes | CMU1.7.1.4 | Auto Scheduled | ชั้นที่ 1 | 160 days | 4 | 182 | 180 |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 23, 2020 05:00 PM | September 29, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
184 | Yes | CMU1.7.1.5 | Auto Scheduled | ชั้นใต้ดิน | 160 days | 4 | 182 | 183SS |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 23, 2020 05:00 PM | September 29, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
185 | Yes | CMU1.7.2 | Auto Scheduled | ระบบแจ้งเหตุเพลิงไหม้ | 670 days | 3 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
186 | Yes | CMU1.7.2.1 | Auto Scheduled | ชั้นที่ 4 | 160 days | 4 | 36FS+14 days |  | 187 | November 30, 2018 8:00 AM | May 8, 2019 5:00 PM | November 30, 2018 05:00 PM | May 08, 2019 05:00 PM | April 24, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
187 | Yes | CMU1.7.2.2 | Auto Scheduled | ชั้นที่ 3 | 175 days | 4 | 186 | 188 | 188 | May 9, 2019 8:00 AM | October 30, 2019 5:00 PM | May 09, 2019 05:00 PM | October 30, 2019 05:00 PM | April 09, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
188 | Yes | CMU1.7.2.3 | Auto Scheduled | ชั้นที่ 2 | 175 days | 4 | 187 | 189 | 189,190 | October 31, 2019 8:00 AM | April 22, 2020 5:00 PM | October 31, 2019 05:00 PM | April 22, 2020 05:00 PM | April 09, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
189 | Yes | CMU1.7.2.4 | Auto Scheduled | ชั้นที่ 1 | 160 days | 4 | 188 | 186 |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 23, 2020 05:00 PM | September 29, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
190 | Yes | CMU1.7.2.5 | Auto Scheduled | ชั้นใต้ดิน | 160 days | 4 | 188 | 189SS |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 23, 2020 05:00 PM | September 29, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
191 | Yes | CMU1.8 | Auto Scheduled | หมวดงานสีภายนอก งานซ่อมแซมและตกแต่งภายนอกอาคาร | 660 days | 2 |  |  |  | November 30, 2018 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | August 06, 2020 05:00 PM | December 16, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 507 days | 12 days | 12 days
192 | Yes | CMU1.8.1 | Auto Scheduled | งานสีภายนอกและงานซ่อมแซมพื้นผิวภายนอกอาคาร | 660 days | 3 |  |  |  | November 30, 2018 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | August 06, 2020 05:00 PM | December 16, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 507 days | 12 days | 12 days
193 | Yes | CMU1.8.1.1 | Auto Scheduled | งานขัดลอกสีทาผนังเดิม | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 12, 2020 05:00 PM | September 23, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
194 | Yes | CMU1.8.1.2 | Auto Scheduled | น้ำยาทาปูนเก่า (สีรองพื้น) | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 12, 2020 05:00 PM | September 23, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
195 | Yes | CMU1.8.1.3 | Auto Scheduled | งานทาสีภายนอก (ทา 2 เที่ยว) ไม่รวมชั้นใต้ดิน | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 12, 2020 05:00 PM | September 23, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
196 | Yes | CMU1.8.1.4 | Auto Scheduled | งานทำความสะอาดและซ่อมแซมผนังกรุอิฐโชว์แนว (อ้างอิงราคางานขัดลอกสี) | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 12, 2020 05:00 PM | September 23, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
197 | Yes | CMU1.8.1.5 | Auto Scheduled | น้ำยาเคลือบผิวผนังอิฐโชว์แนว (อ้างอิงค่าทาน้ำยากันเชื้อรา) | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 12, 2020 05:00 PM | September 23, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
198 | Yes | CMU1.8.1.6 | Auto Scheduled | งานรื้อถอนแผ่นวัสดุกันซึมหลังคาดาดฟ้า (รื้อขนไป) | 90 days | 4 | 36FS+14 days |  |  | November 30, 2018 8:00 AM | February 27, 2019 5:00 PM | December 03, 2018 05:00 PM | March 02, 2019 05:00 PM | July 08, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 582 days | 582 days | 582 days | General worker
199 | Yes | CMU1.8.1.7 | Auto Scheduled | งานแผ่นวัสดุกันซึมแบบเป่าไฟผิวทราย | 90 days | 4 | 36FS+14 days |  |  | November 30, 2018 8:00 AM | February 27, 2019 5:00 PM | December 04, 2018 05:00 PM | March 03, 2019 05:00 PM | July 08, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 582 days | 582 days | 582 days | General worker
200 | Yes | CMU1.8.1.8 | Auto Scheduled | งานกันซึมชนิด Polyurethane สูตรน้ำมัน ชนิดยืดหยุ่นสูงเป็นพิเศษ | 90 days | 4 | 36FS+14 days |  |  | November 30, 2018 8:00 AM | February 27, 2019 5:00 PM | December 03, 2018 05:00 PM | March 02, 2019 05:00 PM | July 08, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 582 days | 582 days | 582 days | General worker
201 | Yes | CMU1.8.2 | Auto Scheduled | งานตกแต่งภายนอกอาคาร | 165 days | 3 |  |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | October 20, 2018 05:00 PM | April 02, 2019 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 12 days | 12 days | 12 days
202 | Yes | CMU1.8.2.1 | Auto Scheduled | ตะแกรงเหล็กฉีกกันนก XS-32 | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 12, 2020 05:00 PM | September 23, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
203 | Yes | CMU1.9 | Auto Scheduled | หมวดงานบริเวณ | 165 days | 2 |  |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | October 22, 2018 05:00 PM | April 04, 2019 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 12 days | 12 days | 12 days
204 | Yes | CMU1.9.1 | Auto Scheduled | งานรื้อถอน งานบริเวณ | 165 days | 3 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 12, 2020 05:00 PM | September 23, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
205 | Yes | CMU1.9.2 | Auto Scheduled | งานโครงสร้างวิศวกรรม งานบริเวณ | 165 days | 3 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 12, 2020 05:00 PM | September 23, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
206 | Yes | CMU1.9.3 | Auto Scheduled | งานสถาปัตยกรรม งานบริเวณ | 165 days | 3 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 12, 2020 05:00 PM | September 23, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
207 | Yes | CMU1.9.4 | Auto Scheduled | งานระบบไฟฟ้า งานบริเวณ | 165 days | 3 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 12, 2020 05:00 PM | September 23, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | Electrician
208 | Yes | CMU1.10 | Auto Scheduled | หมวดงานครุภัณฑ์จัดซื้อ | 670 days | 2 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
209 | Yes | CMU1.10.1 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัว | 510 days | 3 |  |  |  | April 14, 2019 8:00 AM | September 4, 2020 5:00 PM | October 17, 2018 05:00 PM | March 09, 2020 05:00 PM | May 15, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 522 days | 27 days | 27 days
210 | Yes | CMU1.10.1.1 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้นใต้ดิน | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | August 29, 2020 05:00 PM | September 12, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
211 | Yes | CMU1.10.1.2 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้น 1 | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | September 05, 2020 05:00 PM | September 19, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
212 | Yes | CMU1.10.1.3 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้น 2 | 15 days | 4 | 121FS-15 days |  |  | March 24, 2020 8:00 AM | April 7, 2020 5:00 PM | March 30, 2020 05:00 PM | April 13, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Skilled carpenter
213 | Yes | CMU1.10.1.4 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้น 3 | 15 days | 4 | 92FS-15 days |  |  | September 26, 2019 8:00 AM | October 10, 2019 5:00 PM | October 05, 2019 05:00 PM | October 19, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Skilled carpenter
214 | Yes | CMU1.10.1.5 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้น 4 | 15 days | 4 | 63 |  |  | April 14, 2019 8:00 AM | April 28, 2019 5:00 PM | April 24, 2019 05:00 PM | May 08, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 522 days | 522 days | 522 days | Skilled carpenter
215 | Yes | CMU1.10.2 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ | 525 days | 3 |  |  |  | March 30, 2019 8:00 AM | September 4, 2020 5:00 PM | October 17, 2018 05:00 PM | March 24, 2020 05:00 PM | April 30, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 522 days | 27 days | 27 days
216 | Yes | CMU1.10.2.1 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ ชั้น 1 | 30 days | 4 | 152FS-45 days |  |  | August 6, 2020 8:00 AM | September 4, 2020 5:00 PM | August 16, 2020 05:00 PM | September 14, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
217 | Yes | CMU1.10.2.2 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ ชั้น 2 | 30 days | 4 | 121FS-30 days |  |  | March 9, 2020 8:00 AM | April 7, 2020 5:00 PM | March 16, 2020 05:00 PM | April 14, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Skilled carpenter
218 | Yes | CMU1.10.2.3 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ ชั้น 3 | 30 days | 4 | 92FS-30 days |  |  | September 11, 2019 8:00 AM | October 10, 2019 5:00 PM | September 18, 2019 05:00 PM | October 17, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Skilled carpenter
219 | Yes | CMU1.10.2.4 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ ชั้น 4 | 30 days | 4 | 63FS-15 days |  |  | March 30, 2019 8:00 AM | April 28, 2019 5:00 PM | April 02, 2019 05:00 PM | May 01, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 522 days | 522 days | 522 days | Skilled carpenter
220 | Yes | CMU1.10.3 | Auto Scheduled | งานผ้าม่าน | 510 days | 3 |  |  |  | April 14, 2019 8:00 AM | September 4, 2020 5:00 PM | October 17, 2018 05:00 PM | March 09, 2020 05:00 PM | May 15, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 522 days | 27 days | 27 days
221 | Yes | CMU1.10.3.1 | Auto Scheduled | งานผ้าม่าน ชั้น 1 | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | August 30, 2020 05:00 PM | September 13, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
222 | Yes | CMU1.10.3.2 | Auto Scheduled | งานผ้าม่าน ชั้น 2 | 15 days | 4 | 121FS-15 days |  |  | March 24, 2020 8:00 AM | April 7, 2020 5:00 PM | March 31, 2020 05:00 PM | April 14, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Skilled carpenter
223 | Yes | CMU1.10.3.3 | Auto Scheduled | งานผ้าม่าน ชั้น 3 | 15 days | 4 | 92FS-15 days |  |  | September 26, 2019 8:00 AM | October 10, 2019 5:00 PM | October 03, 2019 05:00 PM | October 17, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Skilled carpenter
224 | Yes | CMU1.10.3.4 | Auto Scheduled | งานผ้าม่าน ชั้น 4 | 15 days | 4 | 63 |  |  | April 14, 2019 8:00 AM | April 28, 2019 5:00 PM | April 24, 2019 05:00 PM | May 08, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 522 days | 522 days | 522 days | Skilled carpenter
225 | Yes | CMU1.10.4 | Auto Scheduled | งานป้าย | 510 days | 3 |  |  |  | April 14, 2019 8:00 AM | September 4, 2020 5:00 PM | October 17, 2018 05:00 PM | March 09, 2020 05:00 PM | May 15, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 522 days | 27 days | 27 days
226 | Yes | CMU1.10.4.1 | Auto Scheduled | งานป้าย ชั้นใต้ดิน | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | August 29, 2020 05:00 PM | September 12, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
227 | Yes | CMU1.10.4.2 | Auto Scheduled | งานป้าย ชั้น 1 | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | September 01, 2020 05:00 PM | September 15, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
228 | Yes | CMU1.10.4.3 | Auto Scheduled | งานป้าย ชั้น 2 | 15 days | 4 | 121FS-15 days |  |  | March 24, 2020 8:00 AM | April 7, 2020 5:00 PM | March 31, 2020 05:00 PM | April 14, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Skilled carpenter
229 | Yes | CMU1.10.4.4 | Auto Scheduled | งานป้าย ชั้น 3 | 15 days | 4 | 92FS-15 days |  |  | September 26, 2019 8:00 AM | October 10, 2019 5:00 PM | October 04, 2019 05:00 PM | October 18, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Skilled carpenter
230 | Yes | CMU1.10.4.5 | Auto Scheduled | งานป้าย ชั้น 4 | 15 days | 4 | 63 |  |  | April 14, 2019 8:00 AM | April 28, 2019 5:00 PM | April 19, 2019 05:00 PM | May 03, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 522 days | 522 days | 522 days | Skilled carpenter
231 | Yes | CMU1.10.5 | Auto Scheduled | งานอื่นๆ | 15 days | 3 |  |  |  | August 6, 2020 8:00 AM | August 20, 2020 5:00 PM | October 20, 2018 05:00 PM | November 03, 2018 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 42 days | 42 days | 42 days
232 | Yes | CMU1.10.5.1 | Auto Scheduled | ตู้อลูมิเนียมพับขึ้นรูป พ่นสี ครอบตู้กดน้ำ | 15 days | 4 | 152FS-45 days |  |  | August 6, 2020 8:00 AM | August 20, 2020 5:00 PM | August 15, 2020 05:00 PM | August 29, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 42 days | 42 days | 42 days | General worker
233 | Yes | CMU1.10.6 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ | 670 days | 3 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
234 | Yes | CMU1.10.6.1 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้นใต้ดิน | 160 days | 4 | 236 |  |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 28, 2020 05:00 PM | October 04, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
235 | Yes | CMU1.10.6.2 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้น 1 | 160 days | 4 | 236 |  |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 28, 2020 05:00 PM | October 04, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
236 | Yes | CMU1.10.6.3 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้น 2 | 175 days | 4 | 237 |  | 235,234 | October 31, 2019 8:00 AM | April 22, 2020 5:00 PM | November 05, 2019 05:00 PM | April 27, 2020 05:00 PM | March 12, 2020 05:00 PM | September 02, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
237 | Yes | CMU1.10.6.4 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้น 3 | 175 days | 4 | 238 |  | 236 | May 9, 2019 8:00 AM | October 30, 2019 5:00 PM | May 14, 2019 05:00 PM | November 04, 2019 05:00 PM | March 12, 2020 05:00 PM | September 02, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
238 | Yes | CMU1.10.6.5 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้น 4 | 160 days | 4 | 36FS+14 days |  | 237 | November 30, 2018 8:00 AM | May 8, 2019 5:00 PM | December 02, 2018 05:00 PM | May 10, 2019 05:00 PM | March 27, 2020 05:00 PM | September 02, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
239 | Yes | CMU1.10.7 | Auto Scheduled | งานระบบเครื่องเสียงประกาศ (ใช้ลำโพงของเดิม) | 539 days | 3 |  |  |  | April 7, 2019 8:00 AM | September 26, 2020 5:00 PM | October 17, 2018 05:00 PM | April 07, 2020 05:00 PM | April 16, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 530 days | 5 days | 5 days
240 | Yes | CMU1.10.7.1 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้นใต้ดิน | 7 days | 4 | 241 |  |  | September 20, 2020 8:00 AM | September 26, 2020 5:00 PM | September 28, 2020 05:00 PM | October 04, 2020 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 5 days | 5 days | 5 days | Electrician
241 | Yes | CMU1.10.7.2 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้น 1 | 7 days | 4 | 152FS-7 days |  | 240 | September 13, 2020 8:00 AM | September 19, 2020 5:00 PM | September 17, 2020 05:00 PM | September 23, 2020 05:00 PM | September 09, 2020 05:00 PM | September 15, 2020 05:00 PM | As Soon As Possible |  | No | 5 days | 5 days | 0 days | Electrician
242 | Yes | CMU1.10.7.3 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้น 2 | 7 days | 4 | 121FS-7 days |  |  | April 1, 2020 8:00 AM | April 7, 2020 5:00 PM | April 07, 2020 05:00 PM | April 13, 2020 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Electrician
243 | Yes | CMU1.10.7.4 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้น 3 | 7 days | 4 | 92FS-7 days |  |  | October 4, 2019 8:00 AM | October 10, 2019 5:00 PM | October 12, 2019 05:00 PM | October 18, 2019 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Electrician
244 | Yes | CMU1.10.7.5 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้น 4 | 7 days | 4 | 63FS-7 days |  |  | April 7, 2019 8:00 AM | April 13, 2019 5:00 PM | April 12, 2019 05:00 PM | April 18, 2019 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 537 days | 537 days | 537 days | Electrician
245 | Yes | CMU1.10.8 | Auto Scheduled | งานระบบกล้องวงจรปิด (ใช้กล้องวงจรปิดของเดิม) | 539 days | 3 |  |  |  | April 7, 2019 8:00 AM | September 26, 2020 5:00 PM | October 17, 2018 05:00 PM | April 07, 2020 05:00 PM | April 16, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 530 days | 5 days | 5 days
246 | Yes | CMU1.10.8.1 | Auto Scheduled | งานกล้องวงจรปิด ชั้นใต้ดิน | 7 days | 4 | 247 |  |  | September 20, 2020 8:00 AM | September 26, 2020 5:00 PM | September 28, 2020 05:00 PM | October 04, 2020 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 5 days | 5 days | 5 days | Electrician
247 | Yes | CMU1.10.8.2 | Auto Scheduled | งานกล้องวงจรปิด ชั้น 1 | 7 days | 4 | 152FS-7 days |  | 246 | September 13, 2020 8:00 AM | September 19, 2020 5:00 PM | September 17, 2020 05:00 PM | September 23, 2020 05:00 PM | September 09, 2020 05:00 PM | September 15, 2020 05:00 PM | As Soon As Possible |  | No | 5 days | 5 days | 0 days | Electrician
248 | Yes | CMU1.10.8.3 | Auto Scheduled | งานกล้องวงจรปิด ชั้น 2 | 7 days | 4 | 121FS-7 days |  |  | April 1, 2020 8:00 AM | April 7, 2020 5:00 PM | April 08, 2020 05:00 PM | April 14, 2020 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Electrician
249 | Yes | CMU1.10.8.4 | Auto Scheduled | งานกล้องวงจรปิด ชั้น 3 | 7 days | 4 | 92FS-7 days |  |  | October 4, 2019 8:00 AM | October 10, 2019 5:00 PM | October 13, 2019 05:00 PM | October 19, 2019 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Electrician
250 | Yes | CMU1.10.8.5 | Auto Scheduled | งานกล้องวงจรปิด ชั้น 4 | 7 days | 4 | 63FS-7 days |  |  | April 7, 2019 8:00 AM | April 13, 2019 5:00 PM | April 11, 2019 05:00 PM | April 17, 2019 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 537 days | 537 days | 537 days | Electrician

## solutoion_9
ID | Active | WBS | Task_Mode | Name | Duration | Outline_Level | Predecessors | Predecessors2 | Successors | Start_Date | Finish_Date | Early_Start | Early_Finish | Late_Start | Late_Finish | Constraint_Type | Constraint_Date | Summary | Start_Slack | Finish_Slack | Free_Slack | Resource_Names
1 | Yes | CMU1 | Auto Scheduled | โครงการปรับปรุงสำนักหอสมุด มหาวิทยาลัยเชียงใหม่ | 716 days | 1 |  |  |  | October 17, 2018 8:00 AM | October 1, 2020 5:00 PM | October 17, 2018 05:00 PM | October 01, 2020 05:00 PM | October 21, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 0 days | 0 days | 0 days
2 | Yes | CMU1.1 | Auto Scheduled | หมวดเตรียมการ | 675 days | 2 |  |  |  | October 17, 2018 8:00 AM | August 21, 2020 5:00 PM | October 17, 2018 05:00 PM | August 21, 2020 05:00 PM | December 01, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 41 days | 41 days | 41 days
3 | Yes | CMU1.1.1 | Auto Scheduled | งานอาคารสนามและผังบริเวณโครงการ | 14 days | 3 | 4FS-7 days |  |  | October 26, 2018 8:00 AM | November 8, 2018 5:00 PM | November 01, 2018 05:00 PM | November 14, 2018 05:00 PM | September 22, 2020 05:00 PM | October 05, 2020 05:00 PM | Start No Earlier Than | Oct 24 '18 | No | 693 days | 693 days | 693 days | Engineer
4 | Yes | CMU1.1.2 | Auto Scheduled | งานเชื่อมต่อระบบสาธารณูปโภคโครงการ | 16 days | 3 |  |  | 3FS-7 days | October 17, 2018 8:00 AM | November 1, 2018 5:00 PM | October 19, 2018 05:00 PM | November 03, 2018 05:00 PM | September 13, 2020 05:00 PM | September 28, 2020 05:00 PM | As Soon As Possible |  | No | 693 days | 693 days | 0 days | Engineer
5 | Yes | CMU1.1.3 | Auto Scheduled | งานตรวจทดสอบระบบภายในอาคารก่อนดำเนินการปรับปรุง | 675 days | 3 |  |  |  | October 17, 2018 8:00 AM | August 21, 2020 5:00 PM | October 17, 2018 05:00 PM | August 21, 2020 05:00 PM | December 01, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 41 days | 41 days | 41 days
6 | Yes | CMU1.1.3.1 | Auto Scheduled | ชั้นที่ 4 | 15 days | 4 |  |  | 7FS+150 days | October 17, 2018 8:00 AM | October 31, 2018 5:00 PM | October 19, 2018 05:00 PM | November 02, 2018 05:00 PM | December 01, 2018 05:00 PM | December 15, 2018 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
7 | Yes | CMU1.1.3.2 | Auto Scheduled | ชั้นที่ 3 | 15 days | 4 | 6FS+150 days |  | 8FS+150 days | March 31, 2019 8:00 AM | April 14, 2019 5:00 PM | April 07, 2019 05:00 PM | April 21, 2019 05:00 PM | May 15, 2019 05:00 PM | May 29, 2019 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
8 | Yes | CMU1.1.3.3 | Auto Scheduled | ชั้นที่ 2 | 15 days | 4 | 7FS+150 days |  | 9FS+150 days | September 12, 2019 8:00 AM | September 26, 2019 5:00 PM | September 29, 2019 05:00 PM | October 13, 2019 05:00 PM | October 27, 2019 05:00 PM | November 10, 2019 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
9 | Yes | CMU1.1.3.4 | Auto Scheduled | ชั้นที่ 1 | 15 days | 4 | 8FS+150 days |  | 10FS+150 days | February 24, 2020 8:00 AM | March 9, 2020 5:00 PM | March 20, 2020 05:00 PM | April 03, 2020 05:00 PM | April 09, 2020 05:00 PM | April 23, 2020 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
10 | Yes | CMU1.1.3.5 | Auto Scheduled | ชั้นใต้ดินและภายนอก | 15 days | 4 | 9FS+150 days |  |  | August 7, 2020 8:00 AM | August 21, 2020 5:00 PM | September 12, 2020 05:00 PM | September 26, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 41 days | Engineer
11 | Yes | CMU1.1.4 | Auto Scheduled | งานสำรวจอุปกรณ์ไฟฟ้า, สุขภัณฑ์และครุภัณฑ์ (ของเดิม) ก่อนดำเนินการปรับปรุง | 675 days | 3 |  |  |  | October 17, 2018 8:00 AM | August 21, 2020 5:00 PM | October 17, 2018 05:00 PM | August 21, 2020 05:00 PM | December 01, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 41 days | 41 days | 41 days
12 | Yes | CMU1.1.4.1 | Auto Scheduled | ชั้นที่ 4 | 15 days | 4 |  |  | 13FS+150 days | October 17, 2018 8:00 AM | October 31, 2018 5:00 PM | October 20, 2018 05:00 PM | November 03, 2018 05:00 PM | December 01, 2018 05:00 PM | December 15, 2018 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
13 | Yes | CMU1.1.4.2 | Auto Scheduled | ชั้นที่ 3 | 15 days | 4 | 12FS+150 days |  | 14FS+150 days | March 31, 2019 8:00 AM | April 14, 2019 5:00 PM | April 06, 2019 05:00 PM | April 20, 2019 05:00 PM | May 15, 2019 05:00 PM | May 29, 2019 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
14 | Yes | CMU1.1.4.3 | Auto Scheduled | ชั้นที่ 2 | 15 days | 4 | 13FS+150 days |  | 15FS+150 days | September 12, 2019 8:00 AM | September 26, 2019 5:00 PM | September 24, 2019 05:00 PM | October 08, 2019 05:00 PM | October 27, 2019 05:00 PM | November 10, 2019 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
15 | Yes | CMU1.1.4.4 | Auto Scheduled | ชั้นที่ 1 | 15 days | 4 | 14FS+150 days |  | 16FS+150 days | February 24, 2020 8:00 AM | March 9, 2020 5:00 PM | March 14, 2020 05:00 PM | March 28, 2020 05:00 PM | April 09, 2020 05:00 PM | April 23, 2020 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
16 | Yes | CMU1.1.4.5 | Auto Scheduled | ชั้นใต้ดินและภายนอก | 15 days | 4 | 15FS+150 days |  |  | August 7, 2020 8:00 AM | August 21, 2020 5:00 PM | September 06, 2020 05:00 PM | September 20, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 41 days | Engineer
17 | Yes | CMU1.1.5 | Auto Scheduled | งานเอกสารขออนุมัติใช้วัสดุ, Shop Drawing และครุภัณฑ์ของโครงการ | 106 days | 3 |  |  |  | October 17, 2018 8:00 AM | January 30, 2019 5:00 PM | October 22, 2018 05:00 PM | February 04, 2019 05:00 PM | June 22, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 610 days | 610 days | 610 days
18 | Yes | CMU1.1.5.1 | Auto Scheduled | แบบ Shop Drawing ชั้นที่ 4 | 20 days | 4 |  |  | 19,25SS+14 days,26SS+14 days | October 17, 2018 8:00 AM | November 5, 2018 5:00 PM | October 17, 2018 05:00 PM | November 05, 2018 05:00 PM | October 01, 2018 05:00 PM | October 20, 2018 05:00 PM | As Soon As Possible |  | No | 610 days | 610 days | 0 days | Engineer
19 | Yes | CMU1.1.5.2 | Auto Scheduled | แบบ Shop Drawing ชั้นที่ 3 | 20 days | 4 | 18 |  | 20FS-7 days | November 6, 2018 8:00 AM | November 25, 2018 5:00 PM | November 13, 2018 05:00 PM | December 02, 2018 05:00 PM | July 13, 2020 05:00 PM | August 01, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
20 | Yes | CMU1.1.5.3 | Auto Scheduled | แบบ Shop Drawing ชั้นที่ 2 | 20 days | 4 | 19FS-7 days |  | 21FS-7 days | November 19, 2018 8:00 AM | December 8, 2018 5:00 PM | November 29, 2018 05:00 PM | December 18, 2018 05:00 PM | July 26, 2020 05:00 PM | August 14, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
21 | Yes | CMU1.1.5.4 | Auto Scheduled | แบบ Shop Drawing ชั้นที่ 1 | 20 days | 4 | 20FS-7 days |  | 22FS-7 days | December 2, 2018 8:00 AM | December 21, 2018 5:00 PM | December 18, 2018 05:00 PM | January 06, 2019 05:00 PM | August 08, 2020 05:00 PM | August 27, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
22 | Yes | CMU1.1.5.5 | Auto Scheduled | แบบ Shop Drawing ชั้นใต้ดิน | 20 days | 4 | 21FS-7 days |  | 23FS-7 days | December 15, 2018 8:00 AM | January 3, 2019 5:00 PM | January 07, 2019 05:00 PM | January 26, 2019 05:00 PM | August 21, 2020 05:00 PM | September 09, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
23 | Yes | CMU1.1.5.6 | Auto Scheduled | แบบ Shop Drawing ภายนอกอาคาร | 20 days | 4 | 22FS-7 days |  | 24FS-7 days | December 28, 2018 8:00 AM | January 16, 2019 5:00 PM | January 27, 2019 05:00 PM | February 15, 2019 05:00 PM | September 03, 2020 05:00 PM | September 22, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
24 | Yes | CMU1.1.5.7 | Auto Scheduled | แบบ Shop Drawing landscape | 20 days | 4 | 23FS-7 days |  |  | January 10, 2019 8:00 AM | January 29, 2019 5:00 PM | February 16, 2019 05:00 PM | March 07, 2019 05:00 PM | September 16, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 611 days | Engineer
25 | Yes | CMU1.1.5.8 | Auto Scheduled | แบบ Shop Drawing งานปรับปรุง ครุภัณฑ์ | 92 days | 4 | 18SS+14 days |  |  | October 31, 2018 8:00 AM | January 30, 2019 5:00 PM | November 07, 2018 05:00 PM | February 06, 2019 05:00 PM | July 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 610 days | 610 days | 610 days | Engineer
26 | Yes | CMU1.1.5.9 | Auto Scheduled | แบบ Shop Drawing งานจัดซื้อครุภัณฑ์ | 92 days | 4 | 18SS+14 days |  |  | October 31, 2018 8:00 AM | January 30, 2019 5:00 PM | November 08, 2018 05:00 PM | February 07, 2019 05:00 PM | July 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 610 days | 610 days | 610 days | Engineer
27 | Yes | CMU1.1.6 | Auto Scheduled | งานตรวจทดสอบระบบ, งานอบรมผู้ใช้อาคาร และ As-Built Drawing | 30 days | 3 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 23, 2018 05:00 PM | November 21, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 686 days | 686 days | 686 days
28 | Yes | CMU1.1.6.1 | Auto Scheduled | ชั้นที่ 4 | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 27, 2018 05:00 PM | November 25, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
29 | Yes | CMU1.1.6.2 | Auto Scheduled | ชั้นที่ 3 | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 27, 2018 05:00 PM | November 25, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
30 | Yes | CMU1.1.6.3 | Auto Scheduled | ชั้นที่ 2 | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 22, 2018 05:00 PM | November 20, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
31 | Yes | CMU1.1.6.4 | Auto Scheduled | ชั้นที่ 1 | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 29, 2018 05:00 PM | November 27, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
32 | Yes | CMU1.1.6.5 | Auto Scheduled | ชั้นใต้ดิน | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 25, 2018 05:00 PM | November 23, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
33 | Yes | CMU1.1.6.6 | Auto Scheduled | ทั้งอาคาร | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 23, 2018 05:00 PM | November 21, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
34 | Yes | CMU1.1.7 | Auto Scheduled | งานบริหารงานก่อสร้างและงานอื่น ๆ | 0 days | 3 |  |  |  | October 17, 2018 8:00 AM | October 17, 2018 8:00 AM | October 20, 2018 05:00 PM | October 19, 2018 05:00 PM | October 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 716 days | 716 days | 716 days | Engineer
35 | Yes | CMU1.2 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้น 4 | 471 days | 2 |  |  |  | October 17, 2018 8:00 AM | January 30, 2020 5:00 PM | October 17, 2018 05:00 PM | January 30, 2020 05:00 PM | June 23, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 0 days | 245 days | 0 days
36 | Yes | CMU1.2.1 | Auto Scheduled | งานรื้อถอน ชั้น 4 (รื้อขนไป) | 30 days | 3 |  |  | 39FS+45 days,40FS+45 days,51,63SS+14 days,80,109,140,180FS+14 days,186FS+14 days,198FS+14 days,199FS+14 days,200FS+14 days,238FS+14 days | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 17, 2018 05:00 PM | November 15, 2018 05:00 PM | March 11, 2018 05:00 PM | April 09, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | General worker
37 | Yes | CMU1.2.2 | Auto Scheduled | งานสถาปัตยกรรม ชั้น 4 | 396 days | 3 |  |  |  | December 31, 2018 8:00 AM | January 30, 2020 5:00 PM | October 17, 2018 05:00 PM | November 16, 2019 05:00 PM | September 06, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 326 days | 245 days | 245 days
38 | Yes | CMU1.2.2.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 39,41,42 |  |  | March 1, 2019 8:00 AM | March 30, 2019 5:00 PM | March 14, 2019 05:00 PM | April 12, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 551 days | Skilled carpenter
39 | Yes | CMU1.2.2.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 36FS+45 days |  | 38,43 | December 31, 2018 8:00 AM | February 28, 2019 5:00 PM | January 05, 2019 05:00 PM | March 05, 2019 05:00 PM | July 15, 2020 05:00 PM | September 12, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 0 days | General worker
40 | Yes | CMU1.2.2.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 36FS+45 days |  | 41,42 | December 31, 2018 8:00 AM | January 29, 2019 5:00 PM | January 03, 2019 05:00 PM | February 01, 2019 05:00 PM | August 14, 2020 05:00 PM | September 12, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 0 days | General worker
41 | Yes | CMU1.2.2.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 40 |  | 38,43 | January 30, 2019 8:00 AM | February 28, 2019 5:00 PM | February 05, 2019 05:00 PM | March 06, 2019 05:00 PM | August 14, 2020 05:00 PM | September 12, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 0 days | Skilled carpenter
42 | Yes | CMU1.2.2.5 | Auto Scheduled | งานบันได | 30 days | 4 | 40 |  | 38,43 | January 30, 2019 8:00 AM | February 28, 2019 5:00 PM | February 05, 2019 05:00 PM | March 06, 2019 05:00 PM | August 14, 2020 05:00 PM | September 12, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 0 days | General worker
43 | Yes | CMU1.2.2.6 | Auto Scheduled | งานสี | 30 days | 4 | 39,41,42 |  |  | March 1, 2019 8:00 AM | March 30, 2019 5:00 PM | March 10, 2019 05:00 PM | April 08, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 551 days | General worker
44 | Yes | CMU1.2.2.7 | Auto Scheduled | งานสุขภัณฑ์ | 315 days | 4 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 20, 2018 05:00 PM | August 30, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
45 | Yes | CMU1.2.2.7.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 46FS+135 days |  | 47FS+135 days | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | September 16, 2019 05:00 PM | September 30, 2019 05:00 PM | April 24, 2020 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
46 | Yes | CMU1.2.2.7.2 | Auto Scheduled | ZONE T-2 กลาง | 15 days | 5 | 51,55 |  | 45FS+135 days | March 22, 2019 8:00 AM | April 5, 2019 5:00 PM | April 13, 2019 05:00 PM | April 27, 2019 05:00 PM | November 26, 2019 05:00 PM | December 10, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
47 | Yes | CMU1.2.2.7.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 15 days | 5 | 45FS+135 days |  |  | January 16, 2020 8:00 AM | January 30, 2020 5:00 PM | February 20, 2020 05:00 PM | March 05, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 245 days | Sanitary-Plumber
48 | Yes | CMU1.2.3 | Auto Scheduled | งานระบบสุขาภิบาล ชั้น 4 | 408 days | 3 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
49 | Yes | CMU1.2.3.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
50 | Yes | CMU1.2.3.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 51FS+15 days |  | 52FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 18, 2019 05:00 PM | August 21, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
51 | Yes | CMU1.2.3.1.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 36 |  | 50FS+15 days,46,55SS | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 23, 2018 05:00 PM | March 28, 2019 05:00 PM | August 25, 2019 05:00 PM | December 28, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
52 | Yes | CMU1.2.3.1.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 50FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 10, 2019 05:00 PM | January 13, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
53 | Yes | CMU1.2.3.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
54 | Yes | CMU1.2.3.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 55FS+15 days |  | 56FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 30, 2019 05:00 PM | September 02, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
55 | Yes | CMU1.2.3.2.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 51SS |  | 54FS+15 days,46 | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | December 03, 2018 05:00 PM | April 07, 2019 05:00 PM | August 25, 2019 05:00 PM | December 28, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
56 | Yes | CMU1.2.3.2.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 54FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | October 01, 2019 05:00 PM | February 03, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
57 | Yes | CMU1.2.4 | Auto Scheduled | งานระบบไฟฟ้า ชั้น 4 | 117 days | 3 |  |  |  | November 30, 2018 8:00 AM | March 26, 2019 5:00 PM | October 21, 2018 05:00 PM | February 14, 2019 05:00 PM | June 11, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 555 days | 555 days | 555 days
58 | Yes | CMU1.2.4.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 30 days | 4 | 60FS+7 days |  |  | February 25, 2019 8:00 AM | March 26, 2019 5:00 PM | March 03, 2019 05:00 PM | April 01, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 555 days | 555 days | 555 days | Electrician
59 | Yes | CMU1.2.4.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 30 days | 4 | 60FS+7 days |  |  | February 25, 2019 8:00 AM | March 26, 2019 5:00 PM | March 04, 2019 05:00 PM | April 02, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 555 days | 555 days | 555 days | Electrician
60 | Yes | CMU1.2.4.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 63SS+30 days |  | 58FS+7 days,59FS+7 days | November 30, 2018 8:00 AM | February 17, 2019 5:00 PM | December 03, 2018 05:00 PM | February 20, 2019 05:00 PM | June 11, 2020 05:00 PM | August 29, 2020 05:00 PM | As Soon As Possible |  | No | 555 days | 555 days | 0 days | Electrician
61 | Yes | CMU1.2.4.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 63SS+30 days |  |  | November 30, 2018 8:00 AM | February 17, 2019 5:00 PM | December 03, 2018 05:00 PM | February 20, 2019 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 592 days | 592 days | 592 days | Electrician
62 | Yes | CMU1.2.4.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 63SS+30 days |  |  | November 30, 2018 8:00 AM | February 17, 2019 5:00 PM | December 04, 2018 05:00 PM | February 21, 2019 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 592 days | 592 days | 592 days | Electrician
63 | Yes | CMU1.2.5 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้น 4 | 165 days | 3 | 36SS+14 days |  | 62SS+30 days,60SS+30 days,61SS+30 days,65,214,219FS-15 days,224,230,244FS-7 days,250FS-7 days | October 31, 2018 8:00 AM | April 13, 2019 5:00 PM | October 31, 2018 05:00 PM | April 13, 2019 05:00 PM | June 19, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Skilled carpenter
64 | Yes | CMU1.3 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้น 3 | 441 days | 2 |  |  |  | November 16, 2018 8:00 AM | January 30, 2020 5:00 PM | October 17, 2018 05:00 PM | December 31, 2019 05:00 PM | July 23, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 149 days | 245 days | 149 days
65 | Yes | CMU1.3.1 | Auto Scheduled | งานรื้อถอน ชั้น 3 (รื้อขนไป) | 30 days | 3 | 63 | 121 | 68FS+45 days,69FS+45 days,92SS | April 14, 2019 8:00 AM | May 13, 2019 5:00 PM | April 14, 2019 05:00 PM | May 13, 2019 05:00 PM | July 19, 2018 05:00 PM | August 17, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | General worker
66 | Yes | CMU1.3.2 | Auto Scheduled | งานสถาปัตยกรรม ชั้น 3 | 315 days | 3 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 23, 2018 05:00 PM | September 02, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
67 | Yes | CMU1.3.2.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 68,70,71 |  |  | August 27, 2019 8:00 AM | September 25, 2019 5:00 PM | August 30, 2019 05:00 PM | September 28, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 372 days | Skilled carpenter
68 | Yes | CMU1.3.2.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 65FS+45 days |  | 67,72 | June 28, 2019 8:00 AM | August 26, 2019 5:00 PM | June 28, 2019 05:00 PM | August 26, 2019 05:00 PM | October 02, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 0 days | General worker
69 | Yes | CMU1.3.2.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 65FS+45 days |  | 70,71 | June 28, 2019 8:00 AM | July 27, 2019 5:00 PM | June 28, 2019 05:00 PM | July 27, 2019 05:00 PM | April 15, 2019 05:00 PM | May 14, 2019 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 0 days | General worker
70 | Yes | CMU1.3.2.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 69 |  | 67,72 | July 28, 2019 8:00 AM | August 26, 2019 5:00 PM | July 28, 2019 05:00 PM | August 26, 2019 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 0 days | Skilled carpenter
71 | Yes | CMU1.3.2.5 | Auto Scheduled | งานบันได | 30 days | 4 | 69 |  | 67,72 | July 28, 2019 8:00 AM | August 26, 2019 5:00 PM | July 28, 2019 05:00 PM | August 26, 2019 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 0 days | General worker
72 | Yes | CMU1.3.2.6 | Auto Scheduled | งานสี | 30 days | 4 | 68,70,71 |  |  | August 27, 2019 8:00 AM | September 25, 2019 5:00 PM | August 30, 2019 05:00 PM | September 28, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 372 days | General worker
73 | Yes | CMU1.3.2.7 | Auto Scheduled | งานสุขภัณฑ์ | 315 days | 4 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 21, 2018 05:00 PM | August 31, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
74 | Yes | CMU1.3.2.7.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 75FS+135 days |  | 76FS+135 days | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | August 25, 2019 05:00 PM | September 08, 2019 05:00 PM | April 24, 2020 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
75 | Yes | CMU1.3.2.7.2 | Auto Scheduled | ZONE T-2 กลาง | 15 days | 5 | 80,84 |  | 74FS+135 days | March 22, 2019 8:00 AM | April 5, 2019 5:00 PM | March 24, 2019 05:00 PM | April 07, 2019 05:00 PM | November 26, 2019 05:00 PM | December 10, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
76 | Yes | CMU1.3.2.7.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 15 days | 5 | 74FS+135 days |  |  | January 16, 2020 8:00 AM | January 30, 2020 5:00 PM | January 27, 2020 05:00 PM | February 10, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 245 days | Sanitary-Plumber
77 | Yes | CMU1.3.3 | Auto Scheduled | งานระบบสุขาภิบาล ชั้น 3 | 408 days | 3 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
78 | Yes | CMU1.3.3.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
79 | Yes | CMU1.3.3.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 80FS+15 days |  | 81FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 16, 2019 05:00 PM | August 19, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
80 | Yes | CMU1.3.3.1.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 36 |  | 79FS+15 days,84SS,75 | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 16, 2018 05:00 PM | March 21, 2019 05:00 PM | January 09, 2019 05:00 PM | May 14, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
81 | Yes | CMU1.3.3.1.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 79FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 13, 2019 05:00 PM | January 16, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
82 | Yes | CMU1.3.3.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
83 | Yes | CMU1.3.3.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 84FS+15 days |  | 85FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 12, 2019 05:00 PM | August 15, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
84 | Yes | CMU1.3.3.2.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 80SS |  | 83FS+15 days,75 | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 16, 2018 05:00 PM | March 21, 2019 05:00 PM | January 09, 2019 05:00 PM | May 14, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
85 | Yes | CMU1.3.3.2.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 83FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 11, 2019 05:00 PM | January 14, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
86 | Yes | CMU1.3.4 | Auto Scheduled | งานระบบไฟฟ้า ชั้น 3 | 147 days | 3 |  |  |  | May 14, 2019 8:00 AM | October 7, 2019 5:00 PM | October 21, 2018 05:00 PM | March 16, 2019 05:00 PM | May 12, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 360 days | 360 days | 360 days
87 | Yes | CMU1.3.4.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 60 days | 4 | 89FS+7 days |  |  | August 9, 2019 8:00 AM | October 7, 2019 5:00 PM | August 17, 2019 05:00 PM | October 15, 2019 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 360 days | 360 days | 360 days | Electrician
88 | Yes | CMU1.3.4.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 60 days | 4 | 89FS+7 days |  |  | August 9, 2019 8:00 AM | October 7, 2019 5:00 PM | August 26, 2019 05:00 PM | October 24, 2019 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 360 days | 360 days | 360 days | Electrician
89 | Yes | CMU1.3.4.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 92SS+30 days |  | 88FS+7 days,87FS+7 days | May 14, 2019 8:00 AM | August 1, 2019 5:00 PM | May 19, 2019 05:00 PM | August 06, 2019 05:00 PM | May 12, 2020 05:00 PM | July 30, 2020 05:00 PM | As Soon As Possible |  | No | 360 days | 360 days | 0 days | Electrician
90 | Yes | CMU1.3.4.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 92SS+30 days |  |  | May 14, 2019 8:00 AM | August 1, 2019 5:00 PM | May 22, 2019 05:00 PM | August 09, 2019 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 427 days | 427 days | 427 days | Electrician
91 | Yes | CMU1.3.4.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 92SS+30 days |  |  | May 14, 2019 8:00 AM | August 1, 2019 5:00 PM | May 23, 2019 05:00 PM | August 10, 2019 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 427 days | 427 days | 427 days | Electrician
92 | Yes | CMU1.3.5 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้น 3 | 180 days | 3 | 65SS |  | 91SS+30 days,90SS+30 days,89SS+30 days,94,213FS-15 days,218FS-30 days,223FS-15 days,229FS-15 days,243FS-7 days,249FS-7 days | April 14, 2019 8:00 AM | October 10, 2019 5:00 PM | April 17, 2019 05:00 PM | October 13, 2019 05:00 PM | October 12, 2019 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Skilled carpenter
93 | Yes | CMU1.4 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้น 2 | 509 days | 2 |  |  |  | November 16, 2018 8:00 AM | April 7, 2020 5:00 PM | October 17, 2018 05:00 PM | March 08, 2020 05:00 PM | May 16, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 177 days | 177 days
94 | Yes | CMU1.4.1 | Auto Scheduled | งานรื้อถอน ชั้น 2 (รื้อขนไป) | 30 days | 3 | 92 | 152 | 97FS+45 days,98FS+45 days,121SS | October 11, 2019 8:00 AM | November 9, 2019 5:00 PM | October 14, 2019 05:00 PM | November 12, 2019 05:00 PM | June 04, 2018 05:00 PM | July 03, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | General worker
95 | Yes | CMU1.4.2 | Auto Scheduled | งานสถาปัตยกรรม ชั้น 2 | 368 days | 3 |  |  |  | March 22, 2019 8:00 AM | March 23, 2020 5:00 PM | October 17, 2018 05:00 PM | October 19, 2019 05:00 PM | October 04, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 192 days | 192 days
96 | Yes | CMU1.4.2.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 97,99,100 |  |  | February 23, 2020 8:00 AM | March 23, 2020 5:00 PM | March 06, 2020 05:00 PM | April 04, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 192 days | Skilled carpenter
97 | Yes | CMU1.4.2.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 94FS+45 days |  | 96,101 | December 25, 2019 8:00 AM | February 22, 2020 5:00 PM | December 28, 2019 05:00 PM | February 25, 2020 05:00 PM | February 09, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 0 days | General worker
98 | Yes | CMU1.4.2.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 94FS+45 days |  | 99,100 | December 25, 2019 8:00 AM | January 23, 2020 5:00 PM | December 31, 2019 05:00 PM | January 29, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 0 days | General worker
99 | Yes | CMU1.4.2.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 98 |  | 96,101 | January 24, 2020 8:00 AM | February 22, 2020 5:00 PM | February 02, 2020 05:00 PM | March 02, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 0 days | Skilled carpenter
100 | Yes | CMU1.4.2.5 | Auto Scheduled | งานบันได | 30 days | 4 | 98 |  | 96,101 | January 24, 2020 8:00 AM | February 22, 2020 5:00 PM | February 02, 2020 05:00 PM | March 02, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 0 days | General worker
101 | Yes | CMU1.4.2.6 | Auto Scheduled | งานสี | 30 days | 4 | 97,99,100 |  |  | February 23, 2020 8:00 AM | March 23, 2020 5:00 PM | March 09, 2020 05:00 PM | April 07, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 192 days | General worker
102 | Yes | CMU1.4.2.7 | Auto Scheduled | งานสุขภัณฑ์ | 315 days | 4 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 23, 2018 05:00 PM | September 02, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
103 | Yes | CMU1.4.2.7.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 104FS+135 days |  | 105FS+135 days | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | September 08, 2019 05:00 PM | September 22, 2019 05:00 PM | April 24, 2020 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
104 | Yes | CMU1.4.2.7.2 | Auto Scheduled | ZONE T-2 กลาง | 15 days | 5 | 113,109 |  | 103FS+135 days | March 22, 2019 8:00 AM | April 5, 2019 5:00 PM | April 07, 2019 05:00 PM | April 21, 2019 05:00 PM | November 26, 2019 05:00 PM | December 10, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
105 | Yes | CMU1.4.2.7.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 15 days | 5 | 103FS+135 days |  |  | January 16, 2020 8:00 AM | January 30, 2020 5:00 PM | February 13, 2020 05:00 PM | February 27, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 245 days | Sanitary-Plumber
106 | Yes | CMU1.4.3 | Auto Scheduled | งานระบบสุขาภิบาล ชั้น 2 | 408 days | 3 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
107 | Yes | CMU1.4.3.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
108 | Yes | CMU1.4.3.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 109FS+15 days |  | 110FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 16, 2019 05:00 PM | August 19, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
109 | Yes | CMU1.4.3.1.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 36 |  | 113SS,104,108FS+15 days | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 22, 2018 05:00 PM | March 27, 2019 05:00 PM | August 25, 2019 05:00 PM | December 28, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
110 | Yes | CMU1.4.3.1.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 108FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 07, 2019 05:00 PM | January 10, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
111 | Yes | CMU1.4.3.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
112 | Yes | CMU1.4.3.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 113FS+15 days |  | 114FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 29, 2019 05:00 PM | September 01, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
113 | Yes | CMU1.4.3.2.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 109SS |  | 104,112FS+15 days | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 28, 2018 05:00 PM | April 02, 2019 05:00 PM | August 25, 2019 05:00 PM | December 28, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
114 | Yes | CMU1.4.3.2.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 112FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 21, 2019 05:00 PM | January 24, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
115 | Yes | CMU1.4.4 | Auto Scheduled | งานระบบไฟฟ้า ชั้น 2 | 147 days | 3 |  |  |  | November 10, 2019 8:00 AM | April 4, 2020 5:00 PM | October 20, 2018 05:00 PM | March 15, 2019 05:00 PM | May 12, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 180 days | 180 days | 180 days
116 | Yes | CMU1.4.4.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 60 days | 4 | 118FS+7 days |  |  | February 5, 2020 8:00 AM | April 4, 2020 5:00 PM | February 12, 2020 05:00 PM | April 11, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 180 days | 180 days | 180 days | Electrician
117 | Yes | CMU1.4.4.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 60 days | 4 | 118FS+7 days |  |  | February 5, 2020 8:00 AM | April 4, 2020 5:00 PM | February 13, 2020 05:00 PM | April 12, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 180 days | 180 days | 180 days | Electrician
118 | Yes | CMU1.4.4.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 121SS+30 days |  | 117FS+7 days,116FS+7 days | November 10, 2019 8:00 AM | January 28, 2020 5:00 PM | November 15, 2019 05:00 PM | February 02, 2020 05:00 PM | May 12, 2020 05:00 PM | July 30, 2020 05:00 PM | As Soon As Possible |  | No | 180 days | 180 days | 0 days | Electrician
119 | Yes | CMU1.4.4.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 121SS+30 days |  |  | November 10, 2019 8:00 AM | January 28, 2020 5:00 PM | November 17, 2019 05:00 PM | February 04, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 247 days | 247 days | 247 days | Electrician
120 | Yes | CMU1.4.4.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 121SS+30 days |  |  | November 10, 2019 8:00 AM | January 28, 2020 5:00 PM | November 19, 2019 05:00 PM | February 06, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 247 days | 247 days | 247 days | Electrician
121 | Yes | CMU1.4.5 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้น 2 | 180 days | 3 | 94SS |  | 120SS+30 days,119SS+30 days,118SS+30 days,123,212FS-15 days,217FS-30 days,222FS-15 days,228FS-15 days,242FS-7 days,248FS-7 days | October 11, 2019 8:00 AM | April 7, 2020 5:00 PM | October 14, 2019 05:00 PM | April 10, 2020 05:00 PM | June 04, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Skilled carpenter
122 | Yes | CMU1.5 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้น 1 | 686 days | 2 |  |  |  | November 16, 2018 8:00 AM | October 1, 2020 5:00 PM | October 17, 2018 05:00 PM | September 01, 2020 05:00 PM | November 20, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 0 days | 0 days
123 | Yes | CMU1.5.1 | Auto Scheduled | งานรื้อถอน ชั้น 1 (รื้อขนไป) | 30 days | 3 | 121 | 63 | 124,127FS+45 days,128FS+45 days,131FS+45 days,152SS,193SS,194SS,195SS,196SS,197SS,202SS,204SS,205SS,206SS,207SS | April 8, 2020 8:00 AM | May 7, 2020 5:00 PM | April 11, 2020 05:00 PM | May 10, 2020 05:00 PM | July 19, 2018 05:00 PM | August 17, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | General worker
124 | Yes | CMU1.5.2 | Auto Scheduled | งานโครงสร้างวิศวกรรม ชั้น 1 | 75 days | 3 | 123 |  |  | May 8, 2020 8:00 AM | July 21, 2020 5:00 PM | May 12, 2020 05:00 PM | July 25, 2020 05:00 PM | July 23, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 72 days | 72 days | 72 days | General worker
125 | Yes | CMU1.5.3 | Auto Scheduled | งานสถาปัตยกรรม ชั้น 1 | 548 days | 3 |  |  |  | March 22, 2019 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | April 16, 2020 05:00 PM | April 07, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 12 days | 12 days
126 | Yes | CMU1.5.3.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 127,129,130 |  |  | August 21, 2020 8:00 AM | September 19, 2020 5:00 PM | August 24, 2020 05:00 PM | September 22, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | Skilled carpenter
127 | Yes | CMU1.5.3.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 123FS+45 days |  | 126,132 | June 22, 2020 8:00 AM | August 20, 2020 5:00 PM | June 25, 2020 05:00 PM | August 23, 2020 05:00 PM | October 02, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
128 | Yes | CMU1.5.3.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 123FS+45 days |  | 129,130 | June 22, 2020 8:00 AM | July 21, 2020 5:00 PM | June 25, 2020 05:00 PM | July 24, 2020 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
129 | Yes | CMU1.5.3.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 128 |  | 126,132 | July 22, 2020 8:00 AM | August 20, 2020 5:00 PM | July 25, 2020 05:00 PM | August 23, 2020 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | Skilled carpenter
130 | Yes | CMU1.5.3.5 | Auto Scheduled | งานบันได | 30 days | 4 | 128 |  | 126,132 | July 22, 2020 8:00 AM | August 20, 2020 5:00 PM | July 25, 2020 05:00 PM | August 23, 2020 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
131 | Yes | CMU1.5.3.6 | Auto Scheduled | งานตกแต่งอื่น ๆ | 60 days | 4 | 123FS+45 days |  |  | June 22, 2020 8:00 AM | August 20, 2020 5:00 PM | June 25, 2020 05:00 PM | August 23, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 42 days | 42 days | 42 days | General worker
132 | Yes | CMU1.5.3.7 | Auto Scheduled | งานสี | 30 days | 4 | 127,129,130 |  |  | August 21, 2020 8:00 AM | September 19, 2020 5:00 PM | August 24, 2020 05:00 PM | September 22, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
133 | Yes | CMU1.5.3.8 | Auto Scheduled | งานสุขภัณฑ์ | 315 days | 4 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 24, 2018 05:00 PM | September 03, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
134 | Yes | CMU1.5.3.8.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 135FS+135 days |  | 136FS+135 days | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | August 24, 2019 05:00 PM | September 07, 2019 05:00 PM | April 24, 2020 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
135 | Yes | CMU1.5.3.8.2 | Auto Scheduled | ZONE T-2 กลาง | 15 days | 5 | 140,144 |  | 134FS+135 days,164FS+135 days | March 22, 2019 8:00 AM | April 5, 2019 5:00 PM | March 24, 2019 05:00 PM | April 07, 2019 05:00 PM | November 26, 2019 05:00 PM | December 10, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
136 | Yes | CMU1.5.3.8.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 15 days | 5 | 134FS+135 days |  |  | January 16, 2020 8:00 AM | January 30, 2020 5:00 PM | January 24, 2020 05:00 PM | February 07, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 245 days | Sanitary-Plumber
137 | Yes | CMU1.5.4 | Auto Scheduled | งานระบบสุขาภิบาล ชั้น 1 | 408 days | 3 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 278 days | 44 days
138 | Yes | CMU1.5.4.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 278 days | 44 days
139 | Yes | CMU1.5.4.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 140FS+15 days |  | 141FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 13, 2019 05:00 PM | August 16, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
140 | Yes | CMU1.5.4.1.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 36 |  | 139FS+15 days,144SS,135,167FS+15 days | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 16, 2018 05:00 PM | March 21, 2019 05:00 PM | January 03, 2019 05:00 PM | May 08, 2019 05:00 PM | As Soon As Possible |  | No | 44 days | 44 days | 0 days | Sanitary-Plumber
141 | Yes | CMU1.5.4.1.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 139FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 07, 2019 05:00 PM | January 10, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
142 | Yes | CMU1.5.4.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 278 days | 44 days
143 | Yes | CMU1.5.4.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 144FS+15 days |  | 145FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 12, 2019 05:00 PM | August 15, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
144 | Yes | CMU1.5.4.2.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 140SS |  | 143FS+15 days,135,169FS+15 days | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 16, 2018 05:00 PM | March 21, 2019 05:00 PM | January 03, 2019 05:00 PM | May 08, 2019 05:00 PM | As Soon As Possible |  | No | 44 days | 44 days | 0 days | Sanitary-Plumber
145 | Yes | CMU1.5.4.2.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 143FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 04, 2019 05:00 PM | January 07, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
146 | Yes | CMU1.5.5 | Auto Scheduled | งานระบบไฟฟ้า ชั้น 1 | 147 days | 3 |  |  |  | May 8, 2020 8:00 AM | October 1, 2020 5:00 PM | October 21, 2018 05:00 PM | March 16, 2019 05:00 PM | May 12, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 0 days | 0 days | 0 days
147 | Yes | CMU1.5.5.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 60 days | 4 | 149FS+7 days |  |  | August 3, 2020 8:00 AM | October 1, 2020 5:00 PM | August 06, 2020 05:00 PM | October 04, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Electrician
148 | Yes | CMU1.5.5.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 60 days | 4 | 149FS+7 days |  |  | August 3, 2020 8:00 AM | October 1, 2020 5:00 PM | August 06, 2020 05:00 PM | October 04, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Electrician
149 | Yes | CMU1.5.5.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 152SS+30 days |  | 148FS+7 days,147FS+7 days | May 8, 2020 8:00 AM | July 26, 2020 5:00 PM | May 11, 2020 05:00 PM | July 29, 2020 05:00 PM | May 12, 2020 05:00 PM | July 30, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Electrician
150 | Yes | CMU1.5.5.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 152SS+30 days |  |  | May 8, 2020 8:00 AM | July 26, 2020 5:00 PM | May 11, 2020 05:00 PM | July 29, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 67 days | 67 days | 67 days | Electrician
151 | Yes | CMU1.5.5.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 152SS+30 days |  |  | May 8, 2020 8:00 AM | July 26, 2020 5:00 PM | May 11, 2020 05:00 PM | July 29, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 67 days | 67 days | 67 days | Electrician
152 | Yes | CMU1.5.6 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้น 1 | 165 days | 3 | 123SS |  | 151SS+30 days,150SS+30 days,149SS+30 days,154SS,211FS-30 days,210FS-30 days,216FS-45 days,221FS-30 days,227FS-30 days,226FS-30 days,232FS-45 days,241FS-7 days,247FS-7 days | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 11, 2020 05:00 PM | September 22, 2020 05:00 PM | November 26, 2019 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Skilled carpenter
153 | Yes | CMU1.6 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้นใต้ดิน | 533 days | 2 |  |  |  | April 6, 2019 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | April 01, 2020 05:00 PM | April 22, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 12 days | 12 days
154 | Yes | CMU1.6.1 | Auto Scheduled | งานรื้อถอน ชั้นใต้ดิน (รื้อขนไป) | 30 days | 3 | 152SS |  | 155,158FS+45 days,159FS+45 days,177SS,176SS,175SS,174SS | April 8, 2020 8:00 AM | May 7, 2020 5:00 PM | April 11, 2020 05:00 PM | May 10, 2020 05:00 PM | November 26, 2019 05:00 PM | December 25, 2019 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
155 | Yes | CMU1.6.2 | Auto Scheduled | งานโครงสร้างวิศวกรรม ชั้นใต้ดิน | 75 days | 3 | 154 |  |  | May 8, 2020 8:00 AM | July 21, 2020 5:00 PM | May 12, 2020 05:00 PM | July 25, 2020 05:00 PM | July 23, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 72 days | 72 days | 72 days | General worker
156 | Yes | CMU1.6.3 | Auto Scheduled | งานสถาปัตยกรรม ชั้นใต้ดิน | 398 days | 3 |  |  |  | August 19, 2019 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | November 18, 2019 05:00 PM | September 04, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 320 days | 12 days | 12 days
157 | Yes | CMU1.6.3.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 158,160,161 |  |  | August 21, 2020 8:00 AM | September 19, 2020 5:00 PM | September 12, 2020 05:00 PM | October 11, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | Skilled carpenter
158 | Yes | CMU1.6.3.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 154FS+45 days |  | 157,162 | June 22, 2020 8:00 AM | August 20, 2020 5:00 PM | June 25, 2020 05:00 PM | August 23, 2020 05:00 PM | February 09, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
159 | Yes | CMU1.6.3.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 154FS+45 days |  | 160,161 | June 22, 2020 8:00 AM | July 21, 2020 5:00 PM | July 14, 2020 05:00 PM | August 12, 2020 05:00 PM | August 22, 2020 05:00 PM | September 20, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
160 | Yes | CMU1.6.3.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 159 |  | 157,162 | July 22, 2020 8:00 AM | August 20, 2020 5:00 PM | August 13, 2020 05:00 PM | September 11, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | Skilled carpenter
161 | Yes | CMU1.6.3.5 | Auto Scheduled | งานบันได | 30 days | 4 | 159 |  | 157,162 | July 22, 2020 8:00 AM | August 20, 2020 5:00 PM | August 13, 2020 05:00 PM | September 11, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
162 | Yes | CMU1.6.3.6 | Auto Scheduled | งานสี | 30 days | 4 | 158,160,161 |  |  | August 21, 2020 8:00 AM | September 19, 2020 5:00 PM | September 12, 2020 05:00 PM | October 11, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
163 | Yes | CMU1.6.3.7 | Auto Scheduled | งานสุขภัณฑ์ | 15 days | 4 |  |  |  | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | October 20, 2018 05:00 PM | November 03, 2018 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 395 days | 395 days | 395 days
164 | Yes | CMU1.6.3.7.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 135FS+135 days |  |  | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | August 27, 2019 05:00 PM | September 10, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 395 days | 395 days | 395 days | Sanitary-Plumber
165 | Yes | CMU1.6.4 | Auto Scheduled | งานระบบสุขาภิบาล ชั้นใต้ดิน | 501 days | 3 |  |  |  | April 6, 2019 8:00 AM | August 18, 2020 5:00 PM | October 17, 2018 05:00 PM | February 29, 2020 05:00 PM | May 24, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 44 days | 44 days
166 | Yes | CMU1.6.4.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 126 days | 4 |  |  |  | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | October 21, 2018 05:00 PM | February 23, 2019 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 419 days | 419 days | 419 days
167 | Yes | CMU1.6.4.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 140FS+15 days |  |  | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 14, 2019 05:00 PM | August 17, 2019 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 419 days | 419 days | 419 days | Sanitary-Plumber
168 | Yes | CMU1.6.4.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 126 days | 4 |  |  |  | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | October 21, 2018 05:00 PM | February 23, 2019 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 44 days | 44 days
169 | Yes | CMU1.6.4.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 144FS+15 days |  | 170FS+300 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 06, 2019 05:00 PM | August 09, 2019 05:00 PM | May 24, 2019 05:00 PM | September 26, 2019 05:00 PM | As Soon As Possible |  | No | 44 days | 44 days | 0 days | Sanitary-Plumber
170 | Yes | CMU1.6.4.3 | Auto Scheduled | งานระบบระบายน้ำฝน | 75 days | 4 | 169FS+300 days |  |  | June 5, 2020 8:00 AM | August 18, 2020 5:00 PM | June 05, 2020 05:00 PM | August 18, 2020 05:00 PM | July 23, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 44 days | 44 days | 44 days | Sanitary-Plumber
171 | Yes | CMU1.6.5 | Auto Scheduled | งานระบบไฟฟ้า ชั้นใต้ดิน | 147 days | 3 |  |  |  | April 8, 2020 8:00 AM | September 1, 2020 5:00 PM | October 23, 2018 05:00 PM | March 18, 2019 05:00 PM | May 12, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 30 days | 30 days | 30 days
172 | Yes | CMU1.6.5.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 60 days | 4 | 174FS+7 days |  |  | July 4, 2020 8:00 AM | September 1, 2020 5:00 PM | July 07, 2020 05:00 PM | September 04, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 30 days | 30 days | 30 days | Electrician
173 | Yes | CMU1.6.5.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 60 days | 4 | 174FS+7 days |  |  | July 4, 2020 8:00 AM | September 1, 2020 5:00 PM | July 07, 2020 05:00 PM | September 04, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 30 days | 30 days | 30 days | Electrician
174 | Yes | CMU1.6.5.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 154SS |  | 173FS+7 days,172FS+7 days | April 8, 2020 8:00 AM | June 26, 2020 5:00 PM | April 11, 2020 05:00 PM | June 29, 2020 05:00 PM | May 12, 2020 05:00 PM | July 30, 2020 05:00 PM | As Soon As Possible |  | No | 30 days | 30 days | 0 days | Electrician
175 | Yes | CMU1.6.5.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 154SS |  |  | April 8, 2020 8:00 AM | June 26, 2020 5:00 PM | April 14, 2020 05:00 PM | July 02, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 97 days | 97 days | 97 days | Electrician
176 | Yes | CMU1.6.5.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 154SS |  |  | April 8, 2020 8:00 AM | June 26, 2020 5:00 PM | April 16, 2020 05:00 PM | July 04, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 97 days | 97 days | 97 days | Electrician
177 | Yes | CMU1.6.6 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้นใต้ดิน | 165 days | 3 | 154SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 11, 2020 05:00 PM | September 22, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | Skilled carpenter
178 | Yes | CMU1.7 | Auto Scheduled | หมวดงานระบบคอมพิวเตอร์และแจ้งเหตุเพลิงไหม้ | 670 days | 2 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
179 | Yes | CMU1.7.1 | Auto Scheduled | งานระบบคอมพิวเตอร์ | 670 days | 3 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
180 | Yes | CMU1.7.1.1 | Auto Scheduled | ชั้นที่ 4 | 160 days | 4 | 36FS+14 days |  | 181 | November 30, 2018 8:00 AM | May 8, 2019 5:00 PM | November 30, 2018 05:00 PM | May 08, 2019 05:00 PM | April 24, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
181 | Yes | CMU1.7.1.2 | Auto Scheduled | ชั้นที่ 3 | 175 days | 4 | 180 | 182 | 182 | May 9, 2019 8:00 AM | October 30, 2019 5:00 PM | May 09, 2019 05:00 PM | October 30, 2019 05:00 PM | April 09, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
182 | Yes | CMU1.7.1.3 | Auto Scheduled | ชั้นที่ 2 | 175 days | 4 | 181 | 183 | 183,184 | October 31, 2019 8:00 AM | April 22, 2020 5:00 PM | October 31, 2019 05:00 PM | April 22, 2020 05:00 PM | April 09, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
183 | Yes | CMU1.7.1.4 | Auto Scheduled | ชั้นที่ 1 | 160 days | 4 | 182 | 180 |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 23, 2020 05:00 PM | September 29, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
184 | Yes | CMU1.7.1.5 | Auto Scheduled | ชั้นใต้ดิน | 160 days | 4 | 182 | 183SS |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 23, 2020 05:00 PM | September 29, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
185 | Yes | CMU1.7.2 | Auto Scheduled | ระบบแจ้งเหตุเพลิงไหม้ | 670 days | 3 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
186 | Yes | CMU1.7.2.1 | Auto Scheduled | ชั้นที่ 4 | 160 days | 4 | 36FS+14 days |  | 187 | November 30, 2018 8:00 AM | May 8, 2019 5:00 PM | November 30, 2018 05:00 PM | May 08, 2019 05:00 PM | April 24, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
187 | Yes | CMU1.7.2.2 | Auto Scheduled | ชั้นที่ 3 | 175 days | 4 | 186 | 188 | 188 | May 9, 2019 8:00 AM | October 30, 2019 5:00 PM | May 09, 2019 05:00 PM | October 30, 2019 05:00 PM | April 09, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
188 | Yes | CMU1.7.2.3 | Auto Scheduled | ชั้นที่ 2 | 175 days | 4 | 187 | 189 | 189,190 | October 31, 2019 8:00 AM | April 22, 2020 5:00 PM | October 31, 2019 05:00 PM | April 22, 2020 05:00 PM | April 09, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
189 | Yes | CMU1.7.2.4 | Auto Scheduled | ชั้นที่ 1 | 160 days | 4 | 188 | 186 |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 23, 2020 05:00 PM | September 29, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
190 | Yes | CMU1.7.2.5 | Auto Scheduled | ชั้นใต้ดิน | 160 days | 4 | 188 | 189SS |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 23, 2020 05:00 PM | September 29, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
191 | Yes | CMU1.8 | Auto Scheduled | หมวดงานสีภายนอก งานซ่อมแซมและตกแต่งภายนอกอาคาร | 660 days | 2 |  |  |  | November 30, 2018 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | August 06, 2020 05:00 PM | December 16, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 507 days | 12 days | 12 days
192 | Yes | CMU1.8.1 | Auto Scheduled | งานสีภายนอกและงานซ่อมแซมพื้นผิวภายนอกอาคาร | 660 days | 3 |  |  |  | November 30, 2018 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | August 06, 2020 05:00 PM | December 16, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 507 days | 12 days | 12 days
193 | Yes | CMU1.8.1.1 | Auto Scheduled | งานขัดลอกสีทาผนังเดิม | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 11, 2020 05:00 PM | September 22, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
194 | Yes | CMU1.8.1.2 | Auto Scheduled | น้ำยาทาปูนเก่า (สีรองพื้น) | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 11, 2020 05:00 PM | September 22, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
195 | Yes | CMU1.8.1.3 | Auto Scheduled | งานทาสีภายนอก (ทา 2 เที่ยว) ไม่รวมชั้นใต้ดิน | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 11, 2020 05:00 PM | September 22, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
196 | Yes | CMU1.8.1.4 | Auto Scheduled | งานทำความสะอาดและซ่อมแซมผนังกรุอิฐโชว์แนว (อ้างอิงราคางานขัดลอกสี) | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 11, 2020 05:00 PM | September 22, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
197 | Yes | CMU1.8.1.5 | Auto Scheduled | น้ำยาเคลือบผิวผนังอิฐโชว์แนว (อ้างอิงค่าทาน้ำยากันเชื้อรา) | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 11, 2020 05:00 PM | September 22, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
198 | Yes | CMU1.8.1.6 | Auto Scheduled | งานรื้อถอนแผ่นวัสดุกันซึมหลังคาดาดฟ้า (รื้อขนไป) | 90 days | 4 | 36FS+14 days |  |  | November 30, 2018 8:00 AM | February 27, 2019 5:00 PM | December 03, 2018 05:00 PM | March 02, 2019 05:00 PM | July 08, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 582 days | 582 days | 582 days | General worker
199 | Yes | CMU1.8.1.7 | Auto Scheduled | งานแผ่นวัสดุกันซึมแบบเป่าไฟผิวทราย | 90 days | 4 | 36FS+14 days |  |  | November 30, 2018 8:00 AM | February 27, 2019 5:00 PM | December 04, 2018 05:00 PM | March 03, 2019 05:00 PM | July 08, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 582 days | 582 days | 582 days | General worker
200 | Yes | CMU1.8.1.8 | Auto Scheduled | งานกันซึมชนิด Polyurethane สูตรน้ำมัน ชนิดยืดหยุ่นสูงเป็นพิเศษ | 90 days | 4 | 36FS+14 days |  |  | November 30, 2018 8:00 AM | February 27, 2019 5:00 PM | December 03, 2018 05:00 PM | March 02, 2019 05:00 PM | July 08, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 582 days | 582 days | 582 days | General worker
201 | Yes | CMU1.8.2 | Auto Scheduled | งานตกแต่งภายนอกอาคาร | 165 days | 3 |  |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | October 20, 2018 05:00 PM | April 02, 2019 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 12 days | 12 days | 12 days
202 | Yes | CMU1.8.2.1 | Auto Scheduled | ตะแกรงเหล็กฉีกกันนก XS-32 | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 11, 2020 05:00 PM | September 22, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
203 | Yes | CMU1.9 | Auto Scheduled | หมวดงานบริเวณ | 165 days | 2 |  |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | October 22, 2018 05:00 PM | April 04, 2019 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 12 days | 12 days | 12 days
204 | Yes | CMU1.9.1 | Auto Scheduled | งานรื้อถอน งานบริเวณ | 165 days | 3 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 11, 2020 05:00 PM | September 22, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
205 | Yes | CMU1.9.2 | Auto Scheduled | งานโครงสร้างวิศวกรรม งานบริเวณ | 165 days | 3 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 11, 2020 05:00 PM | September 22, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
206 | Yes | CMU1.9.3 | Auto Scheduled | งานสถาปัตยกรรม งานบริเวณ | 165 days | 3 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 11, 2020 05:00 PM | September 22, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
207 | Yes | CMU1.9.4 | Auto Scheduled | งานระบบไฟฟ้า งานบริเวณ | 165 days | 3 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 11, 2020 05:00 PM | September 22, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | Electrician
208 | Yes | CMU1.10 | Auto Scheduled | หมวดงานครุภัณฑ์จัดซื้อ | 670 days | 2 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
209 | Yes | CMU1.10.1 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัว | 510 days | 3 |  |  |  | April 14, 2019 8:00 AM | September 4, 2020 5:00 PM | October 17, 2018 05:00 PM | March 09, 2020 05:00 PM | May 15, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 522 days | 27 days | 27 days
210 | Yes | CMU1.10.1.1 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้นใต้ดิน | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | August 28, 2020 05:00 PM | September 11, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
211 | Yes | CMU1.10.1.2 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้น 1 | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | August 31, 2020 05:00 PM | September 14, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
212 | Yes | CMU1.10.1.3 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้น 2 | 15 days | 4 | 121FS-15 days |  |  | March 24, 2020 8:00 AM | April 7, 2020 5:00 PM | March 29, 2020 05:00 PM | April 12, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Skilled carpenter
213 | Yes | CMU1.10.1.4 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้น 3 | 15 days | 4 | 92FS-15 days |  |  | September 26, 2019 8:00 AM | October 10, 2019 5:00 PM | October 04, 2019 05:00 PM | October 18, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Skilled carpenter
214 | Yes | CMU1.10.1.5 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้น 4 | 15 days | 4 | 63 |  |  | April 14, 2019 8:00 AM | April 28, 2019 5:00 PM | April 21, 2019 05:00 PM | May 05, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 522 days | 522 days | 522 days | Skilled carpenter
215 | Yes | CMU1.10.2 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ | 525 days | 3 |  |  |  | March 30, 2019 8:00 AM | September 4, 2020 5:00 PM | October 17, 2018 05:00 PM | March 24, 2020 05:00 PM | April 30, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 522 days | 27 days | 27 days
216 | Yes | CMU1.10.2.1 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ ชั้น 1 | 30 days | 4 | 152FS-45 days |  |  | August 6, 2020 8:00 AM | September 4, 2020 5:00 PM | August 15, 2020 05:00 PM | September 13, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
217 | Yes | CMU1.10.2.2 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ ชั้น 2 | 30 days | 4 | 121FS-30 days |  |  | March 9, 2020 8:00 AM | April 7, 2020 5:00 PM | March 15, 2020 05:00 PM | April 13, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Skilled carpenter
218 | Yes | CMU1.10.2.3 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ ชั้น 3 | 30 days | 4 | 92FS-30 days |  |  | September 11, 2019 8:00 AM | October 10, 2019 5:00 PM | September 16, 2019 05:00 PM | October 15, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Skilled carpenter
219 | Yes | CMU1.10.2.4 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ ชั้น 4 | 30 days | 4 | 63FS-15 days |  |  | March 30, 2019 8:00 AM | April 28, 2019 5:00 PM | April 02, 2019 05:00 PM | May 01, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 522 days | 522 days | 522 days | Skilled carpenter
220 | Yes | CMU1.10.3 | Auto Scheduled | งานผ้าม่าน | 510 days | 3 |  |  |  | April 14, 2019 8:00 AM | September 4, 2020 5:00 PM | October 17, 2018 05:00 PM | March 09, 2020 05:00 PM | May 15, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 522 days | 27 days | 27 days
221 | Yes | CMU1.10.3.1 | Auto Scheduled | งานผ้าม่าน ชั้น 1 | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | August 28, 2020 05:00 PM | September 11, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
222 | Yes | CMU1.10.3.2 | Auto Scheduled | งานผ้าม่าน ชั้น 2 | 15 days | 4 | 121FS-15 days |  |  | March 24, 2020 8:00 AM | April 7, 2020 5:00 PM | March 30, 2020 05:00 PM | April 13, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Skilled carpenter
223 | Yes | CMU1.10.3.3 | Auto Scheduled | งานผ้าม่าน ชั้น 3 | 15 days | 4 | 92FS-15 days |  |  | September 26, 2019 8:00 AM | October 10, 2019 5:00 PM | October 03, 2019 05:00 PM | October 17, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Skilled carpenter
224 | Yes | CMU1.10.3.4 | Auto Scheduled | งานผ้าม่าน ชั้น 4 | 15 days | 4 | 63 |  |  | April 14, 2019 8:00 AM | April 28, 2019 5:00 PM | April 25, 2019 05:00 PM | May 09, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 522 days | 522 days | 522 days | Skilled carpenter
225 | Yes | CMU1.10.4 | Auto Scheduled | งานป้าย | 510 days | 3 |  |  |  | April 14, 2019 8:00 AM | September 4, 2020 5:00 PM | October 17, 2018 05:00 PM | March 09, 2020 05:00 PM | May 15, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 522 days | 27 days | 27 days
226 | Yes | CMU1.10.4.1 | Auto Scheduled | งานป้าย ชั้นใต้ดิน | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | August 28, 2020 05:00 PM | September 11, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
227 | Yes | CMU1.10.4.2 | Auto Scheduled | งานป้าย ชั้น 1 | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | August 31, 2020 05:00 PM | September 14, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
228 | Yes | CMU1.10.4.3 | Auto Scheduled | งานป้าย ชั้น 2 | 15 days | 4 | 121FS-15 days |  |  | March 24, 2020 8:00 AM | April 7, 2020 5:00 PM | March 30, 2020 05:00 PM | April 13, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Skilled carpenter
229 | Yes | CMU1.10.4.4 | Auto Scheduled | งานป้าย ชั้น 3 | 15 days | 4 | 92FS-15 days |  |  | September 26, 2019 8:00 AM | October 10, 2019 5:00 PM | October 03, 2019 05:00 PM | October 17, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Skilled carpenter
230 | Yes | CMU1.10.4.5 | Auto Scheduled | งานป้าย ชั้น 4 | 15 days | 4 | 63 |  |  | April 14, 2019 8:00 AM | April 28, 2019 5:00 PM | April 20, 2019 05:00 PM | May 04, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 522 days | 522 days | 522 days | Skilled carpenter
231 | Yes | CMU1.10.5 | Auto Scheduled | งานอื่นๆ | 15 days | 3 |  |  |  | August 6, 2020 8:00 AM | August 20, 2020 5:00 PM | October 20, 2018 05:00 PM | November 03, 2018 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 42 days | 42 days | 42 days
232 | Yes | CMU1.10.5.1 | Auto Scheduled | ตู้อลูมิเนียมพับขึ้นรูป พ่นสี ครอบตู้กดน้ำ | 15 days | 4 | 152FS-45 days |  |  | August 6, 2020 8:00 AM | August 20, 2020 5:00 PM | August 13, 2020 05:00 PM | August 27, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 42 days | 42 days | 42 days | General worker
233 | Yes | CMU1.10.6 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ | 670 days | 3 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
234 | Yes | CMU1.10.6.1 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้นใต้ดิน | 160 days | 4 | 236 |  |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 28, 2020 05:00 PM | October 04, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
235 | Yes | CMU1.10.6.2 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้น 1 | 160 days | 4 | 236 |  |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 28, 2020 05:00 PM | October 04, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
236 | Yes | CMU1.10.6.3 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้น 2 | 175 days | 4 | 237 |  | 235,234 | October 31, 2019 8:00 AM | April 22, 2020 5:00 PM | November 05, 2019 05:00 PM | April 27, 2020 05:00 PM | March 12, 2020 05:00 PM | September 02, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
237 | Yes | CMU1.10.6.4 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้น 3 | 175 days | 4 | 238 |  | 236 | May 9, 2019 8:00 AM | October 30, 2019 5:00 PM | May 14, 2019 05:00 PM | November 04, 2019 05:00 PM | March 12, 2020 05:00 PM | September 02, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
238 | Yes | CMU1.10.6.5 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้น 4 | 160 days | 4 | 36FS+14 days |  | 237 | November 30, 2018 8:00 AM | May 8, 2019 5:00 PM | December 02, 2018 05:00 PM | May 10, 2019 05:00 PM | March 27, 2020 05:00 PM | September 02, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
239 | Yes | CMU1.10.7 | Auto Scheduled | งานระบบเครื่องเสียงประกาศ (ใช้ลำโพงของเดิม) | 539 days | 3 |  |  |  | April 7, 2019 8:00 AM | September 26, 2020 5:00 PM | October 17, 2018 05:00 PM | April 07, 2020 05:00 PM | April 16, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 530 days | 5 days | 5 days
240 | Yes | CMU1.10.7.1 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้นใต้ดิน | 7 days | 4 | 241 |  |  | September 20, 2020 8:00 AM | September 26, 2020 5:00 PM | September 27, 2020 05:00 PM | October 03, 2020 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 5 days | 5 days | 5 days | Electrician
241 | Yes | CMU1.10.7.2 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้น 1 | 7 days | 4 | 152FS-7 days |  | 240 | September 13, 2020 8:00 AM | September 19, 2020 5:00 PM | September 16, 2020 05:00 PM | September 22, 2020 05:00 PM | September 09, 2020 05:00 PM | September 15, 2020 05:00 PM | As Soon As Possible |  | No | 5 days | 5 days | 0 days | Electrician
242 | Yes | CMU1.10.7.3 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้น 2 | 7 days | 4 | 121FS-7 days |  |  | April 1, 2020 8:00 AM | April 7, 2020 5:00 PM | April 06, 2020 05:00 PM | April 12, 2020 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Electrician
243 | Yes | CMU1.10.7.4 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้น 3 | 7 days | 4 | 92FS-7 days |  |  | October 4, 2019 8:00 AM | October 10, 2019 5:00 PM | October 11, 2019 05:00 PM | October 17, 2019 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Electrician
244 | Yes | CMU1.10.7.5 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้น 4 | 7 days | 4 | 63FS-7 days |  |  | April 7, 2019 8:00 AM | April 13, 2019 5:00 PM | April 11, 2019 05:00 PM | April 17, 2019 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 537 days | 537 days | 537 days | Electrician
245 | Yes | CMU1.10.8 | Auto Scheduled | งานระบบกล้องวงจรปิด (ใช้กล้องวงจรปิดของเดิม) | 539 days | 3 |  |  |  | April 7, 2019 8:00 AM | September 26, 2020 5:00 PM | October 17, 2018 05:00 PM | April 07, 2020 05:00 PM | April 16, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 530 days | 5 days | 5 days
246 | Yes | CMU1.10.8.1 | Auto Scheduled | งานกล้องวงจรปิด ชั้นใต้ดิน | 7 days | 4 | 247 |  |  | September 20, 2020 8:00 AM | September 26, 2020 5:00 PM | September 27, 2020 05:00 PM | October 03, 2020 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 5 days | 5 days | 5 days | Electrician
247 | Yes | CMU1.10.8.2 | Auto Scheduled | งานกล้องวงจรปิด ชั้น 1 | 7 days | 4 | 152FS-7 days |  | 246 | September 13, 2020 8:00 AM | September 19, 2020 5:00 PM | September 16, 2020 05:00 PM | September 22, 2020 05:00 PM | September 09, 2020 05:00 PM | September 15, 2020 05:00 PM | As Soon As Possible |  | No | 5 days | 5 days | 0 days | Electrician
248 | Yes | CMU1.10.8.3 | Auto Scheduled | งานกล้องวงจรปิด ชั้น 2 | 7 days | 4 | 121FS-7 days |  |  | April 1, 2020 8:00 AM | April 7, 2020 5:00 PM | April 07, 2020 05:00 PM | April 13, 2020 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Electrician
249 | Yes | CMU1.10.8.4 | Auto Scheduled | งานกล้องวงจรปิด ชั้น 3 | 7 days | 4 | 92FS-7 days |  |  | October 4, 2019 8:00 AM | October 10, 2019 5:00 PM | October 11, 2019 05:00 PM | October 17, 2019 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Electrician
250 | Yes | CMU1.10.8.5 | Auto Scheduled | งานกล้องวงจรปิด ชั้น 4 | 7 days | 4 | 63FS-7 days |  |  | April 7, 2019 8:00 AM | April 13, 2019 5:00 PM | April 10, 2019 05:00 PM | April 16, 2019 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 537 days | 537 days | 537 days | Electrician

## solutoion_10
ID | Active | WBS | Task_Mode | Name | Duration | Outline_Level | Predecessors | Predecessors2 | Successors | Start_Date | Finish_Date | Early_Start | Early_Finish | Late_Start | Late_Finish | Constraint_Type | Constraint_Date | Summary | Start_Slack | Finish_Slack | Free_Slack | Resource_Names
1 | Yes | CMU1 | Auto Scheduled | โครงการปรับปรุงสำนักหอสมุด มหาวิทยาลัยเชียงใหม่ | 716 days | 1 |  |  |  | October 17, 2018 8:00 AM | October 1, 2020 5:00 PM | October 17, 2018 05:00 PM | October 01, 2020 05:00 PM | October 21, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 0 days | 0 days | 0 days
2 | Yes | CMU1.1 | Auto Scheduled | หมวดเตรียมการ | 675 days | 2 |  |  |  | October 17, 2018 8:00 AM | August 21, 2020 5:00 PM | October 17, 2018 05:00 PM | August 21, 2020 05:00 PM | December 01, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 41 days | 41 days | 41 days
3 | Yes | CMU1.1.1 | Auto Scheduled | งานอาคารสนามและผังบริเวณโครงการ | 14 days | 3 | 4FS-7 days |  |  | October 26, 2018 8:00 AM | November 8, 2018 5:00 PM | November 03, 2018 05:00 PM | November 16, 2018 05:00 PM | September 22, 2020 05:00 PM | October 05, 2020 05:00 PM | Start No Earlier Than | Oct 24 '18 | No | 693 days | 693 days | 693 days | Engineer
4 | Yes | CMU1.1.2 | Auto Scheduled | งานเชื่อมต่อระบบสาธารณูปโภคโครงการ | 16 days | 3 |  |  | 3FS-7 days | October 17, 2018 8:00 AM | November 1, 2018 5:00 PM | October 20, 2018 05:00 PM | November 04, 2018 05:00 PM | September 13, 2020 05:00 PM | September 28, 2020 05:00 PM | As Soon As Possible |  | No | 693 days | 693 days | 0 days | Engineer
5 | Yes | CMU1.1.3 | Auto Scheduled | งานตรวจทดสอบระบบภายในอาคารก่อนดำเนินการปรับปรุง | 675 days | 3 |  |  |  | October 17, 2018 8:00 AM | August 21, 2020 5:00 PM | October 17, 2018 05:00 PM | August 21, 2020 05:00 PM | December 01, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 41 days | 41 days | 41 days
6 | Yes | CMU1.1.3.1 | Auto Scheduled | ชั้นที่ 4 | 15 days | 4 |  |  | 7FS+150 days | October 17, 2018 8:00 AM | October 31, 2018 5:00 PM | October 20, 2018 05:00 PM | November 03, 2018 05:00 PM | December 01, 2018 05:00 PM | December 15, 2018 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
7 | Yes | CMU1.1.3.2 | Auto Scheduled | ชั้นที่ 3 | 15 days | 4 | 6FS+150 days |  | 8FS+150 days | March 31, 2019 8:00 AM | April 14, 2019 5:00 PM | April 09, 2019 05:00 PM | April 23, 2019 05:00 PM | May 15, 2019 05:00 PM | May 29, 2019 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
8 | Yes | CMU1.1.3.3 | Auto Scheduled | ชั้นที่ 2 | 15 days | 4 | 7FS+150 days |  | 9FS+150 days | September 12, 2019 8:00 AM | September 26, 2019 5:00 PM | October 06, 2019 05:00 PM | October 20, 2019 05:00 PM | October 27, 2019 05:00 PM | November 10, 2019 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
9 | Yes | CMU1.1.3.4 | Auto Scheduled | ชั้นที่ 1 | 15 days | 4 | 8FS+150 days |  | 10FS+150 days | February 24, 2020 8:00 AM | March 9, 2020 5:00 PM | March 27, 2020 05:00 PM | April 10, 2020 05:00 PM | April 09, 2020 05:00 PM | April 23, 2020 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
10 | Yes | CMU1.1.3.5 | Auto Scheduled | ชั้นใต้ดินและภายนอก | 15 days | 4 | 9FS+150 days |  |  | August 7, 2020 8:00 AM | August 21, 2020 5:00 PM | September 18, 2020 05:00 PM | October 02, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 41 days | Engineer
11 | Yes | CMU1.1.4 | Auto Scheduled | งานสำรวจอุปกรณ์ไฟฟ้า, สุขภัณฑ์และครุภัณฑ์ (ของเดิม) ก่อนดำเนินการปรับปรุง | 675 days | 3 |  |  |  | October 17, 2018 8:00 AM | August 21, 2020 5:00 PM | October 17, 2018 05:00 PM | August 21, 2020 05:00 PM | December 01, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 41 days | 41 days | 41 days
12 | Yes | CMU1.1.4.1 | Auto Scheduled | ชั้นที่ 4 | 15 days | 4 |  |  | 13FS+150 days | October 17, 2018 8:00 AM | October 31, 2018 5:00 PM | October 20, 2018 05:00 PM | November 03, 2018 05:00 PM | December 01, 2018 05:00 PM | December 15, 2018 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
13 | Yes | CMU1.1.4.2 | Auto Scheduled | ชั้นที่ 3 | 15 days | 4 | 12FS+150 days |  | 14FS+150 days | March 31, 2019 8:00 AM | April 14, 2019 5:00 PM | April 06, 2019 05:00 PM | April 20, 2019 05:00 PM | May 15, 2019 05:00 PM | May 29, 2019 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
14 | Yes | CMU1.1.4.3 | Auto Scheduled | ชั้นที่ 2 | 15 days | 4 | 13FS+150 days |  | 15FS+150 days | September 12, 2019 8:00 AM | September 26, 2019 5:00 PM | September 24, 2019 05:00 PM | October 08, 2019 05:00 PM | October 27, 2019 05:00 PM | November 10, 2019 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
15 | Yes | CMU1.1.4.4 | Auto Scheduled | ชั้นที่ 1 | 15 days | 4 | 14FS+150 days |  | 16FS+150 days | February 24, 2020 8:00 AM | March 9, 2020 5:00 PM | March 11, 2020 05:00 PM | March 25, 2020 05:00 PM | April 09, 2020 05:00 PM | April 23, 2020 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
16 | Yes | CMU1.1.4.5 | Auto Scheduled | ชั้นใต้ดินและภายนอก | 15 days | 4 | 15FS+150 days |  |  | August 7, 2020 8:00 AM | August 21, 2020 5:00 PM | September 02, 2020 05:00 PM | September 16, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 41 days | Engineer
17 | Yes | CMU1.1.5 | Auto Scheduled | งานเอกสารขออนุมัติใช้วัสดุ, Shop Drawing และครุภัณฑ์ของโครงการ | 106 days | 3 |  |  |  | October 17, 2018 8:00 AM | January 30, 2019 5:00 PM | October 22, 2018 05:00 PM | February 04, 2019 05:00 PM | June 22, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 610 days | 610 days | 610 days
18 | Yes | CMU1.1.5.1 | Auto Scheduled | แบบ Shop Drawing ชั้นที่ 4 | 20 days | 4 |  |  | 19,25SS+14 days,26SS+14 days | October 17, 2018 8:00 AM | November 5, 2018 5:00 PM | October 17, 2018 05:00 PM | November 05, 2018 05:00 PM | October 01, 2018 05:00 PM | October 20, 2018 05:00 PM | As Soon As Possible |  | No | 610 days | 610 days | 0 days | Engineer
19 | Yes | CMU1.1.5.2 | Auto Scheduled | แบบ Shop Drawing ชั้นที่ 3 | 20 days | 4 | 18 |  | 20FS-7 days | November 6, 2018 8:00 AM | November 25, 2018 5:00 PM | November 13, 2018 05:00 PM | December 02, 2018 05:00 PM | July 13, 2020 05:00 PM | August 01, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
20 | Yes | CMU1.1.5.3 | Auto Scheduled | แบบ Shop Drawing ชั้นที่ 2 | 20 days | 4 | 19FS-7 days |  | 21FS-7 days | November 19, 2018 8:00 AM | December 8, 2018 5:00 PM | November 29, 2018 05:00 PM | December 18, 2018 05:00 PM | July 26, 2020 05:00 PM | August 14, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
21 | Yes | CMU1.1.5.4 | Auto Scheduled | แบบ Shop Drawing ชั้นที่ 1 | 20 days | 4 | 20FS-7 days |  | 22FS-7 days | December 2, 2018 8:00 AM | December 21, 2018 5:00 PM | December 27, 2018 05:00 PM | January 15, 2019 05:00 PM | August 08, 2020 05:00 PM | August 27, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
22 | Yes | CMU1.1.5.5 | Auto Scheduled | แบบ Shop Drawing ชั้นใต้ดิน | 20 days | 4 | 21FS-7 days |  | 23FS-7 days | December 15, 2018 8:00 AM | January 3, 2019 5:00 PM | January 15, 2019 05:00 PM | February 03, 2019 05:00 PM | August 21, 2020 05:00 PM | September 09, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
23 | Yes | CMU1.1.5.6 | Auto Scheduled | แบบ Shop Drawing ภายนอกอาคาร | 20 days | 4 | 22FS-7 days |  | 24FS-7 days | December 28, 2018 8:00 AM | January 16, 2019 5:00 PM | February 05, 2019 05:00 PM | February 24, 2019 05:00 PM | September 03, 2020 05:00 PM | September 22, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
24 | Yes | CMU1.1.5.7 | Auto Scheduled | แบบ Shop Drawing landscape | 20 days | 4 | 23FS-7 days |  |  | January 10, 2019 8:00 AM | January 29, 2019 5:00 PM | February 25, 2019 05:00 PM | March 16, 2019 05:00 PM | September 16, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 611 days | Engineer
25 | Yes | CMU1.1.5.8 | Auto Scheduled | แบบ Shop Drawing งานปรับปรุง ครุภัณฑ์ | 92 days | 4 | 18SS+14 days |  |  | October 31, 2018 8:00 AM | January 30, 2019 5:00 PM | November 12, 2018 05:00 PM | February 11, 2019 05:00 PM | July 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 610 days | 610 days | 610 days | Engineer
26 | Yes | CMU1.1.5.9 | Auto Scheduled | แบบ Shop Drawing งานจัดซื้อครุภัณฑ์ | 92 days | 4 | 18SS+14 days |  |  | October 31, 2018 8:00 AM | January 30, 2019 5:00 PM | November 13, 2018 05:00 PM | February 12, 2019 05:00 PM | July 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 610 days | 610 days | 610 days | Engineer
27 | Yes | CMU1.1.6 | Auto Scheduled | งานตรวจทดสอบระบบ, งานอบรมผู้ใช้อาคาร และ As-Built Drawing | 30 days | 3 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 22, 2018 05:00 PM | November 20, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 686 days | 686 days | 686 days
28 | Yes | CMU1.1.6.1 | Auto Scheduled | ชั้นที่ 4 | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 27, 2018 05:00 PM | November 25, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
29 | Yes | CMU1.1.6.2 | Auto Scheduled | ชั้นที่ 3 | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 30, 2018 05:00 PM | November 28, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
30 | Yes | CMU1.1.6.3 | Auto Scheduled | ชั้นที่ 2 | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 22, 2018 05:00 PM | November 20, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
31 | Yes | CMU1.1.6.4 | Auto Scheduled | ชั้นที่ 1 | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 28, 2018 05:00 PM | November 26, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
32 | Yes | CMU1.1.6.5 | Auto Scheduled | ชั้นใต้ดิน | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 24, 2018 05:00 PM | November 22, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
33 | Yes | CMU1.1.6.6 | Auto Scheduled | ทั้งอาคาร | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 23, 2018 05:00 PM | November 21, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
34 | Yes | CMU1.1.7 | Auto Scheduled | งานบริหารงานก่อสร้างและงานอื่น ๆ | 0 days | 3 |  |  |  | October 17, 2018 8:00 AM | October 17, 2018 8:00 AM | October 20, 2018 05:00 PM | October 19, 2018 05:00 PM | October 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 716 days | 716 days | 716 days | Engineer
35 | Yes | CMU1.2 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้น 4 | 471 days | 2 |  |  |  | October 17, 2018 8:00 AM | January 30, 2020 5:00 PM | October 17, 2018 05:00 PM | January 30, 2020 05:00 PM | June 23, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 0 days | 245 days | 0 days
36 | Yes | CMU1.2.1 | Auto Scheduled | งานรื้อถอน ชั้น 4 (รื้อขนไป) | 30 days | 3 |  |  | 39FS+45 days,40FS+45 days,51,63SS+14 days,80,109,140,180FS+14 days,186FS+14 days,198FS+14 days,199FS+14 days,200FS+14 days,238FS+14 days | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 17, 2018 05:00 PM | November 15, 2018 05:00 PM | March 11, 2018 05:00 PM | April 09, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | General worker
37 | Yes | CMU1.2.2 | Auto Scheduled | งานสถาปัตยกรรม ชั้น 4 | 396 days | 3 |  |  |  | December 31, 2018 8:00 AM | January 30, 2020 5:00 PM | October 17, 2018 05:00 PM | November 16, 2019 05:00 PM | September 06, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 326 days | 245 days | 245 days
38 | Yes | CMU1.2.2.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 39,41,42 |  |  | March 1, 2019 8:00 AM | March 30, 2019 5:00 PM | March 12, 2019 05:00 PM | April 10, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 551 days | Skilled carpenter
39 | Yes | CMU1.2.2.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 36FS+45 days |  | 38,43 | December 31, 2018 8:00 AM | February 28, 2019 5:00 PM | January 05, 2019 05:00 PM | March 05, 2019 05:00 PM | July 15, 2020 05:00 PM | September 12, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 0 days | General worker
40 | Yes | CMU1.2.2.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 36FS+45 days |  | 41,42 | December 31, 2018 8:00 AM | January 29, 2019 5:00 PM | January 03, 2019 05:00 PM | February 01, 2019 05:00 PM | August 14, 2020 05:00 PM | September 12, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 0 days | General worker
41 | Yes | CMU1.2.2.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 40 |  | 38,43 | January 30, 2019 8:00 AM | February 28, 2019 5:00 PM | February 05, 2019 05:00 PM | March 06, 2019 05:00 PM | August 14, 2020 05:00 PM | September 12, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 0 days | Skilled carpenter
42 | Yes | CMU1.2.2.5 | Auto Scheduled | งานบันได | 30 days | 4 | 40 |  | 38,43 | January 30, 2019 8:00 AM | February 28, 2019 5:00 PM | February 05, 2019 05:00 PM | March 06, 2019 05:00 PM | August 14, 2020 05:00 PM | September 12, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 0 days | General worker
43 | Yes | CMU1.2.2.6 | Auto Scheduled | งานสี | 30 days | 4 | 39,41,42 |  |  | March 1, 2019 8:00 AM | March 30, 2019 5:00 PM | March 10, 2019 05:00 PM | April 08, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 551 days | General worker
44 | Yes | CMU1.2.2.7 | Auto Scheduled | งานสุขภัณฑ์ | 315 days | 4 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 20, 2018 05:00 PM | August 30, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
45 | Yes | CMU1.2.2.7.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 46FS+135 days |  | 47FS+135 days | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | September 14, 2019 05:00 PM | September 28, 2019 05:00 PM | April 24, 2020 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
46 | Yes | CMU1.2.2.7.2 | Auto Scheduled | ZONE T-2 กลาง | 15 days | 5 | 51,55 |  | 45FS+135 days | March 22, 2019 8:00 AM | April 5, 2019 5:00 PM | April 08, 2019 05:00 PM | April 22, 2019 05:00 PM | November 26, 2019 05:00 PM | December 10, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
47 | Yes | CMU1.2.2.7.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 15 days | 5 | 45FS+135 days |  |  | January 16, 2020 8:00 AM | January 30, 2020 5:00 PM | February 18, 2020 05:00 PM | March 03, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 245 days | Sanitary-Plumber
48 | Yes | CMU1.2.3 | Auto Scheduled | งานระบบสุขาภิบาล ชั้น 4 | 408 days | 3 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
49 | Yes | CMU1.2.3.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
50 | Yes | CMU1.2.3.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 51FS+15 days |  | 52FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 17, 2019 05:00 PM | August 20, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
51 | Yes | CMU1.2.3.1.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 36 |  | 50FS+15 days,46,55SS | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 23, 2018 05:00 PM | March 28, 2019 05:00 PM | August 25, 2019 05:00 PM | December 28, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
52 | Yes | CMU1.2.3.1.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 50FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 09, 2019 05:00 PM | January 12, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
53 | Yes | CMU1.2.3.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
54 | Yes | CMU1.2.3.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 55FS+15 days |  | 56FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 24, 2019 05:00 PM | August 27, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
55 | Yes | CMU1.2.3.2.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 51SS |  | 54FS+15 days,46 | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 28, 2018 05:00 PM | April 02, 2019 05:00 PM | August 25, 2019 05:00 PM | December 28, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
56 | Yes | CMU1.2.3.2.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 54FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 22, 2019 05:00 PM | January 25, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
57 | Yes | CMU1.2.4 | Auto Scheduled | งานระบบไฟฟ้า ชั้น 4 | 117 days | 3 |  |  |  | November 30, 2018 8:00 AM | March 26, 2019 5:00 PM | October 21, 2018 05:00 PM | February 14, 2019 05:00 PM | June 11, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 555 days | 555 days | 555 days
58 | Yes | CMU1.2.4.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 30 days | 4 | 60FS+7 days |  |  | February 25, 2019 8:00 AM | March 26, 2019 5:00 PM | March 03, 2019 05:00 PM | April 01, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 555 days | 555 days | 555 days | Electrician
59 | Yes | CMU1.2.4.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 30 days | 4 | 60FS+7 days |  |  | February 25, 2019 8:00 AM | March 26, 2019 5:00 PM | March 04, 2019 05:00 PM | April 02, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 555 days | 555 days | 555 days | Electrician
60 | Yes | CMU1.2.4.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 63SS+30 days |  | 58FS+7 days,59FS+7 days | November 30, 2018 8:00 AM | February 17, 2019 5:00 PM | December 03, 2018 05:00 PM | February 20, 2019 05:00 PM | June 11, 2020 05:00 PM | August 29, 2020 05:00 PM | As Soon As Possible |  | No | 555 days | 555 days | 0 days | Electrician
61 | Yes | CMU1.2.4.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 63SS+30 days |  |  | November 30, 2018 8:00 AM | February 17, 2019 5:00 PM | December 04, 2018 05:00 PM | February 21, 2019 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 592 days | 592 days | 592 days | Electrician
62 | Yes | CMU1.2.4.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 63SS+30 days |  |  | November 30, 2018 8:00 AM | February 17, 2019 5:00 PM | December 06, 2018 05:00 PM | February 23, 2019 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 592 days | 592 days | 592 days | Electrician
63 | Yes | CMU1.2.5 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้น 4 | 165 days | 3 | 36SS+14 days |  | 62SS+30 days,60SS+30 days,61SS+30 days,65,214,219FS-15 days,224,230,244FS-7 days,250FS-7 days | October 31, 2018 8:00 AM | April 13, 2019 5:00 PM | October 31, 2018 05:00 PM | April 13, 2019 05:00 PM | June 19, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Skilled carpenter
64 | Yes | CMU1.3 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้น 3 | 441 days | 2 |  |  |  | November 16, 2018 8:00 AM | January 30, 2020 5:00 PM | October 17, 2018 05:00 PM | December 31, 2019 05:00 PM | July 23, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 149 days | 245 days | 149 days
65 | Yes | CMU1.3.1 | Auto Scheduled | งานรื้อถอน ชั้น 3 (รื้อขนไป) | 30 days | 3 | 63 | 121 | 68FS+45 days,69FS+45 days,92SS | April 14, 2019 8:00 AM | May 13, 2019 5:00 PM | April 14, 2019 05:00 PM | May 13, 2019 05:00 PM | July 19, 2018 05:00 PM | August 17, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | General worker
66 | Yes | CMU1.3.2 | Auto Scheduled | งานสถาปัตยกรรม ชั้น 3 | 315 days | 3 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 22, 2018 05:00 PM | September 01, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
67 | Yes | CMU1.3.2.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 68,70,71 |  |  | August 27, 2019 8:00 AM | September 25, 2019 5:00 PM | August 31, 2019 05:00 PM | September 29, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 372 days | Skilled carpenter
68 | Yes | CMU1.3.2.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 65FS+45 days |  | 67,72 | June 28, 2019 8:00 AM | August 26, 2019 5:00 PM | June 28, 2019 05:00 PM | August 26, 2019 05:00 PM | October 02, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 0 days | General worker
69 | Yes | CMU1.3.2.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 65FS+45 days |  | 70,71 | June 28, 2019 8:00 AM | July 27, 2019 5:00 PM | June 28, 2019 05:00 PM | July 27, 2019 05:00 PM | April 15, 2019 05:00 PM | May 14, 2019 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 0 days | General worker
70 | Yes | CMU1.3.2.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 69 |  | 67,72 | July 28, 2019 8:00 AM | August 26, 2019 5:00 PM | July 28, 2019 05:00 PM | August 26, 2019 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 0 days | Skilled carpenter
71 | Yes | CMU1.3.2.5 | Auto Scheduled | งานบันได | 30 days | 4 | 69 |  | 67,72 | July 28, 2019 8:00 AM | August 26, 2019 5:00 PM | July 28, 2019 05:00 PM | August 26, 2019 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 0 days | General worker
72 | Yes | CMU1.3.2.6 | Auto Scheduled | งานสี | 30 days | 4 | 68,70,71 |  |  | August 27, 2019 8:00 AM | September 25, 2019 5:00 PM | August 30, 2019 05:00 PM | September 28, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 372 days | General worker
73 | Yes | CMU1.3.2.7 | Auto Scheduled | งานสุขภัณฑ์ | 315 days | 4 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 21, 2018 05:00 PM | August 31, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
74 | Yes | CMU1.3.2.7.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 75FS+135 days |  | 76FS+135 days | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | August 25, 2019 05:00 PM | September 08, 2019 05:00 PM | April 24, 2020 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
75 | Yes | CMU1.3.2.7.2 | Auto Scheduled | ZONE T-2 กลาง | 15 days | 5 | 80,84 |  | 74FS+135 days | March 22, 2019 8:00 AM | April 5, 2019 5:00 PM | March 24, 2019 05:00 PM | April 07, 2019 05:00 PM | November 26, 2019 05:00 PM | December 10, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
76 | Yes | CMU1.3.2.7.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 15 days | 5 | 74FS+135 days |  |  | January 16, 2020 8:00 AM | January 30, 2020 5:00 PM | January 27, 2020 05:00 PM | February 10, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 245 days | Sanitary-Plumber
77 | Yes | CMU1.3.3 | Auto Scheduled | งานระบบสุขาภิบาล ชั้น 3 | 408 days | 3 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
78 | Yes | CMU1.3.3.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
79 | Yes | CMU1.3.3.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 80FS+15 days |  | 81FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 15, 2019 05:00 PM | August 18, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
80 | Yes | CMU1.3.3.1.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 36 |  | 79FS+15 days,84SS,75 | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 16, 2018 05:00 PM | March 21, 2019 05:00 PM | January 09, 2019 05:00 PM | May 14, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
81 | Yes | CMU1.3.3.1.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 79FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 09, 2019 05:00 PM | January 12, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
82 | Yes | CMU1.3.3.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
83 | Yes | CMU1.3.3.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 84FS+15 days |  | 85FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 11, 2019 05:00 PM | August 14, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
84 | Yes | CMU1.3.3.2.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 80SS |  | 83FS+15 days,75 | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 16, 2018 05:00 PM | March 21, 2019 05:00 PM | January 09, 2019 05:00 PM | May 14, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
85 | Yes | CMU1.3.3.2.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 83FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 08, 2019 05:00 PM | January 11, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
86 | Yes | CMU1.3.4 | Auto Scheduled | งานระบบไฟฟ้า ชั้น 3 | 147 days | 3 |  |  |  | May 14, 2019 8:00 AM | October 7, 2019 5:00 PM | October 21, 2018 05:00 PM | March 16, 2019 05:00 PM | May 12, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 360 days | 360 days | 360 days
87 | Yes | CMU1.3.4.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 60 days | 4 | 89FS+7 days |  |  | August 9, 2019 8:00 AM | October 7, 2019 5:00 PM | August 19, 2019 05:00 PM | October 17, 2019 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 360 days | 360 days | 360 days | Electrician
88 | Yes | CMU1.3.4.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 60 days | 4 | 89FS+7 days |  |  | August 9, 2019 8:00 AM | October 7, 2019 5:00 PM | August 26, 2019 05:00 PM | October 24, 2019 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 360 days | 360 days | 360 days | Electrician
89 | Yes | CMU1.3.4.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 92SS+30 days |  | 88FS+7 days,87FS+7 days | May 14, 2019 8:00 AM | August 1, 2019 5:00 PM | May 21, 2019 05:00 PM | August 08, 2019 05:00 PM | May 12, 2020 05:00 PM | July 30, 2020 05:00 PM | As Soon As Possible |  | No | 360 days | 360 days | 0 days | Electrician
90 | Yes | CMU1.3.4.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 92SS+30 days |  |  | May 14, 2019 8:00 AM | August 1, 2019 5:00 PM | May 24, 2019 05:00 PM | August 11, 2019 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 427 days | 427 days | 427 days | Electrician
91 | Yes | CMU1.3.4.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 92SS+30 days |  |  | May 14, 2019 8:00 AM | August 1, 2019 5:00 PM | May 25, 2019 05:00 PM | August 12, 2019 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 427 days | 427 days | 427 days | Electrician
92 | Yes | CMU1.3.5 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้น 3 | 180 days | 3 | 65SS |  | 91SS+30 days,90SS+30 days,89SS+30 days,94,213FS-15 days,218FS-30 days,223FS-15 days,229FS-15 days,243FS-7 days,249FS-7 days | April 14, 2019 8:00 AM | October 10, 2019 5:00 PM | April 19, 2019 05:00 PM | October 15, 2019 05:00 PM | October 12, 2019 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Skilled carpenter
93 | Yes | CMU1.4 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้น 2 | 509 days | 2 |  |  |  | November 16, 2018 8:00 AM | April 7, 2020 5:00 PM | October 17, 2018 05:00 PM | March 08, 2020 05:00 PM | May 16, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 177 days | 177 days
94 | Yes | CMU1.4.1 | Auto Scheduled | งานรื้อถอน ชั้น 2 (รื้อขนไป) | 30 days | 3 | 92 | 152 | 97FS+45 days,98FS+45 days,121SS | October 11, 2019 8:00 AM | November 9, 2019 5:00 PM | October 16, 2019 05:00 PM | November 14, 2019 05:00 PM | June 04, 2018 05:00 PM | July 03, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | General worker
95 | Yes | CMU1.4.2 | Auto Scheduled | งานสถาปัตยกรรม ชั้น 2 | 368 days | 3 |  |  |  | March 22, 2019 8:00 AM | March 23, 2020 5:00 PM | October 17, 2018 05:00 PM | October 19, 2019 05:00 PM | October 04, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 192 days | 192 days
96 | Yes | CMU1.4.2.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 97,99,100 |  |  | February 23, 2020 8:00 AM | March 23, 2020 5:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 192 days | Skilled carpenter
97 | Yes | CMU1.4.2.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 94FS+45 days |  | 96,101 | December 25, 2019 8:00 AM | February 22, 2020 5:00 PM | December 30, 2019 05:00 PM | February 27, 2020 05:00 PM | February 09, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 0 days | General worker
98 | Yes | CMU1.4.2.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 94FS+45 days |  | 99,100 | December 25, 2019 8:00 AM | January 23, 2020 5:00 PM | January 03, 2020 05:00 PM | February 01, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 0 days | General worker
99 | Yes | CMU1.4.2.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 98 |  | 96,101 | January 24, 2020 8:00 AM | February 22, 2020 5:00 PM | February 06, 2020 05:00 PM | March 06, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 0 days | Skilled carpenter
100 | Yes | CMU1.4.2.5 | Auto Scheduled | งานบันได | 30 days | 4 | 98 |  | 96,101 | January 24, 2020 8:00 AM | February 22, 2020 5:00 PM | February 05, 2020 05:00 PM | March 05, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 0 days | General worker
101 | Yes | CMU1.4.2.6 | Auto Scheduled | งานสี | 30 days | 4 | 97,99,100 |  |  | February 23, 2020 8:00 AM | March 23, 2020 5:00 PM | March 13, 2020 05:00 PM | April 11, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 192 days | General worker
102 | Yes | CMU1.4.2.7 | Auto Scheduled | งานสุขภัณฑ์ | 315 days | 4 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 22, 2018 05:00 PM | September 01, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
103 | Yes | CMU1.4.2.7.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 104FS+135 days |  | 105FS+135 days | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | September 08, 2019 05:00 PM | September 22, 2019 05:00 PM | April 24, 2020 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
104 | Yes | CMU1.4.2.7.2 | Auto Scheduled | ZONE T-2 กลาง | 15 days | 5 | 113,109 |  | 103FS+135 days | March 22, 2019 8:00 AM | April 5, 2019 5:00 PM | April 07, 2019 05:00 PM | April 21, 2019 05:00 PM | November 26, 2019 05:00 PM | December 10, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
105 | Yes | CMU1.4.2.7.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 15 days | 5 | 103FS+135 days |  |  | January 16, 2020 8:00 AM | January 30, 2020 5:00 PM | February 10, 2020 05:00 PM | February 24, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 245 days | Sanitary-Plumber
106 | Yes | CMU1.4.3 | Auto Scheduled | งานระบบสุขาภิบาล ชั้น 2 | 408 days | 3 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
107 | Yes | CMU1.4.3.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
108 | Yes | CMU1.4.3.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 109FS+15 days |  | 110FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 21, 2019 05:00 PM | August 24, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
109 | Yes | CMU1.4.3.1.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 36 |  | 113SS,104,108FS+15 days | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 23, 2018 05:00 PM | March 28, 2019 05:00 PM | August 25, 2019 05:00 PM | December 28, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
110 | Yes | CMU1.4.3.1.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 108FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 12, 2019 05:00 PM | January 15, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
111 | Yes | CMU1.4.3.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
112 | Yes | CMU1.4.3.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 113FS+15 days |  | 114FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 27, 2019 05:00 PM | August 30, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
113 | Yes | CMU1.4.3.2.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 109SS |  | 104,112FS+15 days | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 28, 2018 05:00 PM | April 02, 2019 05:00 PM | August 25, 2019 05:00 PM | December 28, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
114 | Yes | CMU1.4.3.2.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 112FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 19, 2019 05:00 PM | January 22, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
115 | Yes | CMU1.4.4 | Auto Scheduled | งานระบบไฟฟ้า ชั้น 2 | 147 days | 3 |  |  |  | November 10, 2019 8:00 AM | April 4, 2020 5:00 PM | October 20, 2018 05:00 PM | March 15, 2019 05:00 PM | May 12, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 180 days | 180 days | 180 days
116 | Yes | CMU1.4.4.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 60 days | 4 | 118FS+7 days |  |  | February 5, 2020 8:00 AM | April 4, 2020 5:00 PM | February 14, 2020 05:00 PM | April 13, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 180 days | 180 days | 180 days | Electrician
117 | Yes | CMU1.4.4.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 60 days | 4 | 118FS+7 days |  |  | February 5, 2020 8:00 AM | April 4, 2020 5:00 PM | February 16, 2020 05:00 PM | April 15, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 180 days | 180 days | 180 days | Electrician
118 | Yes | CMU1.4.4.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 121SS+30 days |  | 117FS+7 days,116FS+7 days | November 10, 2019 8:00 AM | January 28, 2020 5:00 PM | November 17, 2019 05:00 PM | February 04, 2020 05:00 PM | May 12, 2020 05:00 PM | July 30, 2020 05:00 PM | As Soon As Possible |  | No | 180 days | 180 days | 0 days | Electrician
119 | Yes | CMU1.4.4.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 121SS+30 days |  |  | November 10, 2019 8:00 AM | January 28, 2020 5:00 PM | November 19, 2019 05:00 PM | February 06, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 247 days | 247 days | 247 days | Electrician
120 | Yes | CMU1.4.4.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 121SS+30 days |  |  | November 10, 2019 8:00 AM | January 28, 2020 5:00 PM | November 21, 2019 05:00 PM | February 08, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 247 days | 247 days | 247 days | Electrician
121 | Yes | CMU1.4.5 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้น 2 | 180 days | 3 | 94SS |  | 120SS+30 days,119SS+30 days,118SS+30 days,123,212FS-15 days,217FS-30 days,222FS-15 days,228FS-15 days,242FS-7 days,248FS-7 days | October 11, 2019 8:00 AM | April 7, 2020 5:00 PM | October 16, 2019 05:00 PM | April 12, 2020 05:00 PM | June 04, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Skilled carpenter
122 | Yes | CMU1.5 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้น 1 | 686 days | 2 |  |  |  | November 16, 2018 8:00 AM | October 1, 2020 5:00 PM | October 17, 2018 05:00 PM | September 01, 2020 05:00 PM | November 20, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 0 days | 0 days
123 | Yes | CMU1.5.1 | Auto Scheduled | งานรื้อถอน ชั้น 1 (รื้อขนไป) | 30 days | 3 | 121 | 63 | 124,127FS+45 days,128FS+45 days,131FS+45 days,152SS,193SS,194SS,195SS,196SS,197SS,202SS,204SS,205SS,206SS,207SS | April 8, 2020 8:00 AM | May 7, 2020 5:00 PM | April 13, 2020 05:00 PM | May 12, 2020 05:00 PM | July 19, 2018 05:00 PM | August 17, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | General worker
124 | Yes | CMU1.5.2 | Auto Scheduled | งานโครงสร้างวิศวกรรม ชั้น 1 | 75 days | 3 | 123 |  |  | May 8, 2020 8:00 AM | July 21, 2020 5:00 PM | May 14, 2020 05:00 PM | July 27, 2020 05:00 PM | July 23, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 72 days | 72 days | 72 days | General worker
125 | Yes | CMU1.5.3 | Auto Scheduled | งานสถาปัตยกรรม ชั้น 1 | 548 days | 3 |  |  |  | March 22, 2019 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | April 16, 2020 05:00 PM | April 07, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 12 days | 12 days
126 | Yes | CMU1.5.3.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 127,129,130 |  |  | August 21, 2020 8:00 AM | September 19, 2020 5:00 PM | August 26, 2020 05:00 PM | September 24, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | Skilled carpenter
127 | Yes | CMU1.5.3.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 123FS+45 days |  | 126,132 | June 22, 2020 8:00 AM | August 20, 2020 5:00 PM | June 27, 2020 05:00 PM | August 25, 2020 05:00 PM | October 02, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
128 | Yes | CMU1.5.3.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 123FS+45 days |  | 129,130 | June 22, 2020 8:00 AM | July 21, 2020 5:00 PM | June 27, 2020 05:00 PM | July 26, 2020 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
129 | Yes | CMU1.5.3.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 128 |  | 126,132 | July 22, 2020 8:00 AM | August 20, 2020 5:00 PM | July 27, 2020 05:00 PM | August 25, 2020 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | Skilled carpenter
130 | Yes | CMU1.5.3.5 | Auto Scheduled | งานบันได | 30 days | 4 | 128 |  | 126,132 | July 22, 2020 8:00 AM | August 20, 2020 5:00 PM | July 27, 2020 05:00 PM | August 25, 2020 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
131 | Yes | CMU1.5.3.6 | Auto Scheduled | งานตกแต่งอื่น ๆ | 60 days | 4 | 123FS+45 days |  |  | June 22, 2020 8:00 AM | August 20, 2020 5:00 PM | June 27, 2020 05:00 PM | August 25, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 42 days | 42 days | 42 days | General worker
132 | Yes | CMU1.5.3.7 | Auto Scheduled | งานสี | 30 days | 4 | 127,129,130 |  |  | August 21, 2020 8:00 AM | September 19, 2020 5:00 PM | August 26, 2020 05:00 PM | September 24, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
133 | Yes | CMU1.5.3.8 | Auto Scheduled | งานสุขภัณฑ์ | 315 days | 4 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 22, 2018 05:00 PM | September 01, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
134 | Yes | CMU1.5.3.8.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 135FS+135 days |  | 136FS+135 days | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | August 24, 2019 05:00 PM | September 07, 2019 05:00 PM | April 24, 2020 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
135 | Yes | CMU1.5.3.8.2 | Auto Scheduled | ZONE T-2 กลาง | 15 days | 5 | 140,144 |  | 134FS+135 days,164FS+135 days | March 22, 2019 8:00 AM | April 5, 2019 5:00 PM | March 24, 2019 05:00 PM | April 07, 2019 05:00 PM | November 26, 2019 05:00 PM | December 10, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
136 | Yes | CMU1.5.3.8.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 15 days | 5 | 134FS+135 days |  |  | January 16, 2020 8:00 AM | January 30, 2020 5:00 PM | January 24, 2020 05:00 PM | February 07, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 245 days | Sanitary-Plumber
137 | Yes | CMU1.5.4 | Auto Scheduled | งานระบบสุขาภิบาล ชั้น 1 | 408 days | 3 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 278 days | 44 days
138 | Yes | CMU1.5.4.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 278 days | 44 days
139 | Yes | CMU1.5.4.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 140FS+15 days |  | 141FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 13, 2019 05:00 PM | August 16, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
140 | Yes | CMU1.5.4.1.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 36 |  | 139FS+15 days,144SS,135,167FS+15 days | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 16, 2018 05:00 PM | March 21, 2019 05:00 PM | January 03, 2019 05:00 PM | May 08, 2019 05:00 PM | As Soon As Possible |  | No | 44 days | 44 days | 0 days | Sanitary-Plumber
141 | Yes | CMU1.5.4.1.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 139FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 07, 2019 05:00 PM | January 10, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
142 | Yes | CMU1.5.4.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 278 days | 44 days
143 | Yes | CMU1.5.4.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 144FS+15 days |  | 145FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 11, 2019 05:00 PM | August 14, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
144 | Yes | CMU1.5.4.2.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 140SS |  | 143FS+15 days,135,169FS+15 days | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 16, 2018 05:00 PM | March 21, 2019 05:00 PM | January 03, 2019 05:00 PM | May 08, 2019 05:00 PM | As Soon As Possible |  | No | 44 days | 44 days | 0 days | Sanitary-Plumber
145 | Yes | CMU1.5.4.2.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 143FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 03, 2019 05:00 PM | January 06, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
146 | Yes | CMU1.5.5 | Auto Scheduled | งานระบบไฟฟ้า ชั้น 1 | 147 days | 3 |  |  |  | May 8, 2020 8:00 AM | October 1, 2020 5:00 PM | October 21, 2018 05:00 PM | March 16, 2019 05:00 PM | May 12, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 0 days | 0 days | 0 days
147 | Yes | CMU1.5.5.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 60 days | 4 | 149FS+7 days |  |  | August 3, 2020 8:00 AM | October 1, 2020 5:00 PM | August 08, 2020 05:00 PM | October 06, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Electrician
148 | Yes | CMU1.5.5.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 60 days | 4 | 149FS+7 days |  |  | August 3, 2020 8:00 AM | October 1, 2020 5:00 PM | August 08, 2020 05:00 PM | October 06, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Electrician
149 | Yes | CMU1.5.5.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 152SS+30 days |  | 148FS+7 days,147FS+7 days | May 8, 2020 8:00 AM | July 26, 2020 5:00 PM | May 13, 2020 05:00 PM | July 31, 2020 05:00 PM | May 12, 2020 05:00 PM | July 30, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Electrician
150 | Yes | CMU1.5.5.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 152SS+30 days |  |  | May 8, 2020 8:00 AM | July 26, 2020 5:00 PM | May 13, 2020 05:00 PM | July 31, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 67 days | 67 days | 67 days | Electrician
151 | Yes | CMU1.5.5.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 152SS+30 days |  |  | May 8, 2020 8:00 AM | July 26, 2020 5:00 PM | May 13, 2020 05:00 PM | July 31, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 67 days | 67 days | 67 days | Electrician
152 | Yes | CMU1.5.6 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้น 1 | 165 days | 3 | 123SS |  | 151SS+30 days,150SS+30 days,149SS+30 days,154SS,211FS-30 days,210FS-30 days,216FS-45 days,221FS-30 days,227FS-30 days,226FS-30 days,232FS-45 days,241FS-7 days,247FS-7 days | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 13, 2020 05:00 PM | September 24, 2020 05:00 PM | November 26, 2019 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Skilled carpenter
153 | Yes | CMU1.6 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้นใต้ดิน | 533 days | 2 |  |  |  | April 6, 2019 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | April 01, 2020 05:00 PM | April 22, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 12 days | 12 days
154 | Yes | CMU1.6.1 | Auto Scheduled | งานรื้อถอน ชั้นใต้ดิน (รื้อขนไป) | 30 days | 3 | 152SS |  | 155,158FS+45 days,159FS+45 days,177SS,176SS,175SS,174SS | April 8, 2020 8:00 AM | May 7, 2020 5:00 PM | April 13, 2020 05:00 PM | May 12, 2020 05:00 PM | November 26, 2019 05:00 PM | December 25, 2019 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
155 | Yes | CMU1.6.2 | Auto Scheduled | งานโครงสร้างวิศวกรรม ชั้นใต้ดิน | 75 days | 3 | 154 |  |  | May 8, 2020 8:00 AM | July 21, 2020 5:00 PM | May 14, 2020 05:00 PM | July 27, 2020 05:00 PM | July 23, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 72 days | 72 days | 72 days | General worker
156 | Yes | CMU1.6.3 | Auto Scheduled | งานสถาปัตยกรรม ชั้นใต้ดิน | 398 days | 3 |  |  |  | August 19, 2019 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | November 18, 2019 05:00 PM | September 04, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 320 days | 12 days | 12 days
157 | Yes | CMU1.6.3.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 158,160,161 |  |  | August 21, 2020 8:00 AM | September 19, 2020 5:00 PM | September 12, 2020 05:00 PM | October 11, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | Skilled carpenter
158 | Yes | CMU1.6.3.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 154FS+45 days |  | 157,162 | June 22, 2020 8:00 AM | August 20, 2020 5:00 PM | June 27, 2020 05:00 PM | August 25, 2020 05:00 PM | February 09, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
159 | Yes | CMU1.6.3.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 154FS+45 days |  | 160,161 | June 22, 2020 8:00 AM | July 21, 2020 5:00 PM | July 14, 2020 05:00 PM | August 12, 2020 05:00 PM | August 22, 2020 05:00 PM | September 20, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
160 | Yes | CMU1.6.3.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 159 |  | 157,162 | July 22, 2020 8:00 AM | August 20, 2020 5:00 PM | August 13, 2020 05:00 PM | September 11, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | Skilled carpenter
161 | Yes | CMU1.6.3.5 | Auto Scheduled | งานบันได | 30 days | 4 | 159 |  | 157,162 | July 22, 2020 8:00 AM | August 20, 2020 5:00 PM | August 13, 2020 05:00 PM | September 11, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
162 | Yes | CMU1.6.3.6 | Auto Scheduled | งานสี | 30 days | 4 | 158,160,161 |  |  | August 21, 2020 8:00 AM | September 19, 2020 5:00 PM | September 12, 2020 05:00 PM | October 11, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
163 | Yes | CMU1.6.3.7 | Auto Scheduled | งานสุขภัณฑ์ | 15 days | 4 |  |  |  | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | October 20, 2018 05:00 PM | November 03, 2018 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 395 days | 395 days | 395 days
164 | Yes | CMU1.6.3.7.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 135FS+135 days |  |  | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | August 27, 2019 05:00 PM | September 10, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 395 days | 395 days | 395 days | Sanitary-Plumber
165 | Yes | CMU1.6.4 | Auto Scheduled | งานระบบสุขาภิบาล ชั้นใต้ดิน | 501 days | 3 |  |  |  | April 6, 2019 8:00 AM | August 18, 2020 5:00 PM | October 17, 2018 05:00 PM | February 29, 2020 05:00 PM | May 24, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 44 days | 44 days
166 | Yes | CMU1.6.4.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 126 days | 4 |  |  |  | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | October 21, 2018 05:00 PM | February 23, 2019 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 419 days | 419 days | 419 days
167 | Yes | CMU1.6.4.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 140FS+15 days |  |  | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 13, 2019 05:00 PM | August 16, 2019 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 419 days | 419 days | 419 days | Sanitary-Plumber
168 | Yes | CMU1.6.4.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 126 days | 4 |  |  |  | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | October 21, 2018 05:00 PM | February 23, 2019 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 44 days | 44 days
169 | Yes | CMU1.6.4.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 144FS+15 days |  | 170FS+300 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 06, 2019 05:00 PM | August 09, 2019 05:00 PM | May 24, 2019 05:00 PM | September 26, 2019 05:00 PM | As Soon As Possible |  | No | 44 days | 44 days | 0 days | Sanitary-Plumber
170 | Yes | CMU1.6.4.3 | Auto Scheduled | งานระบบระบายน้ำฝน | 75 days | 4 | 169FS+300 days |  |  | June 5, 2020 8:00 AM | August 18, 2020 5:00 PM | June 05, 2020 05:00 PM | August 18, 2020 05:00 PM | July 23, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 44 days | 44 days | 44 days | Sanitary-Plumber
171 | Yes | CMU1.6.5 | Auto Scheduled | งานระบบไฟฟ้า ชั้นใต้ดิน | 147 days | 3 |  |  |  | April 8, 2020 8:00 AM | September 1, 2020 5:00 PM | October 23, 2018 05:00 PM | March 18, 2019 05:00 PM | May 12, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 30 days | 30 days | 30 days
172 | Yes | CMU1.6.5.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 60 days | 4 | 174FS+7 days |  |  | July 4, 2020 8:00 AM | September 1, 2020 5:00 PM | July 09, 2020 05:00 PM | September 06, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 30 days | 30 days | 30 days | Electrician
173 | Yes | CMU1.6.5.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 60 days | 4 | 174FS+7 days |  |  | July 4, 2020 8:00 AM | September 1, 2020 5:00 PM | July 09, 2020 05:00 PM | September 06, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 30 days | 30 days | 30 days | Electrician
174 | Yes | CMU1.6.5.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 154SS |  | 173FS+7 days,172FS+7 days | April 8, 2020 8:00 AM | June 26, 2020 5:00 PM | April 13, 2020 05:00 PM | July 01, 2020 05:00 PM | May 12, 2020 05:00 PM | July 30, 2020 05:00 PM | As Soon As Possible |  | No | 30 days | 30 days | 0 days | Electrician
175 | Yes | CMU1.6.5.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 154SS |  |  | April 8, 2020 8:00 AM | June 26, 2020 5:00 PM | April 16, 2020 05:00 PM | July 04, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 97 days | 97 days | 97 days | Electrician
176 | Yes | CMU1.6.5.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 154SS |  |  | April 8, 2020 8:00 AM | June 26, 2020 5:00 PM | April 15, 2020 05:00 PM | July 03, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 97 days | 97 days | 97 days | Electrician
177 | Yes | CMU1.6.6 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้นใต้ดิน | 165 days | 3 | 154SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 13, 2020 05:00 PM | September 24, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | Skilled carpenter
178 | Yes | CMU1.7 | Auto Scheduled | หมวดงานระบบคอมพิวเตอร์และแจ้งเหตุเพลิงไหม้ | 670 days | 2 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
179 | Yes | CMU1.7.1 | Auto Scheduled | งานระบบคอมพิวเตอร์ | 670 days | 3 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
180 | Yes | CMU1.7.1.1 | Auto Scheduled | ชั้นที่ 4 | 160 days | 4 | 36FS+14 days |  | 181 | November 30, 2018 8:00 AM | May 8, 2019 5:00 PM | November 30, 2018 05:00 PM | May 08, 2019 05:00 PM | April 24, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
181 | Yes | CMU1.7.1.2 | Auto Scheduled | ชั้นที่ 3 | 175 days | 4 | 180 | 182 | 182 | May 9, 2019 8:00 AM | October 30, 2019 5:00 PM | May 09, 2019 05:00 PM | October 30, 2019 05:00 PM | April 09, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
182 | Yes | CMU1.7.1.3 | Auto Scheduled | ชั้นที่ 2 | 175 days | 4 | 181 | 183 | 183,184 | October 31, 2019 8:00 AM | April 22, 2020 5:00 PM | October 31, 2019 05:00 PM | April 22, 2020 05:00 PM | April 09, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
183 | Yes | CMU1.7.1.4 | Auto Scheduled | ชั้นที่ 1 | 160 days | 4 | 182 | 180 |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 23, 2020 05:00 PM | September 29, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
184 | Yes | CMU1.7.1.5 | Auto Scheduled | ชั้นใต้ดิน | 160 days | 4 | 182 | 183SS |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 23, 2020 05:00 PM | September 29, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
185 | Yes | CMU1.7.2 | Auto Scheduled | ระบบแจ้งเหตุเพลิงไหม้ | 670 days | 3 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
186 | Yes | CMU1.7.2.1 | Auto Scheduled | ชั้นที่ 4 | 160 days | 4 | 36FS+14 days |  | 187 | November 30, 2018 8:00 AM | May 8, 2019 5:00 PM | November 30, 2018 05:00 PM | May 08, 2019 05:00 PM | April 24, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
187 | Yes | CMU1.7.2.2 | Auto Scheduled | ชั้นที่ 3 | 175 days | 4 | 186 | 188 | 188 | May 9, 2019 8:00 AM | October 30, 2019 5:00 PM | May 09, 2019 05:00 PM | October 30, 2019 05:00 PM | April 09, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
188 | Yes | CMU1.7.2.3 | Auto Scheduled | ชั้นที่ 2 | 175 days | 4 | 187 | 189 | 189,190 | October 31, 2019 8:00 AM | April 22, 2020 5:00 PM | October 31, 2019 05:00 PM | April 22, 2020 05:00 PM | April 09, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
189 | Yes | CMU1.7.2.4 | Auto Scheduled | ชั้นที่ 1 | 160 days | 4 | 188 | 186 |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 23, 2020 05:00 PM | September 29, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
190 | Yes | CMU1.7.2.5 | Auto Scheduled | ชั้นใต้ดิน | 160 days | 4 | 188 | 189SS |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 23, 2020 05:00 PM | September 29, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
191 | Yes | CMU1.8 | Auto Scheduled | หมวดงานสีภายนอก งานซ่อมแซมและตกแต่งภายนอกอาคาร | 660 days | 2 |  |  |  | November 30, 2018 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | August 06, 2020 05:00 PM | December 16, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 507 days | 12 days | 12 days
192 | Yes | CMU1.8.1 | Auto Scheduled | งานสีภายนอกและงานซ่อมแซมพื้นผิวภายนอกอาคาร | 660 days | 3 |  |  |  | November 30, 2018 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | August 06, 2020 05:00 PM | December 16, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 507 days | 12 days | 12 days
193 | Yes | CMU1.8.1.1 | Auto Scheduled | งานขัดลอกสีทาผนังเดิม | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 13, 2020 05:00 PM | September 24, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
194 | Yes | CMU1.8.1.2 | Auto Scheduled | น้ำยาทาปูนเก่า (สีรองพื้น) | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 13, 2020 05:00 PM | September 24, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
195 | Yes | CMU1.8.1.3 | Auto Scheduled | งานทาสีภายนอก (ทา 2 เที่ยว) ไม่รวมชั้นใต้ดิน | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 13, 2020 05:00 PM | September 24, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
196 | Yes | CMU1.8.1.4 | Auto Scheduled | งานทำความสะอาดและซ่อมแซมผนังกรุอิฐโชว์แนว (อ้างอิงราคางานขัดลอกสี) | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 13, 2020 05:00 PM | September 24, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
197 | Yes | CMU1.8.1.5 | Auto Scheduled | น้ำยาเคลือบผิวผนังอิฐโชว์แนว (อ้างอิงค่าทาน้ำยากันเชื้อรา) | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 13, 2020 05:00 PM | September 24, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
198 | Yes | CMU1.8.1.6 | Auto Scheduled | งานรื้อถอนแผ่นวัสดุกันซึมหลังคาดาดฟ้า (รื้อขนไป) | 90 days | 4 | 36FS+14 days |  |  | November 30, 2018 8:00 AM | February 27, 2019 5:00 PM | December 03, 2018 05:00 PM | March 02, 2019 05:00 PM | July 08, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 582 days | 582 days | 582 days | General worker
199 | Yes | CMU1.8.1.7 | Auto Scheduled | งานแผ่นวัสดุกันซึมแบบเป่าไฟผิวทราย | 90 days | 4 | 36FS+14 days |  |  | November 30, 2018 8:00 AM | February 27, 2019 5:00 PM | December 04, 2018 05:00 PM | March 03, 2019 05:00 PM | July 08, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 582 days | 582 days | 582 days | General worker
200 | Yes | CMU1.8.1.8 | Auto Scheduled | งานกันซึมชนิด Polyurethane สูตรน้ำมัน ชนิดยืดหยุ่นสูงเป็นพิเศษ | 90 days | 4 | 36FS+14 days |  |  | November 30, 2018 8:00 AM | February 27, 2019 5:00 PM | December 03, 2018 05:00 PM | March 02, 2019 05:00 PM | July 08, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 582 days | 582 days | 582 days | General worker
201 | Yes | CMU1.8.2 | Auto Scheduled | งานตกแต่งภายนอกอาคาร | 165 days | 3 |  |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | October 20, 2018 05:00 PM | April 02, 2019 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 12 days | 12 days | 12 days
202 | Yes | CMU1.8.2.1 | Auto Scheduled | ตะแกรงเหล็กฉีกกันนก XS-32 | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 13, 2020 05:00 PM | September 24, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
203 | Yes | CMU1.9 | Auto Scheduled | หมวดงานบริเวณ | 165 days | 2 |  |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | October 22, 2018 05:00 PM | April 04, 2019 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 12 days | 12 days | 12 days
204 | Yes | CMU1.9.1 | Auto Scheduled | งานรื้อถอน งานบริเวณ | 165 days | 3 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 13, 2020 05:00 PM | September 24, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
205 | Yes | CMU1.9.2 | Auto Scheduled | งานโครงสร้างวิศวกรรม งานบริเวณ | 165 days | 3 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 13, 2020 05:00 PM | September 24, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
206 | Yes | CMU1.9.3 | Auto Scheduled | งานสถาปัตยกรรม งานบริเวณ | 165 days | 3 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 13, 2020 05:00 PM | September 24, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
207 | Yes | CMU1.9.4 | Auto Scheduled | งานระบบไฟฟ้า งานบริเวณ | 165 days | 3 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 13, 2020 05:00 PM | September 24, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | Electrician
208 | Yes | CMU1.10 | Auto Scheduled | หมวดงานครุภัณฑ์จัดซื้อ | 670 days | 2 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
209 | Yes | CMU1.10.1 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัว | 510 days | 3 |  |  |  | April 14, 2019 8:00 AM | September 4, 2020 5:00 PM | October 17, 2018 05:00 PM | March 09, 2020 05:00 PM | May 15, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 522 days | 27 days | 27 days
210 | Yes | CMU1.10.1.1 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้นใต้ดิน | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | August 31, 2020 05:00 PM | September 14, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
211 | Yes | CMU1.10.1.2 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้น 1 | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | September 02, 2020 05:00 PM | September 16, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
212 | Yes | CMU1.10.1.3 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้น 2 | 15 days | 4 | 121FS-15 days |  |  | March 24, 2020 8:00 AM | April 7, 2020 5:00 PM | April 01, 2020 05:00 PM | April 15, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Skilled carpenter
213 | Yes | CMU1.10.1.4 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้น 3 | 15 days | 4 | 92FS-15 days |  |  | September 26, 2019 8:00 AM | October 10, 2019 5:00 PM | October 06, 2019 05:00 PM | October 20, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Skilled carpenter
214 | Yes | CMU1.10.1.5 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้น 4 | 15 days | 4 | 63 |  |  | April 14, 2019 8:00 AM | April 28, 2019 5:00 PM | April 21, 2019 05:00 PM | May 05, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 522 days | 522 days | 522 days | Skilled carpenter
215 | Yes | CMU1.10.2 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ | 525 days | 3 |  |  |  | March 30, 2019 8:00 AM | September 4, 2020 5:00 PM | October 17, 2018 05:00 PM | March 24, 2020 05:00 PM | April 30, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 522 days | 27 days | 27 days
216 | Yes | CMU1.10.2.1 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ ชั้น 1 | 30 days | 4 | 152FS-45 days |  |  | August 6, 2020 8:00 AM | September 4, 2020 5:00 PM | August 17, 2020 05:00 PM | September 15, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
217 | Yes | CMU1.10.2.2 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ ชั้น 2 | 30 days | 4 | 121FS-30 days |  |  | March 9, 2020 8:00 AM | April 7, 2020 5:00 PM | March 17, 2020 05:00 PM | April 15, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Skilled carpenter
218 | Yes | CMU1.10.2.3 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ ชั้น 3 | 30 days | 4 | 92FS-30 days |  |  | September 11, 2019 8:00 AM | October 10, 2019 5:00 PM | September 18, 2019 05:00 PM | October 17, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Skilled carpenter
219 | Yes | CMU1.10.2.4 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ ชั้น 4 | 30 days | 4 | 63FS-15 days |  |  | March 30, 2019 8:00 AM | April 28, 2019 5:00 PM | April 02, 2019 05:00 PM | May 01, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 522 days | 522 days | 522 days | Skilled carpenter
220 | Yes | CMU1.10.3 | Auto Scheduled | งานผ้าม่าน | 510 days | 3 |  |  |  | April 14, 2019 8:00 AM | September 4, 2020 5:00 PM | October 17, 2018 05:00 PM | March 09, 2020 05:00 PM | May 15, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 522 days | 27 days | 27 days
221 | Yes | CMU1.10.3.1 | Auto Scheduled | งานผ้าม่าน ชั้น 1 | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | August 30, 2020 05:00 PM | September 13, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
222 | Yes | CMU1.10.3.2 | Auto Scheduled | งานผ้าม่าน ชั้น 2 | 15 days | 4 | 121FS-15 days |  |  | March 24, 2020 8:00 AM | April 7, 2020 5:00 PM | April 02, 2020 05:00 PM | April 16, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Skilled carpenter
223 | Yes | CMU1.10.3.3 | Auto Scheduled | งานผ้าม่าน ชั้น 3 | 15 days | 4 | 92FS-15 days |  |  | September 26, 2019 8:00 AM | October 10, 2019 5:00 PM | October 05, 2019 05:00 PM | October 19, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Skilled carpenter
224 | Yes | CMU1.10.3.4 | Auto Scheduled | งานผ้าม่าน ชั้น 4 | 15 days | 4 | 63 |  |  | April 14, 2019 8:00 AM | April 28, 2019 5:00 PM | April 24, 2019 05:00 PM | May 08, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 522 days | 522 days | 522 days | Skilled carpenter
225 | Yes | CMU1.10.4 | Auto Scheduled | งานป้าย | 510 days | 3 |  |  |  | April 14, 2019 8:00 AM | September 4, 2020 5:00 PM | October 17, 2018 05:00 PM | March 09, 2020 05:00 PM | May 15, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 522 days | 27 days | 27 days
226 | Yes | CMU1.10.4.1 | Auto Scheduled | งานป้าย ชั้นใต้ดิน | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | August 30, 2020 05:00 PM | September 13, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
227 | Yes | CMU1.10.4.2 | Auto Scheduled | งานป้าย ชั้น 1 | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | September 01, 2020 05:00 PM | September 15, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
228 | Yes | CMU1.10.4.3 | Auto Scheduled | งานป้าย ชั้น 2 | 15 days | 4 | 121FS-15 days |  |  | March 24, 2020 8:00 AM | April 7, 2020 5:00 PM | April 01, 2020 05:00 PM | April 15, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Skilled carpenter
229 | Yes | CMU1.10.4.4 | Auto Scheduled | งานป้าย ชั้น 3 | 15 days | 4 | 92FS-15 days |  |  | September 26, 2019 8:00 AM | October 10, 2019 5:00 PM | October 05, 2019 05:00 PM | October 19, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Skilled carpenter
230 | Yes | CMU1.10.4.5 | Auto Scheduled | งานป้าย ชั้น 4 | 15 days | 4 | 63 |  |  | April 14, 2019 8:00 AM | April 28, 2019 5:00 PM | April 22, 2019 05:00 PM | May 06, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 522 days | 522 days | 522 days | Skilled carpenter
231 | Yes | CMU1.10.5 | Auto Scheduled | งานอื่นๆ | 15 days | 3 |  |  |  | August 6, 2020 8:00 AM | August 20, 2020 5:00 PM | October 20, 2018 05:00 PM | November 03, 2018 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 42 days | 42 days | 42 days
232 | Yes | CMU1.10.5.1 | Auto Scheduled | ตู้อลูมิเนียมพับขึ้นรูป พ่นสี ครอบตู้กดน้ำ | 15 days | 4 | 152FS-45 days |  |  | August 6, 2020 8:00 AM | August 20, 2020 5:00 PM | August 16, 2020 05:00 PM | August 30, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 42 days | 42 days | 42 days | General worker
233 | Yes | CMU1.10.6 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ | 670 days | 3 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
234 | Yes | CMU1.10.6.1 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้นใต้ดิน | 160 days | 4 | 236 |  |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 30, 2020 05:00 PM | October 06, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
235 | Yes | CMU1.10.6.2 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้น 1 | 160 days | 4 | 236 |  |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 30, 2020 05:00 PM | October 06, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
236 | Yes | CMU1.10.6.3 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้น 2 | 175 days | 4 | 237 |  | 235,234 | October 31, 2019 8:00 AM | April 22, 2020 5:00 PM | November 07, 2019 05:00 PM | April 29, 2020 05:00 PM | March 12, 2020 05:00 PM | September 02, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
237 | Yes | CMU1.10.6.4 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้น 3 | 175 days | 4 | 238 |  | 236 | May 9, 2019 8:00 AM | October 30, 2019 5:00 PM | May 16, 2019 05:00 PM | November 06, 2019 05:00 PM | March 12, 2020 05:00 PM | September 02, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
238 | Yes | CMU1.10.6.5 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้น 4 | 160 days | 4 | 36FS+14 days |  | 237 | November 30, 2018 8:00 AM | May 8, 2019 5:00 PM | December 03, 2018 05:00 PM | May 11, 2019 05:00 PM | March 27, 2020 05:00 PM | September 02, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
239 | Yes | CMU1.10.7 | Auto Scheduled | งานระบบเครื่องเสียงประกาศ (ใช้ลำโพงของเดิม) | 539 days | 3 |  |  |  | April 7, 2019 8:00 AM | September 26, 2020 5:00 PM | October 17, 2018 05:00 PM | April 07, 2020 05:00 PM | April 16, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 530 days | 5 days | 5 days
240 | Yes | CMU1.10.7.1 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้นใต้ดิน | 7 days | 4 | 241 |  |  | September 20, 2020 8:00 AM | September 26, 2020 5:00 PM | September 30, 2020 05:00 PM | October 06, 2020 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 5 days | 5 days | 5 days | Electrician
241 | Yes | CMU1.10.7.2 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้น 1 | 7 days | 4 | 152FS-7 days |  | 240 | September 13, 2020 8:00 AM | September 19, 2020 5:00 PM | September 18, 2020 05:00 PM | September 24, 2020 05:00 PM | September 09, 2020 05:00 PM | September 15, 2020 05:00 PM | As Soon As Possible |  | No | 5 days | 5 days | 0 days | Electrician
242 | Yes | CMU1.10.7.3 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้น 2 | 7 days | 4 | 121FS-7 days |  |  | April 1, 2020 8:00 AM | April 7, 2020 5:00 PM | April 08, 2020 05:00 PM | April 14, 2020 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Electrician
243 | Yes | CMU1.10.7.4 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้น 3 | 7 days | 4 | 92FS-7 days |  |  | October 4, 2019 8:00 AM | October 10, 2019 5:00 PM | October 13, 2019 05:00 PM | October 19, 2019 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Electrician
244 | Yes | CMU1.10.7.5 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้น 4 | 7 days | 4 | 63FS-7 days |  |  | April 7, 2019 8:00 AM | April 13, 2019 5:00 PM | April 14, 2019 05:00 PM | April 20, 2019 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 537 days | 537 days | 537 days | Electrician
245 | Yes | CMU1.10.8 | Auto Scheduled | งานระบบกล้องวงจรปิด (ใช้กล้องวงจรปิดของเดิม) | 539 days | 3 |  |  |  | April 7, 2019 8:00 AM | September 26, 2020 5:00 PM | October 17, 2018 05:00 PM | April 07, 2020 05:00 PM | April 16, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 530 days | 5 days | 5 days
246 | Yes | CMU1.10.8.1 | Auto Scheduled | งานกล้องวงจรปิด ชั้นใต้ดิน | 7 days | 4 | 247 |  |  | September 20, 2020 8:00 AM | September 26, 2020 5:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 5 days | 5 days | 5 days | Electrician
247 | Yes | CMU1.10.8.2 | Auto Scheduled | งานกล้องวงจรปิด ชั้น 1 | 7 days | 4 | 152FS-7 days |  | 246 | September 13, 2020 8:00 AM | September 19, 2020 5:00 PM | September 18, 2020 05:00 PM | September 24, 2020 05:00 PM | September 09, 2020 05:00 PM | September 15, 2020 05:00 PM | As Soon As Possible |  | No | 5 days | 5 days | 0 days | Electrician
248 | Yes | CMU1.10.8.3 | Auto Scheduled | งานกล้องวงจรปิด ชั้น 2 | 7 days | 4 | 121FS-7 days |  |  | April 1, 2020 8:00 AM | April 7, 2020 5:00 PM | April 10, 2020 05:00 PM | April 16, 2020 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Electrician
249 | Yes | CMU1.10.8.4 | Auto Scheduled | งานกล้องวงจรปิด ชั้น 3 | 7 days | 4 | 92FS-7 days |  |  | October 4, 2019 8:00 AM | October 10, 2019 5:00 PM | October 13, 2019 05:00 PM | October 19, 2019 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Electrician
250 | Yes | CMU1.10.8.5 | Auto Scheduled | งานกล้องวงจรปิด ชั้น 4 | 7 days | 4 | 63FS-7 days |  |  | April 7, 2019 8:00 AM | April 13, 2019 5:00 PM | April 11, 2019 05:00 PM | April 17, 2019 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 537 days | 537 days | 537 days | Electrician

## solutoion_11
ID | Active | WBS | Task_Mode | Name | Duration | Outline_Level | Predecessors | Predecessors2 | Successors | Start_Date | Finish_Date | Early_Start | Early_Finish | Late_Start | Late_Finish | Constraint_Type | Constraint_Date | Summary | Start_Slack | Finish_Slack | Free_Slack | Resource_Names
1 | Yes | CMU1 | Auto Scheduled | โครงการปรับปรุงสำนักหอสมุด มหาวิทยาลัยเชียงใหม่ | 716 days | 1 |  |  |  | October 17, 2018 8:00 AM | October 1, 2020 5:00 PM | October 17, 2018 05:00 PM | October 01, 2020 05:00 PM | October 21, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 0 days | 0 days | 0 days
2 | Yes | CMU1.1 | Auto Scheduled | หมวดเตรียมการ | 675 days | 2 |  |  |  | October 17, 2018 8:00 AM | August 21, 2020 5:00 PM | October 17, 2018 05:00 PM | August 21, 2020 05:00 PM | December 01, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 41 days | 41 days | 41 days
3 | Yes | CMU1.1.1 | Auto Scheduled | งานอาคารสนามและผังบริเวณโครงการ | 14 days | 3 | 4FS-7 days |  |  | October 26, 2018 8:00 AM | November 8, 2018 5:00 PM | November 01, 2018 05:00 PM | November 14, 2018 05:00 PM | September 22, 2020 05:00 PM | October 05, 2020 05:00 PM | Start No Earlier Than | Oct 24 '18 | No | 693 days | 693 days | 693 days | Engineer
4 | Yes | CMU1.1.2 | Auto Scheduled | งานเชื่อมต่อระบบสาธารณูปโภคโครงการ | 16 days | 3 |  |  | 3FS-7 days | October 17, 2018 8:00 AM | November 1, 2018 5:00 PM | October 19, 2018 05:00 PM | November 03, 2018 05:00 PM | September 13, 2020 05:00 PM | September 28, 2020 05:00 PM | As Soon As Possible |  | No | 693 days | 693 days | 0 days | Engineer
5 | Yes | CMU1.1.3 | Auto Scheduled | งานตรวจทดสอบระบบภายในอาคารก่อนดำเนินการปรับปรุง | 675 days | 3 |  |  |  | October 17, 2018 8:00 AM | August 21, 2020 5:00 PM | October 17, 2018 05:00 PM | August 21, 2020 05:00 PM | December 01, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 41 days | 41 days | 41 days
6 | Yes | CMU1.1.3.1 | Auto Scheduled | ชั้นที่ 4 | 15 days | 4 |  |  | 7FS+150 days | October 17, 2018 8:00 AM | October 31, 2018 5:00 PM | October 19, 2018 05:00 PM | November 02, 2018 05:00 PM | December 01, 2018 05:00 PM | December 15, 2018 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
7 | Yes | CMU1.1.3.2 | Auto Scheduled | ชั้นที่ 3 | 15 days | 4 | 6FS+150 days |  | 8FS+150 days | March 31, 2019 8:00 AM | April 14, 2019 5:00 PM | April 07, 2019 05:00 PM | April 21, 2019 05:00 PM | May 15, 2019 05:00 PM | May 29, 2019 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
8 | Yes | CMU1.1.3.3 | Auto Scheduled | ชั้นที่ 2 | 15 days | 4 | 7FS+150 days |  | 9FS+150 days | September 12, 2019 8:00 AM | September 26, 2019 5:00 PM | September 28, 2019 05:00 PM | October 12, 2019 05:00 PM | October 27, 2019 05:00 PM | November 10, 2019 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
9 | Yes | CMU1.1.3.4 | Auto Scheduled | ชั้นที่ 1 | 15 days | 4 | 8FS+150 days |  | 10FS+150 days | February 24, 2020 8:00 AM | March 9, 2020 5:00 PM | March 19, 2020 05:00 PM | April 02, 2020 05:00 PM | April 09, 2020 05:00 PM | April 23, 2020 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
10 | Yes | CMU1.1.3.5 | Auto Scheduled | ชั้นใต้ดินและภายนอก | 15 days | 4 | 9FS+150 days |  |  | August 7, 2020 8:00 AM | August 21, 2020 5:00 PM | September 11, 2020 05:00 PM | September 25, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 41 days | Engineer
11 | Yes | CMU1.1.4 | Auto Scheduled | งานสำรวจอุปกรณ์ไฟฟ้า, สุขภัณฑ์และครุภัณฑ์ (ของเดิม) ก่อนดำเนินการปรับปรุง | 675 days | 3 |  |  |  | October 17, 2018 8:00 AM | August 21, 2020 5:00 PM | October 17, 2018 05:00 PM | August 21, 2020 05:00 PM | December 01, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 41 days | 41 days | 41 days
12 | Yes | CMU1.1.4.1 | Auto Scheduled | ชั้นที่ 4 | 15 days | 4 |  |  | 13FS+150 days | October 17, 2018 8:00 AM | October 31, 2018 5:00 PM | October 20, 2018 05:00 PM | November 03, 2018 05:00 PM | December 01, 2018 05:00 PM | December 15, 2018 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
13 | Yes | CMU1.1.4.2 | Auto Scheduled | ชั้นที่ 3 | 15 days | 4 | 12FS+150 days |  | 14FS+150 days | March 31, 2019 8:00 AM | April 14, 2019 5:00 PM | April 06, 2019 05:00 PM | April 20, 2019 05:00 PM | May 15, 2019 05:00 PM | May 29, 2019 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
14 | Yes | CMU1.1.4.3 | Auto Scheduled | ชั้นที่ 2 | 15 days | 4 | 13FS+150 days |  | 15FS+150 days | September 12, 2019 8:00 AM | September 26, 2019 5:00 PM | September 24, 2019 05:00 PM | October 08, 2019 05:00 PM | October 27, 2019 05:00 PM | November 10, 2019 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
15 | Yes | CMU1.1.4.4 | Auto Scheduled | ชั้นที่ 1 | 15 days | 4 | 14FS+150 days |  | 16FS+150 days | February 24, 2020 8:00 AM | March 9, 2020 5:00 PM | March 17, 2020 05:00 PM | March 31, 2020 05:00 PM | April 09, 2020 05:00 PM | April 23, 2020 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
16 | Yes | CMU1.1.4.5 | Auto Scheduled | ชั้นใต้ดินและภายนอก | 15 days | 4 | 15FS+150 days |  |  | August 7, 2020 8:00 AM | August 21, 2020 5:00 PM | September 09, 2020 05:00 PM | September 23, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 41 days | Engineer
17 | Yes | CMU1.1.5 | Auto Scheduled | งานเอกสารขออนุมัติใช้วัสดุ, Shop Drawing และครุภัณฑ์ของโครงการ | 106 days | 3 |  |  |  | October 17, 2018 8:00 AM | January 30, 2019 5:00 PM | October 22, 2018 05:00 PM | February 04, 2019 05:00 PM | June 22, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 610 days | 610 days | 610 days
18 | Yes | CMU1.1.5.1 | Auto Scheduled | แบบ Shop Drawing ชั้นที่ 4 | 20 days | 4 |  |  | 19,25SS+14 days,26SS+14 days | October 17, 2018 8:00 AM | November 5, 2018 5:00 PM | October 17, 2018 05:00 PM | November 05, 2018 05:00 PM | October 01, 2018 05:00 PM | October 20, 2018 05:00 PM | As Soon As Possible |  | No | 610 days | 610 days | 0 days | Engineer
19 | Yes | CMU1.1.5.2 | Auto Scheduled | แบบ Shop Drawing ชั้นที่ 3 | 20 days | 4 | 18 |  | 20FS-7 days | November 6, 2018 8:00 AM | November 25, 2018 5:00 PM | November 17, 2018 05:00 PM | December 06, 2018 05:00 PM | July 13, 2020 05:00 PM | August 01, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
20 | Yes | CMU1.1.5.3 | Auto Scheduled | แบบ Shop Drawing ชั้นที่ 2 | 20 days | 4 | 19FS-7 days |  | 21FS-7 days | November 19, 2018 8:00 AM | December 8, 2018 5:00 PM | December 03, 2018 05:00 PM | December 22, 2018 05:00 PM | July 26, 2020 05:00 PM | August 14, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
21 | Yes | CMU1.1.5.4 | Auto Scheduled | แบบ Shop Drawing ชั้นที่ 1 | 20 days | 4 | 20FS-7 days |  | 22FS-7 days | December 2, 2018 8:00 AM | December 21, 2018 5:00 PM | December 22, 2018 05:00 PM | January 10, 2019 05:00 PM | August 08, 2020 05:00 PM | August 27, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
22 | Yes | CMU1.1.5.5 | Auto Scheduled | แบบ Shop Drawing ชั้นใต้ดิน | 20 days | 4 | 21FS-7 days |  | 23FS-7 days | December 15, 2018 8:00 AM | January 3, 2019 5:00 PM | January 11, 2019 05:00 PM | January 30, 2019 05:00 PM | August 21, 2020 05:00 PM | September 09, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
23 | Yes | CMU1.1.5.6 | Auto Scheduled | แบบ Shop Drawing ภายนอกอาคาร | 20 days | 4 | 22FS-7 days |  | 24FS-7 days | December 28, 2018 8:00 AM | January 16, 2019 5:00 PM | January 28, 2019 05:00 PM | February 16, 2019 05:00 PM | September 03, 2020 05:00 PM | September 22, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
24 | Yes | CMU1.1.5.7 | Auto Scheduled | แบบ Shop Drawing landscape | 20 days | 4 | 23FS-7 days |  |  | January 10, 2019 8:00 AM | January 29, 2019 5:00 PM | February 17, 2019 05:00 PM | March 08, 2019 05:00 PM | September 16, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 611 days | Engineer
25 | Yes | CMU1.1.5.8 | Auto Scheduled | แบบ Shop Drawing งานปรับปรุง ครุภัณฑ์ | 92 days | 4 | 18SS+14 days |  |  | October 31, 2018 8:00 AM | January 30, 2019 5:00 PM | November 07, 2018 05:00 PM | February 06, 2019 05:00 PM | July 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 610 days | 610 days | 610 days | Engineer
26 | Yes | CMU1.1.5.9 | Auto Scheduled | แบบ Shop Drawing งานจัดซื้อครุภัณฑ์ | 92 days | 4 | 18SS+14 days |  |  | October 31, 2018 8:00 AM | January 30, 2019 5:00 PM | November 08, 2018 05:00 PM | February 07, 2019 05:00 PM | July 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 610 days | 610 days | 610 days | Engineer
27 | Yes | CMU1.1.6 | Auto Scheduled | งานตรวจทดสอบระบบ, งานอบรมผู้ใช้อาคาร และ As-Built Drawing | 30 days | 3 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 23, 2018 05:00 PM | November 21, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 686 days | 686 days | 686 days
28 | Yes | CMU1.1.6.1 | Auto Scheduled | ชั้นที่ 4 | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 27, 2018 05:00 PM | November 25, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
29 | Yes | CMU1.1.6.2 | Auto Scheduled | ชั้นที่ 3 | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
30 | Yes | CMU1.1.6.3 | Auto Scheduled | ชั้นที่ 2 | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 22, 2018 05:00 PM | November 20, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
31 | Yes | CMU1.1.6.4 | Auto Scheduled | ชั้นที่ 1 | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 28, 2018 05:00 PM | November 26, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
32 | Yes | CMU1.1.6.5 | Auto Scheduled | ชั้นใต้ดิน | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 25, 2018 05:00 PM | November 23, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
33 | Yes | CMU1.1.6.6 | Auto Scheduled | ทั้งอาคาร | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 23, 2018 05:00 PM | November 21, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
34 | Yes | CMU1.1.7 | Auto Scheduled | งานบริหารงานก่อสร้างและงานอื่น ๆ | 0 days | 3 |  |  |  | October 17, 2018 8:00 AM | October 17, 2018 8:00 AM | October 20, 2018 05:00 PM | October 19, 2018 05:00 PM | October 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 716 days | 716 days | 716 days | Engineer
35 | Yes | CMU1.2 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้น 4 | 471 days | 2 |  |  |  | October 17, 2018 8:00 AM | January 30, 2020 5:00 PM | October 17, 2018 05:00 PM | January 30, 2020 05:00 PM | June 23, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 0 days | 245 days | 0 days
36 | Yes | CMU1.2.1 | Auto Scheduled | งานรื้อถอน ชั้น 4 (รื้อขนไป) | 30 days | 3 |  |  | 39FS+45 days,40FS+45 days,51,63SS+14 days,80,109,140,180FS+14 days,186FS+14 days,198FS+14 days,199FS+14 days,200FS+14 days,238FS+14 days | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 17, 2018 05:00 PM | November 15, 2018 05:00 PM | March 11, 2018 05:00 PM | April 09, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | General worker
37 | Yes | CMU1.2.2 | Auto Scheduled | งานสถาปัตยกรรม ชั้น 4 | 396 days | 3 |  |  |  | December 31, 2018 8:00 AM | January 30, 2020 5:00 PM | October 17, 2018 05:00 PM | November 16, 2019 05:00 PM | September 06, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 326 days | 245 days | 245 days
38 | Yes | CMU1.2.2.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 39,41,42 |  |  | March 1, 2019 8:00 AM | March 30, 2019 5:00 PM | March 13, 2019 05:00 PM | April 11, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 551 days | Skilled carpenter
39 | Yes | CMU1.2.2.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 36FS+45 days |  | 38,43 | December 31, 2018 8:00 AM | February 28, 2019 5:00 PM | January 05, 2019 05:00 PM | March 05, 2019 05:00 PM | July 15, 2020 05:00 PM | September 12, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 0 days | General worker
40 | Yes | CMU1.2.2.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 36FS+45 days |  | 41,42 | December 31, 2018 8:00 AM | January 29, 2019 5:00 PM | January 03, 2019 05:00 PM | February 01, 2019 05:00 PM | August 14, 2020 05:00 PM | September 12, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 0 days | General worker
41 | Yes | CMU1.2.2.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 40 |  | 38,43 | January 30, 2019 8:00 AM | February 28, 2019 5:00 PM | February 05, 2019 05:00 PM | March 06, 2019 05:00 PM | August 14, 2020 05:00 PM | September 12, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 0 days | Skilled carpenter
42 | Yes | CMU1.2.2.5 | Auto Scheduled | งานบันได | 30 days | 4 | 40 |  | 38,43 | January 30, 2019 8:00 AM | February 28, 2019 5:00 PM | February 05, 2019 05:00 PM | March 06, 2019 05:00 PM | August 14, 2020 05:00 PM | September 12, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 0 days | General worker
43 | Yes | CMU1.2.2.6 | Auto Scheduled | งานสี | 30 days | 4 | 39,41,42 |  |  | March 1, 2019 8:00 AM | March 30, 2019 5:00 PM | March 10, 2019 05:00 PM | April 08, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 551 days | General worker
44 | Yes | CMU1.2.2.7 | Auto Scheduled | งานสุขภัณฑ์ | 315 days | 4 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 20, 2018 05:00 PM | August 30, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
45 | Yes | CMU1.2.2.7.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 46FS+135 days |  | 47FS+135 days | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | September 18, 2019 05:00 PM | October 02, 2019 05:00 PM | April 24, 2020 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
46 | Yes | CMU1.2.2.7.2 | Auto Scheduled | ZONE T-2 กลาง | 15 days | 5 | 51,55 |  | 45FS+135 days | March 22, 2019 8:00 AM | April 5, 2019 5:00 PM | April 12, 2019 05:00 PM | April 26, 2019 05:00 PM | November 26, 2019 05:00 PM | December 10, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
47 | Yes | CMU1.2.2.7.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 15 days | 5 | 45FS+135 days |  |  | January 16, 2020 8:00 AM | January 30, 2020 5:00 PM | February 22, 2020 05:00 PM | March 07, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 245 days | Sanitary-Plumber
48 | Yes | CMU1.2.3 | Auto Scheduled | งานระบบสุขาภิบาล ชั้น 4 | 408 days | 3 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
49 | Yes | CMU1.2.3.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
50 | Yes | CMU1.2.3.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 51FS+15 days |  | 52FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 18, 2019 05:00 PM | August 21, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
51 | Yes | CMU1.2.3.1.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 36 |  | 50FS+15 days,46,55SS | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 23, 2018 05:00 PM | March 28, 2019 05:00 PM | August 25, 2019 05:00 PM | December 28, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
52 | Yes | CMU1.2.3.1.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 50FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 10, 2019 05:00 PM | January 13, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
53 | Yes | CMU1.2.3.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
54 | Yes | CMU1.2.3.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 55FS+15 days |  | 56FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 29, 2019 05:00 PM | September 01, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
55 | Yes | CMU1.2.3.2.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 51SS |  | 54FS+15 days,46 | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | December 02, 2018 05:00 PM | April 06, 2019 05:00 PM | August 25, 2019 05:00 PM | December 28, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
56 | Yes | CMU1.2.3.2.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 54FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 29, 2019 05:00 PM | February 01, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
57 | Yes | CMU1.2.4 | Auto Scheduled | งานระบบไฟฟ้า ชั้น 4 | 117 days | 3 |  |  |  | November 30, 2018 8:00 AM | March 26, 2019 5:00 PM | October 21, 2018 05:00 PM | February 14, 2019 05:00 PM | June 11, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 555 days | 555 days | 555 days
58 | Yes | CMU1.2.4.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 30 days | 4 | 60FS+7 days |  |  | February 25, 2019 8:00 AM | March 26, 2019 5:00 PM | March 03, 2019 05:00 PM | April 01, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 555 days | 555 days | 555 days | Electrician
59 | Yes | CMU1.2.4.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 30 days | 4 | 60FS+7 days |  |  | February 25, 2019 8:00 AM | March 26, 2019 5:00 PM | March 04, 2019 05:00 PM | April 02, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 555 days | 555 days | 555 days | Electrician
60 | Yes | CMU1.2.4.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 63SS+30 days |  | 58FS+7 days,59FS+7 days | November 30, 2018 8:00 AM | February 17, 2019 5:00 PM | December 03, 2018 05:00 PM | February 20, 2019 05:00 PM | June 11, 2020 05:00 PM | August 29, 2020 05:00 PM | As Soon As Possible |  | No | 555 days | 555 days | 0 days | Electrician
61 | Yes | CMU1.2.4.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 63SS+30 days |  |  | November 30, 2018 8:00 AM | February 17, 2019 5:00 PM | December 03, 2018 05:00 PM | February 20, 2019 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 592 days | 592 days | 592 days | Electrician
62 | Yes | CMU1.2.4.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 63SS+30 days |  |  | November 30, 2018 8:00 AM | February 17, 2019 5:00 PM | December 06, 2018 05:00 PM | February 23, 2019 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 592 days | 592 days | 592 days | Electrician
63 | Yes | CMU1.2.5 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้น 4 | 165 days | 3 | 36SS+14 days |  | 62SS+30 days,60SS+30 days,61SS+30 days,65,214,219FS-15 days,224,230,244FS-7 days,250FS-7 days | October 31, 2018 8:00 AM | April 13, 2019 5:00 PM | October 31, 2018 05:00 PM | April 13, 2019 05:00 PM | June 19, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Skilled carpenter
64 | Yes | CMU1.3 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้น 3 | 441 days | 2 |  |  |  | November 16, 2018 8:00 AM | January 30, 2020 5:00 PM | October 17, 2018 05:00 PM | December 31, 2019 05:00 PM | July 23, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 149 days | 245 days | 149 days
65 | Yes | CMU1.3.1 | Auto Scheduled | งานรื้อถอน ชั้น 3 (รื้อขนไป) | 30 days | 3 | 63 | 121 | 68FS+45 days,69FS+45 days,92SS | April 14, 2019 8:00 AM | May 13, 2019 5:00 PM | April 14, 2019 05:00 PM | May 13, 2019 05:00 PM | July 19, 2018 05:00 PM | August 17, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | General worker
66 | Yes | CMU1.3.2 | Auto Scheduled | งานสถาปัตยกรรม ชั้น 3 | 315 days | 3 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 23, 2018 05:00 PM | September 02, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
67 | Yes | CMU1.3.2.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 68,70,71 |  |  | August 27, 2019 8:00 AM | September 25, 2019 5:00 PM | August 30, 2019 05:00 PM | September 28, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 372 days | Skilled carpenter
68 | Yes | CMU1.3.2.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 65FS+45 days |  | 67,72 | June 28, 2019 8:00 AM | August 26, 2019 5:00 PM | June 28, 2019 05:00 PM | August 26, 2019 05:00 PM | October 02, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 0 days | General worker
69 | Yes | CMU1.3.2.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 65FS+45 days |  | 70,71 | June 28, 2019 8:00 AM | July 27, 2019 5:00 PM | June 28, 2019 05:00 PM | July 27, 2019 05:00 PM | April 15, 2019 05:00 PM | May 14, 2019 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 0 days | General worker
70 | Yes | CMU1.3.2.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 69 |  | 67,72 | July 28, 2019 8:00 AM | August 26, 2019 5:00 PM | July 28, 2019 05:00 PM | August 26, 2019 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 0 days | Skilled carpenter
71 | Yes | CMU1.3.2.5 | Auto Scheduled | งานบันได | 30 days | 4 | 69 |  | 67,72 | July 28, 2019 8:00 AM | August 26, 2019 5:00 PM | July 28, 2019 05:00 PM | August 26, 2019 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 0 days | General worker
72 | Yes | CMU1.3.2.6 | Auto Scheduled | งานสี | 30 days | 4 | 68,70,71 |  |  | August 27, 2019 8:00 AM | September 25, 2019 5:00 PM | August 30, 2019 05:00 PM | September 28, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 372 days | General worker
73 | Yes | CMU1.3.2.7 | Auto Scheduled | งานสุขภัณฑ์ | 315 days | 4 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 21, 2018 05:00 PM | August 31, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
74 | Yes | CMU1.3.2.7.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 75FS+135 days |  | 76FS+135 days | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | August 29, 2019 05:00 PM | September 12, 2019 05:00 PM | April 24, 2020 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
75 | Yes | CMU1.3.2.7.2 | Auto Scheduled | ZONE T-2 กลาง | 15 days | 5 | 80,84 |  | 74FS+135 days | March 22, 2019 8:00 AM | April 5, 2019 5:00 PM | March 28, 2019 05:00 PM | April 11, 2019 05:00 PM | November 26, 2019 05:00 PM | December 10, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
76 | Yes | CMU1.3.2.7.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 15 days | 5 | 74FS+135 days |  |  | January 16, 2020 8:00 AM | January 30, 2020 5:00 PM | January 31, 2020 05:00 PM | February 14, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 245 days | Sanitary-Plumber
77 | Yes | CMU1.3.3 | Auto Scheduled | งานระบบสุขาภิบาล ชั้น 3 | 408 days | 3 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
78 | Yes | CMU1.3.3.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
79 | Yes | CMU1.3.3.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 80FS+15 days |  | 81FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 15, 2019 05:00 PM | August 18, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
80 | Yes | CMU1.3.3.1.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 36 |  | 79FS+15 days,84SS,75 | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 16, 2018 05:00 PM | March 21, 2019 05:00 PM | January 09, 2019 05:00 PM | May 14, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
81 | Yes | CMU1.3.3.1.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 79FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 09, 2019 05:00 PM | January 12, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
82 | Yes | CMU1.3.3.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
83 | Yes | CMU1.3.3.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 84FS+15 days |  | 85FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 12, 2019 05:00 PM | August 15, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
84 | Yes | CMU1.3.3.2.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 80SS |  | 83FS+15 days,75 | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 16, 2018 05:00 PM | March 21, 2019 05:00 PM | January 09, 2019 05:00 PM | May 14, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
85 | Yes | CMU1.3.3.2.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 83FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 10, 2019 05:00 PM | January 13, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
86 | Yes | CMU1.3.4 | Auto Scheduled | งานระบบไฟฟ้า ชั้น 3 | 147 days | 3 |  |  |  | May 14, 2019 8:00 AM | October 7, 2019 5:00 PM | October 21, 2018 05:00 PM | March 16, 2019 05:00 PM | May 12, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 360 days | 360 days | 360 days
87 | Yes | CMU1.3.4.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 60 days | 4 | 89FS+7 days |  |  | August 9, 2019 8:00 AM | October 7, 2019 5:00 PM | August 17, 2019 05:00 PM | October 15, 2019 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 360 days | 360 days | 360 days | Electrician
88 | Yes | CMU1.3.4.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 60 days | 4 | 89FS+7 days |  |  | August 9, 2019 8:00 AM | October 7, 2019 5:00 PM | August 25, 2019 05:00 PM | October 23, 2019 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 360 days | 360 days | 360 days | Electrician
89 | Yes | CMU1.3.4.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 92SS+30 days |  | 88FS+7 days,87FS+7 days | May 14, 2019 8:00 AM | August 1, 2019 5:00 PM | May 19, 2019 05:00 PM | August 06, 2019 05:00 PM | May 12, 2020 05:00 PM | July 30, 2020 05:00 PM | As Soon As Possible |  | No | 360 days | 360 days | 0 days | Electrician
90 | Yes | CMU1.3.4.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 92SS+30 days |  |  | May 14, 2019 8:00 AM | August 1, 2019 5:00 PM | May 22, 2019 05:00 PM | August 09, 2019 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 427 days | 427 days | 427 days | Electrician
91 | Yes | CMU1.3.4.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 92SS+30 days |  |  | May 14, 2019 8:00 AM | August 1, 2019 5:00 PM | May 24, 2019 05:00 PM | August 11, 2019 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 427 days | 427 days | 427 days | Electrician
92 | Yes | CMU1.3.5 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้น 3 | 180 days | 3 | 65SS |  | 91SS+30 days,90SS+30 days,89SS+30 days,94,213FS-15 days,218FS-30 days,223FS-15 days,229FS-15 days,243FS-7 days,249FS-7 days | April 14, 2019 8:00 AM | October 10, 2019 5:00 PM | April 17, 2019 05:00 PM | October 13, 2019 05:00 PM | October 12, 2019 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Skilled carpenter
93 | Yes | CMU1.4 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้น 2 | 509 days | 2 |  |  |  | November 16, 2018 8:00 AM | April 7, 2020 5:00 PM | October 17, 2018 05:00 PM | March 08, 2020 05:00 PM | May 16, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 177 days | 177 days
94 | Yes | CMU1.4.1 | Auto Scheduled | งานรื้อถอน ชั้น 2 (รื้อขนไป) | 30 days | 3 | 92 | 152 | 97FS+45 days,98FS+45 days,121SS | October 11, 2019 8:00 AM | November 9, 2019 5:00 PM | October 14, 2019 05:00 PM | November 12, 2019 05:00 PM | June 04, 2018 05:00 PM | July 03, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | General worker
95 | Yes | CMU1.4.2 | Auto Scheduled | งานสถาปัตยกรรม ชั้น 2 | 368 days | 3 |  |  |  | March 22, 2019 8:00 AM | March 23, 2020 5:00 PM | October 17, 2018 05:00 PM | October 19, 2019 05:00 PM | October 04, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 192 days | 192 days
96 | Yes | CMU1.4.2.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 97,99,100 |  |  | February 23, 2020 8:00 AM | March 23, 2020 5:00 PM | March 06, 2020 05:00 PM | April 04, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 192 days | Skilled carpenter
97 | Yes | CMU1.4.2.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 94FS+45 days |  | 96,101 | December 25, 2019 8:00 AM | February 22, 2020 5:00 PM | December 28, 2019 05:00 PM | February 25, 2020 05:00 PM | February 09, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 0 days | General worker
98 | Yes | CMU1.4.2.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 94FS+45 days |  | 99,100 | December 25, 2019 8:00 AM | January 23, 2020 5:00 PM | December 31, 2019 05:00 PM | January 29, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 0 days | General worker
99 | Yes | CMU1.4.2.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 98 |  | 96,101 | January 24, 2020 8:00 AM | February 22, 2020 5:00 PM | February 02, 2020 05:00 PM | March 02, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 0 days | Skilled carpenter
100 | Yes | CMU1.4.2.5 | Auto Scheduled | งานบันได | 30 days | 4 | 98 |  | 96,101 | January 24, 2020 8:00 AM | February 22, 2020 5:00 PM | February 02, 2020 05:00 PM | March 02, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 0 days | General worker
101 | Yes | CMU1.4.2.6 | Auto Scheduled | งานสี | 30 days | 4 | 97,99,100 |  |  | February 23, 2020 8:00 AM | March 23, 2020 5:00 PM | March 09, 2020 05:00 PM | April 07, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 192 days | General worker
102 | Yes | CMU1.4.2.7 | Auto Scheduled | งานสุขภัณฑ์ | 315 days | 4 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 21, 2018 05:00 PM | August 31, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
103 | Yes | CMU1.4.2.7.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 104FS+135 days |  | 105FS+135 days | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | September 08, 2019 05:00 PM | September 22, 2019 05:00 PM | April 24, 2020 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
104 | Yes | CMU1.4.2.7.2 | Auto Scheduled | ZONE T-2 กลาง | 15 days | 5 | 113,109 |  | 103FS+135 days | March 22, 2019 8:00 AM | April 5, 2019 5:00 PM | April 07, 2019 05:00 PM | April 21, 2019 05:00 PM | November 26, 2019 05:00 PM | December 10, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
105 | Yes | CMU1.4.2.7.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 15 days | 5 | 103FS+135 days |  |  | January 16, 2020 8:00 AM | January 30, 2020 5:00 PM | February 13, 2020 05:00 PM | February 27, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 245 days | Sanitary-Plumber
106 | Yes | CMU1.4.3 | Auto Scheduled | งานระบบสุขาภิบาล ชั้น 2 | 408 days | 3 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
107 | Yes | CMU1.4.3.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
108 | Yes | CMU1.4.3.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 109FS+15 days |  | 110FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 16, 2019 05:00 PM | August 19, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
109 | Yes | CMU1.4.3.1.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 36 |  | 113SS,104,108FS+15 days | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 22, 2018 05:00 PM | March 27, 2019 05:00 PM | August 25, 2019 05:00 PM | December 28, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
110 | Yes | CMU1.4.3.1.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 108FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 07, 2019 05:00 PM | January 10, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
111 | Yes | CMU1.4.3.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
112 | Yes | CMU1.4.3.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 113FS+15 days |  | 114FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 28, 2019 05:00 PM | August 31, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
113 | Yes | CMU1.4.3.2.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 109SS |  | 104,112FS+15 days | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 28, 2018 05:00 PM | April 02, 2019 05:00 PM | August 25, 2019 05:00 PM | December 28, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
114 | Yes | CMU1.4.3.2.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 112FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 20, 2019 05:00 PM | January 23, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
115 | Yes | CMU1.4.4 | Auto Scheduled | งานระบบไฟฟ้า ชั้น 2 | 147 days | 3 |  |  |  | November 10, 2019 8:00 AM | April 4, 2020 5:00 PM | October 20, 2018 05:00 PM | March 15, 2019 05:00 PM | May 12, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 180 days | 180 days | 180 days
116 | Yes | CMU1.4.4.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 60 days | 4 | 118FS+7 days |  |  | February 5, 2020 8:00 AM | April 4, 2020 5:00 PM | February 12, 2020 05:00 PM | April 11, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 180 days | 180 days | 180 days | Electrician
117 | Yes | CMU1.4.4.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 60 days | 4 | 118FS+7 days |  |  | February 5, 2020 8:00 AM | April 4, 2020 5:00 PM | February 13, 2020 05:00 PM | April 12, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 180 days | 180 days | 180 days | Electrician
118 | Yes | CMU1.4.4.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 121SS+30 days |  | 117FS+7 days,116FS+7 days | November 10, 2019 8:00 AM | January 28, 2020 5:00 PM | November 15, 2019 05:00 PM | February 02, 2020 05:00 PM | May 12, 2020 05:00 PM | July 30, 2020 05:00 PM | As Soon As Possible |  | No | 180 days | 180 days | 0 days | Electrician
119 | Yes | CMU1.4.4.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 121SS+30 days |  |  | November 10, 2019 8:00 AM | January 28, 2020 5:00 PM | November 17, 2019 05:00 PM | February 04, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 247 days | 247 days | 247 days | Electrician
120 | Yes | CMU1.4.4.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 121SS+30 days |  |  | November 10, 2019 8:00 AM | January 28, 2020 5:00 PM | November 19, 2019 05:00 PM | February 06, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 247 days | 247 days | 247 days | Electrician
121 | Yes | CMU1.4.5 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้น 2 | 180 days | 3 | 94SS |  | 120SS+30 days,119SS+30 days,118SS+30 days,123,212FS-15 days,217FS-30 days,222FS-15 days,228FS-15 days,242FS-7 days,248FS-7 days | October 11, 2019 8:00 AM | April 7, 2020 5:00 PM | October 14, 2019 05:00 PM | April 10, 2020 05:00 PM | June 04, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Skilled carpenter
122 | Yes | CMU1.5 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้น 1 | 686 days | 2 |  |  |  | November 16, 2018 8:00 AM | October 1, 2020 5:00 PM | October 17, 2018 05:00 PM | September 01, 2020 05:00 PM | November 20, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 0 days | 0 days
123 | Yes | CMU1.5.1 | Auto Scheduled | งานรื้อถอน ชั้น 1 (รื้อขนไป) | 30 days | 3 | 121 | 63 | 124,127FS+45 days,128FS+45 days,131FS+45 days,152SS,193SS,194SS,195SS,196SS,197SS,202SS,204SS,205SS,206SS,207SS | April 8, 2020 8:00 AM | May 7, 2020 5:00 PM | April 11, 2020 05:00 PM | May 10, 2020 05:00 PM | July 19, 2018 05:00 PM | August 17, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | General worker
124 | Yes | CMU1.5.2 | Auto Scheduled | งานโครงสร้างวิศวกรรม ชั้น 1 | 75 days | 3 | 123 |  |  | May 8, 2020 8:00 AM | July 21, 2020 5:00 PM | May 12, 2020 05:00 PM | July 25, 2020 05:00 PM | July 23, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 72 days | 72 days | 72 days | General worker
125 | Yes | CMU1.5.3 | Auto Scheduled | งานสถาปัตยกรรม ชั้น 1 | 548 days | 3 |  |  |  | March 22, 2019 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | April 16, 2020 05:00 PM | April 07, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 12 days | 12 days
126 | Yes | CMU1.5.3.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 127,129,130 |  |  | August 21, 2020 8:00 AM | September 19, 2020 5:00 PM | August 24, 2020 05:00 PM | September 22, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | Skilled carpenter
127 | Yes | CMU1.5.3.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 123FS+45 days |  | 126,132 | June 22, 2020 8:00 AM | August 20, 2020 5:00 PM | June 25, 2020 05:00 PM | August 23, 2020 05:00 PM | October 02, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
128 | Yes | CMU1.5.3.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 123FS+45 days |  | 129,130 | June 22, 2020 8:00 AM | July 21, 2020 5:00 PM | June 25, 2020 05:00 PM | July 24, 2020 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
129 | Yes | CMU1.5.3.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 128 |  | 126,132 | July 22, 2020 8:00 AM | August 20, 2020 5:00 PM | July 25, 2020 05:00 PM | August 23, 2020 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | Skilled carpenter
130 | Yes | CMU1.5.3.5 | Auto Scheduled | งานบันได | 30 days | 4 | 128 |  | 126,132 | July 22, 2020 8:00 AM | August 20, 2020 5:00 PM | July 25, 2020 05:00 PM | August 23, 2020 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
131 | Yes | CMU1.5.3.6 | Auto Scheduled | งานตกแต่งอื่น ๆ | 60 days | 4 | 123FS+45 days |  |  | June 22, 2020 8:00 AM | August 20, 2020 5:00 PM | June 25, 2020 05:00 PM | August 23, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 42 days | 42 days | 42 days | General worker
132 | Yes | CMU1.5.3.7 | Auto Scheduled | งานสี | 30 days | 4 | 127,129,130 |  |  | August 21, 2020 8:00 AM | September 19, 2020 5:00 PM | August 24, 2020 05:00 PM | September 22, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
133 | Yes | CMU1.5.3.8 | Auto Scheduled | งานสุขภัณฑ์ | 315 days | 4 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 22, 2018 05:00 PM | September 01, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
134 | Yes | CMU1.5.3.8.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 135FS+135 days |  | 136FS+135 days | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | August 24, 2019 05:00 PM | September 07, 2019 05:00 PM | April 24, 2020 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
135 | Yes | CMU1.5.3.8.2 | Auto Scheduled | ZONE T-2 กลาง | 15 days | 5 | 140,144 |  | 134FS+135 days,164FS+135 days | March 22, 2019 8:00 AM | April 5, 2019 5:00 PM | March 24, 2019 05:00 PM | April 07, 2019 05:00 PM | November 26, 2019 05:00 PM | December 10, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
136 | Yes | CMU1.5.3.8.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 15 days | 5 | 134FS+135 days |  |  | January 16, 2020 8:00 AM | January 30, 2020 5:00 PM | January 24, 2020 05:00 PM | February 07, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 245 days | Sanitary-Plumber
137 | Yes | CMU1.5.4 | Auto Scheduled | งานระบบสุขาภิบาล ชั้น 1 | 408 days | 3 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 278 days | 44 days
138 | Yes | CMU1.5.4.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 278 days | 44 days
139 | Yes | CMU1.5.4.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 140FS+15 days |  | 141FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 13, 2019 05:00 PM | August 16, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
140 | Yes | CMU1.5.4.1.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 36 |  | 139FS+15 days,144SS,135,167FS+15 days | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 16, 2018 05:00 PM | March 21, 2019 05:00 PM | January 03, 2019 05:00 PM | May 08, 2019 05:00 PM | As Soon As Possible |  | No | 44 days | 44 days | 0 days | Sanitary-Plumber
141 | Yes | CMU1.5.4.1.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 139FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 07, 2019 05:00 PM | January 10, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
142 | Yes | CMU1.5.4.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 278 days | 44 days
143 | Yes | CMU1.5.4.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 144FS+15 days |  | 145FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 12, 2019 05:00 PM | August 15, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
144 | Yes | CMU1.5.4.2.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 140SS |  | 143FS+15 days,135,169FS+15 days | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 16, 2018 05:00 PM | March 21, 2019 05:00 PM | January 03, 2019 05:00 PM | May 08, 2019 05:00 PM | As Soon As Possible |  | No | 44 days | 44 days | 0 days | Sanitary-Plumber
145 | Yes | CMU1.5.4.2.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 143FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 04, 2019 05:00 PM | January 07, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
146 | Yes | CMU1.5.5 | Auto Scheduled | งานระบบไฟฟ้า ชั้น 1 | 147 days | 3 |  |  |  | May 8, 2020 8:00 AM | October 1, 2020 5:00 PM | October 21, 2018 05:00 PM | March 16, 2019 05:00 PM | May 12, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 0 days | 0 days | 0 days
147 | Yes | CMU1.5.5.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 60 days | 4 | 149FS+7 days |  |  | August 3, 2020 8:00 AM | October 1, 2020 5:00 PM | August 06, 2020 05:00 PM | October 04, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Electrician
148 | Yes | CMU1.5.5.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 60 days | 4 | 149FS+7 days |  |  | August 3, 2020 8:00 AM | October 1, 2020 5:00 PM | August 06, 2020 05:00 PM | October 04, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Electrician
149 | Yes | CMU1.5.5.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 152SS+30 days |  | 148FS+7 days,147FS+7 days | May 8, 2020 8:00 AM | July 26, 2020 5:00 PM | May 11, 2020 05:00 PM | July 29, 2020 05:00 PM | May 12, 2020 05:00 PM | July 30, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Electrician
150 | Yes | CMU1.5.5.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 152SS+30 days |  |  | May 8, 2020 8:00 AM | July 26, 2020 5:00 PM | May 11, 2020 05:00 PM | July 29, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 67 days | 67 days | 67 days | Electrician
151 | Yes | CMU1.5.5.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 152SS+30 days |  |  | May 8, 2020 8:00 AM | July 26, 2020 5:00 PM | May 11, 2020 05:00 PM | July 29, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 67 days | 67 days | 67 days | Electrician
152 | Yes | CMU1.5.6 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้น 1 | 165 days | 3 | 123SS |  | 151SS+30 days,150SS+30 days,149SS+30 days,154SS,211FS-30 days,210FS-30 days,216FS-45 days,221FS-30 days,227FS-30 days,226FS-30 days,232FS-45 days,241FS-7 days,247FS-7 days | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 11, 2020 05:00 PM | September 22, 2020 05:00 PM | November 26, 2019 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Skilled carpenter
153 | Yes | CMU1.6 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้นใต้ดิน | 533 days | 2 |  |  |  | April 6, 2019 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | April 01, 2020 05:00 PM | April 22, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 12 days | 12 days
154 | Yes | CMU1.6.1 | Auto Scheduled | งานรื้อถอน ชั้นใต้ดิน (รื้อขนไป) | 30 days | 3 | 152SS |  | 155,158FS+45 days,159FS+45 days,177SS,176SS,175SS,174SS | April 8, 2020 8:00 AM | May 7, 2020 5:00 PM | April 11, 2020 05:00 PM | May 10, 2020 05:00 PM | November 26, 2019 05:00 PM | December 25, 2019 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
155 | Yes | CMU1.6.2 | Auto Scheduled | งานโครงสร้างวิศวกรรม ชั้นใต้ดิน | 75 days | 3 | 154 |  |  | May 8, 2020 8:00 AM | July 21, 2020 5:00 PM | May 12, 2020 05:00 PM | July 25, 2020 05:00 PM | July 23, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 72 days | 72 days | 72 days | General worker
156 | Yes | CMU1.6.3 | Auto Scheduled | งานสถาปัตยกรรม ชั้นใต้ดิน | 398 days | 3 |  |  |  | August 19, 2019 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | November 18, 2019 05:00 PM | September 04, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 320 days | 12 days | 12 days
157 | Yes | CMU1.6.3.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 158,160,161 |  |  | August 21, 2020 8:00 AM | September 19, 2020 5:00 PM | September 13, 2020 05:00 PM | October 12, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | Skilled carpenter
158 | Yes | CMU1.6.3.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 154FS+45 days |  | 157,162 | June 22, 2020 8:00 AM | August 20, 2020 5:00 PM | June 25, 2020 05:00 PM | August 23, 2020 05:00 PM | February 09, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
159 | Yes | CMU1.6.3.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 154FS+45 days |  | 160,161 | June 22, 2020 8:00 AM | July 21, 2020 5:00 PM | July 15, 2020 05:00 PM | August 13, 2020 05:00 PM | August 22, 2020 05:00 PM | September 20, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
160 | Yes | CMU1.6.3.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 159 |  | 157,162 | July 22, 2020 8:00 AM | August 20, 2020 5:00 PM | August 14, 2020 05:00 PM | September 12, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | Skilled carpenter
161 | Yes | CMU1.6.3.5 | Auto Scheduled | งานบันได | 30 days | 4 | 159 |  | 157,162 | July 22, 2020 8:00 AM | August 20, 2020 5:00 PM | August 14, 2020 05:00 PM | September 12, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
162 | Yes | CMU1.6.3.6 | Auto Scheduled | งานสี | 30 days | 4 | 158,160,161 |  |  | August 21, 2020 8:00 AM | September 19, 2020 5:00 PM | September 13, 2020 05:00 PM | October 12, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
163 | Yes | CMU1.6.3.7 | Auto Scheduled | งานสุขภัณฑ์ | 15 days | 4 |  |  |  | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | October 19, 2018 05:00 PM | November 02, 2018 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 395 days | 395 days | 395 days
164 | Yes | CMU1.6.3.7.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 135FS+135 days |  |  | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | August 27, 2019 05:00 PM | September 10, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 395 days | 395 days | 395 days | Sanitary-Plumber
165 | Yes | CMU1.6.4 | Auto Scheduled | งานระบบสุขาภิบาล ชั้นใต้ดิน | 501 days | 3 |  |  |  | April 6, 2019 8:00 AM | August 18, 2020 5:00 PM | October 17, 2018 05:00 PM | February 29, 2020 05:00 PM | May 24, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 44 days | 44 days
166 | Yes | CMU1.6.4.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 126 days | 4 |  |  |  | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | October 21, 2018 05:00 PM | February 23, 2019 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 419 days | 419 days | 419 days
167 | Yes | CMU1.6.4.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 140FS+15 days |  |  | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 14, 2019 05:00 PM | August 17, 2019 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 419 days | 419 days | 419 days | Sanitary-Plumber
168 | Yes | CMU1.6.4.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 126 days | 4 |  |  |  | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | October 26, 2018 05:00 PM | February 28, 2019 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 44 days | 44 days
169 | Yes | CMU1.6.4.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 144FS+15 days |  | 170FS+300 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 06, 2019 05:00 PM | August 09, 2019 05:00 PM | May 24, 2019 05:00 PM | September 26, 2019 05:00 PM | As Soon As Possible |  | No | 44 days | 44 days | 0 days | Sanitary-Plumber
170 | Yes | CMU1.6.4.3 | Auto Scheduled | งานระบบระบายน้ำฝน | 75 days | 4 | 169FS+300 days |  |  | June 5, 2020 8:00 AM | August 18, 2020 5:00 PM | June 05, 2020 05:00 PM | August 18, 2020 05:00 PM | July 23, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 44 days | 44 days | 44 days | Sanitary-Plumber
171 | Yes | CMU1.6.5 | Auto Scheduled | งานระบบไฟฟ้า ชั้นใต้ดิน | 147 days | 3 |  |  |  | April 8, 2020 8:00 AM | September 1, 2020 5:00 PM | October 23, 2018 05:00 PM | March 18, 2019 05:00 PM | May 12, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 30 days | 30 days | 30 days
172 | Yes | CMU1.6.5.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 60 days | 4 | 174FS+7 days |  |  | July 4, 2020 8:00 AM | September 1, 2020 5:00 PM | July 07, 2020 05:00 PM | September 04, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 30 days | 30 days | 30 days | Electrician
173 | Yes | CMU1.6.5.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 60 days | 4 | 174FS+7 days |  |  | July 4, 2020 8:00 AM | September 1, 2020 5:00 PM | July 07, 2020 05:00 PM | September 04, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 30 days | 30 days | 30 days | Electrician
174 | Yes | CMU1.6.5.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 154SS |  | 173FS+7 days,172FS+7 days | April 8, 2020 8:00 AM | June 26, 2020 5:00 PM | April 11, 2020 05:00 PM | June 29, 2020 05:00 PM | May 12, 2020 05:00 PM | July 30, 2020 05:00 PM | As Soon As Possible |  | No | 30 days | 30 days | 0 days | Electrician
175 | Yes | CMU1.6.5.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 154SS |  |  | April 8, 2020 8:00 AM | June 26, 2020 5:00 PM | April 14, 2020 05:00 PM | July 02, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 97 days | 97 days | 97 days | Electrician
176 | Yes | CMU1.6.5.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 154SS |  |  | April 8, 2020 8:00 AM | June 26, 2020 5:00 PM | April 16, 2020 05:00 PM | July 04, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 97 days | 97 days | 97 days | Electrician
177 | Yes | CMU1.6.6 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้นใต้ดิน | 165 days | 3 | 154SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 11, 2020 05:00 PM | September 22, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | Skilled carpenter
178 | Yes | CMU1.7 | Auto Scheduled | หมวดงานระบบคอมพิวเตอร์และแจ้งเหตุเพลิงไหม้ | 670 days | 2 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
179 | Yes | CMU1.7.1 | Auto Scheduled | งานระบบคอมพิวเตอร์ | 670 days | 3 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
180 | Yes | CMU1.7.1.1 | Auto Scheduled | ชั้นที่ 4 | 160 days | 4 | 36FS+14 days |  | 181 | November 30, 2018 8:00 AM | May 8, 2019 5:00 PM | November 30, 2018 05:00 PM | May 08, 2019 05:00 PM | April 24, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
181 | Yes | CMU1.7.1.2 | Auto Scheduled | ชั้นที่ 3 | 175 days | 4 | 180 | 182 | 182 | May 9, 2019 8:00 AM | October 30, 2019 5:00 PM | May 09, 2019 05:00 PM | October 30, 2019 05:00 PM | April 09, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
182 | Yes | CMU1.7.1.3 | Auto Scheduled | ชั้นที่ 2 | 175 days | 4 | 181 | 183 | 183,184 | October 31, 2019 8:00 AM | April 22, 2020 5:00 PM | October 31, 2019 05:00 PM | April 22, 2020 05:00 PM | April 09, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
183 | Yes | CMU1.7.1.4 | Auto Scheduled | ชั้นที่ 1 | 160 days | 4 | 182 | 180 |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 23, 2020 05:00 PM | September 29, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
184 | Yes | CMU1.7.1.5 | Auto Scheduled | ชั้นใต้ดิน | 160 days | 4 | 182 | 183SS |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 23, 2020 05:00 PM | September 29, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
185 | Yes | CMU1.7.2 | Auto Scheduled | ระบบแจ้งเหตุเพลิงไหม้ | 670 days | 3 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
186 | Yes | CMU1.7.2.1 | Auto Scheduled | ชั้นที่ 4 | 160 days | 4 | 36FS+14 days |  | 187 | November 30, 2018 8:00 AM | May 8, 2019 5:00 PM | November 30, 2018 05:00 PM | May 08, 2019 05:00 PM | April 24, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
187 | Yes | CMU1.7.2.2 | Auto Scheduled | ชั้นที่ 3 | 175 days | 4 | 186 | 188 | 188 | May 9, 2019 8:00 AM | October 30, 2019 5:00 PM | May 09, 2019 05:00 PM | October 30, 2019 05:00 PM | April 09, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
188 | Yes | CMU1.7.2.3 | Auto Scheduled | ชั้นที่ 2 | 175 days | 4 | 187 | 189 | 189,190 | October 31, 2019 8:00 AM | April 22, 2020 5:00 PM | October 31, 2019 05:00 PM | April 22, 2020 05:00 PM | April 09, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
189 | Yes | CMU1.7.2.4 | Auto Scheduled | ชั้นที่ 1 | 160 days | 4 | 188 | 186 |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 23, 2020 05:00 PM | September 29, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
190 | Yes | CMU1.7.2.5 | Auto Scheduled | ชั้นใต้ดิน | 160 days | 4 | 188 | 189SS |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 23, 2020 05:00 PM | September 29, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
191 | Yes | CMU1.8 | Auto Scheduled | หมวดงานสีภายนอก งานซ่อมแซมและตกแต่งภายนอกอาคาร | 660 days | 2 |  |  |  | November 30, 2018 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | August 06, 2020 05:00 PM | December 16, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 507 days | 12 days | 12 days
192 | Yes | CMU1.8.1 | Auto Scheduled | งานสีภายนอกและงานซ่อมแซมพื้นผิวภายนอกอาคาร | 660 days | 3 |  |  |  | November 30, 2018 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | August 06, 2020 05:00 PM | December 16, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 507 days | 12 days | 12 days
193 | Yes | CMU1.8.1.1 | Auto Scheduled | งานขัดลอกสีทาผนังเดิม | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 11, 2020 05:00 PM | September 22, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
194 | Yes | CMU1.8.1.2 | Auto Scheduled | น้ำยาทาปูนเก่า (สีรองพื้น) | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 11, 2020 05:00 PM | September 22, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
195 | Yes | CMU1.8.1.3 | Auto Scheduled | งานทาสีภายนอก (ทา 2 เที่ยว) ไม่รวมชั้นใต้ดิน | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 11, 2020 05:00 PM | September 22, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
196 | Yes | CMU1.8.1.4 | Auto Scheduled | งานทำความสะอาดและซ่อมแซมผนังกรุอิฐโชว์แนว (อ้างอิงราคางานขัดลอกสี) | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 11, 2020 05:00 PM | September 22, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
197 | Yes | CMU1.8.1.5 | Auto Scheduled | น้ำยาเคลือบผิวผนังอิฐโชว์แนว (อ้างอิงค่าทาน้ำยากันเชื้อรา) | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 11, 2020 05:00 PM | September 22, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
198 | Yes | CMU1.8.1.6 | Auto Scheduled | งานรื้อถอนแผ่นวัสดุกันซึมหลังคาดาดฟ้า (รื้อขนไป) | 90 days | 4 | 36FS+14 days |  |  | November 30, 2018 8:00 AM | February 27, 2019 5:00 PM | December 03, 2018 05:00 PM | March 02, 2019 05:00 PM | July 08, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 582 days | 582 days | 582 days | General worker
199 | Yes | CMU1.8.1.7 | Auto Scheduled | งานแผ่นวัสดุกันซึมแบบเป่าไฟผิวทราย | 90 days | 4 | 36FS+14 days |  |  | November 30, 2018 8:00 AM | February 27, 2019 5:00 PM | December 04, 2018 05:00 PM | March 03, 2019 05:00 PM | July 08, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 582 days | 582 days | 582 days | General worker
200 | Yes | CMU1.8.1.8 | Auto Scheduled | งานกันซึมชนิด Polyurethane สูตรน้ำมัน ชนิดยืดหยุ่นสูงเป็นพิเศษ | 90 days | 4 | 36FS+14 days |  |  | November 30, 2018 8:00 AM | February 27, 2019 5:00 PM | December 03, 2018 05:00 PM | March 02, 2019 05:00 PM | July 08, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 582 days | 582 days | 582 days | General worker
201 | Yes | CMU1.8.2 | Auto Scheduled | งานตกแต่งภายนอกอาคาร | 165 days | 3 |  |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | October 20, 2018 05:00 PM | April 02, 2019 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 12 days | 12 days | 12 days
202 | Yes | CMU1.8.2.1 | Auto Scheduled | ตะแกรงเหล็กฉีกกันนก XS-32 | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 11, 2020 05:00 PM | September 22, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
203 | Yes | CMU1.9 | Auto Scheduled | หมวดงานบริเวณ | 165 days | 2 |  |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | October 22, 2018 05:00 PM | April 04, 2019 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 12 days | 12 days | 12 days
204 | Yes | CMU1.9.1 | Auto Scheduled | งานรื้อถอน งานบริเวณ | 165 days | 3 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 11, 2020 05:00 PM | September 22, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
205 | Yes | CMU1.9.2 | Auto Scheduled | งานโครงสร้างวิศวกรรม งานบริเวณ | 165 days | 3 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 11, 2020 05:00 PM | September 22, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
206 | Yes | CMU1.9.3 | Auto Scheduled | งานสถาปัตยกรรม งานบริเวณ | 165 days | 3 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 11, 2020 05:00 PM | September 22, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
207 | Yes | CMU1.9.4 | Auto Scheduled | งานระบบไฟฟ้า งานบริเวณ | 165 days | 3 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 11, 2020 05:00 PM | September 22, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | Electrician
208 | Yes | CMU1.10 | Auto Scheduled | หมวดงานครุภัณฑ์จัดซื้อ | 670 days | 2 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
209 | Yes | CMU1.10.1 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัว | 510 days | 3 |  |  |  | April 14, 2019 8:00 AM | September 4, 2020 5:00 PM | October 17, 2018 05:00 PM | March 09, 2020 05:00 PM | May 15, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 522 days | 27 days | 27 days
210 | Yes | CMU1.10.1.1 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้นใต้ดิน | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | August 28, 2020 05:00 PM | September 11, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
211 | Yes | CMU1.10.1.2 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้น 1 | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | August 31, 2020 05:00 PM | September 14, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
212 | Yes | CMU1.10.1.3 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้น 2 | 15 days | 4 | 121FS-15 days |  |  | March 24, 2020 8:00 AM | April 7, 2020 5:00 PM | March 29, 2020 05:00 PM | April 12, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Skilled carpenter
213 | Yes | CMU1.10.1.4 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้น 3 | 15 days | 4 | 92FS-15 days |  |  | September 26, 2019 8:00 AM | October 10, 2019 5:00 PM | October 04, 2019 05:00 PM | October 18, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Skilled carpenter
214 | Yes | CMU1.10.1.5 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้น 4 | 15 days | 4 | 63 |  |  | April 14, 2019 8:00 AM | April 28, 2019 5:00 PM | April 21, 2019 05:00 PM | May 05, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 522 days | 522 days | 522 days | Skilled carpenter
215 | Yes | CMU1.10.2 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ | 525 days | 3 |  |  |  | March 30, 2019 8:00 AM | September 4, 2020 5:00 PM | October 17, 2018 05:00 PM | March 24, 2020 05:00 PM | April 30, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 522 days | 27 days | 27 days
216 | Yes | CMU1.10.2.1 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ ชั้น 1 | 30 days | 4 | 152FS-45 days |  |  | August 6, 2020 8:00 AM | September 4, 2020 5:00 PM | August 15, 2020 05:00 PM | September 13, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
217 | Yes | CMU1.10.2.2 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ ชั้น 2 | 30 days | 4 | 121FS-30 days |  |  | March 9, 2020 8:00 AM | April 7, 2020 5:00 PM | March 15, 2020 05:00 PM | April 13, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Skilled carpenter
218 | Yes | CMU1.10.2.3 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ ชั้น 3 | 30 days | 4 | 92FS-30 days |  |  | September 11, 2019 8:00 AM | October 10, 2019 5:00 PM | September 16, 2019 05:00 PM | October 15, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Skilled carpenter
219 | Yes | CMU1.10.2.4 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ ชั้น 4 | 30 days | 4 | 63FS-15 days |  |  | March 30, 2019 8:00 AM | April 28, 2019 5:00 PM | April 02, 2019 05:00 PM | May 01, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 522 days | 522 days | 522 days | Skilled carpenter
220 | Yes | CMU1.10.3 | Auto Scheduled | งานผ้าม่าน | 510 days | 3 |  |  |  | April 14, 2019 8:00 AM | September 4, 2020 5:00 PM | October 17, 2018 05:00 PM | March 09, 2020 05:00 PM | May 15, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 522 days | 27 days | 27 days
221 | Yes | CMU1.10.3.1 | Auto Scheduled | งานผ้าม่าน ชั้น 1 | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | August 28, 2020 05:00 PM | September 11, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
222 | Yes | CMU1.10.3.2 | Auto Scheduled | งานผ้าม่าน ชั้น 2 | 15 days | 4 | 121FS-15 days |  |  | March 24, 2020 8:00 AM | April 7, 2020 5:00 PM | March 30, 2020 05:00 PM | April 13, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Skilled carpenter
223 | Yes | CMU1.10.3.3 | Auto Scheduled | งานผ้าม่าน ชั้น 3 | 15 days | 4 | 92FS-15 days |  |  | September 26, 2019 8:00 AM | October 10, 2019 5:00 PM | October 02, 2019 05:00 PM | October 16, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Skilled carpenter
224 | Yes | CMU1.10.3.4 | Auto Scheduled | งานผ้าม่าน ชั้น 4 | 15 days | 4 | 63 |  |  | April 14, 2019 8:00 AM | April 28, 2019 5:00 PM | April 24, 2019 05:00 PM | May 08, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 522 days | 522 days | 522 days | Skilled carpenter
225 | Yes | CMU1.10.4 | Auto Scheduled | งานป้าย | 510 days | 3 |  |  |  | April 14, 2019 8:00 AM | September 4, 2020 5:00 PM | October 17, 2018 05:00 PM | March 09, 2020 05:00 PM | May 15, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 522 days | 27 days | 27 days
226 | Yes | CMU1.10.4.1 | Auto Scheduled | งานป้าย ชั้นใต้ดิน | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | August 28, 2020 05:00 PM | September 11, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
227 | Yes | CMU1.10.4.2 | Auto Scheduled | งานป้าย ชั้น 1 | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | August 31, 2020 05:00 PM | September 14, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
228 | Yes | CMU1.10.4.3 | Auto Scheduled | งานป้าย ชั้น 2 | 15 days | 4 | 121FS-15 days |  |  | March 24, 2020 8:00 AM | April 7, 2020 5:00 PM | March 30, 2020 05:00 PM | April 13, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Skilled carpenter
229 | Yes | CMU1.10.4.4 | Auto Scheduled | งานป้าย ชั้น 3 | 15 days | 4 | 92FS-15 days |  |  | September 26, 2019 8:00 AM | October 10, 2019 5:00 PM | October 03, 2019 05:00 PM | October 17, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Skilled carpenter
230 | Yes | CMU1.10.4.5 | Auto Scheduled | งานป้าย ชั้น 4 | 15 days | 4 | 63 |  |  | April 14, 2019 8:00 AM | April 28, 2019 5:00 PM | April 20, 2019 05:00 PM | May 04, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 522 days | 522 days | 522 days | Skilled carpenter
231 | Yes | CMU1.10.5 | Auto Scheduled | งานอื่นๆ | 15 days | 3 |  |  |  | August 6, 2020 8:00 AM | August 20, 2020 5:00 PM | October 20, 2018 05:00 PM | November 03, 2018 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 42 days | 42 days | 42 days
232 | Yes | CMU1.10.5.1 | Auto Scheduled | ตู้อลูมิเนียมพับขึ้นรูป พ่นสี ครอบตู้กดน้ำ | 15 days | 4 | 152FS-45 days |  |  | August 6, 2020 8:00 AM | August 20, 2020 5:00 PM | August 13, 2020 05:00 PM | August 27, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 42 days | 42 days | 42 days | General worker
233 | Yes | CMU1.10.6 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ | 670 days | 3 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
234 | Yes | CMU1.10.6.1 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้นใต้ดิน | 160 days | 4 | 236 |  |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 28, 2020 05:00 PM | October 04, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
235 | Yes | CMU1.10.6.2 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้น 1 | 160 days | 4 | 236 |  |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 28, 2020 05:00 PM | October 04, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
236 | Yes | CMU1.10.6.3 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้น 2 | 175 days | 4 | 237 |  | 235,234 | October 31, 2019 8:00 AM | April 22, 2020 5:00 PM | November 05, 2019 05:00 PM | April 27, 2020 05:00 PM | March 12, 2020 05:00 PM | September 02, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
237 | Yes | CMU1.10.6.4 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้น 3 | 175 days | 4 | 238 |  | 236 | May 9, 2019 8:00 AM | October 30, 2019 5:00 PM | May 14, 2019 05:00 PM | November 04, 2019 05:00 PM | March 12, 2020 05:00 PM | September 02, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
238 | Yes | CMU1.10.6.5 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้น 4 | 160 days | 4 | 36FS+14 days |  | 237 | November 30, 2018 8:00 AM | May 8, 2019 5:00 PM | December 02, 2018 05:00 PM | May 10, 2019 05:00 PM | March 27, 2020 05:00 PM | September 02, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
239 | Yes | CMU1.10.7 | Auto Scheduled | งานระบบเครื่องเสียงประกาศ (ใช้ลำโพงของเดิม) | 539 days | 3 |  |  |  | April 7, 2019 8:00 AM | September 26, 2020 5:00 PM | October 17, 2018 05:00 PM | April 07, 2020 05:00 PM | April 16, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 530 days | 5 days | 5 days
240 | Yes | CMU1.10.7.1 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้นใต้ดิน | 7 days | 4 | 241 |  |  | September 20, 2020 8:00 AM | September 26, 2020 5:00 PM | September 27, 2020 05:00 PM | October 03, 2020 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 5 days | 5 days | 5 days | Electrician
241 | Yes | CMU1.10.7.2 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้น 1 | 7 days | 4 | 152FS-7 days |  | 240 | September 13, 2020 8:00 AM | September 19, 2020 5:00 PM | September 16, 2020 05:00 PM | September 22, 2020 05:00 PM | September 09, 2020 05:00 PM | September 15, 2020 05:00 PM | As Soon As Possible |  | No | 5 days | 5 days | 0 days | Electrician
242 | Yes | CMU1.10.7.3 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้น 2 | 7 days | 4 | 121FS-7 days |  |  | April 1, 2020 8:00 AM | April 7, 2020 5:00 PM | April 06, 2020 05:00 PM | April 12, 2020 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Electrician
243 | Yes | CMU1.10.7.4 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้น 3 | 7 days | 4 | 92FS-7 days |  |  | October 4, 2019 8:00 AM | October 10, 2019 5:00 PM | October 11, 2019 05:00 PM | October 17, 2019 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Electrician
244 | Yes | CMU1.10.7.5 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้น 4 | 7 days | 4 | 63FS-7 days |  |  | April 7, 2019 8:00 AM | April 13, 2019 5:00 PM | April 14, 2019 05:00 PM | April 20, 2019 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 537 days | 537 days | 537 days | Electrician
245 | Yes | CMU1.10.8 | Auto Scheduled | งานระบบกล้องวงจรปิด (ใช้กล้องวงจรปิดของเดิม) | 539 days | 3 |  |  |  | April 7, 2019 8:00 AM | September 26, 2020 5:00 PM | October 17, 2018 05:00 PM | April 07, 2020 05:00 PM | April 16, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 530 days | 5 days | 5 days
246 | Yes | CMU1.10.8.1 | Auto Scheduled | งานกล้องวงจรปิด ชั้นใต้ดิน | 7 days | 4 | 247 |  |  | September 20, 2020 8:00 AM | September 26, 2020 5:00 PM | September 27, 2020 05:00 PM | October 03, 2020 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 5 days | 5 days | 5 days | Electrician
247 | Yes | CMU1.10.8.2 | Auto Scheduled | งานกล้องวงจรปิด ชั้น 1 | 7 days | 4 | 152FS-7 days |  | 246 | September 13, 2020 8:00 AM | September 19, 2020 5:00 PM | September 16, 2020 05:00 PM | September 22, 2020 05:00 PM | September 09, 2020 05:00 PM | September 15, 2020 05:00 PM | As Soon As Possible |  | No | 5 days | 5 days | 0 days | Electrician
248 | Yes | CMU1.10.8.3 | Auto Scheduled | งานกล้องวงจรปิด ชั้น 2 | 7 days | 4 | 121FS-7 days |  |  | April 1, 2020 8:00 AM | April 7, 2020 5:00 PM | April 07, 2020 05:00 PM | April 13, 2020 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Electrician
249 | Yes | CMU1.10.8.4 | Auto Scheduled | งานกล้องวงจรปิด ชั้น 3 | 7 days | 4 | 92FS-7 days |  |  | October 4, 2019 8:00 AM | October 10, 2019 5:00 PM | October 11, 2019 05:00 PM | October 17, 2019 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Electrician
250 | Yes | CMU1.10.8.5 | Auto Scheduled | งานกล้องวงจรปิด ชั้น 4 | 7 days | 4 | 63FS-7 days |  |  | April 7, 2019 8:00 AM | April 13, 2019 5:00 PM | April 11, 2019 05:00 PM | April 17, 2019 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 537 days | 537 days | 537 days | Electrician

## solutoion_12
ID | Active | WBS | Task_Mode | Name | Duration | Outline_Level | Predecessors | Predecessors2 | Successors | Start_Date | Finish_Date | Early_Start | Early_Finish | Late_Start | Late_Finish | Constraint_Type | Constraint_Date | Summary | Start_Slack | Finish_Slack | Free_Slack | Resource_Names
1 | Yes | CMU1 | Auto Scheduled | โครงการปรับปรุงสำนักหอสมุด มหาวิทยาลัยเชียงใหม่ | 716 days | 1 |  |  |  | October 17, 2018 8:00 AM | October 1, 2020 5:00 PM | October 17, 2018 05:00 PM | October 01, 2020 05:00 PM | October 21, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 0 days | 0 days | 0 days
2 | Yes | CMU1.1 | Auto Scheduled | หมวดเตรียมการ | 675 days | 2 |  |  |  | October 17, 2018 8:00 AM | August 21, 2020 5:00 PM | October 17, 2018 05:00 PM | August 21, 2020 05:00 PM | December 01, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 41 days | 41 days | 41 days
3 | Yes | CMU1.1.1 | Auto Scheduled | งานอาคารสนามและผังบริเวณโครงการ | 14 days | 3 | 4FS-7 days |  |  | October 26, 2018 8:00 AM | November 8, 2018 5:00 PM | November 01, 2018 05:00 PM | November 14, 2018 05:00 PM | September 22, 2020 05:00 PM | October 05, 2020 05:00 PM | Start No Earlier Than | Oct 24 '18 | No | 693 days | 693 days | 693 days | Engineer
4 | Yes | CMU1.1.2 | Auto Scheduled | งานเชื่อมต่อระบบสาธารณูปโภคโครงการ | 16 days | 3 |  |  | 3FS-7 days | October 17, 2018 8:00 AM | November 1, 2018 5:00 PM | October 19, 2018 05:00 PM | November 03, 2018 05:00 PM | September 13, 2020 05:00 PM | September 28, 2020 05:00 PM | As Soon As Possible |  | No | 693 days | 693 days | 0 days | Engineer
5 | Yes | CMU1.1.3 | Auto Scheduled | งานตรวจทดสอบระบบภายในอาคารก่อนดำเนินการปรับปรุง | 675 days | 3 |  |  |  | October 17, 2018 8:00 AM | August 21, 2020 5:00 PM | October 17, 2018 05:00 PM | August 21, 2020 05:00 PM | December 01, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 41 days | 41 days | 41 days
6 | Yes | CMU1.1.3.1 | Auto Scheduled | ชั้นที่ 4 | 15 days | 4 |  |  | 7FS+150 days | October 17, 2018 8:00 AM | October 31, 2018 5:00 PM | October 20, 2018 05:00 PM | November 03, 2018 05:00 PM | December 01, 2018 05:00 PM | December 15, 2018 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
7 | Yes | CMU1.1.3.2 | Auto Scheduled | ชั้นที่ 3 | 15 days | 4 | 6FS+150 days |  | 8FS+150 days | March 31, 2019 8:00 AM | April 14, 2019 5:00 PM | April 08, 2019 05:00 PM | April 22, 2019 05:00 PM | May 15, 2019 05:00 PM | May 29, 2019 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
8 | Yes | CMU1.1.3.3 | Auto Scheduled | ชั้นที่ 2 | 15 days | 4 | 7FS+150 days |  | 9FS+150 days | September 12, 2019 8:00 AM | September 26, 2019 5:00 PM | October 01, 2019 05:00 PM | October 15, 2019 05:00 PM | October 27, 2019 05:00 PM | November 10, 2019 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
9 | Yes | CMU1.1.3.4 | Auto Scheduled | ชั้นที่ 1 | 15 days | 4 | 8FS+150 days |  | 10FS+150 days | February 24, 2020 8:00 AM | March 9, 2020 5:00 PM | March 22, 2020 05:00 PM | April 05, 2020 05:00 PM | April 09, 2020 05:00 PM | April 23, 2020 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
10 | Yes | CMU1.1.3.5 | Auto Scheduled | ชั้นใต้ดินและภายนอก | 15 days | 4 | 9FS+150 days |  |  | August 7, 2020 8:00 AM | August 21, 2020 5:00 PM | September 14, 2020 05:00 PM | September 28, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 41 days | Engineer
11 | Yes | CMU1.1.4 | Auto Scheduled | งานสำรวจอุปกรณ์ไฟฟ้า, สุขภัณฑ์และครุภัณฑ์ (ของเดิม) ก่อนดำเนินการปรับปรุง | 675 days | 3 |  |  |  | October 17, 2018 8:00 AM | August 21, 2020 5:00 PM | October 17, 2018 05:00 PM | August 21, 2020 05:00 PM | December 01, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 41 days | 41 days | 41 days
12 | Yes | CMU1.1.4.1 | Auto Scheduled | ชั้นที่ 4 | 15 days | 4 |  |  | 13FS+150 days | October 17, 2018 8:00 AM | October 31, 2018 5:00 PM | October 20, 2018 05:00 PM | November 03, 2018 05:00 PM | December 01, 2018 05:00 PM | December 15, 2018 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
13 | Yes | CMU1.1.4.2 | Auto Scheduled | ชั้นที่ 3 | 15 days | 4 | 12FS+150 days |  | 14FS+150 days | March 31, 2019 8:00 AM | April 14, 2019 5:00 PM | April 06, 2019 05:00 PM | April 20, 2019 05:00 PM | May 15, 2019 05:00 PM | May 29, 2019 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
14 | Yes | CMU1.1.4.3 | Auto Scheduled | ชั้นที่ 2 | 15 days | 4 | 13FS+150 days |  | 15FS+150 days | September 12, 2019 8:00 AM | September 26, 2019 5:00 PM | September 24, 2019 05:00 PM | October 08, 2019 05:00 PM | October 27, 2019 05:00 PM | November 10, 2019 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
15 | Yes | CMU1.1.4.4 | Auto Scheduled | ชั้นที่ 1 | 15 days | 4 | 14FS+150 days |  | 16FS+150 days | February 24, 2020 8:00 AM | March 9, 2020 5:00 PM | March 11, 2020 05:00 PM | March 25, 2020 05:00 PM | April 09, 2020 05:00 PM | April 23, 2020 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
16 | Yes | CMU1.1.4.5 | Auto Scheduled | ชั้นใต้ดินและภายนอก | 15 days | 4 | 15FS+150 days |  |  | August 7, 2020 8:00 AM | August 21, 2020 5:00 PM | September 03, 2020 05:00 PM | September 17, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 41 days | Engineer
17 | Yes | CMU1.1.5 | Auto Scheduled | งานเอกสารขออนุมัติใช้วัสดุ, Shop Drawing และครุภัณฑ์ของโครงการ | 106 days | 3 |  |  |  | October 17, 2018 8:00 AM | January 30, 2019 5:00 PM | October 22, 2018 05:00 PM | February 04, 2019 05:00 PM | June 22, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 610 days | 610 days | 610 days
18 | Yes | CMU1.1.5.1 | Auto Scheduled | แบบ Shop Drawing ชั้นที่ 4 | 20 days | 4 |  |  | 19,25SS+14 days,26SS+14 days | October 17, 2018 8:00 AM | November 5, 2018 5:00 PM | October 17, 2018 05:00 PM | November 05, 2018 05:00 PM | October 01, 2018 05:00 PM | October 20, 2018 05:00 PM | As Soon As Possible |  | No | 610 days | 610 days | 0 days | Engineer
19 | Yes | CMU1.1.5.2 | Auto Scheduled | แบบ Shop Drawing ชั้นที่ 3 | 20 days | 4 | 18 |  | 20FS-7 days | November 6, 2018 8:00 AM | November 25, 2018 5:00 PM | November 13, 2018 05:00 PM | December 02, 2018 05:00 PM | July 13, 2020 05:00 PM | August 01, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
20 | Yes | CMU1.1.5.3 | Auto Scheduled | แบบ Shop Drawing ชั้นที่ 2 | 20 days | 4 | 19FS-7 days |  | 21FS-7 days | November 19, 2018 8:00 AM | December 8, 2018 5:00 PM | November 29, 2018 05:00 PM | December 18, 2018 05:00 PM | July 26, 2020 05:00 PM | August 14, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
21 | Yes | CMU1.1.5.4 | Auto Scheduled | แบบ Shop Drawing ชั้นที่ 1 | 20 days | 4 | 20FS-7 days |  | 22FS-7 days | December 2, 2018 8:00 AM | December 21, 2018 5:00 PM | December 18, 2018 05:00 PM | January 06, 2019 05:00 PM | August 08, 2020 05:00 PM | August 27, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
22 | Yes | CMU1.1.5.5 | Auto Scheduled | แบบ Shop Drawing ชั้นใต้ดิน | 20 days | 4 | 21FS-7 days |  | 23FS-7 days | December 15, 2018 8:00 AM | January 3, 2019 5:00 PM | January 07, 2019 05:00 PM | January 26, 2019 05:00 PM | August 21, 2020 05:00 PM | September 09, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
23 | Yes | CMU1.1.5.6 | Auto Scheduled | แบบ Shop Drawing ภายนอกอาคาร | 20 days | 4 | 22FS-7 days |  | 24FS-7 days | December 28, 2018 8:00 AM | January 16, 2019 5:00 PM | January 24, 2019 05:00 PM | February 12, 2019 05:00 PM | September 03, 2020 05:00 PM | September 22, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
24 | Yes | CMU1.1.5.7 | Auto Scheduled | แบบ Shop Drawing landscape | 20 days | 4 | 23FS-7 days |  |  | January 10, 2019 8:00 AM | January 29, 2019 5:00 PM | February 13, 2019 05:00 PM | March 04, 2019 05:00 PM | September 16, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 611 days | Engineer
25 | Yes | CMU1.1.5.8 | Auto Scheduled | แบบ Shop Drawing งานปรับปรุง ครุภัณฑ์ | 92 days | 4 | 18SS+14 days |  |  | October 31, 2018 8:00 AM | January 30, 2019 5:00 PM | November 08, 2018 05:00 PM | February 07, 2019 05:00 PM | July 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 610 days | 610 days | 610 days | Engineer
26 | Yes | CMU1.1.5.9 | Auto Scheduled | แบบ Shop Drawing งานจัดซื้อครุภัณฑ์ | 92 days | 4 | 18SS+14 days |  |  | October 31, 2018 8:00 AM | January 30, 2019 5:00 PM | November 08, 2018 05:00 PM | February 07, 2019 05:00 PM | July 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 610 days | 610 days | 610 days | Engineer
27 | Yes | CMU1.1.6 | Auto Scheduled | งานตรวจทดสอบระบบ, งานอบรมผู้ใช้อาคาร และ As-Built Drawing | 30 days | 3 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 23, 2018 05:00 PM | November 21, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 686 days | 686 days | 686 days
28 | Yes | CMU1.1.6.1 | Auto Scheduled | ชั้นที่ 4 | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 27, 2018 05:00 PM | November 25, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
29 | Yes | CMU1.1.6.2 | Auto Scheduled | ชั้นที่ 3 | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 27, 2018 05:00 PM | November 25, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
30 | Yes | CMU1.1.6.3 | Auto Scheduled | ชั้นที่ 2 | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 22, 2018 05:00 PM | November 20, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
31 | Yes | CMU1.1.6.4 | Auto Scheduled | ชั้นที่ 1 | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 29, 2018 05:00 PM | November 27, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
32 | Yes | CMU1.1.6.5 | Auto Scheduled | ชั้นใต้ดิน | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 25, 2018 05:00 PM | November 23, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
33 | Yes | CMU1.1.6.6 | Auto Scheduled | ทั้งอาคาร | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 23, 2018 05:00 PM | November 21, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
34 | Yes | CMU1.1.7 | Auto Scheduled | งานบริหารงานก่อสร้างและงานอื่น ๆ | 0 days | 3 |  |  |  | October 17, 2018 8:00 AM | October 17, 2018 8:00 AM | October 20, 2018 05:00 PM | October 19, 2018 05:00 PM | October 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 716 days | 716 days | 716 days | Engineer
35 | Yes | CMU1.2 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้น 4 | 471 days | 2 |  |  |  | October 17, 2018 8:00 AM | January 30, 2020 5:00 PM | October 17, 2018 05:00 PM | January 30, 2020 05:00 PM | June 23, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 0 days | 245 days | 0 days
36 | Yes | CMU1.2.1 | Auto Scheduled | งานรื้อถอน ชั้น 4 (รื้อขนไป) | 30 days | 3 |  |  | 39FS+45 days,40FS+45 days,51,63SS+14 days,80,109,140,180FS+14 days,186FS+14 days,198FS+14 days,199FS+14 days,200FS+14 days,238FS+14 days | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 17, 2018 05:00 PM | November 15, 2018 05:00 PM | March 11, 2018 05:00 PM | April 09, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | General worker
37 | Yes | CMU1.2.2 | Auto Scheduled | งานสถาปัตยกรรม ชั้น 4 | 396 days | 3 |  |  |  | December 31, 2018 8:00 AM | January 30, 2020 5:00 PM | October 17, 2018 05:00 PM | November 16, 2019 05:00 PM | September 06, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 326 days | 245 days | 245 days
38 | Yes | CMU1.2.2.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 39,41,42 |  |  | March 1, 2019 8:00 AM | March 30, 2019 5:00 PM | March 14, 2019 05:00 PM | April 12, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 551 days | Skilled carpenter
39 | Yes | CMU1.2.2.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 36FS+45 days |  | 38,43 | December 31, 2018 8:00 AM | February 28, 2019 5:00 PM | January 05, 2019 05:00 PM | March 05, 2019 05:00 PM | July 15, 2020 05:00 PM | September 12, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 0 days | General worker
40 | Yes | CMU1.2.2.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 36FS+45 days |  | 41,42 | December 31, 2018 8:00 AM | January 29, 2019 5:00 PM | January 03, 2019 05:00 PM | February 01, 2019 05:00 PM | August 14, 2020 05:00 PM | September 12, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 0 days | General worker
41 | Yes | CMU1.2.2.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 40 |  | 38,43 | January 30, 2019 8:00 AM | February 28, 2019 5:00 PM | February 05, 2019 05:00 PM | March 06, 2019 05:00 PM | August 14, 2020 05:00 PM | September 12, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 0 days | Skilled carpenter
42 | Yes | CMU1.2.2.5 | Auto Scheduled | งานบันได | 30 days | 4 | 40 |  | 38,43 | January 30, 2019 8:00 AM | February 28, 2019 5:00 PM | February 05, 2019 05:00 PM | March 06, 2019 05:00 PM | August 14, 2020 05:00 PM | September 12, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 0 days | General worker
43 | Yes | CMU1.2.2.6 | Auto Scheduled | งานสี | 30 days | 4 | 39,41,42 |  |  | March 1, 2019 8:00 AM | March 30, 2019 5:00 PM | March 10, 2019 05:00 PM | April 08, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 551 days | General worker
44 | Yes | CMU1.2.2.7 | Auto Scheduled | งานสุขภัณฑ์ | 315 days | 4 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 20, 2018 05:00 PM | August 30, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
45 | Yes | CMU1.2.2.7.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 46FS+135 days |  | 47FS+135 days | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | September 16, 2019 05:00 PM | September 30, 2019 05:00 PM | April 24, 2020 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
46 | Yes | CMU1.2.2.7.2 | Auto Scheduled | ZONE T-2 กลาง | 15 days | 5 | 51,55 |  | 45FS+135 days | March 22, 2019 8:00 AM | April 5, 2019 5:00 PM | April 13, 2019 05:00 PM | April 27, 2019 05:00 PM | November 26, 2019 05:00 PM | December 10, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
47 | Yes | CMU1.2.2.7.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 15 days | 5 | 45FS+135 days |  |  | January 16, 2020 8:00 AM | January 30, 2020 5:00 PM | February 28, 2020 05:00 PM | March 13, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 245 days | Sanitary-Plumber
48 | Yes | CMU1.2.3 | Auto Scheduled | งานระบบสุขาภิบาล ชั้น 4 | 408 days | 3 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
49 | Yes | CMU1.2.3.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
50 | Yes | CMU1.2.3.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 51FS+15 days |  | 52FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 18, 2019 05:00 PM | August 21, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
51 | Yes | CMU1.2.3.1.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 36 |  | 50FS+15 days,46,55SS | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 23, 2018 05:00 PM | March 28, 2019 05:00 PM | August 25, 2019 05:00 PM | December 28, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
52 | Yes | CMU1.2.3.1.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 50FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 10, 2019 05:00 PM | January 13, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
53 | Yes | CMU1.2.3.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
54 | Yes | CMU1.2.3.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 55FS+15 days |  | 56FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 30, 2019 05:00 PM | September 02, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
55 | Yes | CMU1.2.3.2.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 51SS |  | 54FS+15 days,46 | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | December 03, 2018 05:00 PM | April 07, 2019 05:00 PM | August 25, 2019 05:00 PM | December 28, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
56 | Yes | CMU1.2.3.2.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 54FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | October 01, 2019 05:00 PM | February 03, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
57 | Yes | CMU1.2.4 | Auto Scheduled | งานระบบไฟฟ้า ชั้น 4 | 117 days | 3 |  |  |  | November 30, 2018 8:00 AM | March 26, 2019 5:00 PM | October 21, 2018 05:00 PM | February 14, 2019 05:00 PM | June 11, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 555 days | 555 days | 555 days
58 | Yes | CMU1.2.4.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 30 days | 4 | 60FS+7 days |  |  | February 25, 2019 8:00 AM | March 26, 2019 5:00 PM | March 03, 2019 05:00 PM | April 01, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 555 days | 555 days | 555 days | Electrician
59 | Yes | CMU1.2.4.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 30 days | 4 | 60FS+7 days |  |  | February 25, 2019 8:00 AM | March 26, 2019 5:00 PM | March 04, 2019 05:00 PM | April 02, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 555 days | 555 days | 555 days | Electrician
60 | Yes | CMU1.2.4.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 63SS+30 days |  | 58FS+7 days,59FS+7 days | November 30, 2018 8:00 AM | February 17, 2019 5:00 PM | December 03, 2018 05:00 PM | February 20, 2019 05:00 PM | June 11, 2020 05:00 PM | August 29, 2020 05:00 PM | As Soon As Possible |  | No | 555 days | 555 days | 0 days | Electrician
61 | Yes | CMU1.2.4.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 63SS+30 days |  |  | November 30, 2018 8:00 AM | February 17, 2019 5:00 PM | December 04, 2018 05:00 PM | February 21, 2019 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 592 days | 592 days | 592 days | Electrician
62 | Yes | CMU1.2.4.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 63SS+30 days |  |  | November 30, 2018 8:00 AM | February 17, 2019 5:00 PM | December 05, 2018 05:00 PM | February 22, 2019 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 592 days | 592 days | 592 days | Electrician
63 | Yes | CMU1.2.5 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้น 4 | 165 days | 3 | 36SS+14 days |  | 62SS+30 days,60SS+30 days,61SS+30 days,65,214,219FS-15 days,224,230,244FS-7 days,250FS-7 days | October 31, 2018 8:00 AM | April 13, 2019 5:00 PM | October 31, 2018 05:00 PM | April 13, 2019 05:00 PM | June 19, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Skilled carpenter
64 | Yes | CMU1.3 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้น 3 | 441 days | 2 |  |  |  | November 16, 2018 8:00 AM | January 30, 2020 5:00 PM | October 17, 2018 05:00 PM | December 31, 2019 05:00 PM | July 23, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 149 days | 245 days | 149 days
65 | Yes | CMU1.3.1 | Auto Scheduled | งานรื้อถอน ชั้น 3 (รื้อขนไป) | 30 days | 3 | 63 | 121 | 68FS+45 days,69FS+45 days,92SS | April 14, 2019 8:00 AM | May 13, 2019 5:00 PM | April 14, 2019 05:00 PM | May 13, 2019 05:00 PM | July 19, 2018 05:00 PM | August 17, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | General worker
66 | Yes | CMU1.3.2 | Auto Scheduled | งานสถาปัตยกรรม ชั้น 3 | 315 days | 3 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 23, 2018 05:00 PM | September 02, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
67 | Yes | CMU1.3.2.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 68,70,71 |  |  | August 27, 2019 8:00 AM | September 25, 2019 5:00 PM | August 30, 2019 05:00 PM | September 28, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 372 days | Skilled carpenter
68 | Yes | CMU1.3.2.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 65FS+45 days |  | 67,72 | June 28, 2019 8:00 AM | August 26, 2019 5:00 PM | June 28, 2019 05:00 PM | August 26, 2019 05:00 PM | October 02, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 0 days | General worker
69 | Yes | CMU1.3.2.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 65FS+45 days |  | 70,71 | June 28, 2019 8:00 AM | July 27, 2019 5:00 PM | June 28, 2019 05:00 PM | July 27, 2019 05:00 PM | April 15, 2019 05:00 PM | May 14, 2019 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 0 days | General worker
70 | Yes | CMU1.3.2.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 69 |  | 67,72 | July 28, 2019 8:00 AM | August 26, 2019 5:00 PM | July 28, 2019 05:00 PM | August 26, 2019 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 0 days | Skilled carpenter
71 | Yes | CMU1.3.2.5 | Auto Scheduled | งานบันได | 30 days | 4 | 69 |  | 67,72 | July 28, 2019 8:00 AM | August 26, 2019 5:00 PM | July 28, 2019 05:00 PM | August 26, 2019 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 0 days | General worker
72 | Yes | CMU1.3.2.6 | Auto Scheduled | งานสี | 30 days | 4 | 68,70,71 |  |  | August 27, 2019 8:00 AM | September 25, 2019 5:00 PM | August 30, 2019 05:00 PM | September 28, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 372 days | General worker
73 | Yes | CMU1.3.2.7 | Auto Scheduled | งานสุขภัณฑ์ | 315 days | 4 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 21, 2018 05:00 PM | August 31, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
74 | Yes | CMU1.3.2.7.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 75FS+135 days |  | 76FS+135 days | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | August 25, 2019 05:00 PM | September 08, 2019 05:00 PM | April 24, 2020 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
75 | Yes | CMU1.3.2.7.2 | Auto Scheduled | ZONE T-2 กลาง | 15 days | 5 | 80,84 |  | 74FS+135 days | March 22, 2019 8:00 AM | April 5, 2019 5:00 PM | March 24, 2019 05:00 PM | April 07, 2019 05:00 PM | November 26, 2019 05:00 PM | December 10, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
76 | Yes | CMU1.3.2.7.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 15 days | 5 | 74FS+135 days |  |  | January 16, 2020 8:00 AM | January 30, 2020 5:00 PM | January 29, 2020 05:00 PM | February 12, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 245 days | Sanitary-Plumber
77 | Yes | CMU1.3.3 | Auto Scheduled | งานระบบสุขาภิบาล ชั้น 3 | 408 days | 3 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
78 | Yes | CMU1.3.3.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
79 | Yes | CMU1.3.3.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 80FS+15 days |  | 81FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 16, 2019 05:00 PM | August 19, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
80 | Yes | CMU1.3.3.1.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 36 |  | 79FS+15 days,84SS,75 | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 16, 2018 05:00 PM | March 21, 2019 05:00 PM | January 09, 2019 05:00 PM | May 14, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
81 | Yes | CMU1.3.3.1.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 79FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 11, 2019 05:00 PM | January 14, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
82 | Yes | CMU1.3.3.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
83 | Yes | CMU1.3.3.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 84FS+15 days |  | 85FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 12, 2019 05:00 PM | August 15, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
84 | Yes | CMU1.3.3.2.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 80SS |  | 83FS+15 days,75 | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 16, 2018 05:00 PM | March 21, 2019 05:00 PM | January 09, 2019 05:00 PM | May 14, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
85 | Yes | CMU1.3.3.2.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 83FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 17, 2019 05:00 PM | January 20, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
86 | Yes | CMU1.3.4 | Auto Scheduled | งานระบบไฟฟ้า ชั้น 3 | 147 days | 3 |  |  |  | May 14, 2019 8:00 AM | October 7, 2019 5:00 PM | October 21, 2018 05:00 PM | March 16, 2019 05:00 PM | May 12, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 360 days | 360 days | 360 days
87 | Yes | CMU1.3.4.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 60 days | 4 | 89FS+7 days |  |  | August 9, 2019 8:00 AM | October 7, 2019 5:00 PM | August 17, 2019 05:00 PM | October 15, 2019 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 360 days | 360 days | 360 days | Electrician
88 | Yes | CMU1.3.4.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 60 days | 4 | 89FS+7 days |  |  | August 9, 2019 8:00 AM | October 7, 2019 5:00 PM | August 26, 2019 05:00 PM | October 24, 2019 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 360 days | 360 days | 360 days | Electrician
89 | Yes | CMU1.3.4.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 92SS+30 days |  | 88FS+7 days,87FS+7 days | May 14, 2019 8:00 AM | August 1, 2019 5:00 PM | May 19, 2019 05:00 PM | August 06, 2019 05:00 PM | May 12, 2020 05:00 PM | July 30, 2020 05:00 PM | As Soon As Possible |  | No | 360 days | 360 days | 0 days | Electrician
90 | Yes | CMU1.3.4.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 92SS+30 days |  |  | May 14, 2019 8:00 AM | August 1, 2019 5:00 PM | May 22, 2019 05:00 PM | August 09, 2019 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 427 days | 427 days | 427 days | Electrician
91 | Yes | CMU1.3.4.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 92SS+30 days |  |  | May 14, 2019 8:00 AM | August 1, 2019 5:00 PM | May 23, 2019 05:00 PM | August 10, 2019 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 427 days | 427 days | 427 days | Electrician
92 | Yes | CMU1.3.5 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้น 3 | 180 days | 3 | 65SS |  | 91SS+30 days,90SS+30 days,89SS+30 days,94,213FS-15 days,218FS-30 days,223FS-15 days,229FS-15 days,243FS-7 days,249FS-7 days | April 14, 2019 8:00 AM | October 10, 2019 5:00 PM | April 17, 2019 05:00 PM | October 13, 2019 05:00 PM | October 12, 2019 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Skilled carpenter
93 | Yes | CMU1.4 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้น 2 | 509 days | 2 |  |  |  | November 16, 2018 8:00 AM | April 7, 2020 5:00 PM | October 17, 2018 05:00 PM | March 08, 2020 05:00 PM | May 16, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 177 days | 177 days
94 | Yes | CMU1.4.1 | Auto Scheduled | งานรื้อถอน ชั้น 2 (รื้อขนไป) | 30 days | 3 | 92 | 152 | 97FS+45 days,98FS+45 days,121SS | October 11, 2019 8:00 AM | November 9, 2019 5:00 PM | October 14, 2019 05:00 PM | November 12, 2019 05:00 PM | June 04, 2018 05:00 PM | July 03, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | General worker
95 | Yes | CMU1.4.2 | Auto Scheduled | งานสถาปัตยกรรม ชั้น 2 | 368 days | 3 |  |  |  | March 22, 2019 8:00 AM | March 23, 2020 5:00 PM | October 17, 2018 05:00 PM | October 19, 2019 05:00 PM | October 04, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 192 days | 192 days
96 | Yes | CMU1.4.2.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 97,99,100 |  |  | February 23, 2020 8:00 AM | March 23, 2020 5:00 PM | March 08, 2020 05:00 PM | April 06, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 192 days | Skilled carpenter
97 | Yes | CMU1.4.2.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 94FS+45 days |  | 96,101 | December 25, 2019 8:00 AM | February 22, 2020 5:00 PM | December 28, 2019 05:00 PM | February 25, 2020 05:00 PM | February 09, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 0 days | General worker
98 | Yes | CMU1.4.2.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 94FS+45 days |  | 99,100 | December 25, 2019 8:00 AM | January 23, 2020 5:00 PM | December 31, 2019 05:00 PM | January 29, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 0 days | General worker
99 | Yes | CMU1.4.2.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 98 |  | 96,101 | January 24, 2020 8:00 AM | February 22, 2020 5:00 PM | February 04, 2020 05:00 PM | March 04, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 0 days | Skilled carpenter
100 | Yes | CMU1.4.2.5 | Auto Scheduled | งานบันได | 30 days | 4 | 98 |  | 96,101 | January 24, 2020 8:00 AM | February 22, 2020 5:00 PM | February 02, 2020 05:00 PM | March 02, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 0 days | General worker
101 | Yes | CMU1.4.2.6 | Auto Scheduled | งานสี | 30 days | 4 | 97,99,100 |  |  | February 23, 2020 8:00 AM | March 23, 2020 5:00 PM | March 11, 2020 05:00 PM | April 09, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 192 days | General worker
102 | Yes | CMU1.4.2.7 | Auto Scheduled | งานสุขภัณฑ์ | 315 days | 4 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 21, 2018 05:00 PM | August 31, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
103 | Yes | CMU1.4.2.7.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 104FS+135 days |  | 105FS+135 days | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | September 08, 2019 05:00 PM | September 22, 2019 05:00 PM | April 24, 2020 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
104 | Yes | CMU1.4.2.7.2 | Auto Scheduled | ZONE T-2 กลาง | 15 days | 5 | 113,109 |  | 103FS+135 days | March 22, 2019 8:00 AM | April 5, 2019 5:00 PM | April 07, 2019 05:00 PM | April 21, 2019 05:00 PM | November 26, 2019 05:00 PM | December 10, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
105 | Yes | CMU1.4.2.7.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 15 days | 5 | 103FS+135 days |  |  | January 16, 2020 8:00 AM | January 30, 2020 5:00 PM | February 13, 2020 05:00 PM | February 27, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 245 days | Sanitary-Plumber
106 | Yes | CMU1.4.3 | Auto Scheduled | งานระบบสุขาภิบาล ชั้น 2 | 408 days | 3 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
107 | Yes | CMU1.4.3.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
108 | Yes | CMU1.4.3.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 109FS+15 days |  | 110FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 17, 2019 05:00 PM | August 20, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
109 | Yes | CMU1.4.3.1.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 36 |  | 113SS,104,108FS+15 days | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 22, 2018 05:00 PM | March 27, 2019 05:00 PM | August 25, 2019 05:00 PM | December 28, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
110 | Yes | CMU1.4.3.1.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 108FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 08, 2019 05:00 PM | January 11, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
111 | Yes | CMU1.4.3.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
112 | Yes | CMU1.4.3.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 113FS+15 days |  | 114FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 29, 2019 05:00 PM | September 01, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
113 | Yes | CMU1.4.3.2.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 109SS |  | 104,112FS+15 days | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 28, 2018 05:00 PM | April 02, 2019 05:00 PM | August 25, 2019 05:00 PM | December 28, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
114 | Yes | CMU1.4.3.2.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 112FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 21, 2019 05:00 PM | January 24, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
115 | Yes | CMU1.4.4 | Auto Scheduled | งานระบบไฟฟ้า ชั้น 2 | 147 days | 3 |  |  |  | November 10, 2019 8:00 AM | April 4, 2020 5:00 PM | October 20, 2018 05:00 PM | March 15, 2019 05:00 PM | May 12, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 180 days | 180 days | 180 days
116 | Yes | CMU1.4.4.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 60 days | 4 | 118FS+7 days |  |  | February 5, 2020 8:00 AM | April 4, 2020 5:00 PM | February 12, 2020 05:00 PM | April 11, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 180 days | 180 days | 180 days | Electrician
117 | Yes | CMU1.4.4.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 60 days | 4 | 118FS+7 days |  |  | February 5, 2020 8:00 AM | April 4, 2020 5:00 PM | February 13, 2020 05:00 PM | April 12, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 180 days | 180 days | 180 days | Electrician
118 | Yes | CMU1.4.4.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 121SS+30 days |  | 117FS+7 days,116FS+7 days | November 10, 2019 8:00 AM | January 28, 2020 5:00 PM | November 15, 2019 05:00 PM | February 02, 2020 05:00 PM | May 12, 2020 05:00 PM | July 30, 2020 05:00 PM | As Soon As Possible |  | No | 180 days | 180 days | 0 days | Electrician
119 | Yes | CMU1.4.4.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 121SS+30 days |  |  | November 10, 2019 8:00 AM | January 28, 2020 5:00 PM | November 17, 2019 05:00 PM | February 04, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 247 days | 247 days | 247 days | Electrician
120 | Yes | CMU1.4.4.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 121SS+30 days |  |  | November 10, 2019 8:00 AM | January 28, 2020 5:00 PM | November 19, 2019 05:00 PM | February 06, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 247 days | 247 days | 247 days | Electrician
121 | Yes | CMU1.4.5 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้น 2 | 180 days | 3 | 94SS |  | 120SS+30 days,119SS+30 days,118SS+30 days,123,212FS-15 days,217FS-30 days,222FS-15 days,228FS-15 days,242FS-7 days,248FS-7 days | October 11, 2019 8:00 AM | April 7, 2020 5:00 PM | October 14, 2019 05:00 PM | April 10, 2020 05:00 PM | June 04, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Skilled carpenter
122 | Yes | CMU1.5 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้น 1 | 686 days | 2 |  |  |  | November 16, 2018 8:00 AM | October 1, 2020 5:00 PM | October 17, 2018 05:00 PM | September 01, 2020 05:00 PM | November 20, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 0 days | 0 days
123 | Yes | CMU1.5.1 | Auto Scheduled | งานรื้อถอน ชั้น 1 (รื้อขนไป) | 30 days | 3 | 121 | 63 | 124,127FS+45 days,128FS+45 days,131FS+45 days,152SS,193SS,194SS,195SS,196SS,197SS,202SS,204SS,205SS,206SS,207SS | April 8, 2020 8:00 AM | May 7, 2020 5:00 PM | April 11, 2020 05:00 PM | May 10, 2020 05:00 PM | July 19, 2018 05:00 PM | August 17, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | General worker
124 | Yes | CMU1.5.2 | Auto Scheduled | งานโครงสร้างวิศวกรรม ชั้น 1 | 75 days | 3 | 123 |  |  | May 8, 2020 8:00 AM | July 21, 2020 5:00 PM | May 12, 2020 05:00 PM | July 25, 2020 05:00 PM | July 23, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 72 days | 72 days | 72 days | General worker
125 | Yes | CMU1.5.3 | Auto Scheduled | งานสถาปัตยกรรม ชั้น 1 | 548 days | 3 |  |  |  | March 22, 2019 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | April 16, 2020 05:00 PM | April 07, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 12 days | 12 days
126 | Yes | CMU1.5.3.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 127,129,130 |  |  | August 21, 2020 8:00 AM | September 19, 2020 5:00 PM | August 24, 2020 05:00 PM | September 22, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | Skilled carpenter
127 | Yes | CMU1.5.3.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 123FS+45 days |  | 126,132 | June 22, 2020 8:00 AM | August 20, 2020 5:00 PM | June 25, 2020 05:00 PM | August 23, 2020 05:00 PM | October 02, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
128 | Yes | CMU1.5.3.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 123FS+45 days |  | 129,130 | June 22, 2020 8:00 AM | July 21, 2020 5:00 PM | June 25, 2020 05:00 PM | July 24, 2020 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
129 | Yes | CMU1.5.3.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 128 |  | 126,132 | July 22, 2020 8:00 AM | August 20, 2020 5:00 PM | July 25, 2020 05:00 PM | August 23, 2020 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | Skilled carpenter
130 | Yes | CMU1.5.3.5 | Auto Scheduled | งานบันได | 30 days | 4 | 128 |  | 126,132 | July 22, 2020 8:00 AM | August 20, 2020 5:00 PM | July 25, 2020 05:00 PM | August 23, 2020 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
131 | Yes | CMU1.5.3.6 | Auto Scheduled | งานตกแต่งอื่น ๆ | 60 days | 4 | 123FS+45 days |  |  | June 22, 2020 8:00 AM | August 20, 2020 5:00 PM | June 25, 2020 05:00 PM | August 23, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 42 days | 42 days | 42 days | General worker
132 | Yes | CMU1.5.3.7 | Auto Scheduled | งานสี | 30 days | 4 | 127,129,130 |  |  | August 21, 2020 8:00 AM | September 19, 2020 5:00 PM | August 24, 2020 05:00 PM | September 22, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
133 | Yes | CMU1.5.3.8 | Auto Scheduled | งานสุขภัณฑ์ | 315 days | 4 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 22, 2018 05:00 PM | September 01, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
134 | Yes | CMU1.5.3.8.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 135FS+135 days |  | 136FS+135 days | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | August 24, 2019 05:00 PM | September 07, 2019 05:00 PM | April 24, 2020 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
135 | Yes | CMU1.5.3.8.2 | Auto Scheduled | ZONE T-2 กลาง | 15 days | 5 | 140,144 |  | 134FS+135 days,164FS+135 days | March 22, 2019 8:00 AM | April 5, 2019 5:00 PM | March 24, 2019 05:00 PM | April 07, 2019 05:00 PM | November 26, 2019 05:00 PM | December 10, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
136 | Yes | CMU1.5.3.8.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 15 days | 5 | 134FS+135 days |  |  | January 16, 2020 8:00 AM | January 30, 2020 5:00 PM | January 25, 2020 05:00 PM | February 08, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 245 days | Sanitary-Plumber
137 | Yes | CMU1.5.4 | Auto Scheduled | งานระบบสุขาภิบาล ชั้น 1 | 408 days | 3 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 278 days | 44 days
138 | Yes | CMU1.5.4.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 278 days | 44 days
139 | Yes | CMU1.5.4.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 140FS+15 days |  | 141FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 13, 2019 05:00 PM | August 16, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
140 | Yes | CMU1.5.4.1.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 36 |  | 139FS+15 days,144SS,135,167FS+15 days | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 16, 2018 05:00 PM | March 21, 2019 05:00 PM | January 03, 2019 05:00 PM | May 08, 2019 05:00 PM | As Soon As Possible |  | No | 44 days | 44 days | 0 days | Sanitary-Plumber
141 | Yes | CMU1.5.4.1.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 139FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 07, 2019 05:00 PM | January 10, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
142 | Yes | CMU1.5.4.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 278 days | 44 days
143 | Yes | CMU1.5.4.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 144FS+15 days |  | 145FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 12, 2019 05:00 PM | August 15, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
144 | Yes | CMU1.5.4.2.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 140SS |  | 143FS+15 days,135,169FS+15 days | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 16, 2018 05:00 PM | March 21, 2019 05:00 PM | January 03, 2019 05:00 PM | May 08, 2019 05:00 PM | As Soon As Possible |  | No | 44 days | 44 days | 0 days | Sanitary-Plumber
145 | Yes | CMU1.5.4.2.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 143FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 04, 2019 05:00 PM | January 07, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
146 | Yes | CMU1.5.5 | Auto Scheduled | งานระบบไฟฟ้า ชั้น 1 | 147 days | 3 |  |  |  | May 8, 2020 8:00 AM | October 1, 2020 5:00 PM | October 21, 2018 05:00 PM | March 16, 2019 05:00 PM | May 12, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 0 days | 0 days | 0 days
147 | Yes | CMU1.5.5.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 60 days | 4 | 149FS+7 days |  |  | August 3, 2020 8:00 AM | October 1, 2020 5:00 PM | August 06, 2020 05:00 PM | October 04, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Electrician
148 | Yes | CMU1.5.5.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 60 days | 4 | 149FS+7 days |  |  | August 3, 2020 8:00 AM | October 1, 2020 5:00 PM | August 06, 2020 05:00 PM | October 04, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Electrician
149 | Yes | CMU1.5.5.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 152SS+30 days |  | 148FS+7 days,147FS+7 days | May 8, 2020 8:00 AM | July 26, 2020 5:00 PM | May 11, 2020 05:00 PM | July 29, 2020 05:00 PM | May 12, 2020 05:00 PM | July 30, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Electrician
150 | Yes | CMU1.5.5.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 152SS+30 days |  |  | May 8, 2020 8:00 AM | July 26, 2020 5:00 PM | May 11, 2020 05:00 PM | July 29, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 67 days | 67 days | 67 days | Electrician
151 | Yes | CMU1.5.5.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 152SS+30 days |  |  | May 8, 2020 8:00 AM | July 26, 2020 5:00 PM | May 11, 2020 05:00 PM | July 29, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 67 days | 67 days | 67 days | Electrician
152 | Yes | CMU1.5.6 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้น 1 | 165 days | 3 | 123SS |  | 151SS+30 days,150SS+30 days,149SS+30 days,154SS,211FS-30 days,210FS-30 days,216FS-45 days,221FS-30 days,227FS-30 days,226FS-30 days,232FS-45 days,241FS-7 days,247FS-7 days | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 11, 2020 05:00 PM | September 22, 2020 05:00 PM | November 26, 2019 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Skilled carpenter
153 | Yes | CMU1.6 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้นใต้ดิน | 533 days | 2 |  |  |  | April 6, 2019 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | April 01, 2020 05:00 PM | April 22, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 12 days | 12 days
154 | Yes | CMU1.6.1 | Auto Scheduled | งานรื้อถอน ชั้นใต้ดิน (รื้อขนไป) | 30 days | 3 | 152SS |  | 155,158FS+45 days,159FS+45 days,177SS,176SS,175SS,174SS | April 8, 2020 8:00 AM | May 7, 2020 5:00 PM | April 11, 2020 05:00 PM | May 10, 2020 05:00 PM | November 26, 2019 05:00 PM | December 25, 2019 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
155 | Yes | CMU1.6.2 | Auto Scheduled | งานโครงสร้างวิศวกรรม ชั้นใต้ดิน | 75 days | 3 | 154 |  |  | May 8, 2020 8:00 AM | July 21, 2020 5:00 PM | May 12, 2020 05:00 PM | July 25, 2020 05:00 PM | July 23, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 72 days | 72 days | 72 days | General worker
156 | Yes | CMU1.6.3 | Auto Scheduled | งานสถาปัตยกรรม ชั้นใต้ดิน | 398 days | 3 |  |  |  | August 19, 2019 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | November 18, 2019 05:00 PM | September 04, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 320 days | 12 days | 12 days
157 | Yes | CMU1.6.3.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 158,160,161 |  |  | August 21, 2020 8:00 AM | September 19, 2020 5:00 PM | September 14, 2020 05:00 PM | October 13, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | Skilled carpenter
158 | Yes | CMU1.6.3.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 154FS+45 days |  | 157,162 | June 22, 2020 8:00 AM | August 20, 2020 5:00 PM | June 25, 2020 05:00 PM | August 23, 2020 05:00 PM | February 09, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
159 | Yes | CMU1.6.3.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 154FS+45 days |  | 160,161 | June 22, 2020 8:00 AM | July 21, 2020 5:00 PM | July 16, 2020 05:00 PM | August 14, 2020 05:00 PM | August 22, 2020 05:00 PM | September 20, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
160 | Yes | CMU1.6.3.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 159 |  | 157,162 | July 22, 2020 8:00 AM | August 20, 2020 5:00 PM | August 15, 2020 05:00 PM | September 13, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | Skilled carpenter
161 | Yes | CMU1.6.3.5 | Auto Scheduled | งานบันได | 30 days | 4 | 159 |  | 157,162 | July 22, 2020 8:00 AM | August 20, 2020 5:00 PM | August 15, 2020 05:00 PM | September 13, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
162 | Yes | CMU1.6.3.6 | Auto Scheduled | งานสี | 30 days | 4 | 158,160,161 |  |  | August 21, 2020 8:00 AM | September 19, 2020 5:00 PM | September 14, 2020 05:00 PM | October 13, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
163 | Yes | CMU1.6.3.7 | Auto Scheduled | งานสุขภัณฑ์ | 15 days | 4 |  |  |  | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | October 20, 2018 05:00 PM | November 03, 2018 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 395 days | 395 days | 395 days
164 | Yes | CMU1.6.3.7.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 135FS+135 days |  |  | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | August 27, 2019 05:00 PM | September 10, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 395 days | 395 days | 395 days | Sanitary-Plumber
165 | Yes | CMU1.6.4 | Auto Scheduled | งานระบบสุขาภิบาล ชั้นใต้ดิน | 501 days | 3 |  |  |  | April 6, 2019 8:00 AM | August 18, 2020 5:00 PM | October 17, 2018 05:00 PM | February 29, 2020 05:00 PM | May 24, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 44 days | 44 days
166 | Yes | CMU1.6.4.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 126 days | 4 |  |  |  | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | October 21, 2018 05:00 PM | February 23, 2019 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 419 days | 419 days | 419 days
167 | Yes | CMU1.6.4.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 140FS+15 days |  |  | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 14, 2019 05:00 PM | August 17, 2019 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 419 days | 419 days | 419 days | Sanitary-Plumber
168 | Yes | CMU1.6.4.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 126 days | 4 |  |  |  | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | October 21, 2018 05:00 PM | February 23, 2019 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 44 days | 44 days
169 | Yes | CMU1.6.4.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 144FS+15 days |  | 170FS+300 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 06, 2019 05:00 PM | August 09, 2019 05:00 PM | May 24, 2019 05:00 PM | September 26, 2019 05:00 PM | As Soon As Possible |  | No | 44 days | 44 days | 0 days | Sanitary-Plumber
170 | Yes | CMU1.6.4.3 | Auto Scheduled | งานระบบระบายน้ำฝน | 75 days | 4 | 169FS+300 days |  |  | June 5, 2020 8:00 AM | August 18, 2020 5:00 PM | June 05, 2020 05:00 PM | August 18, 2020 05:00 PM | July 23, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 44 days | 44 days | 44 days | Sanitary-Plumber
171 | Yes | CMU1.6.5 | Auto Scheduled | งานระบบไฟฟ้า ชั้นใต้ดิน | 147 days | 3 |  |  |  | April 8, 2020 8:00 AM | September 1, 2020 5:00 PM | October 23, 2018 05:00 PM | March 18, 2019 05:00 PM | May 12, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 30 days | 30 days | 30 days
172 | Yes | CMU1.6.5.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 60 days | 4 | 174FS+7 days |  |  | July 4, 2020 8:00 AM | September 1, 2020 5:00 PM | July 07, 2020 05:00 PM | September 04, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 30 days | 30 days | 30 days | Electrician
173 | Yes | CMU1.6.5.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 60 days | 4 | 174FS+7 days |  |  | July 4, 2020 8:00 AM | September 1, 2020 5:00 PM | July 07, 2020 05:00 PM | September 04, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 30 days | 30 days | 30 days | Electrician
174 | Yes | CMU1.6.5.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 154SS |  | 173FS+7 days,172FS+7 days | April 8, 2020 8:00 AM | June 26, 2020 5:00 PM | April 11, 2020 05:00 PM | June 29, 2020 05:00 PM | May 12, 2020 05:00 PM | July 30, 2020 05:00 PM | As Soon As Possible |  | No | 30 days | 30 days | 0 days | Electrician
175 | Yes | CMU1.6.5.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 154SS |  |  | April 8, 2020 8:00 AM | June 26, 2020 5:00 PM | April 14, 2020 05:00 PM | July 02, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 97 days | 97 days | 97 days | Electrician
176 | Yes | CMU1.6.5.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 154SS |  |  | April 8, 2020 8:00 AM | June 26, 2020 5:00 PM | April 16, 2020 05:00 PM | July 04, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 97 days | 97 days | 97 days | Electrician
177 | Yes | CMU1.6.6 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้นใต้ดิน | 165 days | 3 | 154SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 11, 2020 05:00 PM | September 22, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | Skilled carpenter
178 | Yes | CMU1.7 | Auto Scheduled | หมวดงานระบบคอมพิวเตอร์และแจ้งเหตุเพลิงไหม้ | 670 days | 2 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
179 | Yes | CMU1.7.1 | Auto Scheduled | งานระบบคอมพิวเตอร์ | 670 days | 3 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
180 | Yes | CMU1.7.1.1 | Auto Scheduled | ชั้นที่ 4 | 160 days | 4 | 36FS+14 days |  | 181 | November 30, 2018 8:00 AM | May 8, 2019 5:00 PM | November 30, 2018 05:00 PM | May 08, 2019 05:00 PM | April 24, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
181 | Yes | CMU1.7.1.2 | Auto Scheduled | ชั้นที่ 3 | 175 days | 4 | 180 | 182 | 182 | May 9, 2019 8:00 AM | October 30, 2019 5:00 PM | May 09, 2019 05:00 PM | October 30, 2019 05:00 PM | April 09, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
182 | Yes | CMU1.7.1.3 | Auto Scheduled | ชั้นที่ 2 | 175 days | 4 | 181 | 183 | 183,184 | October 31, 2019 8:00 AM | April 22, 2020 5:00 PM | October 31, 2019 05:00 PM | April 22, 2020 05:00 PM | April 09, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
183 | Yes | CMU1.7.1.4 | Auto Scheduled | ชั้นที่ 1 | 160 days | 4 | 182 | 180 |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 23, 2020 05:00 PM | September 29, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
184 | Yes | CMU1.7.1.5 | Auto Scheduled | ชั้นใต้ดิน | 160 days | 4 | 182 | 183SS |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 23, 2020 05:00 PM | September 29, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
185 | Yes | CMU1.7.2 | Auto Scheduled | ระบบแจ้งเหตุเพลิงไหม้ | 670 days | 3 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
186 | Yes | CMU1.7.2.1 | Auto Scheduled | ชั้นที่ 4 | 160 days | 4 | 36FS+14 days |  | 187 | November 30, 2018 8:00 AM | May 8, 2019 5:00 PM | November 30, 2018 05:00 PM | May 08, 2019 05:00 PM | April 24, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
187 | Yes | CMU1.7.2.2 | Auto Scheduled | ชั้นที่ 3 | 175 days | 4 | 186 | 188 | 188 | May 9, 2019 8:00 AM | October 30, 2019 5:00 PM | May 09, 2019 05:00 PM | October 30, 2019 05:00 PM | April 09, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
188 | Yes | CMU1.7.2.3 | Auto Scheduled | ชั้นที่ 2 | 175 days | 4 | 187 | 189 | 189,190 | October 31, 2019 8:00 AM | April 22, 2020 5:00 PM | October 31, 2019 05:00 PM | April 22, 2020 05:00 PM | April 09, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
189 | Yes | CMU1.7.2.4 | Auto Scheduled | ชั้นที่ 1 | 160 days | 4 | 188 | 186 |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 23, 2020 05:00 PM | September 29, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
190 | Yes | CMU1.7.2.5 | Auto Scheduled | ชั้นใต้ดิน | 160 days | 4 | 188 | 189SS |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 23, 2020 05:00 PM | September 29, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
191 | Yes | CMU1.8 | Auto Scheduled | หมวดงานสีภายนอก งานซ่อมแซมและตกแต่งภายนอกอาคาร | 660 days | 2 |  |  |  | November 30, 2018 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | August 06, 2020 05:00 PM | December 16, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 507 days | 12 days | 12 days
192 | Yes | CMU1.8.1 | Auto Scheduled | งานสีภายนอกและงานซ่อมแซมพื้นผิวภายนอกอาคาร | 660 days | 3 |  |  |  | November 30, 2018 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | August 06, 2020 05:00 PM | December 16, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 507 days | 12 days | 12 days
193 | Yes | CMU1.8.1.1 | Auto Scheduled | งานขัดลอกสีทาผนังเดิม | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 11, 2020 05:00 PM | September 22, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
194 | Yes | CMU1.8.1.2 | Auto Scheduled | น้ำยาทาปูนเก่า (สีรองพื้น) | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 11, 2020 05:00 PM | September 22, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
195 | Yes | CMU1.8.1.3 | Auto Scheduled | งานทาสีภายนอก (ทา 2 เที่ยว) ไม่รวมชั้นใต้ดิน | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 11, 2020 05:00 PM | September 22, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
196 | Yes | CMU1.8.1.4 | Auto Scheduled | งานทำความสะอาดและซ่อมแซมผนังกรุอิฐโชว์แนว (อ้างอิงราคางานขัดลอกสี) | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 11, 2020 05:00 PM | September 22, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
197 | Yes | CMU1.8.1.5 | Auto Scheduled | น้ำยาเคลือบผิวผนังอิฐโชว์แนว (อ้างอิงค่าทาน้ำยากันเชื้อรา) | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 11, 2020 05:00 PM | September 22, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
198 | Yes | CMU1.8.1.6 | Auto Scheduled | งานรื้อถอนแผ่นวัสดุกันซึมหลังคาดาดฟ้า (รื้อขนไป) | 90 days | 4 | 36FS+14 days |  |  | November 30, 2018 8:00 AM | February 27, 2019 5:00 PM | December 03, 2018 05:00 PM | March 02, 2019 05:00 PM | July 08, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 582 days | 582 days | 582 days | General worker
199 | Yes | CMU1.8.1.7 | Auto Scheduled | งานแผ่นวัสดุกันซึมแบบเป่าไฟผิวทราย | 90 days | 4 | 36FS+14 days |  |  | November 30, 2018 8:00 AM | February 27, 2019 5:00 PM | December 04, 2018 05:00 PM | March 03, 2019 05:00 PM | July 08, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 582 days | 582 days | 582 days | General worker
200 | Yes | CMU1.8.1.8 | Auto Scheduled | งานกันซึมชนิด Polyurethane สูตรน้ำมัน ชนิดยืดหยุ่นสูงเป็นพิเศษ | 90 days | 4 | 36FS+14 days |  |  | November 30, 2018 8:00 AM | February 27, 2019 5:00 PM | December 03, 2018 05:00 PM | March 02, 2019 05:00 PM | July 08, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 582 days | 582 days | 582 days | General worker
201 | Yes | CMU1.8.2 | Auto Scheduled | งานตกแต่งภายนอกอาคาร | 165 days | 3 |  |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | October 20, 2018 05:00 PM | April 02, 2019 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 12 days | 12 days | 12 days
202 | Yes | CMU1.8.2.1 | Auto Scheduled | ตะแกรงเหล็กฉีกกันนก XS-32 | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 11, 2020 05:00 PM | September 22, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
203 | Yes | CMU1.9 | Auto Scheduled | หมวดงานบริเวณ | 165 days | 2 |  |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | October 22, 2018 05:00 PM | April 04, 2019 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 12 days | 12 days | 12 days
204 | Yes | CMU1.9.1 | Auto Scheduled | งานรื้อถอน งานบริเวณ | 165 days | 3 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 11, 2020 05:00 PM | September 22, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
205 | Yes | CMU1.9.2 | Auto Scheduled | งานโครงสร้างวิศวกรรม งานบริเวณ | 165 days | 3 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 11, 2020 05:00 PM | September 22, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
206 | Yes | CMU1.9.3 | Auto Scheduled | งานสถาปัตยกรรม งานบริเวณ | 165 days | 3 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 11, 2020 05:00 PM | September 22, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
207 | Yes | CMU1.9.4 | Auto Scheduled | งานระบบไฟฟ้า งานบริเวณ | 165 days | 3 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 11, 2020 05:00 PM | September 22, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | Electrician
208 | Yes | CMU1.10 | Auto Scheduled | หมวดงานครุภัณฑ์จัดซื้อ | 670 days | 2 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
209 | Yes | CMU1.10.1 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัว | 510 days | 3 |  |  |  | April 14, 2019 8:00 AM | September 4, 2020 5:00 PM | October 17, 2018 05:00 PM | March 09, 2020 05:00 PM | May 15, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 522 days | 27 days | 27 days
210 | Yes | CMU1.10.1.1 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้นใต้ดิน | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | August 28, 2020 05:00 PM | September 11, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
211 | Yes | CMU1.10.1.2 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้น 1 | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | August 31, 2020 05:00 PM | September 14, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
212 | Yes | CMU1.10.1.3 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้น 2 | 15 days | 4 | 121FS-15 days |  |  | March 24, 2020 8:00 AM | April 7, 2020 5:00 PM | March 31, 2020 05:00 PM | April 14, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Skilled carpenter
213 | Yes | CMU1.10.1.4 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้น 3 | 15 days | 4 | 92FS-15 days |  |  | September 26, 2019 8:00 AM | October 10, 2019 5:00 PM | October 04, 2019 05:00 PM | October 18, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Skilled carpenter
214 | Yes | CMU1.10.1.5 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้น 4 | 15 days | 4 | 63 |  |  | April 14, 2019 8:00 AM | April 28, 2019 5:00 PM | April 21, 2019 05:00 PM | May 05, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 522 days | 522 days | 522 days | Skilled carpenter
215 | Yes | CMU1.10.2 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ | 525 days | 3 |  |  |  | March 30, 2019 8:00 AM | September 4, 2020 5:00 PM | October 17, 2018 05:00 PM | March 24, 2020 05:00 PM | April 30, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 522 days | 27 days | 27 days
216 | Yes | CMU1.10.2.1 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ ชั้น 1 | 30 days | 4 | 152FS-45 days |  |  | August 6, 2020 8:00 AM | September 4, 2020 5:00 PM | August 15, 2020 05:00 PM | September 13, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
217 | Yes | CMU1.10.2.2 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ ชั้น 2 | 30 days | 4 | 121FS-30 days |  |  | March 9, 2020 8:00 AM | April 7, 2020 5:00 PM | March 15, 2020 05:00 PM | April 13, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Skilled carpenter
218 | Yes | CMU1.10.2.3 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ ชั้น 3 | 30 days | 4 | 92FS-30 days |  |  | September 11, 2019 8:00 AM | October 10, 2019 5:00 PM | September 16, 2019 05:00 PM | October 15, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Skilled carpenter
219 | Yes | CMU1.10.2.4 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ ชั้น 4 | 30 days | 4 | 63FS-15 days |  |  | March 30, 2019 8:00 AM | April 28, 2019 5:00 PM | April 02, 2019 05:00 PM | May 01, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 522 days | 522 days | 522 days | Skilled carpenter
220 | Yes | CMU1.10.3 | Auto Scheduled | งานผ้าม่าน | 510 days | 3 |  |  |  | April 14, 2019 8:00 AM | September 4, 2020 5:00 PM | October 17, 2018 05:00 PM | March 09, 2020 05:00 PM | May 15, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 522 days | 27 days | 27 days
221 | Yes | CMU1.10.3.1 | Auto Scheduled | งานผ้าม่าน ชั้น 1 | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | August 28, 2020 05:00 PM | September 11, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
222 | Yes | CMU1.10.3.2 | Auto Scheduled | งานผ้าม่าน ชั้น 2 | 15 days | 4 | 121FS-15 days |  |  | March 24, 2020 8:00 AM | April 7, 2020 5:00 PM | March 30, 2020 05:00 PM | April 13, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Skilled carpenter
223 | Yes | CMU1.10.3.3 | Auto Scheduled | งานผ้าม่าน ชั้น 3 | 15 days | 4 | 92FS-15 days |  |  | September 26, 2019 8:00 AM | October 10, 2019 5:00 PM | October 02, 2019 05:00 PM | October 16, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Skilled carpenter
224 | Yes | CMU1.10.3.4 | Auto Scheduled | งานผ้าม่าน ชั้น 4 | 15 days | 4 | 63 |  |  | April 14, 2019 8:00 AM | April 28, 2019 5:00 PM | April 25, 2019 05:00 PM | May 09, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 522 days | 522 days | 522 days | Skilled carpenter
225 | Yes | CMU1.10.4 | Auto Scheduled | งานป้าย | 510 days | 3 |  |  |  | April 14, 2019 8:00 AM | September 4, 2020 5:00 PM | October 17, 2018 05:00 PM | March 09, 2020 05:00 PM | May 15, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 522 days | 27 days | 27 days
226 | Yes | CMU1.10.4.1 | Auto Scheduled | งานป้าย ชั้นใต้ดิน | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | August 28, 2020 05:00 PM | September 11, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
227 | Yes | CMU1.10.4.2 | Auto Scheduled | งานป้าย ชั้น 1 | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | August 31, 2020 05:00 PM | September 14, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
228 | Yes | CMU1.10.4.3 | Auto Scheduled | งานป้าย ชั้น 2 | 15 days | 4 | 121FS-15 days |  |  | March 24, 2020 8:00 AM | April 7, 2020 5:00 PM | March 30, 2020 05:00 PM | April 13, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Skilled carpenter
229 | Yes | CMU1.10.4.4 | Auto Scheduled | งานป้าย ชั้น 3 | 15 days | 4 | 92FS-15 days |  |  | September 26, 2019 8:00 AM | October 10, 2019 5:00 PM | October 03, 2019 05:00 PM | October 17, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Skilled carpenter
230 | Yes | CMU1.10.4.5 | Auto Scheduled | งานป้าย ชั้น 4 | 15 days | 4 | 63 |  |  | April 14, 2019 8:00 AM | April 28, 2019 5:00 PM | April 20, 2019 05:00 PM | May 04, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 522 days | 522 days | 522 days | Skilled carpenter
231 | Yes | CMU1.10.5 | Auto Scheduled | งานอื่นๆ | 15 days | 3 |  |  |  | August 6, 2020 8:00 AM | August 20, 2020 5:00 PM | October 20, 2018 05:00 PM | November 03, 2018 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 42 days | 42 days | 42 days
232 | Yes | CMU1.10.5.1 | Auto Scheduled | ตู้อลูมิเนียมพับขึ้นรูป พ่นสี ครอบตู้กดน้ำ | 15 days | 4 | 152FS-45 days |  |  | August 6, 2020 8:00 AM | August 20, 2020 5:00 PM | August 13, 2020 05:00 PM | August 27, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 42 days | 42 days | 42 days | General worker
233 | Yes | CMU1.10.6 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ | 670 days | 3 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
234 | Yes | CMU1.10.6.1 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้นใต้ดิน | 160 days | 4 | 236 |  |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | May 07, 2020 05:00 PM | October 13, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
235 | Yes | CMU1.10.6.2 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้น 1 | 160 days | 4 | 236 |  |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | May 07, 2020 05:00 PM | October 13, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
236 | Yes | CMU1.10.6.3 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้น 2 | 175 days | 4 | 237 |  | 235,234 | October 31, 2019 8:00 AM | April 22, 2020 5:00 PM | November 14, 2019 05:00 PM | May 06, 2020 05:00 PM | March 12, 2020 05:00 PM | September 02, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
237 | Yes | CMU1.10.6.4 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้น 3 | 175 days | 4 | 238 |  | 236 | May 9, 2019 8:00 AM | October 30, 2019 5:00 PM | May 23, 2019 05:00 PM | November 13, 2019 05:00 PM | March 12, 2020 05:00 PM | September 02, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
238 | Yes | CMU1.10.6.5 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้น 4 | 160 days | 4 | 36FS+14 days |  | 237 | November 30, 2018 8:00 AM | May 8, 2019 5:00 PM | December 02, 2018 05:00 PM | May 10, 2019 05:00 PM | March 27, 2020 05:00 PM | September 02, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
239 | Yes | CMU1.10.7 | Auto Scheduled | งานระบบเครื่องเสียงประกาศ (ใช้ลำโพงของเดิม) | 539 days | 3 |  |  |  | April 7, 2019 8:00 AM | September 26, 2020 5:00 PM | October 17, 2018 05:00 PM | April 07, 2020 05:00 PM | April 16, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 530 days | 5 days | 5 days
240 | Yes | CMU1.10.7.1 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้นใต้ดิน | 7 days | 4 | 241 |  |  | September 20, 2020 8:00 AM | September 26, 2020 5:00 PM | September 27, 2020 05:00 PM | October 03, 2020 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 5 days | 5 days | 5 days | Electrician
241 | Yes | CMU1.10.7.2 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้น 1 | 7 days | 4 | 152FS-7 days |  | 240 | September 13, 2020 8:00 AM | September 19, 2020 5:00 PM | September 16, 2020 05:00 PM | September 22, 2020 05:00 PM | September 09, 2020 05:00 PM | September 15, 2020 05:00 PM | As Soon As Possible |  | No | 5 days | 5 days | 0 days | Electrician
242 | Yes | CMU1.10.7.3 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้น 2 | 7 days | 4 | 121FS-7 days |  |  | April 1, 2020 8:00 AM | April 7, 2020 5:00 PM | April 06, 2020 05:00 PM | April 12, 2020 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Electrician
243 | Yes | CMU1.10.7.4 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้น 3 | 7 days | 4 | 92FS-7 days |  |  | October 4, 2019 8:00 AM | October 10, 2019 5:00 PM | October 11, 2019 05:00 PM | October 17, 2019 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Electrician
244 | Yes | CMU1.10.7.5 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้น 4 | 7 days | 4 | 63FS-7 days |  |  | April 7, 2019 8:00 AM | April 13, 2019 5:00 PM | April 11, 2019 05:00 PM | April 17, 2019 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 537 days | 537 days | 537 days | Electrician
245 | Yes | CMU1.10.8 | Auto Scheduled | งานระบบกล้องวงจรปิด (ใช้กล้องวงจรปิดของเดิม) | 539 days | 3 |  |  |  | April 7, 2019 8:00 AM | September 26, 2020 5:00 PM | October 17, 2018 05:00 PM | April 07, 2020 05:00 PM | April 16, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 530 days | 5 days | 5 days
246 | Yes | CMU1.10.8.1 | Auto Scheduled | งานกล้องวงจรปิด ชั้นใต้ดิน | 7 days | 4 | 247 |  |  | September 20, 2020 8:00 AM | September 26, 2020 5:00 PM | September 27, 2020 05:00 PM | October 03, 2020 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 5 days | 5 days | 5 days | Electrician
247 | Yes | CMU1.10.8.2 | Auto Scheduled | งานกล้องวงจรปิด ชั้น 1 | 7 days | 4 | 152FS-7 days |  | 246 | September 13, 2020 8:00 AM | September 19, 2020 5:00 PM | September 16, 2020 05:00 PM | September 22, 2020 05:00 PM | September 09, 2020 05:00 PM | September 15, 2020 05:00 PM | As Soon As Possible |  | No | 5 days | 5 days | 0 days | Electrician
248 | Yes | CMU1.10.8.3 | Auto Scheduled | งานกล้องวงจรปิด ชั้น 2 | 7 days | 4 | 121FS-7 days |  |  | April 1, 2020 8:00 AM | April 7, 2020 5:00 PM | April 07, 2020 05:00 PM | April 13, 2020 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Electrician
249 | Yes | CMU1.10.8.4 | Auto Scheduled | งานกล้องวงจรปิด ชั้น 3 | 7 days | 4 | 92FS-7 days |  |  | October 4, 2019 8:00 AM | October 10, 2019 5:00 PM | October 11, 2019 05:00 PM | October 17, 2019 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Electrician
250 | Yes | CMU1.10.8.5 | Auto Scheduled | งานกล้องวงจรปิด ชั้น 4 | 7 days | 4 | 63FS-7 days |  |  | April 7, 2019 8:00 AM | April 13, 2019 5:00 PM | April 10, 2019 05:00 PM | April 16, 2019 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 537 days | 537 days | 537 days | Electrician

## solutoion_13
ID | Active | WBS | Task_Mode | Name | Duration | Outline_Level | Predecessors | Predecessors2 | Successors | Start_Date | Finish_Date | Early_Start | Early_Finish | Late_Start | Late_Finish | Constraint_Type | Constraint_Date | Summary | Start_Slack | Finish_Slack | Free_Slack | Resource_Names
1 | Yes | CMU1 | Auto Scheduled | โครงการปรับปรุงสำนักหอสมุด มหาวิทยาลัยเชียงใหม่ | 716 days | 1 |  |  |  | October 17, 2018 8:00 AM | October 1, 2020 5:00 PM | October 17, 2018 05:00 PM | October 01, 2020 05:00 PM | October 21, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 0 days | 0 days | 0 days
2 | Yes | CMU1.1 | Auto Scheduled | หมวดเตรียมการ | 675 days | 2 |  |  |  | October 17, 2018 8:00 AM | August 21, 2020 5:00 PM | October 17, 2018 05:00 PM | August 21, 2020 05:00 PM | December 01, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 41 days | 41 days | 41 days
3 | Yes | CMU1.1.1 | Auto Scheduled | งานอาคารสนามและผังบริเวณโครงการ | 14 days | 3 | 4FS-7 days |  |  | October 26, 2018 8:00 AM | November 8, 2018 5:00 PM | November 01, 2018 05:00 PM | November 14, 2018 05:00 PM | September 22, 2020 05:00 PM | October 05, 2020 05:00 PM | Start No Earlier Than | Oct 24 '18 | No | 693 days | 693 days | 693 days | Engineer
4 | Yes | CMU1.1.2 | Auto Scheduled | งานเชื่อมต่อระบบสาธารณูปโภคโครงการ | 16 days | 3 |  |  | 3FS-7 days | October 17, 2018 8:00 AM | November 1, 2018 5:00 PM | October 19, 2018 05:00 PM | November 03, 2018 05:00 PM | September 13, 2020 05:00 PM | September 28, 2020 05:00 PM | As Soon As Possible |  | No | 693 days | 693 days | 0 days | Engineer
5 | Yes | CMU1.1.3 | Auto Scheduled | งานตรวจทดสอบระบบภายในอาคารก่อนดำเนินการปรับปรุง | 675 days | 3 |  |  |  | October 17, 2018 8:00 AM | August 21, 2020 5:00 PM | October 17, 2018 05:00 PM | August 21, 2020 05:00 PM | December 01, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 41 days | 41 days | 41 days
6 | Yes | CMU1.1.3.1 | Auto Scheduled | ชั้นที่ 4 | 15 days | 4 |  |  | 7FS+150 days | October 17, 2018 8:00 AM | October 31, 2018 5:00 PM | October 20, 2018 05:00 PM | November 03, 2018 05:00 PM | December 01, 2018 05:00 PM | December 15, 2018 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
7 | Yes | CMU1.1.3.2 | Auto Scheduled | ชั้นที่ 3 | 15 days | 4 | 6FS+150 days |  | 8FS+150 days | March 31, 2019 8:00 AM | April 14, 2019 5:00 PM | April 09, 2019 05:00 PM | April 23, 2019 05:00 PM | May 15, 2019 05:00 PM | May 29, 2019 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
8 | Yes | CMU1.1.3.3 | Auto Scheduled | ชั้นที่ 2 | 15 days | 4 | 7FS+150 days |  | 9FS+150 days | September 12, 2019 8:00 AM | September 26, 2019 5:00 PM | October 03, 2019 05:00 PM | October 17, 2019 05:00 PM | October 27, 2019 05:00 PM | November 10, 2019 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
9 | Yes | CMU1.1.3.4 | Auto Scheduled | ชั้นที่ 1 | 15 days | 4 | 8FS+150 days |  | 10FS+150 days | February 24, 2020 8:00 AM | March 9, 2020 5:00 PM | March 24, 2020 05:00 PM | April 07, 2020 05:00 PM | April 09, 2020 05:00 PM | April 23, 2020 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
10 | Yes | CMU1.1.3.5 | Auto Scheduled | ชั้นใต้ดินและภายนอก | 15 days | 4 | 9FS+150 days |  |  | August 7, 2020 8:00 AM | August 21, 2020 5:00 PM | September 16, 2020 05:00 PM | September 30, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 41 days | Engineer
11 | Yes | CMU1.1.4 | Auto Scheduled | งานสำรวจอุปกรณ์ไฟฟ้า, สุขภัณฑ์และครุภัณฑ์ (ของเดิม) ก่อนดำเนินการปรับปรุง | 675 days | 3 |  |  |  | October 17, 2018 8:00 AM | August 21, 2020 5:00 PM | October 17, 2018 05:00 PM | August 21, 2020 05:00 PM | December 01, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 41 days | 41 days | 41 days
12 | Yes | CMU1.1.4.1 | Auto Scheduled | ชั้นที่ 4 | 15 days | 4 |  |  | 13FS+150 days | October 17, 2018 8:00 AM | October 31, 2018 5:00 PM | October 20, 2018 05:00 PM | November 03, 2018 05:00 PM | December 01, 2018 05:00 PM | December 15, 2018 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
13 | Yes | CMU1.1.4.2 | Auto Scheduled | ชั้นที่ 3 | 15 days | 4 | 12FS+150 days |  | 14FS+150 days | March 31, 2019 8:00 AM | April 14, 2019 5:00 PM | April 06, 2019 05:00 PM | April 20, 2019 05:00 PM | May 15, 2019 05:00 PM | May 29, 2019 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
14 | Yes | CMU1.1.4.3 | Auto Scheduled | ชั้นที่ 2 | 15 days | 4 | 13FS+150 days |  | 15FS+150 days | September 12, 2019 8:00 AM | September 26, 2019 5:00 PM | September 24, 2019 05:00 PM | October 08, 2019 05:00 PM | October 27, 2019 05:00 PM | November 10, 2019 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
15 | Yes | CMU1.1.4.4 | Auto Scheduled | ชั้นที่ 1 | 15 days | 4 | 14FS+150 days |  | 16FS+150 days | February 24, 2020 8:00 AM | March 9, 2020 5:00 PM | March 15, 2020 05:00 PM | March 29, 2020 05:00 PM | April 09, 2020 05:00 PM | April 23, 2020 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
16 | Yes | CMU1.1.4.5 | Auto Scheduled | ชั้นใต้ดินและภายนอก | 15 days | 4 | 15FS+150 days |  |  | August 7, 2020 8:00 AM | August 21, 2020 5:00 PM | September 06, 2020 05:00 PM | September 20, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 41 days | Engineer
17 | Yes | CMU1.1.5 | Auto Scheduled | งานเอกสารขออนุมัติใช้วัสดุ, Shop Drawing และครุภัณฑ์ของโครงการ | 106 days | 3 |  |  |  | October 17, 2018 8:00 AM | January 30, 2019 5:00 PM | October 22, 2018 05:00 PM | February 04, 2019 05:00 PM | June 22, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 610 days | 610 days | 610 days
18 | Yes | CMU1.1.5.1 | Auto Scheduled | แบบ Shop Drawing ชั้นที่ 4 | 20 days | 4 |  |  | 19,25SS+14 days,26SS+14 days | October 17, 2018 8:00 AM | November 5, 2018 5:00 PM | October 17, 2018 05:00 PM | November 05, 2018 05:00 PM | October 01, 2018 05:00 PM | October 20, 2018 05:00 PM | As Soon As Possible |  | No | 610 days | 610 days | 0 days | Engineer
19 | Yes | CMU1.1.5.2 | Auto Scheduled | แบบ Shop Drawing ชั้นที่ 3 | 20 days | 4 | 18 |  | 20FS-7 days | November 6, 2018 8:00 AM | November 25, 2018 5:00 PM | November 14, 2018 05:00 PM | December 03, 2018 05:00 PM | July 13, 2020 05:00 PM | August 01, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
20 | Yes | CMU1.1.5.3 | Auto Scheduled | แบบ Shop Drawing ชั้นที่ 2 | 20 days | 4 | 19FS-7 days |  | 21FS-7 days | November 19, 2018 8:00 AM | December 8, 2018 5:00 PM | November 30, 2018 05:00 PM | December 19, 2018 05:00 PM | July 26, 2020 05:00 PM | August 14, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
21 | Yes | CMU1.1.5.4 | Auto Scheduled | แบบ Shop Drawing ชั้นที่ 1 | 20 days | 4 | 20FS-7 days |  | 22FS-7 days | December 2, 2018 8:00 AM | December 21, 2018 5:00 PM | December 19, 2018 05:00 PM | January 07, 2019 05:00 PM | August 08, 2020 05:00 PM | August 27, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
22 | Yes | CMU1.1.5.5 | Auto Scheduled | แบบ Shop Drawing ชั้นใต้ดิน | 20 days | 4 | 21FS-7 days |  | 23FS-7 days | December 15, 2018 8:00 AM | January 3, 2019 5:00 PM | January 08, 2019 05:00 PM | January 27, 2019 05:00 PM | August 21, 2020 05:00 PM | September 09, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
23 | Yes | CMU1.1.5.6 | Auto Scheduled | แบบ Shop Drawing ภายนอกอาคาร | 20 days | 4 | 22FS-7 days |  | 24FS-7 days | December 28, 2018 8:00 AM | January 16, 2019 5:00 PM | February 01, 2019 05:00 PM | February 20, 2019 05:00 PM | September 03, 2020 05:00 PM | September 22, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
24 | Yes | CMU1.1.5.7 | Auto Scheduled | แบบ Shop Drawing landscape | 20 days | 4 | 23FS-7 days |  |  | January 10, 2019 8:00 AM | January 29, 2019 5:00 PM | February 24, 2019 05:00 PM | March 15, 2019 05:00 PM | September 16, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 611 days | Engineer
25 | Yes | CMU1.1.5.8 | Auto Scheduled | แบบ Shop Drawing งานปรับปรุง ครุภัณฑ์ | 92 days | 4 | 18SS+14 days |  |  | October 31, 2018 8:00 AM | January 30, 2019 5:00 PM | November 07, 2018 05:00 PM | February 06, 2019 05:00 PM | July 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 610 days | 610 days | 610 days | Engineer
26 | Yes | CMU1.1.5.9 | Auto Scheduled | แบบ Shop Drawing งานจัดซื้อครุภัณฑ์ | 92 days | 4 | 18SS+14 days |  |  | October 31, 2018 8:00 AM | January 30, 2019 5:00 PM | November 08, 2018 05:00 PM | February 07, 2019 05:00 PM | July 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 610 days | 610 days | 610 days | Engineer
27 | Yes | CMU1.1.6 | Auto Scheduled | งานตรวจทดสอบระบบ, งานอบรมผู้ใช้อาคาร และ As-Built Drawing | 30 days | 3 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 23, 2018 05:00 PM | November 21, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 686 days | 686 days | 686 days
28 | Yes | CMU1.1.6.1 | Auto Scheduled | ชั้นที่ 4 | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 27, 2018 05:00 PM | November 25, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
29 | Yes | CMU1.1.6.2 | Auto Scheduled | ชั้นที่ 3 | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 30, 2018 05:00 PM | November 28, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
30 | Yes | CMU1.1.6.3 | Auto Scheduled | ชั้นที่ 2 | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 30, 2018 05:00 PM | November 28, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
31 | Yes | CMU1.1.6.4 | Auto Scheduled | ชั้นที่ 1 | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 29, 2018 05:00 PM | November 27, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
32 | Yes | CMU1.1.6.5 | Auto Scheduled | ชั้นใต้ดิน | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 25, 2018 05:00 PM | November 23, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
33 | Yes | CMU1.1.6.6 | Auto Scheduled | ทั้งอาคาร | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 23, 2018 05:00 PM | November 21, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
34 | Yes | CMU1.1.7 | Auto Scheduled | งานบริหารงานก่อสร้างและงานอื่น ๆ | 0 days | 3 |  |  |  | October 17, 2018 8:00 AM | October 17, 2018 8:00 AM | October 20, 2018 05:00 PM | October 19, 2018 05:00 PM | October 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 716 days | 716 days | 716 days | Engineer
35 | Yes | CMU1.2 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้น 4 | 471 days | 2 |  |  |  | October 17, 2018 8:00 AM | January 30, 2020 5:00 PM | October 17, 2018 05:00 PM | January 30, 2020 05:00 PM | June 23, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 0 days | 245 days | 0 days
36 | Yes | CMU1.2.1 | Auto Scheduled | งานรื้อถอน ชั้น 4 (รื้อขนไป) | 30 days | 3 |  |  | 39FS+45 days,40FS+45 days,51,63SS+14 days,80,109,140,180FS+14 days,186FS+14 days,198FS+14 days,199FS+14 days,200FS+14 days,238FS+14 days | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 17, 2018 05:00 PM | November 15, 2018 05:00 PM | March 11, 2018 05:00 PM | April 09, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | General worker
37 | Yes | CMU1.2.2 | Auto Scheduled | งานสถาปัตยกรรม ชั้น 4 | 396 days | 3 |  |  |  | December 31, 2018 8:00 AM | January 30, 2020 5:00 PM | October 17, 2018 05:00 PM | November 16, 2019 05:00 PM | September 06, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 326 days | 245 days | 245 days
38 | Yes | CMU1.2.2.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 39,41,42 |  |  | March 1, 2019 8:00 AM | March 30, 2019 5:00 PM | March 16, 2019 05:00 PM | April 14, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 551 days | Skilled carpenter
39 | Yes | CMU1.2.2.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 36FS+45 days |  | 38,43 | December 31, 2018 8:00 AM | February 28, 2019 5:00 PM | January 05, 2019 05:00 PM | March 05, 2019 05:00 PM | July 15, 2020 05:00 PM | September 12, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 0 days | General worker
40 | Yes | CMU1.2.2.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 36FS+45 days |  | 41,42 | December 31, 2018 8:00 AM | January 29, 2019 5:00 PM | January 03, 2019 05:00 PM | February 01, 2019 05:00 PM | August 14, 2020 05:00 PM | September 12, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 0 days | General worker
41 | Yes | CMU1.2.2.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 40 |  | 38,43 | January 30, 2019 8:00 AM | February 28, 2019 5:00 PM | February 05, 2019 05:00 PM | March 06, 2019 05:00 PM | August 14, 2020 05:00 PM | September 12, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 0 days | Skilled carpenter
42 | Yes | CMU1.2.2.5 | Auto Scheduled | งานบันได | 30 days | 4 | 40 |  | 38,43 | January 30, 2019 8:00 AM | February 28, 2019 5:00 PM | February 06, 2019 05:00 PM | March 07, 2019 05:00 PM | August 14, 2020 05:00 PM | September 12, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 0 days | General worker
43 | Yes | CMU1.2.2.6 | Auto Scheduled | งานสี | 30 days | 4 | 39,41,42 |  |  | March 1, 2019 8:00 AM | March 30, 2019 5:00 PM | March 11, 2019 05:00 PM | April 09, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 551 days | General worker
44 | Yes | CMU1.2.2.7 | Auto Scheduled | งานสุขภัณฑ์ | 315 days | 4 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 20, 2018 05:00 PM | August 30, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
45 | Yes | CMU1.2.2.7.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 46FS+135 days |  | 47FS+135 days | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | September 18, 2019 05:00 PM | October 02, 2019 05:00 PM | April 24, 2020 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
46 | Yes | CMU1.2.2.7.2 | Auto Scheduled | ZONE T-2 กลาง | 15 days | 5 | 51,55 |  | 45FS+135 days | March 22, 2019 8:00 AM | April 5, 2019 5:00 PM | April 12, 2019 05:00 PM | April 26, 2019 05:00 PM | November 26, 2019 05:00 PM | December 10, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
47 | Yes | CMU1.2.2.7.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 15 days | 5 | 45FS+135 days |  |  | January 16, 2020 8:00 AM | January 30, 2020 5:00 PM | February 22, 2020 05:00 PM | March 07, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 245 days | Sanitary-Plumber
48 | Yes | CMU1.2.3 | Auto Scheduled | งานระบบสุขาภิบาล ชั้น 4 | 408 days | 3 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
49 | Yes | CMU1.2.3.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
50 | Yes | CMU1.2.3.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 51FS+15 days |  | 52FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 22, 2019 05:00 PM | August 25, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
51 | Yes | CMU1.2.3.1.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 36 |  | 50FS+15 days,46,55SS | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 23, 2018 05:00 PM | March 28, 2019 05:00 PM | August 25, 2019 05:00 PM | December 28, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
52 | Yes | CMU1.2.3.1.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 50FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 14, 2019 05:00 PM | January 17, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
53 | Yes | CMU1.2.3.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
54 | Yes | CMU1.2.3.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 55FS+15 days |  | 56FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 29, 2019 05:00 PM | September 01, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
55 | Yes | CMU1.2.3.2.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 51SS |  | 54FS+15 days,46 | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | December 02, 2018 05:00 PM | April 06, 2019 05:00 PM | August 25, 2019 05:00 PM | December 28, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
56 | Yes | CMU1.2.3.2.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 54FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 29, 2019 05:00 PM | February 01, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
57 | Yes | CMU1.2.4 | Auto Scheduled | งานระบบไฟฟ้า ชั้น 4 | 117 days | 3 |  |  |  | November 30, 2018 8:00 AM | March 26, 2019 5:00 PM | October 21, 2018 05:00 PM | February 14, 2019 05:00 PM | June 11, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 555 days | 555 days | 555 days
58 | Yes | CMU1.2.4.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 30 days | 4 | 60FS+7 days |  |  | February 25, 2019 8:00 AM | March 26, 2019 5:00 PM | March 05, 2019 05:00 PM | April 03, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 555 days | 555 days | 555 days | Electrician
59 | Yes | CMU1.2.4.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 30 days | 4 | 60FS+7 days |  |  | February 25, 2019 8:00 AM | March 26, 2019 5:00 PM | March 05, 2019 05:00 PM | April 03, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 555 days | 555 days | 555 days | Electrician
60 | Yes | CMU1.2.4.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 63SS+30 days |  | 58FS+7 days,59FS+7 days | November 30, 2018 8:00 AM | February 17, 2019 5:00 PM | December 04, 2018 05:00 PM | February 21, 2019 05:00 PM | June 11, 2020 05:00 PM | August 29, 2020 05:00 PM | As Soon As Possible |  | No | 555 days | 555 days | 0 days | Electrician
61 | Yes | CMU1.2.4.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 63SS+30 days |  |  | November 30, 2018 8:00 AM | February 17, 2019 5:00 PM | December 04, 2018 05:00 PM | February 21, 2019 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 592 days | 592 days | 592 days | Electrician
62 | Yes | CMU1.2.4.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 63SS+30 days |  |  | November 30, 2018 8:00 AM | February 17, 2019 5:00 PM | December 07, 2018 05:00 PM | February 24, 2019 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 592 days | 592 days | 592 days | Electrician
63 | Yes | CMU1.2.5 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้น 4 | 165 days | 3 | 36SS+14 days |  | 62SS+30 days,60SS+30 days,61SS+30 days,65,214,219FS-15 days,224,230,244FS-7 days,250FS-7 days | October 31, 2018 8:00 AM | April 13, 2019 5:00 PM | October 31, 2018 05:00 PM | April 13, 2019 05:00 PM | June 19, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Skilled carpenter
64 | Yes | CMU1.3 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้น 3 | 441 days | 2 |  |  |  | November 16, 2018 8:00 AM | January 30, 2020 5:00 PM | October 17, 2018 05:00 PM | December 31, 2019 05:00 PM | July 23, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 149 days | 245 days | 149 days
65 | Yes | CMU1.3.1 | Auto Scheduled | งานรื้อถอน ชั้น 3 (รื้อขนไป) | 30 days | 3 | 63 | 121 | 68FS+45 days,69FS+45 days,92SS | April 14, 2019 8:00 AM | May 13, 2019 5:00 PM | April 14, 2019 05:00 PM | May 13, 2019 05:00 PM | July 19, 2018 05:00 PM | August 17, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | General worker
66 | Yes | CMU1.3.2 | Auto Scheduled | งานสถาปัตยกรรม ชั้น 3 | 315 days | 3 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 23, 2018 05:00 PM | September 02, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
67 | Yes | CMU1.3.2.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 68,70,71 |  |  | August 27, 2019 8:00 AM | September 25, 2019 5:00 PM | August 31, 2019 05:00 PM | September 29, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 372 days | Skilled carpenter
68 | Yes | CMU1.3.2.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 65FS+45 days |  | 67,72 | June 28, 2019 8:00 AM | August 26, 2019 5:00 PM | June 28, 2019 05:00 PM | August 26, 2019 05:00 PM | October 02, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 0 days | General worker
69 | Yes | CMU1.3.2.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 65FS+45 days |  | 70,71 | June 28, 2019 8:00 AM | July 27, 2019 5:00 PM | June 28, 2019 05:00 PM | July 27, 2019 05:00 PM | April 15, 2019 05:00 PM | May 14, 2019 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 0 days | General worker
70 | Yes | CMU1.3.2.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 69 |  | 67,72 | July 28, 2019 8:00 AM | August 26, 2019 5:00 PM | July 28, 2019 05:00 PM | August 26, 2019 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 0 days | Skilled carpenter
71 | Yes | CMU1.3.2.5 | Auto Scheduled | งานบันได | 30 days | 4 | 69 |  | 67,72 | July 28, 2019 8:00 AM | August 26, 2019 5:00 PM | July 28, 2019 05:00 PM | August 26, 2019 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 0 days | General worker
72 | Yes | CMU1.3.2.6 | Auto Scheduled | งานสี | 30 days | 4 | 68,70,71 |  |  | August 27, 2019 8:00 AM | September 25, 2019 5:00 PM | August 30, 2019 05:00 PM | September 28, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 372 days | General worker
73 | Yes | CMU1.3.2.7 | Auto Scheduled | งานสุขภัณฑ์ | 315 days | 4 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 25, 2018 05:00 PM | September 04, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
74 | Yes | CMU1.3.2.7.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 75FS+135 days |  | 76FS+135 days | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | August 25, 2019 05:00 PM | September 08, 2019 05:00 PM | April 24, 2020 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
75 | Yes | CMU1.3.2.7.2 | Auto Scheduled | ZONE T-2 กลาง | 15 days | 5 | 80,84 |  | 74FS+135 days | March 22, 2019 8:00 AM | April 5, 2019 5:00 PM | March 24, 2019 05:00 PM | April 07, 2019 05:00 PM | November 26, 2019 05:00 PM | December 10, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
76 | Yes | CMU1.3.2.7.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 15 days | 5 | 74FS+135 days |  |  | January 16, 2020 8:00 AM | January 30, 2020 5:00 PM | January 28, 2020 05:00 PM | February 11, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 245 days | Sanitary-Plumber
77 | Yes | CMU1.3.3 | Auto Scheduled | งานระบบสุขาภิบาล ชั้น 3 | 408 days | 3 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
78 | Yes | CMU1.3.3.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
79 | Yes | CMU1.3.3.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 80FS+15 days |  | 81FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 21, 2019 05:00 PM | August 24, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
80 | Yes | CMU1.3.3.1.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 36 |  | 79FS+15 days,84SS,75 | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 16, 2018 05:00 PM | March 21, 2019 05:00 PM | January 09, 2019 05:00 PM | May 14, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
81 | Yes | CMU1.3.3.1.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 79FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 16, 2019 05:00 PM | January 19, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
82 | Yes | CMU1.3.3.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
83 | Yes | CMU1.3.3.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 84FS+15 days |  | 85FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 12, 2019 05:00 PM | August 15, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
84 | Yes | CMU1.3.3.2.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 80SS |  | 83FS+15 days,75 | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 16, 2018 05:00 PM | March 21, 2019 05:00 PM | January 09, 2019 05:00 PM | May 14, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
85 | Yes | CMU1.3.3.2.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 83FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 11, 2019 05:00 PM | January 14, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
86 | Yes | CMU1.3.4 | Auto Scheduled | งานระบบไฟฟ้า ชั้น 3 | 147 days | 3 |  |  |  | May 14, 2019 8:00 AM | October 7, 2019 5:00 PM | October 21, 2018 05:00 PM | March 16, 2019 05:00 PM | May 12, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 360 days | 360 days | 360 days
87 | Yes | CMU1.3.4.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 60 days | 4 | 89FS+7 days |  |  | August 9, 2019 8:00 AM | October 7, 2019 5:00 PM | August 19, 2019 05:00 PM | October 17, 2019 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 360 days | 360 days | 360 days | Electrician
88 | Yes | CMU1.3.4.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 60 days | 4 | 89FS+7 days |  |  | August 9, 2019 8:00 AM | October 7, 2019 5:00 PM | August 28, 2019 05:00 PM | October 26, 2019 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 360 days | 360 days | 360 days | Electrician
89 | Yes | CMU1.3.4.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 92SS+30 days |  | 88FS+7 days,87FS+7 days | May 14, 2019 8:00 AM | August 1, 2019 5:00 PM | May 21, 2019 05:00 PM | August 08, 2019 05:00 PM | May 12, 2020 05:00 PM | July 30, 2020 05:00 PM | As Soon As Possible |  | No | 360 days | 360 days | 0 days | Electrician
90 | Yes | CMU1.3.4.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 92SS+30 days |  |  | May 14, 2019 8:00 AM | August 1, 2019 5:00 PM | May 24, 2019 05:00 PM | August 11, 2019 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 427 days | 427 days | 427 days | Electrician
91 | Yes | CMU1.3.4.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 92SS+30 days |  |  | May 14, 2019 8:00 AM | August 1, 2019 5:00 PM | May 25, 2019 05:00 PM | August 12, 2019 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 427 days | 427 days | 427 days | Electrician
92 | Yes | CMU1.3.5 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้น 3 | 180 days | 3 | 65SS |  | 91SS+30 days,90SS+30 days,89SS+30 days,94,213FS-15 days,218FS-30 days,223FS-15 days,229FS-15 days,243FS-7 days,249FS-7 days | April 14, 2019 8:00 AM | October 10, 2019 5:00 PM | April 19, 2019 05:00 PM | October 15, 2019 05:00 PM | October 12, 2019 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Skilled carpenter
93 | Yes | CMU1.4 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้น 2 | 509 days | 2 |  |  |  | November 16, 2018 8:00 AM | April 7, 2020 5:00 PM | October 17, 2018 05:00 PM | March 08, 2020 05:00 PM | May 16, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 177 days | 177 days
94 | Yes | CMU1.4.1 | Auto Scheduled | งานรื้อถอน ชั้น 2 (รื้อขนไป) | 30 days | 3 | 92 | 152 | 97FS+45 days,98FS+45 days,121SS | October 11, 2019 8:00 AM | November 9, 2019 5:00 PM | October 16, 2019 05:00 PM | November 14, 2019 05:00 PM | June 04, 2018 05:00 PM | July 03, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | General worker
95 | Yes | CMU1.4.2 | Auto Scheduled | งานสถาปัตยกรรม ชั้น 2 | 368 days | 3 |  |  |  | March 22, 2019 8:00 AM | March 23, 2020 5:00 PM | October 17, 2018 05:00 PM | October 19, 2019 05:00 PM | October 04, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 192 days | 192 days
96 | Yes | CMU1.4.2.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 97,99,100 |  |  | February 23, 2020 8:00 AM | March 23, 2020 5:00 PM | March 09, 2020 05:00 PM | April 07, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 192 days | Skilled carpenter
97 | Yes | CMU1.4.2.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 94FS+45 days |  | 96,101 | December 25, 2019 8:00 AM | February 22, 2020 5:00 PM | December 30, 2019 05:00 PM | February 27, 2020 05:00 PM | February 09, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 0 days | General worker
98 | Yes | CMU1.4.2.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 94FS+45 days |  | 99,100 | December 25, 2019 8:00 AM | January 23, 2020 5:00 PM | January 03, 2020 05:00 PM | February 01, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 0 days | General worker
99 | Yes | CMU1.4.2.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 98 |  | 96,101 | January 24, 2020 8:00 AM | February 22, 2020 5:00 PM | February 05, 2020 05:00 PM | March 05, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 0 days | Skilled carpenter
100 | Yes | CMU1.4.2.5 | Auto Scheduled | งานบันได | 30 days | 4 | 98 |  | 96,101 | January 24, 2020 8:00 AM | February 22, 2020 5:00 PM | February 05, 2020 05:00 PM | March 05, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 0 days | General worker
101 | Yes | CMU1.4.2.6 | Auto Scheduled | งานสี | 30 days | 4 | 97,99,100 |  |  | February 23, 2020 8:00 AM | March 23, 2020 5:00 PM | March 12, 2020 05:00 PM | April 10, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 192 days | General worker
102 | Yes | CMU1.4.2.7 | Auto Scheduled | งานสุขภัณฑ์ | 315 days | 4 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 22, 2018 05:00 PM | September 01, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
103 | Yes | CMU1.4.2.7.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 104FS+135 days |  | 105FS+135 days | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | September 19, 2019 05:00 PM | October 03, 2019 05:00 PM | April 24, 2020 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
104 | Yes | CMU1.4.2.7.2 | Auto Scheduled | ZONE T-2 กลาง | 15 days | 5 | 113,109 |  | 103FS+135 days | March 22, 2019 8:00 AM | April 5, 2019 5:00 PM | April 18, 2019 05:00 PM | May 02, 2019 05:00 PM | November 26, 2019 05:00 PM | December 10, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
105 | Yes | CMU1.4.2.7.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 15 days | 5 | 103FS+135 days |  |  | January 16, 2020 8:00 AM | January 30, 2020 5:00 PM | February 24, 2020 05:00 PM | March 09, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 245 days | Sanitary-Plumber
106 | Yes | CMU1.4.3 | Auto Scheduled | งานระบบสุขาภิบาล ชั้น 2 | 408 days | 3 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
107 | Yes | CMU1.4.3.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
108 | Yes | CMU1.4.3.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 109FS+15 days |  | 110FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 25, 2019 05:00 PM | August 28, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
109 | Yes | CMU1.4.3.1.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 36 |  | 113SS,104,108FS+15 days | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 28, 2018 05:00 PM | April 02, 2019 05:00 PM | August 25, 2019 05:00 PM | December 28, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
110 | Yes | CMU1.4.3.1.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 108FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 16, 2019 05:00 PM | January 19, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
111 | Yes | CMU1.4.3.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
112 | Yes | CMU1.4.3.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 113FS+15 days |  | 114FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | May 05, 2019 05:00 PM | September 07, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
113 | Yes | CMU1.4.3.2.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 109SS |  | 104,112FS+15 days | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | December 04, 2018 05:00 PM | April 08, 2019 05:00 PM | August 25, 2019 05:00 PM | December 28, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
114 | Yes | CMU1.4.3.2.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 112FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 27, 2019 05:00 PM | January 30, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
115 | Yes | CMU1.4.4 | Auto Scheduled | งานระบบไฟฟ้า ชั้น 2 | 147 days | 3 |  |  |  | November 10, 2019 8:00 AM | April 4, 2020 5:00 PM | October 20, 2018 05:00 PM | March 15, 2019 05:00 PM | May 12, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 180 days | 180 days | 180 days
116 | Yes | CMU1.4.4.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 60 days | 4 | 118FS+7 days |  |  | February 5, 2020 8:00 AM | April 4, 2020 5:00 PM | February 14, 2020 05:00 PM | April 13, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 180 days | 180 days | 180 days | Electrician
117 | Yes | CMU1.4.4.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 60 days | 4 | 118FS+7 days |  |  | February 5, 2020 8:00 AM | April 4, 2020 5:00 PM | February 16, 2020 05:00 PM | April 15, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 180 days | 180 days | 180 days | Electrician
118 | Yes | CMU1.4.4.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 121SS+30 days |  | 117FS+7 days,116FS+7 days | November 10, 2019 8:00 AM | January 28, 2020 5:00 PM | November 17, 2019 05:00 PM | February 04, 2020 05:00 PM | May 12, 2020 05:00 PM | July 30, 2020 05:00 PM | As Soon As Possible |  | No | 180 days | 180 days | 0 days | Electrician
119 | Yes | CMU1.4.4.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 121SS+30 days |  |  | November 10, 2019 8:00 AM | January 28, 2020 5:00 PM | November 19, 2019 05:00 PM | February 06, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 247 days | 247 days | 247 days | Electrician
120 | Yes | CMU1.4.4.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 121SS+30 days |  |  | November 10, 2019 8:00 AM | January 28, 2020 5:00 PM | November 22, 2019 05:00 PM | February 09, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 247 days | 247 days | 247 days | Electrician
121 | Yes | CMU1.4.5 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้น 2 | 180 days | 3 | 94SS |  | 120SS+30 days,119SS+30 days,118SS+30 days,123,212FS-15 days,217FS-30 days,222FS-15 days,228FS-15 days,242FS-7 days,248FS-7 days | October 11, 2019 8:00 AM | April 7, 2020 5:00 PM | October 16, 2019 05:00 PM | April 12, 2020 05:00 PM | June 04, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Skilled carpenter
122 | Yes | CMU1.5 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้น 1 | 686 days | 2 |  |  |  | November 16, 2018 8:00 AM | October 1, 2020 5:00 PM | October 17, 2018 05:00 PM | September 01, 2020 05:00 PM | November 20, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 0 days | 0 days
123 | Yes | CMU1.5.1 | Auto Scheduled | งานรื้อถอน ชั้น 1 (รื้อขนไป) | 30 days | 3 | 121 | 63 | 124,127FS+45 days,128FS+45 days,131FS+45 days,152SS,193SS,194SS,195SS,196SS,197SS,202SS,204SS,205SS,206SS,207SS | April 8, 2020 8:00 AM | May 7, 2020 5:00 PM | April 13, 2020 05:00 PM | May 12, 2020 05:00 PM | July 19, 2018 05:00 PM | August 17, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | General worker
124 | Yes | CMU1.5.2 | Auto Scheduled | งานโครงสร้างวิศวกรรม ชั้น 1 | 75 days | 3 | 123 |  |  | May 8, 2020 8:00 AM | July 21, 2020 5:00 PM | May 14, 2020 05:00 PM | July 27, 2020 05:00 PM | July 23, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 72 days | 72 days | 72 days | General worker
125 | Yes | CMU1.5.3 | Auto Scheduled | งานสถาปัตยกรรม ชั้น 1 | 548 days | 3 |  |  |  | March 22, 2019 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | April 16, 2020 05:00 PM | April 07, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 12 days | 12 days
126 | Yes | CMU1.5.3.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 127,129,130 |  |  | August 21, 2020 8:00 AM | September 19, 2020 5:00 PM | August 26, 2020 05:00 PM | September 24, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | Skilled carpenter
127 | Yes | CMU1.5.3.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 123FS+45 days |  | 126,132 | June 22, 2020 8:00 AM | August 20, 2020 5:00 PM | June 27, 2020 05:00 PM | August 25, 2020 05:00 PM | October 02, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
128 | Yes | CMU1.5.3.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 123FS+45 days |  | 129,130 | June 22, 2020 8:00 AM | July 21, 2020 5:00 PM | June 27, 2020 05:00 PM | July 26, 2020 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
129 | Yes | CMU1.5.3.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 128 |  | 126,132 | July 22, 2020 8:00 AM | August 20, 2020 5:00 PM | July 27, 2020 05:00 PM | August 25, 2020 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | Skilled carpenter
130 | Yes | CMU1.5.3.5 | Auto Scheduled | งานบันได | 30 days | 4 | 128 |  | 126,132 | July 22, 2020 8:00 AM | August 20, 2020 5:00 PM | July 27, 2020 05:00 PM | August 25, 2020 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
131 | Yes | CMU1.5.3.6 | Auto Scheduled | งานตกแต่งอื่น ๆ | 60 days | 4 | 123FS+45 days |  |  | June 22, 2020 8:00 AM | August 20, 2020 5:00 PM | June 27, 2020 05:00 PM | August 25, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 42 days | 42 days | 42 days | General worker
132 | Yes | CMU1.5.3.7 | Auto Scheduled | งานสี | 30 days | 4 | 127,129,130 |  |  | August 21, 2020 8:00 AM | September 19, 2020 5:00 PM | August 26, 2020 05:00 PM | September 24, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
133 | Yes | CMU1.5.3.8 | Auto Scheduled | งานสุขภัณฑ์ | 315 days | 4 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 27, 2018 05:00 PM | September 06, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
134 | Yes | CMU1.5.3.8.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 135FS+135 days |  | 136FS+135 days | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | August 24, 2019 05:00 PM | September 07, 2019 05:00 PM | April 24, 2020 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
135 | Yes | CMU1.5.3.8.2 | Auto Scheduled | ZONE T-2 กลาง | 15 days | 5 | 140,144 |  | 134FS+135 days,164FS+135 days | March 22, 2019 8:00 AM | April 5, 2019 5:00 PM | March 24, 2019 05:00 PM | April 07, 2019 05:00 PM | November 26, 2019 05:00 PM | December 10, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
136 | Yes | CMU1.5.3.8.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 15 days | 5 | 134FS+135 days |  |  | January 16, 2020 8:00 AM | January 30, 2020 5:00 PM | January 26, 2020 05:00 PM | February 09, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 245 days | Sanitary-Plumber
137 | Yes | CMU1.5.4 | Auto Scheduled | งานระบบสุขาภิบาล ชั้น 1 | 408 days | 3 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 278 days | 44 days
138 | Yes | CMU1.5.4.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 278 days | 44 days
139 | Yes | CMU1.5.4.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 140FS+15 days |  | 141FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 13, 2019 05:00 PM | August 16, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
140 | Yes | CMU1.5.4.1.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 36 |  | 139FS+15 days,144SS,135,167FS+15 days | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 16, 2018 05:00 PM | March 21, 2019 05:00 PM | January 03, 2019 05:00 PM | May 08, 2019 05:00 PM | As Soon As Possible |  | No | 44 days | 44 days | 0 days | Sanitary-Plumber
141 | Yes | CMU1.5.4.1.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 139FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 07, 2019 05:00 PM | January 10, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
142 | Yes | CMU1.5.4.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 278 days | 44 days
143 | Yes | CMU1.5.4.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 144FS+15 days |  | 145FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 13, 2019 05:00 PM | August 16, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
144 | Yes | CMU1.5.4.2.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 140SS |  | 143FS+15 days,135,169FS+15 days | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 16, 2018 05:00 PM | March 21, 2019 05:00 PM | January 03, 2019 05:00 PM | May 08, 2019 05:00 PM | As Soon As Possible |  | No | 44 days | 44 days | 0 days | Sanitary-Plumber
145 | Yes | CMU1.5.4.2.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 143FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 05, 2019 05:00 PM | January 08, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
146 | Yes | CMU1.5.5 | Auto Scheduled | งานระบบไฟฟ้า ชั้น 1 | 147 days | 3 |  |  |  | May 8, 2020 8:00 AM | October 1, 2020 5:00 PM | October 21, 2018 05:00 PM | March 16, 2019 05:00 PM | May 12, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 0 days | 0 days | 0 days
147 | Yes | CMU1.5.5.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 60 days | 4 | 149FS+7 days |  |  | August 3, 2020 8:00 AM | October 1, 2020 5:00 PM | August 08, 2020 05:00 PM | October 06, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Electrician
148 | Yes | CMU1.5.5.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 60 days | 4 | 149FS+7 days |  |  | August 3, 2020 8:00 AM | October 1, 2020 5:00 PM | August 08, 2020 05:00 PM | October 06, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Electrician
149 | Yes | CMU1.5.5.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 152SS+30 days |  | 148FS+7 days,147FS+7 days | May 8, 2020 8:00 AM | July 26, 2020 5:00 PM | May 13, 2020 05:00 PM | July 31, 2020 05:00 PM | May 12, 2020 05:00 PM | July 30, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Electrician
150 | Yes | CMU1.5.5.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 152SS+30 days |  |  | May 8, 2020 8:00 AM | July 26, 2020 5:00 PM | May 13, 2020 05:00 PM | July 31, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 67 days | 67 days | 67 days | Electrician
151 | Yes | CMU1.5.5.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 152SS+30 days |  |  | May 8, 2020 8:00 AM | July 26, 2020 5:00 PM | May 13, 2020 05:00 PM | July 31, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 67 days | 67 days | 67 days | Electrician
152 | Yes | CMU1.5.6 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้น 1 | 165 days | 3 | 123SS |  | 151SS+30 days,150SS+30 days,149SS+30 days,154SS,211FS-30 days,210FS-30 days,216FS-45 days,221FS-30 days,227FS-30 days,226FS-30 days,232FS-45 days,241FS-7 days,247FS-7 days | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 13, 2020 05:00 PM | September 24, 2020 05:00 PM | November 26, 2019 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Skilled carpenter
153 | Yes | CMU1.6 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้นใต้ดิน | 533 days | 2 |  |  |  | April 6, 2019 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | April 01, 2020 05:00 PM | April 22, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 12 days | 12 days
154 | Yes | CMU1.6.1 | Auto Scheduled | งานรื้อถอน ชั้นใต้ดิน (รื้อขนไป) | 30 days | 3 | 152SS |  | 155,158FS+45 days,159FS+45 days,177SS,176SS,175SS,174SS | April 8, 2020 8:00 AM | May 7, 2020 5:00 PM | April 13, 2020 05:00 PM | May 12, 2020 05:00 PM | November 26, 2019 05:00 PM | December 25, 2019 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
155 | Yes | CMU1.6.2 | Auto Scheduled | งานโครงสร้างวิศวกรรม ชั้นใต้ดิน | 75 days | 3 | 154 |  |  | May 8, 2020 8:00 AM | July 21, 2020 5:00 PM | May 15, 2020 05:00 PM | July 28, 2020 05:00 PM | July 23, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 72 days | 72 days | 72 days | General worker
156 | Yes | CMU1.6.3 | Auto Scheduled | งานสถาปัตยกรรม ชั้นใต้ดิน | 398 days | 3 |  |  |  | August 19, 2019 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | November 18, 2019 05:00 PM | September 04, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 320 days | 12 days | 12 days
157 | Yes | CMU1.6.3.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 158,160,161 |  |  | August 21, 2020 8:00 AM | September 19, 2020 5:00 PM | September 15, 2020 05:00 PM | October 14, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | Skilled carpenter
158 | Yes | CMU1.6.3.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 154FS+45 days |  | 157,162 | June 22, 2020 8:00 AM | August 20, 2020 5:00 PM | June 27, 2020 05:00 PM | August 25, 2020 05:00 PM | February 09, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
159 | Yes | CMU1.6.3.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 154FS+45 days |  | 160,161 | June 22, 2020 8:00 AM | July 21, 2020 5:00 PM | July 17, 2020 05:00 PM | August 15, 2020 05:00 PM | August 22, 2020 05:00 PM | September 20, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
160 | Yes | CMU1.6.3.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 159 |  | 157,162 | July 22, 2020 8:00 AM | August 20, 2020 5:00 PM | August 16, 2020 05:00 PM | September 14, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | Skilled carpenter
161 | Yes | CMU1.6.3.5 | Auto Scheduled | งานบันได | 30 days | 4 | 159 |  | 157,162 | July 22, 2020 8:00 AM | August 20, 2020 5:00 PM | August 16, 2020 05:00 PM | September 14, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
162 | Yes | CMU1.6.3.6 | Auto Scheduled | งานสี | 30 days | 4 | 158,160,161 |  |  | August 21, 2020 8:00 AM | September 19, 2020 5:00 PM | September 15, 2020 05:00 PM | October 14, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
163 | Yes | CMU1.6.3.7 | Auto Scheduled | งานสุขภัณฑ์ | 15 days | 4 |  |  |  | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | October 21, 2018 05:00 PM | November 04, 2018 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 395 days | 395 days | 395 days
164 | Yes | CMU1.6.3.7.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 135FS+135 days |  |  | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | August 27, 2019 05:00 PM | September 10, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 395 days | 395 days | 395 days | Sanitary-Plumber
165 | Yes | CMU1.6.4 | Auto Scheduled | งานระบบสุขาภิบาล ชั้นใต้ดิน | 501 days | 3 |  |  |  | April 6, 2019 8:00 AM | August 18, 2020 5:00 PM | October 17, 2018 05:00 PM | February 29, 2020 05:00 PM | May 24, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 44 days | 44 days
166 | Yes | CMU1.6.4.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 126 days | 4 |  |  |  | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | October 25, 2018 05:00 PM | February 27, 2019 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 419 days | 419 days | 419 days
167 | Yes | CMU1.6.4.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 140FS+15 days |  |  | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 14, 2019 05:00 PM | August 17, 2019 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 419 days | 419 days | 419 days | Sanitary-Plumber
168 | Yes | CMU1.6.4.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 126 days | 4 |  |  |  | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | October 22, 2018 05:00 PM | February 24, 2019 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 44 days | 44 days
169 | Yes | CMU1.6.4.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 144FS+15 days |  | 170FS+300 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 06, 2019 05:00 PM | August 09, 2019 05:00 PM | May 24, 2019 05:00 PM | September 26, 2019 05:00 PM | As Soon As Possible |  | No | 44 days | 44 days | 0 days | Sanitary-Plumber
170 | Yes | CMU1.6.4.3 | Auto Scheduled | งานระบบระบายน้ำฝน | 75 days | 4 | 169FS+300 days |  |  | June 5, 2020 8:00 AM | August 18, 2020 5:00 PM | June 05, 2020 05:00 PM | August 18, 2020 05:00 PM | July 23, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 44 days | 44 days | 44 days | Sanitary-Plumber
171 | Yes | CMU1.6.5 | Auto Scheduled | งานระบบไฟฟ้า ชั้นใต้ดิน | 147 days | 3 |  |  |  | April 8, 2020 8:00 AM | September 1, 2020 5:00 PM | October 23, 2018 05:00 PM | March 18, 2019 05:00 PM | May 12, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 30 days | 30 days | 30 days
172 | Yes | CMU1.6.5.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 60 days | 4 | 174FS+7 days |  |  | July 4, 2020 8:00 AM | September 1, 2020 5:00 PM | July 09, 2020 05:00 PM | September 06, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 30 days | 30 days | 30 days | Electrician
173 | Yes | CMU1.6.5.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 60 days | 4 | 174FS+7 days |  |  | July 4, 2020 8:00 AM | September 1, 2020 5:00 PM | July 09, 2020 05:00 PM | September 06, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 30 days | 30 days | 30 days | Electrician
174 | Yes | CMU1.6.5.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 154SS |  | 173FS+7 days,172FS+7 days | April 8, 2020 8:00 AM | June 26, 2020 5:00 PM | April 13, 2020 05:00 PM | July 01, 2020 05:00 PM | May 12, 2020 05:00 PM | July 30, 2020 05:00 PM | As Soon As Possible |  | No | 30 days | 30 days | 0 days | Electrician
175 | Yes | CMU1.6.5.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 154SS |  |  | April 8, 2020 8:00 AM | June 26, 2020 5:00 PM | April 16, 2020 05:00 PM | July 04, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 97 days | 97 days | 97 days | Electrician
176 | Yes | CMU1.6.5.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 154SS |  |  | April 8, 2020 8:00 AM | June 26, 2020 5:00 PM | April 18, 2020 05:00 PM | July 06, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 97 days | 97 days | 97 days | Electrician
177 | Yes | CMU1.6.6 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้นใต้ดิน | 165 days | 3 | 154SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 13, 2020 05:00 PM | September 24, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | Skilled carpenter
178 | Yes | CMU1.7 | Auto Scheduled | หมวดงานระบบคอมพิวเตอร์และแจ้งเหตุเพลิงไหม้ | 670 days | 2 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
179 | Yes | CMU1.7.1 | Auto Scheduled | งานระบบคอมพิวเตอร์ | 670 days | 3 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
180 | Yes | CMU1.7.1.1 | Auto Scheduled | ชั้นที่ 4 | 160 days | 4 | 36FS+14 days |  | 181 | November 30, 2018 8:00 AM | May 8, 2019 5:00 PM | November 30, 2018 05:00 PM | May 08, 2019 05:00 PM | April 24, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
181 | Yes | CMU1.7.1.2 | Auto Scheduled | ชั้นที่ 3 | 175 days | 4 | 180 | 182 | 182 | May 9, 2019 8:00 AM | October 30, 2019 5:00 PM | May 09, 2019 05:00 PM | October 30, 2019 05:00 PM | April 09, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
182 | Yes | CMU1.7.1.3 | Auto Scheduled | ชั้นที่ 2 | 175 days | 4 | 181 | 183 | 183,184 | October 31, 2019 8:00 AM | April 22, 2020 5:00 PM | October 31, 2019 05:00 PM | April 22, 2020 05:00 PM | April 09, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
183 | Yes | CMU1.7.1.4 | Auto Scheduled | ชั้นที่ 1 | 160 days | 4 | 182 | 180 |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 23, 2020 05:00 PM | September 29, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
184 | Yes | CMU1.7.1.5 | Auto Scheduled | ชั้นใต้ดิน | 160 days | 4 | 182 | 183SS |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 23, 2020 05:00 PM | September 29, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
185 | Yes | CMU1.7.2 | Auto Scheduled | ระบบแจ้งเหตุเพลิงไหม้ | 670 days | 3 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
186 | Yes | CMU1.7.2.1 | Auto Scheduled | ชั้นที่ 4 | 160 days | 4 | 36FS+14 days |  | 187 | November 30, 2018 8:00 AM | May 8, 2019 5:00 PM | November 30, 2018 05:00 PM | May 08, 2019 05:00 PM | April 24, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
187 | Yes | CMU1.7.2.2 | Auto Scheduled | ชั้นที่ 3 | 175 days | 4 | 186 | 188 | 188 | May 9, 2019 8:00 AM | October 30, 2019 5:00 PM | May 09, 2019 05:00 PM | October 30, 2019 05:00 PM | April 09, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
188 | Yes | CMU1.7.2.3 | Auto Scheduled | ชั้นที่ 2 | 175 days | 4 | 187 | 189 | 189,190 | October 31, 2019 8:00 AM | April 22, 2020 5:00 PM | October 31, 2019 05:00 PM | April 22, 2020 05:00 PM | April 09, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
189 | Yes | CMU1.7.2.4 | Auto Scheduled | ชั้นที่ 1 | 160 days | 4 | 188 | 186 |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 23, 2020 05:00 PM | September 29, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
190 | Yes | CMU1.7.2.5 | Auto Scheduled | ชั้นใต้ดิน | 160 days | 4 | 188 | 189SS |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 23, 2020 05:00 PM | September 29, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
191 | Yes | CMU1.8 | Auto Scheduled | หมวดงานสีภายนอก งานซ่อมแซมและตกแต่งภายนอกอาคาร | 660 days | 2 |  |  |  | November 30, 2018 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | August 06, 2020 05:00 PM | December 16, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 507 days | 12 days | 12 days
192 | Yes | CMU1.8.1 | Auto Scheduled | งานสีภายนอกและงานซ่อมแซมพื้นผิวภายนอกอาคาร | 660 days | 3 |  |  |  | November 30, 2018 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | August 06, 2020 05:00 PM | December 16, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 507 days | 12 days | 12 days
193 | Yes | CMU1.8.1.1 | Auto Scheduled | งานขัดลอกสีทาผนังเดิม | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 13, 2020 05:00 PM | September 24, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
194 | Yes | CMU1.8.1.2 | Auto Scheduled | น้ำยาทาปูนเก่า (สีรองพื้น) | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 13, 2020 05:00 PM | September 24, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
195 | Yes | CMU1.8.1.3 | Auto Scheduled | งานทาสีภายนอก (ทา 2 เที่ยว) ไม่รวมชั้นใต้ดิน | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 13, 2020 05:00 PM | September 24, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
196 | Yes | CMU1.8.1.4 | Auto Scheduled | งานทำความสะอาดและซ่อมแซมผนังกรุอิฐโชว์แนว (อ้างอิงราคางานขัดลอกสี) | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 13, 2020 05:00 PM | September 24, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
197 | Yes | CMU1.8.1.5 | Auto Scheduled | น้ำยาเคลือบผิวผนังอิฐโชว์แนว (อ้างอิงค่าทาน้ำยากันเชื้อรา) | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 13, 2020 05:00 PM | September 24, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
198 | Yes | CMU1.8.1.6 | Auto Scheduled | งานรื้อถอนแผ่นวัสดุกันซึมหลังคาดาดฟ้า (รื้อขนไป) | 90 days | 4 | 36FS+14 days |  |  | November 30, 2018 8:00 AM | February 27, 2019 5:00 PM | December 04, 2018 05:00 PM | March 03, 2019 05:00 PM | July 08, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 582 days | 582 days | 582 days | General worker
199 | Yes | CMU1.8.1.7 | Auto Scheduled | งานแผ่นวัสดุกันซึมแบบเป่าไฟผิวทราย | 90 days | 4 | 36FS+14 days |  |  | November 30, 2018 8:00 AM | February 27, 2019 5:00 PM | December 04, 2018 05:00 PM | March 03, 2019 05:00 PM | July 08, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 582 days | 582 days | 582 days | General worker
200 | Yes | CMU1.8.1.8 | Auto Scheduled | งานกันซึมชนิด Polyurethane สูตรน้ำมัน ชนิดยืดหยุ่นสูงเป็นพิเศษ | 90 days | 4 | 36FS+14 days |  |  | November 30, 2018 8:00 AM | February 27, 2019 5:00 PM | December 03, 2018 05:00 PM | March 02, 2019 05:00 PM | July 08, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 582 days | 582 days | 582 days | General worker
201 | Yes | CMU1.8.2 | Auto Scheduled | งานตกแต่งภายนอกอาคาร | 165 days | 3 |  |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | October 20, 2018 05:00 PM | April 02, 2019 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 12 days | 12 days | 12 days
202 | Yes | CMU1.8.2.1 | Auto Scheduled | ตะแกรงเหล็กฉีกกันนก XS-32 | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 13, 2020 05:00 PM | September 24, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
203 | Yes | CMU1.9 | Auto Scheduled | หมวดงานบริเวณ | 165 days | 2 |  |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | October 23, 2018 05:00 PM | April 05, 2019 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 12 days | 12 days | 12 days
204 | Yes | CMU1.9.1 | Auto Scheduled | งานรื้อถอน งานบริเวณ | 165 days | 3 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 13, 2020 05:00 PM | September 24, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
205 | Yes | CMU1.9.2 | Auto Scheduled | งานโครงสร้างวิศวกรรม งานบริเวณ | 165 days | 3 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 13, 2020 05:00 PM | September 24, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
206 | Yes | CMU1.9.3 | Auto Scheduled | งานสถาปัตยกรรม งานบริเวณ | 165 days | 3 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 13, 2020 05:00 PM | September 24, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
207 | Yes | CMU1.9.4 | Auto Scheduled | งานระบบไฟฟ้า งานบริเวณ | 165 days | 3 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 13, 2020 05:00 PM | September 24, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | Electrician
208 | Yes | CMU1.10 | Auto Scheduled | หมวดงานครุภัณฑ์จัดซื้อ | 670 days | 2 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
209 | Yes | CMU1.10.1 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัว | 510 days | 3 |  |  |  | April 14, 2019 8:00 AM | September 4, 2020 5:00 PM | October 17, 2018 05:00 PM | March 09, 2020 05:00 PM | May 15, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 522 days | 27 days | 27 days
210 | Yes | CMU1.10.1.1 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้นใต้ดิน | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | August 30, 2020 05:00 PM | September 13, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
211 | Yes | CMU1.10.1.2 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้น 1 | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | September 10, 2020 05:00 PM | September 24, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
212 | Yes | CMU1.10.1.3 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้น 2 | 15 days | 4 | 121FS-15 days |  |  | March 24, 2020 8:00 AM | April 7, 2020 5:00 PM | March 31, 2020 05:00 PM | April 14, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Skilled carpenter
213 | Yes | CMU1.10.1.4 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้น 3 | 15 days | 4 | 92FS-15 days |  |  | September 26, 2019 8:00 AM | October 10, 2019 5:00 PM | October 06, 2019 05:00 PM | October 20, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Skilled carpenter
214 | Yes | CMU1.10.1.5 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้น 4 | 15 days | 4 | 63 |  |  | April 14, 2019 8:00 AM | April 28, 2019 5:00 PM | April 26, 2019 05:00 PM | May 10, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 522 days | 522 days | 522 days | Skilled carpenter
215 | Yes | CMU1.10.2 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ | 525 days | 3 |  |  |  | March 30, 2019 8:00 AM | September 4, 2020 5:00 PM | October 17, 2018 05:00 PM | March 24, 2020 05:00 PM | April 30, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 522 days | 27 days | 27 days
216 | Yes | CMU1.10.2.1 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ ชั้น 1 | 30 days | 4 | 152FS-45 days |  |  | August 6, 2020 8:00 AM | September 4, 2020 5:00 PM | August 17, 2020 05:00 PM | September 15, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
217 | Yes | CMU1.10.2.2 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ ชั้น 2 | 30 days | 4 | 121FS-30 days |  |  | March 9, 2020 8:00 AM | April 7, 2020 5:00 PM | March 17, 2020 05:00 PM | April 15, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Skilled carpenter
218 | Yes | CMU1.10.2.3 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ ชั้น 3 | 30 days | 4 | 92FS-30 days |  |  | September 11, 2019 8:00 AM | October 10, 2019 5:00 PM | September 20, 2019 05:00 PM | October 19, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Skilled carpenter
219 | Yes | CMU1.10.2.4 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ ชั้น 4 | 30 days | 4 | 63FS-15 days |  |  | March 30, 2019 8:00 AM | April 28, 2019 5:00 PM | April 02, 2019 05:00 PM | May 01, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 522 days | 522 days | 522 days | Skilled carpenter
220 | Yes | CMU1.10.3 | Auto Scheduled | งานผ้าม่าน | 510 days | 3 |  |  |  | April 14, 2019 8:00 AM | September 4, 2020 5:00 PM | October 17, 2018 05:00 PM | March 09, 2020 05:00 PM | May 15, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 522 days | 27 days | 27 days
221 | Yes | CMU1.10.3.1 | Auto Scheduled | งานผ้าม่าน ชั้น 1 | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | September 01, 2020 05:00 PM | September 15, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
222 | Yes | CMU1.10.3.2 | Auto Scheduled | งานผ้าม่าน ชั้น 2 | 15 days | 4 | 121FS-15 days |  |  | March 24, 2020 8:00 AM | April 7, 2020 5:00 PM | April 02, 2020 05:00 PM | April 16, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Skilled carpenter
223 | Yes | CMU1.10.3.3 | Auto Scheduled | งานผ้าม่าน ชั้น 3 | 15 days | 4 | 92FS-15 days |  |  | September 26, 2019 8:00 AM | October 10, 2019 5:00 PM | October 05, 2019 05:00 PM | October 19, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Skilled carpenter
224 | Yes | CMU1.10.3.4 | Auto Scheduled | งานผ้าม่าน ชั้น 4 | 15 days | 4 | 63 |  |  | April 14, 2019 8:00 AM | April 28, 2019 5:00 PM | April 25, 2019 05:00 PM | May 09, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 522 days | 522 days | 522 days | Skilled carpenter
225 | Yes | CMU1.10.4 | Auto Scheduled | งานป้าย | 510 days | 3 |  |  |  | April 14, 2019 8:00 AM | September 4, 2020 5:00 PM | October 17, 2018 05:00 PM | March 09, 2020 05:00 PM | May 15, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 522 days | 27 days | 27 days
226 | Yes | CMU1.10.4.1 | Auto Scheduled | งานป้าย ชั้นใต้ดิน | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | August 30, 2020 05:00 PM | September 13, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
227 | Yes | CMU1.10.4.2 | Auto Scheduled | งานป้าย ชั้น 1 | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | September 02, 2020 05:00 PM | September 16, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
228 | Yes | CMU1.10.4.3 | Auto Scheduled | งานป้าย ชั้น 2 | 15 days | 4 | 121FS-15 days |  |  | March 24, 2020 8:00 AM | April 7, 2020 5:00 PM | April 01, 2020 05:00 PM | April 15, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Skilled carpenter
229 | Yes | CMU1.10.4.4 | Auto Scheduled | งานป้าย ชั้น 3 | 15 days | 4 | 92FS-15 days |  |  | September 26, 2019 8:00 AM | October 10, 2019 5:00 PM | October 06, 2019 05:00 PM | October 20, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Skilled carpenter
230 | Yes | CMU1.10.4.5 | Auto Scheduled | งานป้าย ชั้น 4 | 15 days | 4 | 63 |  |  | April 14, 2019 8:00 AM | April 28, 2019 5:00 PM | April 21, 2019 05:00 PM | May 05, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 522 days | 522 days | 522 days | Skilled carpenter
231 | Yes | CMU1.10.5 | Auto Scheduled | งานอื่นๆ | 15 days | 3 |  |  |  | August 6, 2020 8:00 AM | August 20, 2020 5:00 PM | October 20, 2018 05:00 PM | November 03, 2018 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 42 days | 42 days | 42 days
232 | Yes | CMU1.10.5.1 | Auto Scheduled | ตู้อลูมิเนียมพับขึ้นรูป พ่นสี ครอบตู้กดน้ำ | 15 days | 4 | 152FS-45 days |  |  | August 6, 2020 8:00 AM | August 20, 2020 5:00 PM | August 16, 2020 05:00 PM | August 30, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 42 days | 42 days | 42 days | General worker
233 | Yes | CMU1.10.6 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ | 670 days | 3 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
234 | Yes | CMU1.10.6.1 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้นใต้ดิน | 160 days | 4 | 236 |  |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
235 | Yes | CMU1.10.6.2 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้น 1 | 160 days | 4 | 236 |  |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
236 | Yes | CMU1.10.6.3 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้น 2 | 175 days | 4 | 237 |  | 235,234 | October 31, 2019 8:00 AM | April 22, 2020 5:00 PM | November 06, 2019 05:00 PM | April 28, 2020 05:00 PM | March 12, 2020 05:00 PM | September 02, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
237 | Yes | CMU1.10.6.4 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้น 3 | 175 days | 4 | 238 |  | 236 | May 9, 2019 8:00 AM | October 30, 2019 5:00 PM | May 15, 2019 05:00 PM | November 05, 2019 05:00 PM | March 12, 2020 05:00 PM | September 02, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
238 | Yes | CMU1.10.6.5 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้น 4 | 160 days | 4 | 36FS+14 days |  | 237 | November 30, 2018 8:00 AM | May 8, 2019 5:00 PM | December 03, 2018 05:00 PM | May 11, 2019 05:00 PM | March 27, 2020 05:00 PM | September 02, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
239 | Yes | CMU1.10.7 | Auto Scheduled | งานระบบเครื่องเสียงประกาศ (ใช้ลำโพงของเดิม) | 539 days | 3 |  |  |  | April 7, 2019 8:00 AM | September 26, 2020 5:00 PM | October 17, 2018 05:00 PM | April 07, 2020 05:00 PM | April 16, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 530 days | 5 days | 5 days
240 | Yes | CMU1.10.7.1 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้นใต้ดิน | 7 days | 4 | 241 |  |  | September 20, 2020 8:00 AM | September 26, 2020 5:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 5 days | 5 days | 5 days | Electrician
241 | Yes | CMU1.10.7.2 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้น 1 | 7 days | 4 | 152FS-7 days |  | 240 | September 13, 2020 8:00 AM | September 19, 2020 5:00 PM | September 18, 2020 05:00 PM | September 24, 2020 05:00 PM | September 09, 2020 05:00 PM | September 15, 2020 05:00 PM | As Soon As Possible |  | No | 5 days | 5 days | 0 days | Electrician
242 | Yes | CMU1.10.7.3 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้น 2 | 7 days | 4 | 121FS-7 days |  |  | April 1, 2020 8:00 AM | April 7, 2020 5:00 PM | April 08, 2020 05:00 PM | April 14, 2020 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Electrician
243 | Yes | CMU1.10.7.4 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้น 3 | 7 days | 4 | 92FS-7 days |  |  | October 4, 2019 8:00 AM | October 10, 2019 5:00 PM | October 13, 2019 05:00 PM | October 19, 2019 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Electrician
244 | Yes | CMU1.10.7.5 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้น 4 | 7 days | 4 | 63FS-7 days |  |  | April 7, 2019 8:00 AM | April 13, 2019 5:00 PM | April 14, 2019 05:00 PM | April 20, 2019 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 537 days | 537 days | 537 days | Electrician
245 | Yes | CMU1.10.8 | Auto Scheduled | งานระบบกล้องวงจรปิด (ใช้กล้องวงจรปิดของเดิม) | 539 days | 3 |  |  |  | April 7, 2019 8:00 AM | September 26, 2020 5:00 PM | October 17, 2018 05:00 PM | April 07, 2020 05:00 PM | April 16, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 530 days | 5 days | 5 days
246 | Yes | CMU1.10.8.1 | Auto Scheduled | งานกล้องวงจรปิด ชั้นใต้ดิน | 7 days | 4 | 247 |  |  | September 20, 2020 8:00 AM | September 26, 2020 5:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 5 days | 5 days | 5 days | Electrician
247 | Yes | CMU1.10.8.2 | Auto Scheduled | งานกล้องวงจรปิด ชั้น 1 | 7 days | 4 | 152FS-7 days |  | 246 | September 13, 2020 8:00 AM | September 19, 2020 5:00 PM | September 18, 2020 05:00 PM | September 24, 2020 05:00 PM | September 09, 2020 05:00 PM | September 15, 2020 05:00 PM | As Soon As Possible |  | No | 5 days | 5 days | 0 days | Electrician
248 | Yes | CMU1.10.8.3 | Auto Scheduled | งานกล้องวงจรปิด ชั้น 2 | 7 days | 4 | 121FS-7 days |  |  | April 1, 2020 8:00 AM | April 7, 2020 5:00 PM | April 10, 2020 05:00 PM | April 16, 2020 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Electrician
249 | Yes | CMU1.10.8.4 | Auto Scheduled | งานกล้องวงจรปิด ชั้น 3 | 7 days | 4 | 92FS-7 days |  |  | October 4, 2019 8:00 AM | October 10, 2019 5:00 PM | October 16, 2019 05:00 PM | October 22, 2019 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Electrician
250 | Yes | CMU1.10.8.5 | Auto Scheduled | งานกล้องวงจรปิด ชั้น 4 | 7 days | 4 | 63FS-7 days |  |  | April 7, 2019 8:00 AM | April 13, 2019 5:00 PM | April 12, 2019 05:00 PM | April 18, 2019 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 537 days | 537 days | 537 days | Electrician

## solutoion_14
ID | Active | WBS | Task_Mode | Name | Duration | Outline_Level | Predecessors | Predecessors2 | Successors | Start_Date | Finish_Date | Early_Start | Early_Finish | Late_Start | Late_Finish | Constraint_Type | Constraint_Date | Summary | Start_Slack | Finish_Slack | Free_Slack | Resource_Names
1 | Yes | CMU1 | Auto Scheduled | โครงการปรับปรุงสำนักหอสมุด มหาวิทยาลัยเชียงใหม่ | 716 days | 1 |  |  |  | October 17, 2018 8:00 AM | October 1, 2020 5:00 PM | October 17, 2018 05:00 PM | October 01, 2020 05:00 PM | October 21, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 0 days | 0 days | 0 days
2 | Yes | CMU1.1 | Auto Scheduled | หมวดเตรียมการ | 675 days | 2 |  |  |  | October 17, 2018 8:00 AM | August 21, 2020 5:00 PM | October 17, 2018 05:00 PM | August 21, 2020 05:00 PM | December 01, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 41 days | 41 days | 41 days
3 | Yes | CMU1.1.1 | Auto Scheduled | งานอาคารสนามและผังบริเวณโครงการ | 14 days | 3 | 4FS-7 days |  |  | October 26, 2018 8:00 AM | November 8, 2018 5:00 PM | November 01, 2018 05:00 PM | November 14, 2018 05:00 PM | September 22, 2020 05:00 PM | October 05, 2020 05:00 PM | Start No Earlier Than | Oct 24 '18 | No | 693 days | 693 days | 693 days | Engineer
4 | Yes | CMU1.1.2 | Auto Scheduled | งานเชื่อมต่อระบบสาธารณูปโภคโครงการ | 16 days | 3 |  |  | 3FS-7 days | October 17, 2018 8:00 AM | November 1, 2018 5:00 PM | October 19, 2018 05:00 PM | November 03, 2018 05:00 PM | September 13, 2020 05:00 PM | September 28, 2020 05:00 PM | As Soon As Possible |  | No | 693 days | 693 days | 0 days | Engineer
5 | Yes | CMU1.1.3 | Auto Scheduled | งานตรวจทดสอบระบบภายในอาคารก่อนดำเนินการปรับปรุง | 675 days | 3 |  |  |  | October 17, 2018 8:00 AM | August 21, 2020 5:00 PM | October 17, 2018 05:00 PM | August 21, 2020 05:00 PM | December 01, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 41 days | 41 days | 41 days
6 | Yes | CMU1.1.3.1 | Auto Scheduled | ชั้นที่ 4 | 15 days | 4 |  |  | 7FS+150 days | October 17, 2018 8:00 AM | October 31, 2018 5:00 PM | October 19, 2018 05:00 PM | November 02, 2018 05:00 PM | December 01, 2018 05:00 PM | December 15, 2018 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
7 | Yes | CMU1.1.3.2 | Auto Scheduled | ชั้นที่ 3 | 15 days | 4 | 6FS+150 days |  | 8FS+150 days | March 31, 2019 8:00 AM | April 14, 2019 5:00 PM | April 08, 2019 05:00 PM | April 22, 2019 05:00 PM | May 15, 2019 05:00 PM | May 29, 2019 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
8 | Yes | CMU1.1.3.3 | Auto Scheduled | ชั้นที่ 2 | 15 days | 4 | 7FS+150 days |  | 9FS+150 days | September 12, 2019 8:00 AM | September 26, 2019 5:00 PM | October 02, 2019 05:00 PM | October 16, 2019 05:00 PM | October 27, 2019 05:00 PM | November 10, 2019 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
9 | Yes | CMU1.1.3.4 | Auto Scheduled | ชั้นที่ 1 | 15 days | 4 | 8FS+150 days |  | 10FS+150 days | February 24, 2020 8:00 AM | March 9, 2020 5:00 PM | March 23, 2020 05:00 PM | April 06, 2020 05:00 PM | April 09, 2020 05:00 PM | April 23, 2020 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
10 | Yes | CMU1.1.3.5 | Auto Scheduled | ชั้นใต้ดินและภายนอก | 15 days | 4 | 9FS+150 days |  |  | August 7, 2020 8:00 AM | August 21, 2020 5:00 PM | September 15, 2020 05:00 PM | September 29, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 41 days | Engineer
11 | Yes | CMU1.1.4 | Auto Scheduled | งานสำรวจอุปกรณ์ไฟฟ้า, สุขภัณฑ์และครุภัณฑ์ (ของเดิม) ก่อนดำเนินการปรับปรุง | 675 days | 3 |  |  |  | October 17, 2018 8:00 AM | August 21, 2020 5:00 PM | October 17, 2018 05:00 PM | August 21, 2020 05:00 PM | December 01, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 41 days | 41 days | 41 days
12 | Yes | CMU1.1.4.1 | Auto Scheduled | ชั้นที่ 4 | 15 days | 4 |  |  | 13FS+150 days | October 17, 2018 8:00 AM | October 31, 2018 5:00 PM | October 20, 2018 05:00 PM | November 03, 2018 05:00 PM | December 01, 2018 05:00 PM | December 15, 2018 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
13 | Yes | CMU1.1.4.2 | Auto Scheduled | ชั้นที่ 3 | 15 days | 4 | 12FS+150 days |  | 14FS+150 days | March 31, 2019 8:00 AM | April 14, 2019 5:00 PM | April 06, 2019 05:00 PM | April 20, 2019 05:00 PM | May 15, 2019 05:00 PM | May 29, 2019 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
14 | Yes | CMU1.1.4.3 | Auto Scheduled | ชั้นที่ 2 | 15 days | 4 | 13FS+150 days |  | 15FS+150 days | September 12, 2019 8:00 AM | September 26, 2019 5:00 PM | September 24, 2019 05:00 PM | October 08, 2019 05:00 PM | October 27, 2019 05:00 PM | November 10, 2019 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
15 | Yes | CMU1.1.4.4 | Auto Scheduled | ชั้นที่ 1 | 15 days | 4 | 14FS+150 days |  | 16FS+150 days | February 24, 2020 8:00 AM | March 9, 2020 5:00 PM | March 15, 2020 05:00 PM | March 29, 2020 05:00 PM | April 09, 2020 05:00 PM | April 23, 2020 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
16 | Yes | CMU1.1.4.5 | Auto Scheduled | ชั้นใต้ดินและภายนอก | 15 days | 4 | 15FS+150 days |  |  | August 7, 2020 8:00 AM | August 21, 2020 5:00 PM | September 07, 2020 05:00 PM | September 21, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 41 days | Engineer
17 | Yes | CMU1.1.5 | Auto Scheduled | งานเอกสารขออนุมัติใช้วัสดุ, Shop Drawing และครุภัณฑ์ของโครงการ | 106 days | 3 |  |  |  | October 17, 2018 8:00 AM | January 30, 2019 5:00 PM | October 22, 2018 05:00 PM | February 04, 2019 05:00 PM | June 22, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 610 days | 610 days | 610 days
18 | Yes | CMU1.1.5.1 | Auto Scheduled | แบบ Shop Drawing ชั้นที่ 4 | 20 days | 4 |  |  | 19,25SS+14 days,26SS+14 days | October 17, 2018 8:00 AM | November 5, 2018 5:00 PM | October 17, 2018 05:00 PM | November 05, 2018 05:00 PM | October 01, 2018 05:00 PM | October 20, 2018 05:00 PM | As Soon As Possible |  | No | 610 days | 610 days | 0 days | Engineer
19 | Yes | CMU1.1.5.2 | Auto Scheduled | แบบ Shop Drawing ชั้นที่ 3 | 20 days | 4 | 18 |  | 20FS-7 days | November 6, 2018 8:00 AM | November 25, 2018 5:00 PM | November 14, 2018 05:00 PM | December 03, 2018 05:00 PM | July 13, 2020 05:00 PM | August 01, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
20 | Yes | CMU1.1.5.3 | Auto Scheduled | แบบ Shop Drawing ชั้นที่ 2 | 20 days | 4 | 19FS-7 days |  | 21FS-7 days | November 19, 2018 8:00 AM | December 8, 2018 5:00 PM | November 30, 2018 05:00 PM | December 19, 2018 05:00 PM | July 26, 2020 05:00 PM | August 14, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
21 | Yes | CMU1.1.5.4 | Auto Scheduled | แบบ Shop Drawing ชั้นที่ 1 | 20 days | 4 | 20FS-7 days |  | 22FS-7 days | December 2, 2018 8:00 AM | December 21, 2018 5:00 PM | December 19, 2018 05:00 PM | January 07, 2019 05:00 PM | August 08, 2020 05:00 PM | August 27, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
22 | Yes | CMU1.1.5.5 | Auto Scheduled | แบบ Shop Drawing ชั้นใต้ดิน | 20 days | 4 | 21FS-7 days |  | 23FS-7 days | December 15, 2018 8:00 AM | January 3, 2019 5:00 PM | January 08, 2019 05:00 PM | January 27, 2019 05:00 PM | August 21, 2020 05:00 PM | September 09, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
23 | Yes | CMU1.1.5.6 | Auto Scheduled | แบบ Shop Drawing ภายนอกอาคาร | 20 days | 4 | 22FS-7 days |  | 24FS-7 days | December 28, 2018 8:00 AM | January 16, 2019 5:00 PM | February 01, 2019 05:00 PM | February 20, 2019 05:00 PM | September 03, 2020 05:00 PM | September 22, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
24 | Yes | CMU1.1.5.7 | Auto Scheduled | แบบ Shop Drawing landscape | 20 days | 4 | 23FS-7 days |  |  | January 10, 2019 8:00 AM | January 29, 2019 5:00 PM | February 24, 2019 05:00 PM | March 15, 2019 05:00 PM | September 16, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 611 days | Engineer
25 | Yes | CMU1.1.5.8 | Auto Scheduled | แบบ Shop Drawing งานปรับปรุง ครุภัณฑ์ | 92 days | 4 | 18SS+14 days |  |  | October 31, 2018 8:00 AM | January 30, 2019 5:00 PM | November 07, 2018 05:00 PM | February 06, 2019 05:00 PM | July 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 610 days | 610 days | 610 days | Engineer
26 | Yes | CMU1.1.5.9 | Auto Scheduled | แบบ Shop Drawing งานจัดซื้อครุภัณฑ์ | 92 days | 4 | 18SS+14 days |  |  | October 31, 2018 8:00 AM | January 30, 2019 5:00 PM | November 08, 2018 05:00 PM | February 07, 2019 05:00 PM | July 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 610 days | 610 days | 610 days | Engineer
27 | Yes | CMU1.1.6 | Auto Scheduled | งานตรวจทดสอบระบบ, งานอบรมผู้ใช้อาคาร และ As-Built Drawing | 30 days | 3 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 23, 2018 05:00 PM | November 21, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 686 days | 686 days | 686 days
28 | Yes | CMU1.1.6.1 | Auto Scheduled | ชั้นที่ 4 | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 27, 2018 05:00 PM | November 25, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
29 | Yes | CMU1.1.6.2 | Auto Scheduled | ชั้นที่ 3 | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 31, 2018 05:00 PM | November 29, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
30 | Yes | CMU1.1.6.3 | Auto Scheduled | ชั้นที่ 2 | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 22, 2018 05:00 PM | November 20, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
31 | Yes | CMU1.1.6.4 | Auto Scheduled | ชั้นที่ 1 | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 29, 2018 05:00 PM | November 27, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
32 | Yes | CMU1.1.6.5 | Auto Scheduled | ชั้นใต้ดิน | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 25, 2018 05:00 PM | November 23, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
33 | Yes | CMU1.1.6.6 | Auto Scheduled | ทั้งอาคาร | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 23, 2018 05:00 PM | November 21, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
34 | Yes | CMU1.1.7 | Auto Scheduled | งานบริหารงานก่อสร้างและงานอื่น ๆ | 0 days | 3 |  |  |  | October 17, 2018 8:00 AM | October 17, 2018 8:00 AM | October 20, 2018 05:00 PM | October 19, 2018 05:00 PM | October 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 716 days | 716 days | 716 days | Engineer
35 | Yes | CMU1.2 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้น 4 | 471 days | 2 |  |  |  | October 17, 2018 8:00 AM | January 30, 2020 5:00 PM | October 17, 2018 05:00 PM | January 30, 2020 05:00 PM | June 23, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 0 days | 245 days | 0 days
36 | Yes | CMU1.2.1 | Auto Scheduled | งานรื้อถอน ชั้น 4 (รื้อขนไป) | 30 days | 3 |  |  | 39FS+45 days,40FS+45 days,51,63SS+14 days,80,109,140,180FS+14 days,186FS+14 days,198FS+14 days,199FS+14 days,200FS+14 days,238FS+14 days | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 17, 2018 05:00 PM | November 15, 2018 05:00 PM | March 11, 2018 05:00 PM | April 09, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | General worker
37 | Yes | CMU1.2.2 | Auto Scheduled | งานสถาปัตยกรรม ชั้น 4 | 396 days | 3 |  |  |  | December 31, 2018 8:00 AM | January 30, 2020 5:00 PM | October 17, 2018 05:00 PM | November 16, 2019 05:00 PM | September 06, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 326 days | 245 days | 245 days
38 | Yes | CMU1.2.2.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 39,41,42 |  |  | March 1, 2019 8:00 AM | March 30, 2019 5:00 PM | March 16, 2019 05:00 PM | April 14, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 551 days | Skilled carpenter
39 | Yes | CMU1.2.2.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 36FS+45 days |  | 38,43 | December 31, 2018 8:00 AM | February 28, 2019 5:00 PM | January 05, 2019 05:00 PM | March 05, 2019 05:00 PM | July 15, 2020 05:00 PM | September 12, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 0 days | General worker
40 | Yes | CMU1.2.2.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 36FS+45 days |  | 41,42 | December 31, 2018 8:00 AM | January 29, 2019 5:00 PM | January 03, 2019 05:00 PM | February 01, 2019 05:00 PM | August 14, 2020 05:00 PM | September 12, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 0 days | General worker
41 | Yes | CMU1.2.2.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 40 |  | 38,43 | January 30, 2019 8:00 AM | February 28, 2019 5:00 PM | February 05, 2019 05:00 PM | March 06, 2019 05:00 PM | August 14, 2020 05:00 PM | September 12, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 0 days | Skilled carpenter
42 | Yes | CMU1.2.2.5 | Auto Scheduled | งานบันได | 30 days | 4 | 40 |  | 38,43 | January 30, 2019 8:00 AM | February 28, 2019 5:00 PM | February 06, 2019 05:00 PM | March 07, 2019 05:00 PM | August 14, 2020 05:00 PM | September 12, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 0 days | General worker
43 | Yes | CMU1.2.2.6 | Auto Scheduled | งานสี | 30 days | 4 | 39,41,42 |  |  | March 1, 2019 8:00 AM | March 30, 2019 5:00 PM | March 11, 2019 05:00 PM | April 09, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 551 days | General worker
44 | Yes | CMU1.2.2.7 | Auto Scheduled | งานสุขภัณฑ์ | 315 days | 4 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 20, 2018 05:00 PM | August 30, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
45 | Yes | CMU1.2.2.7.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 46FS+135 days |  | 47FS+135 days | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | September 19, 2019 05:00 PM | October 03, 2019 05:00 PM | April 24, 2020 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
46 | Yes | CMU1.2.2.7.2 | Auto Scheduled | ZONE T-2 กลาง | 15 days | 5 | 51,55 |  | 45FS+135 days | March 22, 2019 8:00 AM | April 5, 2019 5:00 PM | April 13, 2019 05:00 PM | April 27, 2019 05:00 PM | November 26, 2019 05:00 PM | December 10, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
47 | Yes | CMU1.2.2.7.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 15 days | 5 | 45FS+135 days |  |  | January 16, 2020 8:00 AM | January 30, 2020 5:00 PM | February 23, 2020 05:00 PM | March 08, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 245 days | Sanitary-Plumber
48 | Yes | CMU1.2.3 | Auto Scheduled | งานระบบสุขาภิบาล ชั้น 4 | 408 days | 3 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
49 | Yes | CMU1.2.3.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
50 | Yes | CMU1.2.3.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 51FS+15 days |  | 52FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 22, 2019 05:00 PM | August 25, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
51 | Yes | CMU1.2.3.1.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 36 |  | 50FS+15 days,46,55SS | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 23, 2018 05:00 PM | March 28, 2019 05:00 PM | August 25, 2019 05:00 PM | December 28, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
52 | Yes | CMU1.2.3.1.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 50FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 14, 2019 05:00 PM | January 17, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
53 | Yes | CMU1.2.3.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
54 | Yes | CMU1.2.3.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 55FS+15 days |  | 56FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 30, 2019 05:00 PM | September 02, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
55 | Yes | CMU1.2.3.2.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 51SS |  | 54FS+15 days,46 | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | December 03, 2018 05:00 PM | April 07, 2019 05:00 PM | August 25, 2019 05:00 PM | December 28, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
56 | Yes | CMU1.2.3.2.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 54FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | October 01, 2019 05:00 PM | February 03, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
57 | Yes | CMU1.2.4 | Auto Scheduled | งานระบบไฟฟ้า ชั้น 4 | 117 days | 3 |  |  |  | November 30, 2018 8:00 AM | March 26, 2019 5:00 PM | October 21, 2018 05:00 PM | February 14, 2019 05:00 PM | June 11, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 555 days | 555 days | 555 days
58 | Yes | CMU1.2.4.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 30 days | 4 | 60FS+7 days |  |  | February 25, 2019 8:00 AM | March 26, 2019 5:00 PM | March 05, 2019 05:00 PM | April 03, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 555 days | 555 days | 555 days | Electrician
59 | Yes | CMU1.2.4.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 30 days | 4 | 60FS+7 days |  |  | February 25, 2019 8:00 AM | March 26, 2019 5:00 PM | March 05, 2019 05:00 PM | April 03, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 555 days | 555 days | 555 days | Electrician
60 | Yes | CMU1.2.4.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 63SS+30 days |  | 58FS+7 days,59FS+7 days | November 30, 2018 8:00 AM | February 17, 2019 5:00 PM | December 04, 2018 05:00 PM | February 21, 2019 05:00 PM | June 11, 2020 05:00 PM | August 29, 2020 05:00 PM | As Soon As Possible |  | No | 555 days | 555 days | 0 days | Electrician
61 | Yes | CMU1.2.4.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 63SS+30 days |  |  | November 30, 2018 8:00 AM | February 17, 2019 5:00 PM | December 04, 2018 05:00 PM | February 21, 2019 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 592 days | 592 days | 592 days | Electrician
62 | Yes | CMU1.2.4.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 63SS+30 days |  |  | November 30, 2018 8:00 AM | February 17, 2019 5:00 PM | December 07, 2018 05:00 PM | February 24, 2019 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 592 days | 592 days | 592 days | Electrician
63 | Yes | CMU1.2.5 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้น 4 | 165 days | 3 | 36SS+14 days |  | 62SS+30 days,60SS+30 days,61SS+30 days,65,214,219FS-15 days,224,230,244FS-7 days,250FS-7 days | October 31, 2018 8:00 AM | April 13, 2019 5:00 PM | October 31, 2018 05:00 PM | April 13, 2019 05:00 PM | June 19, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Skilled carpenter
64 | Yes | CMU1.3 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้น 3 | 441 days | 2 |  |  |  | November 16, 2018 8:00 AM | January 30, 2020 5:00 PM | October 17, 2018 05:00 PM | December 31, 2019 05:00 PM | July 23, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 149 days | 245 days | 149 days
65 | Yes | CMU1.3.1 | Auto Scheduled | งานรื้อถอน ชั้น 3 (รื้อขนไป) | 30 days | 3 | 63 | 121 | 68FS+45 days,69FS+45 days,92SS | April 14, 2019 8:00 AM | May 13, 2019 5:00 PM | April 14, 2019 05:00 PM | May 13, 2019 05:00 PM | July 19, 2018 05:00 PM | August 17, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | General worker
66 | Yes | CMU1.3.2 | Auto Scheduled | งานสถาปัตยกรรม ชั้น 3 | 315 days | 3 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 23, 2018 05:00 PM | September 02, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
67 | Yes | CMU1.3.2.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 68,70,71 |  |  | August 27, 2019 8:00 AM | September 25, 2019 5:00 PM | August 31, 2019 05:00 PM | September 29, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 372 days | Skilled carpenter
68 | Yes | CMU1.3.2.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 65FS+45 days |  | 67,72 | June 28, 2019 8:00 AM | August 26, 2019 5:00 PM | June 28, 2019 05:00 PM | August 26, 2019 05:00 PM | October 02, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 0 days | General worker
69 | Yes | CMU1.3.2.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 65FS+45 days |  | 70,71 | June 28, 2019 8:00 AM | July 27, 2019 5:00 PM | June 28, 2019 05:00 PM | July 27, 2019 05:00 PM | April 15, 2019 05:00 PM | May 14, 2019 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 0 days | General worker
70 | Yes | CMU1.3.2.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 69 |  | 67,72 | July 28, 2019 8:00 AM | August 26, 2019 5:00 PM | July 28, 2019 05:00 PM | August 26, 2019 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 0 days | Skilled carpenter
71 | Yes | CMU1.3.2.5 | Auto Scheduled | งานบันได | 30 days | 4 | 69 |  | 67,72 | July 28, 2019 8:00 AM | August 26, 2019 5:00 PM | July 28, 2019 05:00 PM | August 26, 2019 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 0 days | General worker
72 | Yes | CMU1.3.2.6 | Auto Scheduled | งานสี | 30 days | 4 | 68,70,71 |  |  | August 27, 2019 8:00 AM | September 25, 2019 5:00 PM | August 30, 2019 05:00 PM | September 28, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 372 days | General worker
73 | Yes | CMU1.3.2.7 | Auto Scheduled | งานสุขภัณฑ์ | 315 days | 4 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 25, 2018 05:00 PM | September 04, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
74 | Yes | CMU1.3.2.7.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 75FS+135 days |  | 76FS+135 days | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | August 25, 2019 05:00 PM | September 08, 2019 05:00 PM | April 24, 2020 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
75 | Yes | CMU1.3.2.7.2 | Auto Scheduled | ZONE T-2 กลาง | 15 days | 5 | 80,84 |  | 74FS+135 days | March 22, 2019 8:00 AM | April 5, 2019 5:00 PM | March 24, 2019 05:00 PM | April 07, 2019 05:00 PM | November 26, 2019 05:00 PM | December 10, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
76 | Yes | CMU1.3.2.7.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 15 days | 5 | 74FS+135 days |  |  | January 16, 2020 8:00 AM | January 30, 2020 5:00 PM | January 28, 2020 05:00 PM | February 11, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 245 days | Sanitary-Plumber
77 | Yes | CMU1.3.3 | Auto Scheduled | งานระบบสุขาภิบาล ชั้น 3 | 408 days | 3 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
78 | Yes | CMU1.3.3.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
79 | Yes | CMU1.3.3.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 80FS+15 days |  | 81FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 21, 2019 05:00 PM | August 24, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
80 | Yes | CMU1.3.3.1.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 36 |  | 79FS+15 days,84SS,75 | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 16, 2018 05:00 PM | March 21, 2019 05:00 PM | January 09, 2019 05:00 PM | May 14, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
81 | Yes | CMU1.3.3.1.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 79FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 16, 2019 05:00 PM | January 19, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
82 | Yes | CMU1.3.3.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
83 | Yes | CMU1.3.3.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 84FS+15 days |  | 85FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 12, 2019 05:00 PM | August 15, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
84 | Yes | CMU1.3.3.2.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 80SS |  | 83FS+15 days,75 | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 16, 2018 05:00 PM | March 21, 2019 05:00 PM | January 09, 2019 05:00 PM | May 14, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
85 | Yes | CMU1.3.3.2.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 83FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 11, 2019 05:00 PM | January 14, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
86 | Yes | CMU1.3.4 | Auto Scheduled | งานระบบไฟฟ้า ชั้น 3 | 147 days | 3 |  |  |  | May 14, 2019 8:00 AM | October 7, 2019 5:00 PM | October 21, 2018 05:00 PM | March 16, 2019 05:00 PM | May 12, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 360 days | 360 days | 360 days
87 | Yes | CMU1.3.4.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 60 days | 4 | 89FS+7 days |  |  | August 9, 2019 8:00 AM | October 7, 2019 5:00 PM | August 19, 2019 05:00 PM | October 17, 2019 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 360 days | 360 days | 360 days | Electrician
88 | Yes | CMU1.3.4.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 60 days | 4 | 89FS+7 days |  |  | August 9, 2019 8:00 AM | October 7, 2019 5:00 PM | August 28, 2019 05:00 PM | October 26, 2019 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 360 days | 360 days | 360 days | Electrician
89 | Yes | CMU1.3.4.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 92SS+30 days |  | 88FS+7 days,87FS+7 days | May 14, 2019 8:00 AM | August 1, 2019 5:00 PM | May 21, 2019 05:00 PM | August 08, 2019 05:00 PM | May 12, 2020 05:00 PM | July 30, 2020 05:00 PM | As Soon As Possible |  | No | 360 days | 360 days | 0 days | Electrician
90 | Yes | CMU1.3.4.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 92SS+30 days |  |  | May 14, 2019 8:00 AM | August 1, 2019 5:00 PM | May 24, 2019 05:00 PM | August 11, 2019 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 427 days | 427 days | 427 days | Electrician
91 | Yes | CMU1.3.4.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 92SS+30 days |  |  | May 14, 2019 8:00 AM | August 1, 2019 5:00 PM | May 25, 2019 05:00 PM | August 12, 2019 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 427 days | 427 days | 427 days | Electrician
92 | Yes | CMU1.3.5 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้น 3 | 180 days | 3 | 65SS |  | 91SS+30 days,90SS+30 days,89SS+30 days,94,213FS-15 days,218FS-30 days,223FS-15 days,229FS-15 days,243FS-7 days,249FS-7 days | April 14, 2019 8:00 AM | October 10, 2019 5:00 PM | April 19, 2019 05:00 PM | October 15, 2019 05:00 PM | October 12, 2019 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Skilled carpenter
93 | Yes | CMU1.4 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้น 2 | 509 days | 2 |  |  |  | November 16, 2018 8:00 AM | April 7, 2020 5:00 PM | October 17, 2018 05:00 PM | March 08, 2020 05:00 PM | May 16, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 177 days | 177 days
94 | Yes | CMU1.4.1 | Auto Scheduled | งานรื้อถอน ชั้น 2 (รื้อขนไป) | 30 days | 3 | 92 | 152 | 97FS+45 days,98FS+45 days,121SS | October 11, 2019 8:00 AM | November 9, 2019 5:00 PM | October 16, 2019 05:00 PM | November 14, 2019 05:00 PM | June 04, 2018 05:00 PM | July 03, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | General worker
95 | Yes | CMU1.4.2 | Auto Scheduled | งานสถาปัตยกรรม ชั้น 2 | 368 days | 3 |  |  |  | March 22, 2019 8:00 AM | March 23, 2020 5:00 PM | October 17, 2018 05:00 PM | October 19, 2019 05:00 PM | October 04, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 192 days | 192 days
96 | Yes | CMU1.4.2.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 97,99,100 |  |  | February 23, 2020 8:00 AM | March 23, 2020 5:00 PM | March 09, 2020 05:00 PM | April 07, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 192 days | Skilled carpenter
97 | Yes | CMU1.4.2.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 94FS+45 days |  | 96,101 | December 25, 2019 8:00 AM | February 22, 2020 5:00 PM | December 30, 2019 05:00 PM | February 27, 2020 05:00 PM | February 09, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 0 days | General worker
98 | Yes | CMU1.4.2.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 94FS+45 days |  | 99,100 | December 25, 2019 8:00 AM | January 23, 2020 5:00 PM | January 03, 2020 05:00 PM | February 01, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 0 days | General worker
99 | Yes | CMU1.4.2.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 98 |  | 96,101 | January 24, 2020 8:00 AM | February 22, 2020 5:00 PM | February 05, 2020 05:00 PM | March 05, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 0 days | Skilled carpenter
100 | Yes | CMU1.4.2.5 | Auto Scheduled | งานบันได | 30 days | 4 | 98 |  | 96,101 | January 24, 2020 8:00 AM | February 22, 2020 5:00 PM | February 05, 2020 05:00 PM | March 05, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 0 days | General worker
101 | Yes | CMU1.4.2.6 | Auto Scheduled | งานสี | 30 days | 4 | 97,99,100 |  |  | February 23, 2020 8:00 AM | March 23, 2020 5:00 PM | March 12, 2020 05:00 PM | April 10, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 192 days | General worker
102 | Yes | CMU1.4.2.7 | Auto Scheduled | งานสุขภัณฑ์ | 315 days | 4 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 21, 2018 05:00 PM | August 31, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
103 | Yes | CMU1.4.2.7.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 104FS+135 days |  | 105FS+135 days | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | September 21, 2019 05:00 PM | October 05, 2019 05:00 PM | April 24, 2020 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
104 | Yes | CMU1.4.2.7.2 | Auto Scheduled | ZONE T-2 กลาง | 15 days | 5 | 113,109 |  | 103FS+135 days | March 22, 2019 8:00 AM | April 5, 2019 5:00 PM | April 20, 2019 05:00 PM | May 04, 2019 05:00 PM | November 26, 2019 05:00 PM | December 10, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
105 | Yes | CMU1.4.2.7.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 15 days | 5 | 103FS+135 days |  |  | January 16, 2020 8:00 AM | January 30, 2020 5:00 PM | February 26, 2020 05:00 PM | March 11, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 245 days | Sanitary-Plumber
106 | Yes | CMU1.4.3 | Auto Scheduled | งานระบบสุขาภิบาล ชั้น 2 | 408 days | 3 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
107 | Yes | CMU1.4.3.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
108 | Yes | CMU1.4.3.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 109FS+15 days |  | 110FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 24, 2019 05:00 PM | August 27, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
109 | Yes | CMU1.4.3.1.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 36 |  | 113SS,104,108FS+15 days | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 29, 2018 05:00 PM | April 03, 2019 05:00 PM | August 25, 2019 05:00 PM | December 28, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
110 | Yes | CMU1.4.3.1.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 108FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 15, 2019 05:00 PM | January 18, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
111 | Yes | CMU1.4.3.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
112 | Yes | CMU1.4.3.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 113FS+15 days |  | 114FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | May 06, 2019 05:00 PM | September 08, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
113 | Yes | CMU1.4.3.2.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 109SS |  | 104,112FS+15 days | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | December 05, 2018 05:00 PM | April 09, 2019 05:00 PM | August 25, 2019 05:00 PM | December 28, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
114 | Yes | CMU1.4.3.2.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 112FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 28, 2019 05:00 PM | January 31, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
115 | Yes | CMU1.4.4 | Auto Scheduled | งานระบบไฟฟ้า ชั้น 2 | 147 days | 3 |  |  |  | November 10, 2019 8:00 AM | April 4, 2020 5:00 PM | October 20, 2018 05:00 PM | March 15, 2019 05:00 PM | May 12, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 180 days | 180 days | 180 days
116 | Yes | CMU1.4.4.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 60 days | 4 | 118FS+7 days |  |  | February 5, 2020 8:00 AM | April 4, 2020 5:00 PM | February 14, 2020 05:00 PM | April 13, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 180 days | 180 days | 180 days | Electrician
117 | Yes | CMU1.4.4.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 60 days | 4 | 118FS+7 days |  |  | February 5, 2020 8:00 AM | April 4, 2020 5:00 PM | February 16, 2020 05:00 PM | April 15, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 180 days | 180 days | 180 days | Electrician
118 | Yes | CMU1.4.4.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 121SS+30 days |  | 117FS+7 days,116FS+7 days | November 10, 2019 8:00 AM | January 28, 2020 5:00 PM | November 17, 2019 05:00 PM | February 04, 2020 05:00 PM | May 12, 2020 05:00 PM | July 30, 2020 05:00 PM | As Soon As Possible |  | No | 180 days | 180 days | 0 days | Electrician
119 | Yes | CMU1.4.4.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 121SS+30 days |  |  | November 10, 2019 8:00 AM | January 28, 2020 5:00 PM | November 19, 2019 05:00 PM | February 06, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 247 days | 247 days | 247 days | Electrician
120 | Yes | CMU1.4.4.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 121SS+30 days |  |  | November 10, 2019 8:00 AM | January 28, 2020 5:00 PM | November 22, 2019 05:00 PM | February 09, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 247 days | 247 days | 247 days | Electrician
121 | Yes | CMU1.4.5 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้น 2 | 180 days | 3 | 94SS |  | 120SS+30 days,119SS+30 days,118SS+30 days,123,212FS-15 days,217FS-30 days,222FS-15 days,228FS-15 days,242FS-7 days,248FS-7 days | October 11, 2019 8:00 AM | April 7, 2020 5:00 PM | October 16, 2019 05:00 PM | April 12, 2020 05:00 PM | June 04, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Skilled carpenter
122 | Yes | CMU1.5 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้น 1 | 686 days | 2 |  |  |  | November 16, 2018 8:00 AM | October 1, 2020 5:00 PM | October 17, 2018 05:00 PM | September 01, 2020 05:00 PM | November 20, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 0 days | 0 days
123 | Yes | CMU1.5.1 | Auto Scheduled | งานรื้อถอน ชั้น 1 (รื้อขนไป) | 30 days | 3 | 121 | 63 | 124,127FS+45 days,128FS+45 days,131FS+45 days,152SS,193SS,194SS,195SS,196SS,197SS,202SS,204SS,205SS,206SS,207SS | April 8, 2020 8:00 AM | May 7, 2020 5:00 PM | April 13, 2020 05:00 PM | May 12, 2020 05:00 PM | July 19, 2018 05:00 PM | August 17, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | General worker
124 | Yes | CMU1.5.2 | Auto Scheduled | งานโครงสร้างวิศวกรรม ชั้น 1 | 75 days | 3 | 123 |  |  | May 8, 2020 8:00 AM | July 21, 2020 5:00 PM | May 14, 2020 05:00 PM | July 27, 2020 05:00 PM | July 23, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 72 days | 72 days | 72 days | General worker
125 | Yes | CMU1.5.3 | Auto Scheduled | งานสถาปัตยกรรม ชั้น 1 | 548 days | 3 |  |  |  | March 22, 2019 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | April 16, 2020 05:00 PM | April 07, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 12 days | 12 days
126 | Yes | CMU1.5.3.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 127,129,130 |  |  | August 21, 2020 8:00 AM | September 19, 2020 5:00 PM | August 26, 2020 05:00 PM | September 24, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | Skilled carpenter
127 | Yes | CMU1.5.3.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 123FS+45 days |  | 126,132 | June 22, 2020 8:00 AM | August 20, 2020 5:00 PM | June 27, 2020 05:00 PM | August 25, 2020 05:00 PM | October 02, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
128 | Yes | CMU1.5.3.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 123FS+45 days |  | 129,130 | June 22, 2020 8:00 AM | July 21, 2020 5:00 PM | June 27, 2020 05:00 PM | July 26, 2020 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
129 | Yes | CMU1.5.3.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 128 |  | 126,132 | July 22, 2020 8:00 AM | August 20, 2020 5:00 PM | July 27, 2020 05:00 PM | August 25, 2020 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | Skilled carpenter
130 | Yes | CMU1.5.3.5 | Auto Scheduled | งานบันได | 30 days | 4 | 128 |  | 126,132 | July 22, 2020 8:00 AM | August 20, 2020 5:00 PM | July 27, 2020 05:00 PM | August 25, 2020 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
131 | Yes | CMU1.5.3.6 | Auto Scheduled | งานตกแต่งอื่น ๆ | 60 days | 4 | 123FS+45 days |  |  | June 22, 2020 8:00 AM | August 20, 2020 5:00 PM | June 27, 2020 05:00 PM | August 25, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 42 days | 42 days | 42 days | General worker
132 | Yes | CMU1.5.3.7 | Auto Scheduled | งานสี | 30 days | 4 | 127,129,130 |  |  | August 21, 2020 8:00 AM | September 19, 2020 5:00 PM | August 26, 2020 05:00 PM | September 24, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
133 | Yes | CMU1.5.3.8 | Auto Scheduled | งานสุขภัณฑ์ | 315 days | 4 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 27, 2018 05:00 PM | September 06, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
134 | Yes | CMU1.5.3.8.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 135FS+135 days |  | 136FS+135 days | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | August 24, 2019 05:00 PM | September 07, 2019 05:00 PM | April 24, 2020 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
135 | Yes | CMU1.5.3.8.2 | Auto Scheduled | ZONE T-2 กลาง | 15 days | 5 | 140,144 |  | 134FS+135 days,164FS+135 days | March 22, 2019 8:00 AM | April 5, 2019 5:00 PM | March 24, 2019 05:00 PM | April 07, 2019 05:00 PM | November 26, 2019 05:00 PM | December 10, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
136 | Yes | CMU1.5.3.8.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 15 days | 5 | 134FS+135 days |  |  | January 16, 2020 8:00 AM | January 30, 2020 5:00 PM | January 26, 2020 05:00 PM | February 09, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 245 days | Sanitary-Plumber
137 | Yes | CMU1.5.4 | Auto Scheduled | งานระบบสุขาภิบาล ชั้น 1 | 408 days | 3 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 278 days | 44 days
138 | Yes | CMU1.5.4.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 278 days | 44 days
139 | Yes | CMU1.5.4.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 140FS+15 days |  | 141FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 13, 2019 05:00 PM | August 16, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
140 | Yes | CMU1.5.4.1.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 36 |  | 139FS+15 days,144SS,135,167FS+15 days | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 16, 2018 05:00 PM | March 21, 2019 05:00 PM | January 03, 2019 05:00 PM | May 08, 2019 05:00 PM | As Soon As Possible |  | No | 44 days | 44 days | 0 days | Sanitary-Plumber
141 | Yes | CMU1.5.4.1.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 139FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 07, 2019 05:00 PM | January 10, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
142 | Yes | CMU1.5.4.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 278 days | 44 days
143 | Yes | CMU1.5.4.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 144FS+15 days |  | 145FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 13, 2019 05:00 PM | August 16, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
144 | Yes | CMU1.5.4.2.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 140SS |  | 143FS+15 days,135,169FS+15 days | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 16, 2018 05:00 PM | March 21, 2019 05:00 PM | January 03, 2019 05:00 PM | May 08, 2019 05:00 PM | As Soon As Possible |  | No | 44 days | 44 days | 0 days | Sanitary-Plumber
145 | Yes | CMU1.5.4.2.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 143FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 05, 2019 05:00 PM | January 08, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
146 | Yes | CMU1.5.5 | Auto Scheduled | งานระบบไฟฟ้า ชั้น 1 | 147 days | 3 |  |  |  | May 8, 2020 8:00 AM | October 1, 2020 5:00 PM | October 21, 2018 05:00 PM | March 16, 2019 05:00 PM | May 12, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 0 days | 0 days | 0 days
147 | Yes | CMU1.5.5.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 60 days | 4 | 149FS+7 days |  |  | August 3, 2020 8:00 AM | October 1, 2020 5:00 PM | August 08, 2020 05:00 PM | October 06, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Electrician
148 | Yes | CMU1.5.5.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 60 days | 4 | 149FS+7 days |  |  | August 3, 2020 8:00 AM | October 1, 2020 5:00 PM | August 08, 2020 05:00 PM | October 06, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Electrician
149 | Yes | CMU1.5.5.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 152SS+30 days |  | 148FS+7 days,147FS+7 days | May 8, 2020 8:00 AM | July 26, 2020 5:00 PM | May 13, 2020 05:00 PM | July 31, 2020 05:00 PM | May 12, 2020 05:00 PM | July 30, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Electrician
150 | Yes | CMU1.5.5.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 152SS+30 days |  |  | May 8, 2020 8:00 AM | July 26, 2020 5:00 PM | May 13, 2020 05:00 PM | July 31, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 67 days | 67 days | 67 days | Electrician
151 | Yes | CMU1.5.5.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 152SS+30 days |  |  | May 8, 2020 8:00 AM | July 26, 2020 5:00 PM | May 13, 2020 05:00 PM | July 31, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 67 days | 67 days | 67 days | Electrician
152 | Yes | CMU1.5.6 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้น 1 | 165 days | 3 | 123SS |  | 151SS+30 days,150SS+30 days,149SS+30 days,154SS,211FS-30 days,210FS-30 days,216FS-45 days,221FS-30 days,227FS-30 days,226FS-30 days,232FS-45 days,241FS-7 days,247FS-7 days | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 13, 2020 05:00 PM | September 24, 2020 05:00 PM | November 26, 2019 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Skilled carpenter
153 | Yes | CMU1.6 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้นใต้ดิน | 533 days | 2 |  |  |  | April 6, 2019 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | April 01, 2020 05:00 PM | April 22, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 12 days | 12 days
154 | Yes | CMU1.6.1 | Auto Scheduled | งานรื้อถอน ชั้นใต้ดิน (รื้อขนไป) | 30 days | 3 | 152SS |  | 155,158FS+45 days,159FS+45 days,177SS,176SS,175SS,174SS | April 8, 2020 8:00 AM | May 7, 2020 5:00 PM | April 13, 2020 05:00 PM | May 12, 2020 05:00 PM | November 26, 2019 05:00 PM | December 25, 2019 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
155 | Yes | CMU1.6.2 | Auto Scheduled | งานโครงสร้างวิศวกรรม ชั้นใต้ดิน | 75 days | 3 | 154 |  |  | May 8, 2020 8:00 AM | July 21, 2020 5:00 PM | May 15, 2020 05:00 PM | July 28, 2020 05:00 PM | July 23, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 72 days | 72 days | 72 days | General worker
156 | Yes | CMU1.6.3 | Auto Scheduled | งานสถาปัตยกรรม ชั้นใต้ดิน | 398 days | 3 |  |  |  | August 19, 2019 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | November 18, 2019 05:00 PM | September 04, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 320 days | 12 days | 12 days
157 | Yes | CMU1.6.3.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 158,160,161 |  |  | August 21, 2020 8:00 AM | September 19, 2020 5:00 PM | September 16, 2020 05:00 PM | October 15, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | Skilled carpenter
158 | Yes | CMU1.6.3.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 154FS+45 days |  | 157,162 | June 22, 2020 8:00 AM | August 20, 2020 5:00 PM | June 27, 2020 05:00 PM | August 25, 2020 05:00 PM | February 09, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
159 | Yes | CMU1.6.3.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 154FS+45 days |  | 160,161 | June 22, 2020 8:00 AM | July 21, 2020 5:00 PM | July 18, 2020 05:00 PM | August 16, 2020 05:00 PM | August 22, 2020 05:00 PM | September 20, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
160 | Yes | CMU1.6.3.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 159 |  | 157,162 | July 22, 2020 8:00 AM | August 20, 2020 5:00 PM | August 17, 2020 05:00 PM | September 15, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | Skilled carpenter
161 | Yes | CMU1.6.3.5 | Auto Scheduled | งานบันได | 30 days | 4 | 159 |  | 157,162 | July 22, 2020 8:00 AM | August 20, 2020 5:00 PM | August 17, 2020 05:00 PM | September 15, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
162 | Yes | CMU1.6.3.6 | Auto Scheduled | งานสี | 30 days | 4 | 158,160,161 |  |  | August 21, 2020 8:00 AM | September 19, 2020 5:00 PM | September 16, 2020 05:00 PM | October 15, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
163 | Yes | CMU1.6.3.7 | Auto Scheduled | งานสุขภัณฑ์ | 15 days | 4 |  |  |  | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | October 21, 2018 05:00 PM | November 04, 2018 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 395 days | 395 days | 395 days
164 | Yes | CMU1.6.3.7.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 135FS+135 days |  |  | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | August 27, 2019 05:00 PM | September 10, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 395 days | 395 days | 395 days | Sanitary-Plumber
165 | Yes | CMU1.6.4 | Auto Scheduled | งานระบบสุขาภิบาล ชั้นใต้ดิน | 501 days | 3 |  |  |  | April 6, 2019 8:00 AM | August 18, 2020 5:00 PM | October 17, 2018 05:00 PM | February 29, 2020 05:00 PM | May 24, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 44 days | 44 days
166 | Yes | CMU1.6.4.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 126 days | 4 |  |  |  | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | October 25, 2018 05:00 PM | February 27, 2019 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 419 days | 419 days | 419 days
167 | Yes | CMU1.6.4.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 140FS+15 days |  |  | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 14, 2019 05:00 PM | August 17, 2019 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 419 days | 419 days | 419 days | Sanitary-Plumber
168 | Yes | CMU1.6.4.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 126 days | 4 |  |  |  | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | October 22, 2018 05:00 PM | February 24, 2019 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 44 days | 44 days
169 | Yes | CMU1.6.4.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 144FS+15 days |  | 170FS+300 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 06, 2019 05:00 PM | August 09, 2019 05:00 PM | May 24, 2019 05:00 PM | September 26, 2019 05:00 PM | As Soon As Possible |  | No | 44 days | 44 days | 0 days | Sanitary-Plumber
170 | Yes | CMU1.6.4.3 | Auto Scheduled | งานระบบระบายน้ำฝน | 75 days | 4 | 169FS+300 days |  |  | June 5, 2020 8:00 AM | August 18, 2020 5:00 PM | June 05, 2020 05:00 PM | August 18, 2020 05:00 PM | July 23, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 44 days | 44 days | 44 days | Sanitary-Plumber
171 | Yes | CMU1.6.5 | Auto Scheduled | งานระบบไฟฟ้า ชั้นใต้ดิน | 147 days | 3 |  |  |  | April 8, 2020 8:00 AM | September 1, 2020 5:00 PM | October 23, 2018 05:00 PM | March 18, 2019 05:00 PM | May 12, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 30 days | 30 days | 30 days
172 | Yes | CMU1.6.5.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 60 days | 4 | 174FS+7 days |  |  | July 4, 2020 8:00 AM | September 1, 2020 5:00 PM | July 09, 2020 05:00 PM | September 06, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 30 days | 30 days | 30 days | Electrician
173 | Yes | CMU1.6.5.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 60 days | 4 | 174FS+7 days |  |  | July 4, 2020 8:00 AM | September 1, 2020 5:00 PM | July 09, 2020 05:00 PM | September 06, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 30 days | 30 days | 30 days | Electrician
174 | Yes | CMU1.6.5.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 154SS |  | 173FS+7 days,172FS+7 days | April 8, 2020 8:00 AM | June 26, 2020 5:00 PM | April 13, 2020 05:00 PM | July 01, 2020 05:00 PM | May 12, 2020 05:00 PM | July 30, 2020 05:00 PM | As Soon As Possible |  | No | 30 days | 30 days | 0 days | Electrician
175 | Yes | CMU1.6.5.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 154SS |  |  | April 8, 2020 8:00 AM | June 26, 2020 5:00 PM | April 16, 2020 05:00 PM | July 04, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 97 days | 97 days | 97 days | Electrician
176 | Yes | CMU1.6.5.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 154SS |  |  | April 8, 2020 8:00 AM | June 26, 2020 5:00 PM | April 18, 2020 05:00 PM | July 06, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 97 days | 97 days | 97 days | Electrician
177 | Yes | CMU1.6.6 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้นใต้ดิน | 165 days | 3 | 154SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 13, 2020 05:00 PM | September 24, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | Skilled carpenter
178 | Yes | CMU1.7 | Auto Scheduled | หมวดงานระบบคอมพิวเตอร์และแจ้งเหตุเพลิงไหม้ | 670 days | 2 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
179 | Yes | CMU1.7.1 | Auto Scheduled | งานระบบคอมพิวเตอร์ | 670 days | 3 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
180 | Yes | CMU1.7.1.1 | Auto Scheduled | ชั้นที่ 4 | 160 days | 4 | 36FS+14 days |  | 181 | November 30, 2018 8:00 AM | May 8, 2019 5:00 PM | November 30, 2018 05:00 PM | May 08, 2019 05:00 PM | April 24, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
181 | Yes | CMU1.7.1.2 | Auto Scheduled | ชั้นที่ 3 | 175 days | 4 | 180 | 182 | 182 | May 9, 2019 8:00 AM | October 30, 2019 5:00 PM | May 09, 2019 05:00 PM | October 30, 2019 05:00 PM | April 09, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
182 | Yes | CMU1.7.1.3 | Auto Scheduled | ชั้นที่ 2 | 175 days | 4 | 181 | 183 | 183,184 | October 31, 2019 8:00 AM | April 22, 2020 5:00 PM | October 31, 2019 05:00 PM | April 22, 2020 05:00 PM | April 09, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
183 | Yes | CMU1.7.1.4 | Auto Scheduled | ชั้นที่ 1 | 160 days | 4 | 182 | 180 |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 23, 2020 05:00 PM | September 29, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
184 | Yes | CMU1.7.1.5 | Auto Scheduled | ชั้นใต้ดิน | 160 days | 4 | 182 | 183SS |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 23, 2020 05:00 PM | September 29, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
185 | Yes | CMU1.7.2 | Auto Scheduled | ระบบแจ้งเหตุเพลิงไหม้ | 670 days | 3 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
186 | Yes | CMU1.7.2.1 | Auto Scheduled | ชั้นที่ 4 | 160 days | 4 | 36FS+14 days |  | 187 | November 30, 2018 8:00 AM | May 8, 2019 5:00 PM | November 30, 2018 05:00 PM | May 08, 2019 05:00 PM | April 24, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
187 | Yes | CMU1.7.2.2 | Auto Scheduled | ชั้นที่ 3 | 175 days | 4 | 186 | 188 | 188 | May 9, 2019 8:00 AM | October 30, 2019 5:00 PM | May 09, 2019 05:00 PM | October 30, 2019 05:00 PM | April 09, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
188 | Yes | CMU1.7.2.3 | Auto Scheduled | ชั้นที่ 2 | 175 days | 4 | 187 | 189 | 189,190 | October 31, 2019 8:00 AM | April 22, 2020 5:00 PM | October 31, 2019 05:00 PM | April 22, 2020 05:00 PM | April 09, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
189 | Yes | CMU1.7.2.4 | Auto Scheduled | ชั้นที่ 1 | 160 days | 4 | 188 | 186 |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 23, 2020 05:00 PM | September 29, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
190 | Yes | CMU1.7.2.5 | Auto Scheduled | ชั้นใต้ดิน | 160 days | 4 | 188 | 189SS |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 23, 2020 05:00 PM | September 29, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
191 | Yes | CMU1.8 | Auto Scheduled | หมวดงานสีภายนอก งานซ่อมแซมและตกแต่งภายนอกอาคาร | 660 days | 2 |  |  |  | November 30, 2018 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | August 06, 2020 05:00 PM | December 16, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 507 days | 12 days | 12 days
192 | Yes | CMU1.8.1 | Auto Scheduled | งานสีภายนอกและงานซ่อมแซมพื้นผิวภายนอกอาคาร | 660 days | 3 |  |  |  | November 30, 2018 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | August 06, 2020 05:00 PM | December 16, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 507 days | 12 days | 12 days
193 | Yes | CMU1.8.1.1 | Auto Scheduled | งานขัดลอกสีทาผนังเดิม | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 13, 2020 05:00 PM | September 24, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
194 | Yes | CMU1.8.1.2 | Auto Scheduled | น้ำยาทาปูนเก่า (สีรองพื้น) | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 13, 2020 05:00 PM | September 24, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
195 | Yes | CMU1.8.1.3 | Auto Scheduled | งานทาสีภายนอก (ทา 2 เที่ยว) ไม่รวมชั้นใต้ดิน | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 13, 2020 05:00 PM | September 24, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
196 | Yes | CMU1.8.1.4 | Auto Scheduled | งานทำความสะอาดและซ่อมแซมผนังกรุอิฐโชว์แนว (อ้างอิงราคางานขัดลอกสี) | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 13, 2020 05:00 PM | September 24, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
197 | Yes | CMU1.8.1.5 | Auto Scheduled | น้ำยาเคลือบผิวผนังอิฐโชว์แนว (อ้างอิงค่าทาน้ำยากันเชื้อรา) | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 13, 2020 05:00 PM | September 24, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
198 | Yes | CMU1.8.1.6 | Auto Scheduled | งานรื้อถอนแผ่นวัสดุกันซึมหลังคาดาดฟ้า (รื้อขนไป) | 90 days | 4 | 36FS+14 days |  |  | November 30, 2018 8:00 AM | February 27, 2019 5:00 PM | December 04, 2018 05:00 PM | March 03, 2019 05:00 PM | July 08, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 582 days | 582 days | 582 days | General worker
199 | Yes | CMU1.8.1.7 | Auto Scheduled | งานแผ่นวัสดุกันซึมแบบเป่าไฟผิวทราย | 90 days | 4 | 36FS+14 days |  |  | November 30, 2018 8:00 AM | February 27, 2019 5:00 PM | December 04, 2018 05:00 PM | March 03, 2019 05:00 PM | July 08, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 582 days | 582 days | 582 days | General worker
200 | Yes | CMU1.8.1.8 | Auto Scheduled | งานกันซึมชนิด Polyurethane สูตรน้ำมัน ชนิดยืดหยุ่นสูงเป็นพิเศษ | 90 days | 4 | 36FS+14 days |  |  | November 30, 2018 8:00 AM | February 27, 2019 5:00 PM | December 03, 2018 05:00 PM | March 02, 2019 05:00 PM | July 08, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 582 days | 582 days | 582 days | General worker
201 | Yes | CMU1.8.2 | Auto Scheduled | งานตกแต่งภายนอกอาคาร | 165 days | 3 |  |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | October 20, 2018 05:00 PM | April 02, 2019 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 12 days | 12 days | 12 days
202 | Yes | CMU1.8.2.1 | Auto Scheduled | ตะแกรงเหล็กฉีกกันนก XS-32 | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 13, 2020 05:00 PM | September 24, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
203 | Yes | CMU1.9 | Auto Scheduled | หมวดงานบริเวณ | 165 days | 2 |  |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | October 23, 2018 05:00 PM | April 05, 2019 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 12 days | 12 days | 12 days
204 | Yes | CMU1.9.1 | Auto Scheduled | งานรื้อถอน งานบริเวณ | 165 days | 3 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 13, 2020 05:00 PM | September 24, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
205 | Yes | CMU1.9.2 | Auto Scheduled | งานโครงสร้างวิศวกรรม งานบริเวณ | 165 days | 3 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 13, 2020 05:00 PM | September 24, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
206 | Yes | CMU1.9.3 | Auto Scheduled | งานสถาปัตยกรรม งานบริเวณ | 165 days | 3 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 13, 2020 05:00 PM | September 24, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
207 | Yes | CMU1.9.4 | Auto Scheduled | งานระบบไฟฟ้า งานบริเวณ | 165 days | 3 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 13, 2020 05:00 PM | September 24, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | Electrician
208 | Yes | CMU1.10 | Auto Scheduled | หมวดงานครุภัณฑ์จัดซื้อ | 670 days | 2 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
209 | Yes | CMU1.10.1 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัว | 510 days | 3 |  |  |  | April 14, 2019 8:00 AM | September 4, 2020 5:00 PM | October 17, 2018 05:00 PM | March 09, 2020 05:00 PM | May 15, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 522 days | 27 days | 27 days
210 | Yes | CMU1.10.1.1 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้นใต้ดิน | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | August 30, 2020 05:00 PM | September 13, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
211 | Yes | CMU1.10.1.2 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้น 1 | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | September 11, 2020 05:00 PM | September 25, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
212 | Yes | CMU1.10.1.3 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้น 2 | 15 days | 4 | 121FS-15 days |  |  | March 24, 2020 8:00 AM | April 7, 2020 5:00 PM | March 31, 2020 05:00 PM | April 14, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Skilled carpenter
213 | Yes | CMU1.10.1.4 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้น 3 | 15 days | 4 | 92FS-15 days |  |  | September 26, 2019 8:00 AM | October 10, 2019 5:00 PM | October 06, 2019 05:00 PM | October 20, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Skilled carpenter
214 | Yes | CMU1.10.1.5 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้น 4 | 15 days | 4 | 63 |  |  | April 14, 2019 8:00 AM | April 28, 2019 5:00 PM | April 27, 2019 05:00 PM | May 11, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 522 days | 522 days | 522 days | Skilled carpenter
215 | Yes | CMU1.10.2 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ | 525 days | 3 |  |  |  | March 30, 2019 8:00 AM | September 4, 2020 5:00 PM | October 17, 2018 05:00 PM | March 24, 2020 05:00 PM | April 30, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 522 days | 27 days | 27 days
216 | Yes | CMU1.10.2.1 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ ชั้น 1 | 30 days | 4 | 152FS-45 days |  |  | August 6, 2020 8:00 AM | September 4, 2020 5:00 PM | August 17, 2020 05:00 PM | September 15, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
217 | Yes | CMU1.10.2.2 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ ชั้น 2 | 30 days | 4 | 121FS-30 days |  |  | March 9, 2020 8:00 AM | April 7, 2020 5:00 PM | March 17, 2020 05:00 PM | April 15, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Skilled carpenter
218 | Yes | CMU1.10.2.3 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ ชั้น 3 | 30 days | 4 | 92FS-30 days |  |  | September 11, 2019 8:00 AM | October 10, 2019 5:00 PM | September 20, 2019 05:00 PM | October 19, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Skilled carpenter
219 | Yes | CMU1.10.2.4 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ ชั้น 4 | 30 days | 4 | 63FS-15 days |  |  | March 30, 2019 8:00 AM | April 28, 2019 5:00 PM | April 02, 2019 05:00 PM | May 01, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 522 days | 522 days | 522 days | Skilled carpenter
220 | Yes | CMU1.10.3 | Auto Scheduled | งานผ้าม่าน | 510 days | 3 |  |  |  | April 14, 2019 8:00 AM | September 4, 2020 5:00 PM | October 17, 2018 05:00 PM | March 09, 2020 05:00 PM | May 15, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 522 days | 27 days | 27 days
221 | Yes | CMU1.10.3.1 | Auto Scheduled | งานผ้าม่าน ชั้น 1 | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | September 01, 2020 05:00 PM | September 15, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
222 | Yes | CMU1.10.3.2 | Auto Scheduled | งานผ้าม่าน ชั้น 2 | 15 days | 4 | 121FS-15 days |  |  | March 24, 2020 8:00 AM | April 7, 2020 5:00 PM | April 01, 2020 05:00 PM | April 15, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Skilled carpenter
223 | Yes | CMU1.10.3.3 | Auto Scheduled | งานผ้าม่าน ชั้น 3 | 15 days | 4 | 92FS-15 days |  |  | September 26, 2019 8:00 AM | October 10, 2019 5:00 PM | October 05, 2019 05:00 PM | October 19, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Skilled carpenter
224 | Yes | CMU1.10.3.4 | Auto Scheduled | งานผ้าม่าน ชั้น 4 | 15 days | 4 | 63 |  |  | April 14, 2019 8:00 AM | April 28, 2019 5:00 PM | April 25, 2019 05:00 PM | May 09, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 522 days | 522 days | 522 days | Skilled carpenter
225 | Yes | CMU1.10.4 | Auto Scheduled | งานป้าย | 510 days | 3 |  |  |  | April 14, 2019 8:00 AM | September 4, 2020 5:00 PM | October 17, 2018 05:00 PM | March 09, 2020 05:00 PM | May 15, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 522 days | 27 days | 27 days
226 | Yes | CMU1.10.4.1 | Auto Scheduled | งานป้าย ชั้นใต้ดิน | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | August 30, 2020 05:00 PM | September 13, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
227 | Yes | CMU1.10.4.2 | Auto Scheduled | งานป้าย ชั้น 1 | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | September 02, 2020 05:00 PM | September 16, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
228 | Yes | CMU1.10.4.3 | Auto Scheduled | งานป้าย ชั้น 2 | 15 days | 4 | 121FS-15 days |  |  | March 24, 2020 8:00 AM | April 7, 2020 5:00 PM | April 01, 2020 05:00 PM | April 15, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Skilled carpenter
229 | Yes | CMU1.10.4.4 | Auto Scheduled | งานป้าย ชั้น 3 | 15 days | 4 | 92FS-15 days |  |  | September 26, 2019 8:00 AM | October 10, 2019 5:00 PM | October 06, 2019 05:00 PM | October 20, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Skilled carpenter
230 | Yes | CMU1.10.4.5 | Auto Scheduled | งานป้าย ชั้น 4 | 15 days | 4 | 63 |  |  | April 14, 2019 8:00 AM | April 28, 2019 5:00 PM | April 20, 2019 05:00 PM | May 04, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 522 days | 522 days | 522 days | Skilled carpenter
231 | Yes | CMU1.10.5 | Auto Scheduled | งานอื่นๆ | 15 days | 3 |  |  |  | August 6, 2020 8:00 AM | August 20, 2020 5:00 PM | October 20, 2018 05:00 PM | November 03, 2018 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 42 days | 42 days | 42 days
232 | Yes | CMU1.10.5.1 | Auto Scheduled | ตู้อลูมิเนียมพับขึ้นรูป พ่นสี ครอบตู้กดน้ำ | 15 days | 4 | 152FS-45 days |  |  | August 6, 2020 8:00 AM | August 20, 2020 5:00 PM | August 16, 2020 05:00 PM | August 30, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 42 days | 42 days | 42 days | General worker
233 | Yes | CMU1.10.6 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ | 670 days | 3 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
234 | Yes | CMU1.10.6.1 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้นใต้ดิน | 160 days | 4 | 236 |  |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
235 | Yes | CMU1.10.6.2 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้น 1 | 160 days | 4 | 236 |  |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
236 | Yes | CMU1.10.6.3 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้น 2 | 175 days | 4 | 237 |  | 235,234 | October 31, 2019 8:00 AM | April 22, 2020 5:00 PM | November 06, 2019 05:00 PM | April 28, 2020 05:00 PM | March 12, 2020 05:00 PM | September 02, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
237 | Yes | CMU1.10.6.4 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้น 3 | 175 days | 4 | 238 |  | 236 | May 9, 2019 8:00 AM | October 30, 2019 5:00 PM | May 15, 2019 05:00 PM | November 05, 2019 05:00 PM | March 12, 2020 05:00 PM | September 02, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
238 | Yes | CMU1.10.6.5 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้น 4 | 160 days | 4 | 36FS+14 days |  | 237 | November 30, 2018 8:00 AM | May 8, 2019 5:00 PM | December 03, 2018 05:00 PM | May 11, 2019 05:00 PM | March 27, 2020 05:00 PM | September 02, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
239 | Yes | CMU1.10.7 | Auto Scheduled | งานระบบเครื่องเสียงประกาศ (ใช้ลำโพงของเดิม) | 539 days | 3 |  |  |  | April 7, 2019 8:00 AM | September 26, 2020 5:00 PM | October 17, 2018 05:00 PM | April 07, 2020 05:00 PM | April 16, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 530 days | 5 days | 5 days
240 | Yes | CMU1.10.7.1 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้นใต้ดิน | 7 days | 4 | 241 |  |  | September 20, 2020 8:00 AM | September 26, 2020 5:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 5 days | 5 days | 5 days | Electrician
241 | Yes | CMU1.10.7.2 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้น 1 | 7 days | 4 | 152FS-7 days |  | 240 | September 13, 2020 8:00 AM | September 19, 2020 5:00 PM | September 18, 2020 05:00 PM | September 24, 2020 05:00 PM | September 09, 2020 05:00 PM | September 15, 2020 05:00 PM | As Soon As Possible |  | No | 5 days | 5 days | 0 days | Electrician
242 | Yes | CMU1.10.7.3 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้น 2 | 7 days | 4 | 121FS-7 days |  |  | April 1, 2020 8:00 AM | April 7, 2020 5:00 PM | April 08, 2020 05:00 PM | April 14, 2020 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Electrician
243 | Yes | CMU1.10.7.4 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้น 3 | 7 days | 4 | 92FS-7 days |  |  | October 4, 2019 8:00 AM | October 10, 2019 5:00 PM | October 13, 2019 05:00 PM | October 19, 2019 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Electrician
244 | Yes | CMU1.10.7.5 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้น 4 | 7 days | 4 | 63FS-7 days |  |  | April 7, 2019 8:00 AM | April 13, 2019 5:00 PM | April 14, 2019 05:00 PM | April 20, 2019 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 537 days | 537 days | 537 days | Electrician
245 | Yes | CMU1.10.8 | Auto Scheduled | งานระบบกล้องวงจรปิด (ใช้กล้องวงจรปิดของเดิม) | 539 days | 3 |  |  |  | April 7, 2019 8:00 AM | September 26, 2020 5:00 PM | October 17, 2018 05:00 PM | April 07, 2020 05:00 PM | April 16, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 530 days | 5 days | 5 days
246 | Yes | CMU1.10.8.1 | Auto Scheduled | งานกล้องวงจรปิด ชั้นใต้ดิน | 7 days | 4 | 247 |  |  | September 20, 2020 8:00 AM | September 26, 2020 5:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 5 days | 5 days | 5 days | Electrician
247 | Yes | CMU1.10.8.2 | Auto Scheduled | งานกล้องวงจรปิด ชั้น 1 | 7 days | 4 | 152FS-7 days |  | 246 | September 13, 2020 8:00 AM | September 19, 2020 5:00 PM | September 18, 2020 05:00 PM | September 24, 2020 05:00 PM | September 09, 2020 05:00 PM | September 15, 2020 05:00 PM | As Soon As Possible |  | No | 5 days | 5 days | 0 days | Electrician
248 | Yes | CMU1.10.8.3 | Auto Scheduled | งานกล้องวงจรปิด ชั้น 2 | 7 days | 4 | 121FS-7 days |  |  | April 1, 2020 8:00 AM | April 7, 2020 5:00 PM | April 10, 2020 05:00 PM | April 16, 2020 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Electrician
249 | Yes | CMU1.10.8.4 | Auto Scheduled | งานกล้องวงจรปิด ชั้น 3 | 7 days | 4 | 92FS-7 days |  |  | October 4, 2019 8:00 AM | October 10, 2019 5:00 PM | October 16, 2019 05:00 PM | October 22, 2019 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Electrician
250 | Yes | CMU1.10.8.5 | Auto Scheduled | งานกล้องวงจรปิด ชั้น 4 | 7 days | 4 | 63FS-7 days |  |  | April 7, 2019 8:00 AM | April 13, 2019 5:00 PM | April 12, 2019 05:00 PM | April 18, 2019 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 537 days | 537 days | 537 days | Electrician

## solutoion_15
ID | Active | WBS | Task_Mode | Name | Duration | Outline_Level | Predecessors | Predecessors2 | Successors | Start_Date | Finish_Date | Early_Start | Early_Finish | Late_Start | Late_Finish | Constraint_Type | Constraint_Date | Summary | Start_Slack | Finish_Slack | Free_Slack | Resource_Names
1 | Yes | CMU1 | Auto Scheduled | โครงการปรับปรุงสำนักหอสมุด มหาวิทยาลัยเชียงใหม่ | 716 days | 1 |  |  |  | October 17, 2018 8:00 AM | October 1, 2020 5:00 PM | October 17, 2018 05:00 PM | October 01, 2020 05:00 PM | October 21, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 0 days | 0 days | 0 days
2 | Yes | CMU1.1 | Auto Scheduled | หมวดเตรียมการ | 675 days | 2 |  |  |  | October 17, 2018 8:00 AM | August 21, 2020 5:00 PM | October 17, 2018 05:00 PM | August 21, 2020 05:00 PM | December 01, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 41 days | 41 days | 41 days
3 | Yes | CMU1.1.1 | Auto Scheduled | งานอาคารสนามและผังบริเวณโครงการ | 14 days | 3 | 4FS-7 days |  |  | October 26, 2018 8:00 AM | November 8, 2018 5:00 PM | November 01, 2018 05:00 PM | November 14, 2018 05:00 PM | September 22, 2020 05:00 PM | October 05, 2020 05:00 PM | Start No Earlier Than | Oct 24 '18 | No | 693 days | 693 days | 693 days | Engineer
4 | Yes | CMU1.1.2 | Auto Scheduled | งานเชื่อมต่อระบบสาธารณูปโภคโครงการ | 16 days | 3 |  |  | 3FS-7 days | October 17, 2018 8:00 AM | November 1, 2018 5:00 PM | October 19, 2018 05:00 PM | November 03, 2018 05:00 PM | September 13, 2020 05:00 PM | September 28, 2020 05:00 PM | As Soon As Possible |  | No | 693 days | 693 days | 0 days | Engineer
5 | Yes | CMU1.1.3 | Auto Scheduled | งานตรวจทดสอบระบบภายในอาคารก่อนดำเนินการปรับปรุง | 675 days | 3 |  |  |  | October 17, 2018 8:00 AM | August 21, 2020 5:00 PM | October 17, 2018 05:00 PM | August 21, 2020 05:00 PM | December 01, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 41 days | 41 days | 41 days
6 | Yes | CMU1.1.3.1 | Auto Scheduled | ชั้นที่ 4 | 15 days | 4 |  |  | 7FS+150 days | October 17, 2018 8:00 AM | October 31, 2018 5:00 PM | October 19, 2018 05:00 PM | November 02, 2018 05:00 PM | December 01, 2018 05:00 PM | December 15, 2018 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
7 | Yes | CMU1.1.3.2 | Auto Scheduled | ชั้นที่ 3 | 15 days | 4 | 6FS+150 days |  | 8FS+150 days | March 31, 2019 8:00 AM | April 14, 2019 5:00 PM | April 07, 2019 05:00 PM | April 21, 2019 05:00 PM | May 15, 2019 05:00 PM | May 29, 2019 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
8 | Yes | CMU1.1.3.3 | Auto Scheduled | ชั้นที่ 2 | 15 days | 4 | 7FS+150 days |  | 9FS+150 days | September 12, 2019 8:00 AM | September 26, 2019 5:00 PM | September 28, 2019 05:00 PM | October 12, 2019 05:00 PM | October 27, 2019 05:00 PM | November 10, 2019 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
9 | Yes | CMU1.1.3.4 | Auto Scheduled | ชั้นที่ 1 | 15 days | 4 | 8FS+150 days |  | 10FS+150 days | February 24, 2020 8:00 AM | March 9, 2020 5:00 PM | March 19, 2020 05:00 PM | April 02, 2020 05:00 PM | April 09, 2020 05:00 PM | April 23, 2020 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
10 | Yes | CMU1.1.3.5 | Auto Scheduled | ชั้นใต้ดินและภายนอก | 15 days | 4 | 9FS+150 days |  |  | August 7, 2020 8:00 AM | August 21, 2020 5:00 PM | September 10, 2020 05:00 PM | September 24, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 41 days | Engineer
11 | Yes | CMU1.1.4 | Auto Scheduled | งานสำรวจอุปกรณ์ไฟฟ้า, สุขภัณฑ์และครุภัณฑ์ (ของเดิม) ก่อนดำเนินการปรับปรุง | 675 days | 3 |  |  |  | October 17, 2018 8:00 AM | August 21, 2020 5:00 PM | October 17, 2018 05:00 PM | August 21, 2020 05:00 PM | December 01, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 41 days | 41 days | 41 days
12 | Yes | CMU1.1.4.1 | Auto Scheduled | ชั้นที่ 4 | 15 days | 4 |  |  | 13FS+150 days | October 17, 2018 8:00 AM | October 31, 2018 5:00 PM | October 20, 2018 05:00 PM | November 03, 2018 05:00 PM | December 01, 2018 05:00 PM | December 15, 2018 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
13 | Yes | CMU1.1.4.2 | Auto Scheduled | ชั้นที่ 3 | 15 days | 4 | 12FS+150 days |  | 14FS+150 days | March 31, 2019 8:00 AM | April 14, 2019 5:00 PM | April 06, 2019 05:00 PM | April 20, 2019 05:00 PM | May 15, 2019 05:00 PM | May 29, 2019 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
14 | Yes | CMU1.1.4.3 | Auto Scheduled | ชั้นที่ 2 | 15 days | 4 | 13FS+150 days |  | 15FS+150 days | September 12, 2019 8:00 AM | September 26, 2019 5:00 PM | September 24, 2019 05:00 PM | October 08, 2019 05:00 PM | October 27, 2019 05:00 PM | November 10, 2019 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
15 | Yes | CMU1.1.4.4 | Auto Scheduled | ชั้นที่ 1 | 15 days | 4 | 14FS+150 days |  | 16FS+150 days | February 24, 2020 8:00 AM | March 9, 2020 5:00 PM | March 11, 2020 05:00 PM | March 25, 2020 05:00 PM | April 09, 2020 05:00 PM | April 23, 2020 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
16 | Yes | CMU1.1.4.5 | Auto Scheduled | ชั้นใต้ดินและภายนอก | 15 days | 4 | 15FS+150 days |  |  | August 7, 2020 8:00 AM | August 21, 2020 5:00 PM | August 30, 2020 05:00 PM | September 13, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 41 days | Engineer
17 | Yes | CMU1.1.5 | Auto Scheduled | งานเอกสารขออนุมัติใช้วัสดุ, Shop Drawing และครุภัณฑ์ของโครงการ | 106 days | 3 |  |  |  | October 17, 2018 8:00 AM | January 30, 2019 5:00 PM | October 22, 2018 05:00 PM | February 04, 2019 05:00 PM | June 22, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 610 days | 610 days | 610 days
18 | Yes | CMU1.1.5.1 | Auto Scheduled | แบบ Shop Drawing ชั้นที่ 4 | 20 days | 4 |  |  | 19,25SS+14 days,26SS+14 days | October 17, 2018 8:00 AM | November 5, 2018 5:00 PM | October 17, 2018 05:00 PM | November 05, 2018 05:00 PM | October 01, 2018 05:00 PM | October 20, 2018 05:00 PM | As Soon As Possible |  | No | 610 days | 610 days | 0 days | Engineer
19 | Yes | CMU1.1.5.2 | Auto Scheduled | แบบ Shop Drawing ชั้นที่ 3 | 20 days | 4 | 18 |  | 20FS-7 days | November 6, 2018 8:00 AM | November 25, 2018 5:00 PM | November 13, 2018 05:00 PM | December 02, 2018 05:00 PM | July 13, 2020 05:00 PM | August 01, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
20 | Yes | CMU1.1.5.3 | Auto Scheduled | แบบ Shop Drawing ชั้นที่ 2 | 20 days | 4 | 19FS-7 days |  | 21FS-7 days | November 19, 2018 8:00 AM | December 8, 2018 5:00 PM | November 29, 2018 05:00 PM | December 18, 2018 05:00 PM | July 26, 2020 05:00 PM | August 14, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
21 | Yes | CMU1.1.5.4 | Auto Scheduled | แบบ Shop Drawing ชั้นที่ 1 | 20 days | 4 | 20FS-7 days |  | 22FS-7 days | December 2, 2018 8:00 AM | December 21, 2018 5:00 PM | December 18, 2018 05:00 PM | January 06, 2019 05:00 PM | August 08, 2020 05:00 PM | August 27, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
22 | Yes | CMU1.1.5.5 | Auto Scheduled | แบบ Shop Drawing ชั้นใต้ดิน | 20 days | 4 | 21FS-7 days |  | 23FS-7 days | December 15, 2018 8:00 AM | January 3, 2019 5:00 PM | January 06, 2019 05:00 PM | January 25, 2019 05:00 PM | August 21, 2020 05:00 PM | September 09, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
23 | Yes | CMU1.1.5.6 | Auto Scheduled | แบบ Shop Drawing ภายนอกอาคาร | 20 days | 4 | 22FS-7 days |  | 24FS-7 days | December 28, 2018 8:00 AM | January 16, 2019 5:00 PM | January 23, 2019 05:00 PM | February 11, 2019 05:00 PM | September 03, 2020 05:00 PM | September 22, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
24 | Yes | CMU1.1.5.7 | Auto Scheduled | แบบ Shop Drawing landscape | 20 days | 4 | 23FS-7 days |  |  | January 10, 2019 8:00 AM | January 29, 2019 5:00 PM | February 12, 2019 05:00 PM | March 03, 2019 05:00 PM | September 16, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 611 days | Engineer
25 | Yes | CMU1.1.5.8 | Auto Scheduled | แบบ Shop Drawing งานปรับปรุง ครุภัณฑ์ | 92 days | 4 | 18SS+14 days |  |  | October 31, 2018 8:00 AM | January 30, 2019 5:00 PM | November 07, 2018 05:00 PM | February 06, 2019 05:00 PM | July 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 610 days | 610 days | 610 days | Engineer
26 | Yes | CMU1.1.5.9 | Auto Scheduled | แบบ Shop Drawing งานจัดซื้อครุภัณฑ์ | 92 days | 4 | 18SS+14 days |  |  | October 31, 2018 8:00 AM | January 30, 2019 5:00 PM | November 07, 2018 05:00 PM | February 06, 2019 05:00 PM | July 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 610 days | 610 days | 610 days | Engineer
27 | Yes | CMU1.1.6 | Auto Scheduled | งานตรวจทดสอบระบบ, งานอบรมผู้ใช้อาคาร และ As-Built Drawing | 30 days | 3 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 22, 2018 05:00 PM | November 20, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 686 days | 686 days | 686 days
28 | Yes | CMU1.1.6.1 | Auto Scheduled | ชั้นที่ 4 | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 27, 2018 05:00 PM | November 25, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
29 | Yes | CMU1.1.6.2 | Auto Scheduled | ชั้นที่ 3 | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 24, 2018 05:00 PM | November 22, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
30 | Yes | CMU1.1.6.3 | Auto Scheduled | ชั้นที่ 2 | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 22, 2018 05:00 PM | November 20, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
31 | Yes | CMU1.1.6.4 | Auto Scheduled | ชั้นที่ 1 | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 29, 2018 05:00 PM | November 27, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
32 | Yes | CMU1.1.6.5 | Auto Scheduled | ชั้นใต้ดิน | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 24, 2018 05:00 PM | November 22, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
33 | Yes | CMU1.1.6.6 | Auto Scheduled | ทั้งอาคาร | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 23, 2018 05:00 PM | November 21, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
34 | Yes | CMU1.1.7 | Auto Scheduled | งานบริหารงานก่อสร้างและงานอื่น ๆ | 0 days | 3 |  |  |  | October 17, 2018 8:00 AM | October 17, 2018 8:00 AM | October 20, 2018 05:00 PM | October 19, 2018 05:00 PM | October 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 716 days | 716 days | 716 days | Engineer
35 | Yes | CMU1.2 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้น 4 | 471 days | 2 |  |  |  | October 17, 2018 8:00 AM | January 30, 2020 5:00 PM | October 17, 2018 05:00 PM | January 30, 2020 05:00 PM | June 23, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 0 days | 245 days | 0 days
36 | Yes | CMU1.2.1 | Auto Scheduled | งานรื้อถอน ชั้น 4 (รื้อขนไป) | 30 days | 3 |  |  | 39FS+45 days,40FS+45 days,51,63SS+14 days,80,109,140,180FS+14 days,186FS+14 days,198FS+14 days,199FS+14 days,200FS+14 days,238FS+14 days | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 17, 2018 05:00 PM | November 15, 2018 05:00 PM | March 11, 2018 05:00 PM | April 09, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | General worker
37 | Yes | CMU1.2.2 | Auto Scheduled | งานสถาปัตยกรรม ชั้น 4 | 396 days | 3 |  |  |  | December 31, 2018 8:00 AM | January 30, 2020 5:00 PM | October 17, 2018 05:00 PM | November 16, 2019 05:00 PM | September 06, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 326 days | 245 days | 245 days
38 | Yes | CMU1.2.2.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 39,41,42 |  |  | March 1, 2019 8:00 AM | March 30, 2019 5:00 PM | March 13, 2019 05:00 PM | April 11, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 551 days | Skilled carpenter
39 | Yes | CMU1.2.2.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 36FS+45 days |  | 38,43 | December 31, 2018 8:00 AM | February 28, 2019 5:00 PM | January 05, 2019 05:00 PM | March 05, 2019 05:00 PM | July 15, 2020 05:00 PM | September 12, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 0 days | General worker
40 | Yes | CMU1.2.2.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 36FS+45 days |  | 41,42 | December 31, 2018 8:00 AM | January 29, 2019 5:00 PM | January 03, 2019 05:00 PM | February 01, 2019 05:00 PM | August 14, 2020 05:00 PM | September 12, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 0 days | General worker
41 | Yes | CMU1.2.2.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 40 |  | 38,43 | January 30, 2019 8:00 AM | February 28, 2019 5:00 PM | February 05, 2019 05:00 PM | March 06, 2019 05:00 PM | August 14, 2020 05:00 PM | September 12, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 0 days | Skilled carpenter
42 | Yes | CMU1.2.2.5 | Auto Scheduled | งานบันได | 30 days | 4 | 40 |  | 38,43 | January 30, 2019 8:00 AM | February 28, 2019 5:00 PM | February 05, 2019 05:00 PM | March 06, 2019 05:00 PM | August 14, 2020 05:00 PM | September 12, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 0 days | General worker
43 | Yes | CMU1.2.2.6 | Auto Scheduled | งานสี | 30 days | 4 | 39,41,42 |  |  | March 1, 2019 8:00 AM | March 30, 2019 5:00 PM | March 10, 2019 05:00 PM | April 08, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 551 days | General worker
44 | Yes | CMU1.2.2.7 | Auto Scheduled | งานสุขภัณฑ์ | 315 days | 4 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 20, 2018 05:00 PM | August 30, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
45 | Yes | CMU1.2.2.7.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 46FS+135 days |  | 47FS+135 days | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | September 11, 2019 05:00 PM | September 25, 2019 05:00 PM | April 24, 2020 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
46 | Yes | CMU1.2.2.7.2 | Auto Scheduled | ZONE T-2 กลาง | 15 days | 5 | 51,55 |  | 45FS+135 days | March 22, 2019 8:00 AM | April 5, 2019 5:00 PM | April 08, 2019 05:00 PM | April 22, 2019 05:00 PM | November 26, 2019 05:00 PM | December 10, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
47 | Yes | CMU1.2.2.7.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 15 days | 5 | 45FS+135 days |  |  | January 16, 2020 8:00 AM | January 30, 2020 5:00 PM | February 15, 2020 05:00 PM | February 29, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 245 days | Sanitary-Plumber
48 | Yes | CMU1.2.3 | Auto Scheduled | งานระบบสุขาภิบาล ชั้น 4 | 408 days | 3 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
49 | Yes | CMU1.2.3.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
50 | Yes | CMU1.2.3.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 51FS+15 days |  | 52FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 17, 2019 05:00 PM | August 20, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
51 | Yes | CMU1.2.3.1.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 36 |  | 50FS+15 days,46,55SS | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 23, 2018 05:00 PM | March 28, 2019 05:00 PM | August 25, 2019 05:00 PM | December 28, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
52 | Yes | CMU1.2.3.1.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 50FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 09, 2019 05:00 PM | January 12, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
53 | Yes | CMU1.2.3.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
54 | Yes | CMU1.2.3.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 55FS+15 days |  | 56FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 25, 2019 05:00 PM | August 28, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
55 | Yes | CMU1.2.3.2.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 51SS |  | 54FS+15 days,46 | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 28, 2018 05:00 PM | April 02, 2019 05:00 PM | August 25, 2019 05:00 PM | December 28, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
56 | Yes | CMU1.2.3.2.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 54FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 24, 2019 05:00 PM | January 27, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
57 | Yes | CMU1.2.4 | Auto Scheduled | งานระบบไฟฟ้า ชั้น 4 | 117 days | 3 |  |  |  | November 30, 2018 8:00 AM | March 26, 2019 5:00 PM | October 21, 2018 05:00 PM | February 14, 2019 05:00 PM | June 11, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 555 days | 555 days | 555 days
58 | Yes | CMU1.2.4.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 30 days | 4 | 60FS+7 days |  |  | February 25, 2019 8:00 AM | March 26, 2019 5:00 PM | March 03, 2019 05:00 PM | April 01, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 555 days | 555 days | 555 days | Electrician
59 | Yes | CMU1.2.4.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 30 days | 4 | 60FS+7 days |  |  | February 25, 2019 8:00 AM | March 26, 2019 5:00 PM | March 04, 2019 05:00 PM | April 02, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 555 days | 555 days | 555 days | Electrician
60 | Yes | CMU1.2.4.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 63SS+30 days |  | 58FS+7 days,59FS+7 days | November 30, 2018 8:00 AM | February 17, 2019 5:00 PM | December 03, 2018 05:00 PM | February 20, 2019 05:00 PM | June 11, 2020 05:00 PM | August 29, 2020 05:00 PM | As Soon As Possible |  | No | 555 days | 555 days | 0 days | Electrician
61 | Yes | CMU1.2.4.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 63SS+30 days |  |  | November 30, 2018 8:00 AM | February 17, 2019 5:00 PM | December 03, 2018 05:00 PM | February 20, 2019 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 592 days | 592 days | 592 days | Electrician
62 | Yes | CMU1.2.4.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 63SS+30 days |  |  | November 30, 2018 8:00 AM | February 17, 2019 5:00 PM | December 04, 2018 05:00 PM | February 21, 2019 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 592 days | 592 days | 592 days | Electrician
63 | Yes | CMU1.2.5 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้น 4 | 165 days | 3 | 36SS+14 days |  | 62SS+30 days,60SS+30 days,61SS+30 days,65,214,219FS-15 days,224,230,244FS-7 days,250FS-7 days | October 31, 2018 8:00 AM | April 13, 2019 5:00 PM | October 31, 2018 05:00 PM | April 13, 2019 05:00 PM | June 19, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Skilled carpenter
64 | Yes | CMU1.3 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้น 3 | 441 days | 2 |  |  |  | November 16, 2018 8:00 AM | January 30, 2020 5:00 PM | October 17, 2018 05:00 PM | December 31, 2019 05:00 PM | July 23, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 149 days | 245 days | 149 days
65 | Yes | CMU1.3.1 | Auto Scheduled | งานรื้อถอน ชั้น 3 (รื้อขนไป) | 30 days | 3 | 63 | 121 | 68FS+45 days,69FS+45 days,92SS | April 14, 2019 8:00 AM | May 13, 2019 5:00 PM | April 14, 2019 05:00 PM | May 13, 2019 05:00 PM | July 19, 2018 05:00 PM | August 17, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | General worker
66 | Yes | CMU1.3.2 | Auto Scheduled | งานสถาปัตยกรรม ชั้น 3 | 315 days | 3 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 23, 2018 05:00 PM | September 02, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
67 | Yes | CMU1.3.2.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 68,70,71 |  |  | August 27, 2019 8:00 AM | September 25, 2019 5:00 PM | August 30, 2019 05:00 PM | September 28, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 372 days | Skilled carpenter
68 | Yes | CMU1.3.2.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 65FS+45 days |  | 67,72 | June 28, 2019 8:00 AM | August 26, 2019 5:00 PM | June 28, 2019 05:00 PM | August 26, 2019 05:00 PM | October 02, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 0 days | General worker
69 | Yes | CMU1.3.2.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 65FS+45 days |  | 70,71 | June 28, 2019 8:00 AM | July 27, 2019 5:00 PM | June 28, 2019 05:00 PM | July 27, 2019 05:00 PM | April 15, 2019 05:00 PM | May 14, 2019 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 0 days | General worker
70 | Yes | CMU1.3.2.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 69 |  | 67,72 | July 28, 2019 8:00 AM | August 26, 2019 5:00 PM | July 28, 2019 05:00 PM | August 26, 2019 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 0 days | Skilled carpenter
71 | Yes | CMU1.3.2.5 | Auto Scheduled | งานบันได | 30 days | 4 | 69 |  | 67,72 | July 28, 2019 8:00 AM | August 26, 2019 5:00 PM | July 28, 2019 05:00 PM | August 26, 2019 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 0 days | General worker
72 | Yes | CMU1.3.2.6 | Auto Scheduled | งานสี | 30 days | 4 | 68,70,71 |  |  | August 27, 2019 8:00 AM | September 25, 2019 5:00 PM | August 30, 2019 05:00 PM | September 28, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 372 days | General worker
73 | Yes | CMU1.3.2.7 | Auto Scheduled | งานสุขภัณฑ์ | 315 days | 4 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 21, 2018 05:00 PM | August 31, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
74 | Yes | CMU1.3.2.7.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 75FS+135 days |  | 76FS+135 days | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | August 25, 2019 05:00 PM | September 08, 2019 05:00 PM | April 24, 2020 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
75 | Yes | CMU1.3.2.7.2 | Auto Scheduled | ZONE T-2 กลาง | 15 days | 5 | 80,84 |  | 74FS+135 days | March 22, 2019 8:00 AM | April 5, 2019 5:00 PM | March 24, 2019 05:00 PM | April 07, 2019 05:00 PM | November 26, 2019 05:00 PM | December 10, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
76 | Yes | CMU1.3.2.7.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 15 days | 5 | 74FS+135 days |  |  | January 16, 2020 8:00 AM | January 30, 2020 5:00 PM | January 27, 2020 05:00 PM | February 10, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 245 days | Sanitary-Plumber
77 | Yes | CMU1.3.3 | Auto Scheduled | งานระบบสุขาภิบาล ชั้น 3 | 408 days | 3 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
78 | Yes | CMU1.3.3.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
79 | Yes | CMU1.3.3.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 80FS+15 days |  | 81FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 16, 2019 05:00 PM | August 19, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
80 | Yes | CMU1.3.3.1.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 36 |  | 79FS+15 days,84SS,75 | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 16, 2018 05:00 PM | March 21, 2019 05:00 PM | January 09, 2019 05:00 PM | May 14, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
81 | Yes | CMU1.3.3.1.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 79FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 08, 2019 05:00 PM | January 11, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
82 | Yes | CMU1.3.3.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
83 | Yes | CMU1.3.3.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 84FS+15 days |  | 85FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 12, 2019 05:00 PM | August 15, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
84 | Yes | CMU1.3.3.2.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 80SS |  | 83FS+15 days,75 | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 16, 2018 05:00 PM | March 21, 2019 05:00 PM | January 09, 2019 05:00 PM | May 14, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
85 | Yes | CMU1.3.3.2.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 83FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 10, 2019 05:00 PM | January 13, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
86 | Yes | CMU1.3.4 | Auto Scheduled | งานระบบไฟฟ้า ชั้น 3 | 147 days | 3 |  |  |  | May 14, 2019 8:00 AM | October 7, 2019 5:00 PM | October 21, 2018 05:00 PM | March 16, 2019 05:00 PM | May 12, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 360 days | 360 days | 360 days
87 | Yes | CMU1.3.4.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 60 days | 4 | 89FS+7 days |  |  | August 9, 2019 8:00 AM | October 7, 2019 5:00 PM | August 17, 2019 05:00 PM | October 15, 2019 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 360 days | 360 days | 360 days | Electrician
88 | Yes | CMU1.3.4.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 60 days | 4 | 89FS+7 days |  |  | August 9, 2019 8:00 AM | October 7, 2019 5:00 PM | August 23, 2019 05:00 PM | October 21, 2019 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 360 days | 360 days | 360 days | Electrician
89 | Yes | CMU1.3.4.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 92SS+30 days |  | 88FS+7 days,87FS+7 days | May 14, 2019 8:00 AM | August 1, 2019 5:00 PM | May 19, 2019 05:00 PM | August 06, 2019 05:00 PM | May 12, 2020 05:00 PM | July 30, 2020 05:00 PM | As Soon As Possible |  | No | 360 days | 360 days | 0 days | Electrician
90 | Yes | CMU1.3.4.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 92SS+30 days |  |  | May 14, 2019 8:00 AM | August 1, 2019 5:00 PM | May 22, 2019 05:00 PM | August 09, 2019 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 427 days | 427 days | 427 days | Electrician
91 | Yes | CMU1.3.4.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 92SS+30 days |  |  | May 14, 2019 8:00 AM | August 1, 2019 5:00 PM | May 23, 2019 05:00 PM | August 10, 2019 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 427 days | 427 days | 427 days | Electrician
92 | Yes | CMU1.3.5 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้น 3 | 180 days | 3 | 65SS |  | 91SS+30 days,90SS+30 days,89SS+30 days,94,213FS-15 days,218FS-30 days,223FS-15 days,229FS-15 days,243FS-7 days,249FS-7 days | April 14, 2019 8:00 AM | October 10, 2019 5:00 PM | April 17, 2019 05:00 PM | October 13, 2019 05:00 PM | October 12, 2019 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Skilled carpenter
93 | Yes | CMU1.4 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้น 2 | 509 days | 2 |  |  |  | November 16, 2018 8:00 AM | April 7, 2020 5:00 PM | October 17, 2018 05:00 PM | March 08, 2020 05:00 PM | May 16, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 177 days | 177 days
94 | Yes | CMU1.4.1 | Auto Scheduled | งานรื้อถอน ชั้น 2 (รื้อขนไป) | 30 days | 3 | 92 | 152 | 97FS+45 days,98FS+45 days,121SS | October 11, 2019 8:00 AM | November 9, 2019 5:00 PM | October 14, 2019 05:00 PM | November 12, 2019 05:00 PM | June 04, 2018 05:00 PM | July 03, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | General worker
95 | Yes | CMU1.4.2 | Auto Scheduled | งานสถาปัตยกรรม ชั้น 2 | 368 days | 3 |  |  |  | March 22, 2019 8:00 AM | March 23, 2020 5:00 PM | October 17, 2018 05:00 PM | October 19, 2019 05:00 PM | October 04, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 192 days | 192 days
96 | Yes | CMU1.4.2.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 97,99,100 |  |  | February 23, 2020 8:00 AM | March 23, 2020 5:00 PM | March 06, 2020 05:00 PM | April 04, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 192 days | Skilled carpenter
97 | Yes | CMU1.4.2.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 94FS+45 days |  | 96,101 | December 25, 2019 8:00 AM | February 22, 2020 5:00 PM | December 28, 2019 05:00 PM | February 25, 2020 05:00 PM | February 09, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 0 days | General worker
98 | Yes | CMU1.4.2.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 94FS+45 days |  | 99,100 | December 25, 2019 8:00 AM | January 23, 2020 5:00 PM | December 31, 2019 05:00 PM | January 29, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 0 days | General worker
99 | Yes | CMU1.4.2.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 98 |  | 96,101 | January 24, 2020 8:00 AM | February 22, 2020 5:00 PM | February 02, 2020 05:00 PM | March 02, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 0 days | Skilled carpenter
100 | Yes | CMU1.4.2.5 | Auto Scheduled | งานบันได | 30 days | 4 | 98 |  | 96,101 | January 24, 2020 8:00 AM | February 22, 2020 5:00 PM | February 02, 2020 05:00 PM | March 02, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 0 days | General worker
101 | Yes | CMU1.4.2.6 | Auto Scheduled | งานสี | 30 days | 4 | 97,99,100 |  |  | February 23, 2020 8:00 AM | March 23, 2020 5:00 PM | March 09, 2020 05:00 PM | April 07, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 192 days | General worker
102 | Yes | CMU1.4.2.7 | Auto Scheduled | งานสุขภัณฑ์ | 315 days | 4 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 21, 2018 05:00 PM | August 31, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
103 | Yes | CMU1.4.2.7.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 104FS+135 days |  | 105FS+135 days | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | September 08, 2019 05:00 PM | September 22, 2019 05:00 PM | April 24, 2020 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
104 | Yes | CMU1.4.2.7.2 | Auto Scheduled | ZONE T-2 กลาง | 15 days | 5 | 113,109 |  | 103FS+135 days | March 22, 2019 8:00 AM | April 5, 2019 5:00 PM | April 07, 2019 05:00 PM | April 21, 2019 05:00 PM | November 26, 2019 05:00 PM | December 10, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
105 | Yes | CMU1.4.2.7.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 15 days | 5 | 103FS+135 days |  |  | January 16, 2020 8:00 AM | January 30, 2020 5:00 PM | February 09, 2020 05:00 PM | February 23, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 245 days | Sanitary-Plumber
106 | Yes | CMU1.4.3 | Auto Scheduled | งานระบบสุขาภิบาล ชั้น 2 | 408 days | 3 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
107 | Yes | CMU1.4.3.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
108 | Yes | CMU1.4.3.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 109FS+15 days |  | 110FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 16, 2019 05:00 PM | August 19, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
109 | Yes | CMU1.4.3.1.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 36 |  | 113SS,104,108FS+15 days | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 22, 2018 05:00 PM | March 27, 2019 05:00 PM | August 25, 2019 05:00 PM | December 28, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
110 | Yes | CMU1.4.3.1.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 108FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 07, 2019 05:00 PM | January 10, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
111 | Yes | CMU1.4.3.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
112 | Yes | CMU1.4.3.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 113FS+15 days |  | 114FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 27, 2019 05:00 PM | August 30, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
113 | Yes | CMU1.4.3.2.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 109SS |  | 104,112FS+15 days | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 28, 2018 05:00 PM | April 02, 2019 05:00 PM | August 25, 2019 05:00 PM | December 28, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
114 | Yes | CMU1.4.3.2.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 112FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 19, 2019 05:00 PM | January 22, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
115 | Yes | CMU1.4.4 | Auto Scheduled | งานระบบไฟฟ้า ชั้น 2 | 147 days | 3 |  |  |  | November 10, 2019 8:00 AM | April 4, 2020 5:00 PM | October 20, 2018 05:00 PM | March 15, 2019 05:00 PM | May 12, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 180 days | 180 days | 180 days
116 | Yes | CMU1.4.4.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 60 days | 4 | 118FS+7 days |  |  | February 5, 2020 8:00 AM | April 4, 2020 5:00 PM | February 12, 2020 05:00 PM | April 11, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 180 days | 180 days | 180 days | Electrician
117 | Yes | CMU1.4.4.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 60 days | 4 | 118FS+7 days |  |  | February 5, 2020 8:00 AM | April 4, 2020 5:00 PM | February 13, 2020 05:00 PM | April 12, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 180 days | 180 days | 180 days | Electrician
118 | Yes | CMU1.4.4.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 121SS+30 days |  | 117FS+7 days,116FS+7 days | November 10, 2019 8:00 AM | January 28, 2020 5:00 PM | November 15, 2019 05:00 PM | February 02, 2020 05:00 PM | May 12, 2020 05:00 PM | July 30, 2020 05:00 PM | As Soon As Possible |  | No | 180 days | 180 days | 0 days | Electrician
119 | Yes | CMU1.4.4.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 121SS+30 days |  |  | November 10, 2019 8:00 AM | January 28, 2020 5:00 PM | November 17, 2019 05:00 PM | February 04, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 247 days | 247 days | 247 days | Electrician
120 | Yes | CMU1.4.4.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 121SS+30 days |  |  | November 10, 2019 8:00 AM | January 28, 2020 5:00 PM | November 17, 2019 05:00 PM | February 04, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 247 days | 247 days | 247 days | Electrician
121 | Yes | CMU1.4.5 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้น 2 | 180 days | 3 | 94SS |  | 120SS+30 days,119SS+30 days,118SS+30 days,123,212FS-15 days,217FS-30 days,222FS-15 days,228FS-15 days,242FS-7 days,248FS-7 days | October 11, 2019 8:00 AM | April 7, 2020 5:00 PM | October 14, 2019 05:00 PM | April 10, 2020 05:00 PM | June 04, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Skilled carpenter
122 | Yes | CMU1.5 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้น 1 | 686 days | 2 |  |  |  | November 16, 2018 8:00 AM | October 1, 2020 5:00 PM | October 17, 2018 05:00 PM | September 01, 2020 05:00 PM | November 20, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 0 days | 0 days
123 | Yes | CMU1.5.1 | Auto Scheduled | งานรื้อถอน ชั้น 1 (รื้อขนไป) | 30 days | 3 | 121 | 63 | 124,127FS+45 days,128FS+45 days,131FS+45 days,152SS,193SS,194SS,195SS,196SS,197SS,202SS,204SS,205SS,206SS,207SS | April 8, 2020 8:00 AM | May 7, 2020 5:00 PM | April 11, 2020 05:00 PM | May 10, 2020 05:00 PM | July 19, 2018 05:00 PM | August 17, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | General worker
124 | Yes | CMU1.5.2 | Auto Scheduled | งานโครงสร้างวิศวกรรม ชั้น 1 | 75 days | 3 | 123 |  |  | May 8, 2020 8:00 AM | July 21, 2020 5:00 PM | May 12, 2020 05:00 PM | July 25, 2020 05:00 PM | July 23, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 72 days | 72 days | 72 days | General worker
125 | Yes | CMU1.5.3 | Auto Scheduled | งานสถาปัตยกรรม ชั้น 1 | 548 days | 3 |  |  |  | March 22, 2019 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | April 16, 2020 05:00 PM | April 07, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 12 days | 12 days
126 | Yes | CMU1.5.3.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 127,129,130 |  |  | August 21, 2020 8:00 AM | September 19, 2020 5:00 PM | August 24, 2020 05:00 PM | September 22, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | Skilled carpenter
127 | Yes | CMU1.5.3.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 123FS+45 days |  | 126,132 | June 22, 2020 8:00 AM | August 20, 2020 5:00 PM | June 25, 2020 05:00 PM | August 23, 2020 05:00 PM | October 02, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
128 | Yes | CMU1.5.3.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 123FS+45 days |  | 129,130 | June 22, 2020 8:00 AM | July 21, 2020 5:00 PM | June 25, 2020 05:00 PM | July 24, 2020 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
129 | Yes | CMU1.5.3.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 128 |  | 126,132 | July 22, 2020 8:00 AM | August 20, 2020 5:00 PM | July 25, 2020 05:00 PM | August 23, 2020 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | Skilled carpenter
130 | Yes | CMU1.5.3.5 | Auto Scheduled | งานบันได | 30 days | 4 | 128 |  | 126,132 | July 22, 2020 8:00 AM | August 20, 2020 5:00 PM | July 25, 2020 05:00 PM | August 23, 2020 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
131 | Yes | CMU1.5.3.6 | Auto Scheduled | งานตกแต่งอื่น ๆ | 60 days | 4 | 123FS+45 days |  |  | June 22, 2020 8:00 AM | August 20, 2020 5:00 PM | June 25, 2020 05:00 PM | August 23, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 42 days | 42 days | 42 days | General worker
132 | Yes | CMU1.5.3.7 | Auto Scheduled | งานสี | 30 days | 4 | 127,129,130 |  |  | August 21, 2020 8:00 AM | September 19, 2020 5:00 PM | August 24, 2020 05:00 PM | September 22, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
133 | Yes | CMU1.5.3.8 | Auto Scheduled | งานสุขภัณฑ์ | 315 days | 4 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 22, 2018 05:00 PM | September 01, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
134 | Yes | CMU1.5.3.8.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 135FS+135 days |  | 136FS+135 days | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | August 24, 2019 05:00 PM | September 07, 2019 05:00 PM | April 24, 2020 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
135 | Yes | CMU1.5.3.8.2 | Auto Scheduled | ZONE T-2 กลาง | 15 days | 5 | 140,144 |  | 134FS+135 days,164FS+135 days | March 22, 2019 8:00 AM | April 5, 2019 5:00 PM | March 24, 2019 05:00 PM | April 07, 2019 05:00 PM | November 26, 2019 05:00 PM | December 10, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
136 | Yes | CMU1.5.3.8.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 15 days | 5 | 134FS+135 days |  |  | January 16, 2020 8:00 AM | January 30, 2020 5:00 PM | January 24, 2020 05:00 PM | February 07, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 245 days | Sanitary-Plumber
137 | Yes | CMU1.5.4 | Auto Scheduled | งานระบบสุขาภิบาล ชั้น 1 | 408 days | 3 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 278 days | 44 days
138 | Yes | CMU1.5.4.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 278 days | 44 days
139 | Yes | CMU1.5.4.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 140FS+15 days |  | 141FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 13, 2019 05:00 PM | August 16, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
140 | Yes | CMU1.5.4.1.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 36 |  | 139FS+15 days,144SS,135,167FS+15 days | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 16, 2018 05:00 PM | March 21, 2019 05:00 PM | January 03, 2019 05:00 PM | May 08, 2019 05:00 PM | As Soon As Possible |  | No | 44 days | 44 days | 0 days | Sanitary-Plumber
141 | Yes | CMU1.5.4.1.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 139FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 07, 2019 05:00 PM | January 10, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
142 | Yes | CMU1.5.4.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 278 days | 44 days
143 | Yes | CMU1.5.4.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 144FS+15 days |  | 145FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 12, 2019 05:00 PM | August 15, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
144 | Yes | CMU1.5.4.2.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 140SS |  | 143FS+15 days,135,169FS+15 days | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 16, 2018 05:00 PM | March 21, 2019 05:00 PM | January 03, 2019 05:00 PM | May 08, 2019 05:00 PM | As Soon As Possible |  | No | 44 days | 44 days | 0 days | Sanitary-Plumber
145 | Yes | CMU1.5.4.2.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 143FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 04, 2019 05:00 PM | January 07, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
146 | Yes | CMU1.5.5 | Auto Scheduled | งานระบบไฟฟ้า ชั้น 1 | 147 days | 3 |  |  |  | May 8, 2020 8:00 AM | October 1, 2020 5:00 PM | October 21, 2018 05:00 PM | March 16, 2019 05:00 PM | May 12, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 0 days | 0 days | 0 days
147 | Yes | CMU1.5.5.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 60 days | 4 | 149FS+7 days |  |  | August 3, 2020 8:00 AM | October 1, 2020 5:00 PM | August 06, 2020 05:00 PM | October 04, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Electrician
148 | Yes | CMU1.5.5.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 60 days | 4 | 149FS+7 days |  |  | August 3, 2020 8:00 AM | October 1, 2020 5:00 PM | August 06, 2020 05:00 PM | October 04, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Electrician
149 | Yes | CMU1.5.5.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 152SS+30 days |  | 148FS+7 days,147FS+7 days | May 8, 2020 8:00 AM | July 26, 2020 5:00 PM | May 11, 2020 05:00 PM | July 29, 2020 05:00 PM | May 12, 2020 05:00 PM | July 30, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Electrician
150 | Yes | CMU1.5.5.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 152SS+30 days |  |  | May 8, 2020 8:00 AM | July 26, 2020 5:00 PM | May 11, 2020 05:00 PM | July 29, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 67 days | 67 days | 67 days | Electrician
151 | Yes | CMU1.5.5.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 152SS+30 days |  |  | May 8, 2020 8:00 AM | July 26, 2020 5:00 PM | May 11, 2020 05:00 PM | July 29, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 67 days | 67 days | 67 days | Electrician
152 | Yes | CMU1.5.6 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้น 1 | 165 days | 3 | 123SS |  | 151SS+30 days,150SS+30 days,149SS+30 days,154SS,211FS-30 days,210FS-30 days,216FS-45 days,221FS-30 days,227FS-30 days,226FS-30 days,232FS-45 days,241FS-7 days,247FS-7 days | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 11, 2020 05:00 PM | September 22, 2020 05:00 PM | November 26, 2019 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Skilled carpenter
153 | Yes | CMU1.6 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้นใต้ดิน | 533 days | 2 |  |  |  | April 6, 2019 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | April 01, 2020 05:00 PM | April 22, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 12 days | 12 days
154 | Yes | CMU1.6.1 | Auto Scheduled | งานรื้อถอน ชั้นใต้ดิน (รื้อขนไป) | 30 days | 3 | 152SS |  | 155,158FS+45 days,159FS+45 days,177SS,176SS,175SS,174SS | April 8, 2020 8:00 AM | May 7, 2020 5:00 PM | April 11, 2020 05:00 PM | May 10, 2020 05:00 PM | November 26, 2019 05:00 PM | December 25, 2019 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
155 | Yes | CMU1.6.2 | Auto Scheduled | งานโครงสร้างวิศวกรรม ชั้นใต้ดิน | 75 days | 3 | 154 |  |  | May 8, 2020 8:00 AM | July 21, 2020 5:00 PM | May 12, 2020 05:00 PM | July 25, 2020 05:00 PM | July 23, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 72 days | 72 days | 72 days | General worker
156 | Yes | CMU1.6.3 | Auto Scheduled | งานสถาปัตยกรรม ชั้นใต้ดิน | 398 days | 3 |  |  |  | August 19, 2019 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | November 18, 2019 05:00 PM | September 04, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 320 days | 12 days | 12 days
157 | Yes | CMU1.6.3.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 158,160,161 |  |  | August 21, 2020 8:00 AM | September 19, 2020 5:00 PM | September 21, 2020 05:00 PM | October 20, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | Skilled carpenter
158 | Yes | CMU1.6.3.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 154FS+45 days |  | 157,162 | June 22, 2020 8:00 AM | August 20, 2020 5:00 PM | June 25, 2020 05:00 PM | August 23, 2020 05:00 PM | February 09, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
159 | Yes | CMU1.6.3.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 154FS+45 days |  | 160,161 | June 22, 2020 8:00 AM | July 21, 2020 5:00 PM | July 23, 2020 05:00 PM | August 21, 2020 05:00 PM | August 22, 2020 05:00 PM | September 20, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
160 | Yes | CMU1.6.3.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 159 |  | 157,162 | July 22, 2020 8:00 AM | August 20, 2020 5:00 PM | August 22, 2020 05:00 PM | September 20, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | Skilled carpenter
161 | Yes | CMU1.6.3.5 | Auto Scheduled | งานบันได | 30 days | 4 | 159 |  | 157,162 | July 22, 2020 8:00 AM | August 20, 2020 5:00 PM | August 22, 2020 05:00 PM | September 20, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
162 | Yes | CMU1.6.3.6 | Auto Scheduled | งานสี | 30 days | 4 | 158,160,161 |  |  | August 21, 2020 8:00 AM | September 19, 2020 5:00 PM | September 21, 2020 05:00 PM | October 20, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
163 | Yes | CMU1.6.3.7 | Auto Scheduled | งานสุขภัณฑ์ | 15 days | 4 |  |  |  | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | October 19, 2018 05:00 PM | November 02, 2018 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 395 days | 395 days | 395 days
164 | Yes | CMU1.6.3.7.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 135FS+135 days |  |  | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | August 27, 2019 05:00 PM | September 10, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 395 days | 395 days | 395 days | Sanitary-Plumber
165 | Yes | CMU1.6.4 | Auto Scheduled | งานระบบสุขาภิบาล ชั้นใต้ดิน | 501 days | 3 |  |  |  | April 6, 2019 8:00 AM | August 18, 2020 5:00 PM | October 17, 2018 05:00 PM | February 29, 2020 05:00 PM | May 24, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 44 days | 44 days
166 | Yes | CMU1.6.4.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 126 days | 4 |  |  |  | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | October 21, 2018 05:00 PM | February 23, 2019 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 419 days | 419 days | 419 days
167 | Yes | CMU1.6.4.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 140FS+15 days |  |  | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 14, 2019 05:00 PM | August 17, 2019 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 419 days | 419 days | 419 days | Sanitary-Plumber
168 | Yes | CMU1.6.4.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 126 days | 4 |  |  |  | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | October 21, 2018 05:00 PM | February 23, 2019 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 44 days | 44 days
169 | Yes | CMU1.6.4.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 144FS+15 days |  | 170FS+300 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 06, 2019 05:00 PM | August 09, 2019 05:00 PM | May 24, 2019 05:00 PM | September 26, 2019 05:00 PM | As Soon As Possible |  | No | 44 days | 44 days | 0 days | Sanitary-Plumber
170 | Yes | CMU1.6.4.3 | Auto Scheduled | งานระบบระบายน้ำฝน | 75 days | 4 | 169FS+300 days |  |  | June 5, 2020 8:00 AM | August 18, 2020 5:00 PM | June 05, 2020 05:00 PM | August 18, 2020 05:00 PM | July 23, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 44 days | 44 days | 44 days | Sanitary-Plumber
171 | Yes | CMU1.6.5 | Auto Scheduled | งานระบบไฟฟ้า ชั้นใต้ดิน | 147 days | 3 |  |  |  | April 8, 2020 8:00 AM | September 1, 2020 5:00 PM | October 23, 2018 05:00 PM | March 18, 2019 05:00 PM | May 12, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 30 days | 30 days | 30 days
172 | Yes | CMU1.6.5.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 60 days | 4 | 174FS+7 days |  |  | July 4, 2020 8:00 AM | September 1, 2020 5:00 PM | July 07, 2020 05:00 PM | September 04, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 30 days | 30 days | 30 days | Electrician
173 | Yes | CMU1.6.5.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 60 days | 4 | 174FS+7 days |  |  | July 4, 2020 8:00 AM | September 1, 2020 5:00 PM | July 07, 2020 05:00 PM | September 04, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 30 days | 30 days | 30 days | Electrician
174 | Yes | CMU1.6.5.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 154SS |  | 173FS+7 days,172FS+7 days | April 8, 2020 8:00 AM | June 26, 2020 5:00 PM | April 11, 2020 05:00 PM | June 29, 2020 05:00 PM | May 12, 2020 05:00 PM | July 30, 2020 05:00 PM | As Soon As Possible |  | No | 30 days | 30 days | 0 days | Electrician
175 | Yes | CMU1.6.5.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 154SS |  |  | April 8, 2020 8:00 AM | June 26, 2020 5:00 PM | April 14, 2020 05:00 PM | July 02, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 97 days | 97 days | 97 days | Electrician
176 | Yes | CMU1.6.5.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 154SS |  |  | April 8, 2020 8:00 AM | June 26, 2020 5:00 PM | April 14, 2020 05:00 PM | July 02, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 97 days | 97 days | 97 days | Electrician
177 | Yes | CMU1.6.6 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้นใต้ดิน | 165 days | 3 | 154SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 11, 2020 05:00 PM | September 22, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | Skilled carpenter
178 | Yes | CMU1.7 | Auto Scheduled | หมวดงานระบบคอมพิวเตอร์และแจ้งเหตุเพลิงไหม้ | 670 days | 2 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
179 | Yes | CMU1.7.1 | Auto Scheduled | งานระบบคอมพิวเตอร์ | 670 days | 3 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
180 | Yes | CMU1.7.1.1 | Auto Scheduled | ชั้นที่ 4 | 160 days | 4 | 36FS+14 days |  | 181 | November 30, 2018 8:00 AM | May 8, 2019 5:00 PM | November 30, 2018 05:00 PM | May 08, 2019 05:00 PM | April 24, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
181 | Yes | CMU1.7.1.2 | Auto Scheduled | ชั้นที่ 3 | 175 days | 4 | 180 | 182 | 182 | May 9, 2019 8:00 AM | October 30, 2019 5:00 PM | May 09, 2019 05:00 PM | October 30, 2019 05:00 PM | April 09, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
182 | Yes | CMU1.7.1.3 | Auto Scheduled | ชั้นที่ 2 | 175 days | 4 | 181 | 183 | 183,184 | October 31, 2019 8:00 AM | April 22, 2020 5:00 PM | October 31, 2019 05:00 PM | April 22, 2020 05:00 PM | April 09, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
183 | Yes | CMU1.7.1.4 | Auto Scheduled | ชั้นที่ 1 | 160 days | 4 | 182 | 180 |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 23, 2020 05:00 PM | September 29, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
184 | Yes | CMU1.7.1.5 | Auto Scheduled | ชั้นใต้ดิน | 160 days | 4 | 182 | 183SS |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 23, 2020 05:00 PM | September 29, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
185 | Yes | CMU1.7.2 | Auto Scheduled | ระบบแจ้งเหตุเพลิงไหม้ | 670 days | 3 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
186 | Yes | CMU1.7.2.1 | Auto Scheduled | ชั้นที่ 4 | 160 days | 4 | 36FS+14 days |  | 187 | November 30, 2018 8:00 AM | May 8, 2019 5:00 PM | November 30, 2018 05:00 PM | May 08, 2019 05:00 PM | April 24, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
187 | Yes | CMU1.7.2.2 | Auto Scheduled | ชั้นที่ 3 | 175 days | 4 | 186 | 188 | 188 | May 9, 2019 8:00 AM | October 30, 2019 5:00 PM | May 09, 2019 05:00 PM | October 30, 2019 05:00 PM | April 09, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
188 | Yes | CMU1.7.2.3 | Auto Scheduled | ชั้นที่ 2 | 175 days | 4 | 187 | 189 | 189,190 | October 31, 2019 8:00 AM | April 22, 2020 5:00 PM | October 31, 2019 05:00 PM | April 22, 2020 05:00 PM | April 09, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
189 | Yes | CMU1.7.2.4 | Auto Scheduled | ชั้นที่ 1 | 160 days | 4 | 188 | 186 |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 23, 2020 05:00 PM | September 29, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
190 | Yes | CMU1.7.2.5 | Auto Scheduled | ชั้นใต้ดิน | 160 days | 4 | 188 | 189SS |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 23, 2020 05:00 PM | September 29, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
191 | Yes | CMU1.8 | Auto Scheduled | หมวดงานสีภายนอก งานซ่อมแซมและตกแต่งภายนอกอาคาร | 660 days | 2 |  |  |  | November 30, 2018 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | August 06, 2020 05:00 PM | December 16, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 507 days | 12 days | 12 days
192 | Yes | CMU1.8.1 | Auto Scheduled | งานสีภายนอกและงานซ่อมแซมพื้นผิวภายนอกอาคาร | 660 days | 3 |  |  |  | November 30, 2018 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | August 06, 2020 05:00 PM | December 16, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 507 days | 12 days | 12 days
193 | Yes | CMU1.8.1.1 | Auto Scheduled | งานขัดลอกสีทาผนังเดิม | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 11, 2020 05:00 PM | September 22, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
194 | Yes | CMU1.8.1.2 | Auto Scheduled | น้ำยาทาปูนเก่า (สีรองพื้น) | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 11, 2020 05:00 PM | September 22, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
195 | Yes | CMU1.8.1.3 | Auto Scheduled | งานทาสีภายนอก (ทา 2 เที่ยว) ไม่รวมชั้นใต้ดิน | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 11, 2020 05:00 PM | September 22, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
196 | Yes | CMU1.8.1.4 | Auto Scheduled | งานทำความสะอาดและซ่อมแซมผนังกรุอิฐโชว์แนว (อ้างอิงราคางานขัดลอกสี) | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 11, 2020 05:00 PM | September 22, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
197 | Yes | CMU1.8.1.5 | Auto Scheduled | น้ำยาเคลือบผิวผนังอิฐโชว์แนว (อ้างอิงค่าทาน้ำยากันเชื้อรา) | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 11, 2020 05:00 PM | September 22, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
198 | Yes | CMU1.8.1.6 | Auto Scheduled | งานรื้อถอนแผ่นวัสดุกันซึมหลังคาดาดฟ้า (รื้อขนไป) | 90 days | 4 | 36FS+14 days |  |  | November 30, 2018 8:00 AM | February 27, 2019 5:00 PM | December 03, 2018 05:00 PM | March 02, 2019 05:00 PM | July 08, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 582 days | 582 days | 582 days | General worker
199 | Yes | CMU1.8.1.7 | Auto Scheduled | งานแผ่นวัสดุกันซึมแบบเป่าไฟผิวทราย | 90 days | 4 | 36FS+14 days |  |  | November 30, 2018 8:00 AM | February 27, 2019 5:00 PM | December 04, 2018 05:00 PM | March 03, 2019 05:00 PM | July 08, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 582 days | 582 days | 582 days | General worker
200 | Yes | CMU1.8.1.8 | Auto Scheduled | งานกันซึมชนิด Polyurethane สูตรน้ำมัน ชนิดยืดหยุ่นสูงเป็นพิเศษ | 90 days | 4 | 36FS+14 days |  |  | November 30, 2018 8:00 AM | February 27, 2019 5:00 PM | December 03, 2018 05:00 PM | March 02, 2019 05:00 PM | July 08, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 582 days | 582 days | 582 days | General worker
201 | Yes | CMU1.8.2 | Auto Scheduled | งานตกแต่งภายนอกอาคาร | 165 days | 3 |  |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | October 20, 2018 05:00 PM | April 02, 2019 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 12 days | 12 days | 12 days
202 | Yes | CMU1.8.2.1 | Auto Scheduled | ตะแกรงเหล็กฉีกกันนก XS-32 | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 11, 2020 05:00 PM | September 22, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
203 | Yes | CMU1.9 | Auto Scheduled | หมวดงานบริเวณ | 165 days | 2 |  |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | October 22, 2018 05:00 PM | April 04, 2019 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 12 days | 12 days | 12 days
204 | Yes | CMU1.9.1 | Auto Scheduled | งานรื้อถอน งานบริเวณ | 165 days | 3 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 11, 2020 05:00 PM | September 22, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
205 | Yes | CMU1.9.2 | Auto Scheduled | งานโครงสร้างวิศวกรรม งานบริเวณ | 165 days | 3 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 11, 2020 05:00 PM | September 22, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
206 | Yes | CMU1.9.3 | Auto Scheduled | งานสถาปัตยกรรม งานบริเวณ | 165 days | 3 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 11, 2020 05:00 PM | September 22, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
207 | Yes | CMU1.9.4 | Auto Scheduled | งานระบบไฟฟ้า งานบริเวณ | 165 days | 3 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 11, 2020 05:00 PM | September 22, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | Electrician
208 | Yes | CMU1.10 | Auto Scheduled | หมวดงานครุภัณฑ์จัดซื้อ | 670 days | 2 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
209 | Yes | CMU1.10.1 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัว | 510 days | 3 |  |  |  | April 14, 2019 8:00 AM | September 4, 2020 5:00 PM | October 17, 2018 05:00 PM | March 09, 2020 05:00 PM | May 15, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 522 days | 27 days | 27 days
210 | Yes | CMU1.10.1.1 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้นใต้ดิน | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | August 28, 2020 05:00 PM | September 11, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
211 | Yes | CMU1.10.1.2 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้น 1 | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | August 31, 2020 05:00 PM | September 14, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
212 | Yes | CMU1.10.1.3 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้น 2 | 15 days | 4 | 121FS-15 days |  |  | March 24, 2020 8:00 AM | April 7, 2020 5:00 PM | March 29, 2020 05:00 PM | April 12, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Skilled carpenter
213 | Yes | CMU1.10.1.4 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้น 3 | 15 days | 4 | 92FS-15 days |  |  | September 26, 2019 8:00 AM | October 10, 2019 5:00 PM | October 04, 2019 05:00 PM | October 18, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Skilled carpenter
214 | Yes | CMU1.10.1.5 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้น 4 | 15 days | 4 | 63 |  |  | April 14, 2019 8:00 AM | April 28, 2019 5:00 PM | April 21, 2019 05:00 PM | May 05, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 522 days | 522 days | 522 days | Skilled carpenter
215 | Yes | CMU1.10.2 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ | 525 days | 3 |  |  |  | March 30, 2019 8:00 AM | September 4, 2020 5:00 PM | October 17, 2018 05:00 PM | March 24, 2020 05:00 PM | April 30, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 522 days | 27 days | 27 days
216 | Yes | CMU1.10.2.1 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ ชั้น 1 | 30 days | 4 | 152FS-45 days |  |  | August 6, 2020 8:00 AM | September 4, 2020 5:00 PM | August 15, 2020 05:00 PM | September 13, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
217 | Yes | CMU1.10.2.2 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ ชั้น 2 | 30 days | 4 | 121FS-30 days |  |  | March 9, 2020 8:00 AM | April 7, 2020 5:00 PM | March 15, 2020 05:00 PM | April 13, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Skilled carpenter
218 | Yes | CMU1.10.2.3 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ ชั้น 3 | 30 days | 4 | 92FS-30 days |  |  | September 11, 2019 8:00 AM | October 10, 2019 5:00 PM | September 16, 2019 05:00 PM | October 15, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Skilled carpenter
219 | Yes | CMU1.10.2.4 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ ชั้น 4 | 30 days | 4 | 63FS-15 days |  |  | March 30, 2019 8:00 AM | April 28, 2019 5:00 PM | April 02, 2019 05:00 PM | May 01, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 522 days | 522 days | 522 days | Skilled carpenter
220 | Yes | CMU1.10.3 | Auto Scheduled | งานผ้าม่าน | 510 days | 3 |  |  |  | April 14, 2019 8:00 AM | September 4, 2020 5:00 PM | October 17, 2018 05:00 PM | March 09, 2020 05:00 PM | May 15, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 522 days | 27 days | 27 days
221 | Yes | CMU1.10.3.1 | Auto Scheduled | งานผ้าม่าน ชั้น 1 | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | August 28, 2020 05:00 PM | September 11, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
222 | Yes | CMU1.10.3.2 | Auto Scheduled | งานผ้าม่าน ชั้น 2 | 15 days | 4 | 121FS-15 days |  |  | March 24, 2020 8:00 AM | April 7, 2020 5:00 PM | March 30, 2020 05:00 PM | April 13, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Skilled carpenter
223 | Yes | CMU1.10.3.3 | Auto Scheduled | งานผ้าม่าน ชั้น 3 | 15 days | 4 | 92FS-15 days |  |  | September 26, 2019 8:00 AM | October 10, 2019 5:00 PM | October 02, 2019 05:00 PM | October 16, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Skilled carpenter
224 | Yes | CMU1.10.3.4 | Auto Scheduled | งานผ้าม่าน ชั้น 4 | 15 days | 4 | 63 |  |  | April 14, 2019 8:00 AM | April 28, 2019 5:00 PM | April 24, 2019 05:00 PM | May 08, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 522 days | 522 days | 522 days | Skilled carpenter
225 | Yes | CMU1.10.4 | Auto Scheduled | งานป้าย | 510 days | 3 |  |  |  | April 14, 2019 8:00 AM | September 4, 2020 5:00 PM | October 17, 2018 05:00 PM | March 09, 2020 05:00 PM | May 15, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 522 days | 27 days | 27 days
226 | Yes | CMU1.10.4.1 | Auto Scheduled | งานป้าย ชั้นใต้ดิน | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | August 28, 2020 05:00 PM | September 11, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
227 | Yes | CMU1.10.4.2 | Auto Scheduled | งานป้าย ชั้น 1 | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | August 31, 2020 05:00 PM | September 14, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
228 | Yes | CMU1.10.4.3 | Auto Scheduled | งานป้าย ชั้น 2 | 15 days | 4 | 121FS-15 days |  |  | March 24, 2020 8:00 AM | April 7, 2020 5:00 PM | March 30, 2020 05:00 PM | April 13, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Skilled carpenter
229 | Yes | CMU1.10.4.4 | Auto Scheduled | งานป้าย ชั้น 3 | 15 days | 4 | 92FS-15 days |  |  | September 26, 2019 8:00 AM | October 10, 2019 5:00 PM | October 02, 2019 05:00 PM | October 16, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Skilled carpenter
230 | Yes | CMU1.10.4.5 | Auto Scheduled | งานป้าย ชั้น 4 | 15 days | 4 | 63 |  |  | April 14, 2019 8:00 AM | April 28, 2019 5:00 PM | April 19, 2019 05:00 PM | May 03, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 522 days | 522 days | 522 days | Skilled carpenter
231 | Yes | CMU1.10.5 | Auto Scheduled | งานอื่นๆ | 15 days | 3 |  |  |  | August 6, 2020 8:00 AM | August 20, 2020 5:00 PM | October 20, 2018 05:00 PM | November 03, 2018 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 42 days | 42 days | 42 days
232 | Yes | CMU1.10.5.1 | Auto Scheduled | ตู้อลูมิเนียมพับขึ้นรูป พ่นสี ครอบตู้กดน้ำ | 15 days | 4 | 152FS-45 days |  |  | August 6, 2020 8:00 AM | August 20, 2020 5:00 PM | August 13, 2020 05:00 PM | August 27, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 42 days | 42 days | 42 days | General worker
233 | Yes | CMU1.10.6 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ | 670 days | 3 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
234 | Yes | CMU1.10.6.1 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้นใต้ดิน | 160 days | 4 | 236 |  |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 28, 2020 05:00 PM | October 04, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
235 | Yes | CMU1.10.6.2 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้น 1 | 160 days | 4 | 236 |  |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 28, 2020 05:00 PM | October 04, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
236 | Yes | CMU1.10.6.3 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้น 2 | 175 days | 4 | 237 |  | 235,234 | October 31, 2019 8:00 AM | April 22, 2020 5:00 PM | November 05, 2019 05:00 PM | April 27, 2020 05:00 PM | March 12, 2020 05:00 PM | September 02, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
237 | Yes | CMU1.10.6.4 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้น 3 | 175 days | 4 | 238 |  | 236 | May 9, 2019 8:00 AM | October 30, 2019 5:00 PM | May 14, 2019 05:00 PM | November 04, 2019 05:00 PM | March 12, 2020 05:00 PM | September 02, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
238 | Yes | CMU1.10.6.5 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้น 4 | 160 days | 4 | 36FS+14 days |  | 237 | November 30, 2018 8:00 AM | May 8, 2019 5:00 PM | December 02, 2018 05:00 PM | May 10, 2019 05:00 PM | March 27, 2020 05:00 PM | September 02, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
239 | Yes | CMU1.10.7 | Auto Scheduled | งานระบบเครื่องเสียงประกาศ (ใช้ลำโพงของเดิม) | 539 days | 3 |  |  |  | April 7, 2019 8:00 AM | September 26, 2020 5:00 PM | October 17, 2018 05:00 PM | April 07, 2020 05:00 PM | April 16, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 530 days | 5 days | 5 days
240 | Yes | CMU1.10.7.1 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้นใต้ดิน | 7 days | 4 | 241 |  |  | September 20, 2020 8:00 AM | September 26, 2020 5:00 PM | September 27, 2020 05:00 PM | October 03, 2020 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 5 days | 5 days | 5 days | Electrician
241 | Yes | CMU1.10.7.2 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้น 1 | 7 days | 4 | 152FS-7 days |  | 240 | September 13, 2020 8:00 AM | September 19, 2020 5:00 PM | September 16, 2020 05:00 PM | September 22, 2020 05:00 PM | September 09, 2020 05:00 PM | September 15, 2020 05:00 PM | As Soon As Possible |  | No | 5 days | 5 days | 0 days | Electrician
242 | Yes | CMU1.10.7.3 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้น 2 | 7 days | 4 | 121FS-7 days |  |  | April 1, 2020 8:00 AM | April 7, 2020 5:00 PM | April 06, 2020 05:00 PM | April 12, 2020 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Electrician
243 | Yes | CMU1.10.7.4 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้น 3 | 7 days | 4 | 92FS-7 days |  |  | October 4, 2019 8:00 AM | October 10, 2019 5:00 PM | October 11, 2019 05:00 PM | October 17, 2019 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Electrician
244 | Yes | CMU1.10.7.5 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้น 4 | 7 days | 4 | 63FS-7 days |  |  | April 7, 2019 8:00 AM | April 13, 2019 5:00 PM | April 11, 2019 05:00 PM | April 17, 2019 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 537 days | 537 days | 537 days | Electrician
245 | Yes | CMU1.10.8 | Auto Scheduled | งานระบบกล้องวงจรปิด (ใช้กล้องวงจรปิดของเดิม) | 539 days | 3 |  |  |  | April 7, 2019 8:00 AM | September 26, 2020 5:00 PM | October 17, 2018 05:00 PM | April 07, 2020 05:00 PM | April 16, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 530 days | 5 days | 5 days
246 | Yes | CMU1.10.8.1 | Auto Scheduled | งานกล้องวงจรปิด ชั้นใต้ดิน | 7 days | 4 | 247 |  |  | September 20, 2020 8:00 AM | September 26, 2020 5:00 PM | September 27, 2020 05:00 PM | October 03, 2020 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 5 days | 5 days | 5 days | Electrician
247 | Yes | CMU1.10.8.2 | Auto Scheduled | งานกล้องวงจรปิด ชั้น 1 | 7 days | 4 | 152FS-7 days |  | 246 | September 13, 2020 8:00 AM | September 19, 2020 5:00 PM | September 16, 2020 05:00 PM | September 22, 2020 05:00 PM | September 09, 2020 05:00 PM | September 15, 2020 05:00 PM | As Soon As Possible |  | No | 5 days | 5 days | 0 days | Electrician
248 | Yes | CMU1.10.8.3 | Auto Scheduled | งานกล้องวงจรปิด ชั้น 2 | 7 days | 4 | 121FS-7 days |  |  | April 1, 2020 8:00 AM | April 7, 2020 5:00 PM | April 07, 2020 05:00 PM | April 13, 2020 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Electrician
249 | Yes | CMU1.10.8.4 | Auto Scheduled | งานกล้องวงจรปิด ชั้น 3 | 7 days | 4 | 92FS-7 days |  |  | October 4, 2019 8:00 AM | October 10, 2019 5:00 PM | October 11, 2019 05:00 PM | October 17, 2019 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Electrician
250 | Yes | CMU1.10.8.5 | Auto Scheduled | งานกล้องวงจรปิด ชั้น 4 | 7 days | 4 | 63FS-7 days |  |  | April 7, 2019 8:00 AM | April 13, 2019 5:00 PM | April 10, 2019 05:00 PM | April 16, 2019 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 537 days | 537 days | 537 days | Electrician

## solutoion_16
ID | Active | WBS | Task_Mode | Name | Duration | Outline_Level | Predecessors | Predecessors2 | Successors | Start_Date | Finish_Date | Early_Start | Early_Finish | Late_Start | Late_Finish | Constraint_Type | Constraint_Date | Summary | Start_Slack | Finish_Slack | Free_Slack | Resource_Names
1 | Yes | CMU1 | Auto Scheduled | โครงการปรับปรุงสำนักหอสมุด มหาวิทยาลัยเชียงใหม่ | 716 days | 1 |  |  |  | October 17, 2018 8:00 AM | October 1, 2020 5:00 PM | October 17, 2018 05:00 PM | October 01, 2020 05:00 PM | October 21, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 0 days | 0 days | 0 days
2 | Yes | CMU1.1 | Auto Scheduled | หมวดเตรียมการ | 675 days | 2 |  |  |  | October 17, 2018 8:00 AM | August 21, 2020 5:00 PM | October 17, 2018 05:00 PM | August 21, 2020 05:00 PM | December 01, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 41 days | 41 days | 41 days
3 | Yes | CMU1.1.1 | Auto Scheduled | งานอาคารสนามและผังบริเวณโครงการ | 14 days | 3 | 4FS-7 days |  |  | October 26, 2018 8:00 AM | November 8, 2018 5:00 PM | November 01, 2018 05:00 PM | November 14, 2018 05:00 PM | September 22, 2020 05:00 PM | October 05, 2020 05:00 PM | Start No Earlier Than | Oct 24 '18 | No | 693 days | 693 days | 693 days | Engineer
4 | Yes | CMU1.1.2 | Auto Scheduled | งานเชื่อมต่อระบบสาธารณูปโภคโครงการ | 16 days | 3 |  |  | 3FS-7 days | October 17, 2018 8:00 AM | November 1, 2018 5:00 PM | October 19, 2018 05:00 PM | November 03, 2018 05:00 PM | September 13, 2020 05:00 PM | September 28, 2020 05:00 PM | As Soon As Possible |  | No | 693 days | 693 days | 0 days | Engineer
5 | Yes | CMU1.1.3 | Auto Scheduled | งานตรวจทดสอบระบบภายในอาคารก่อนดำเนินการปรับปรุง | 675 days | 3 |  |  |  | October 17, 2018 8:00 AM | August 21, 2020 5:00 PM | October 17, 2018 05:00 PM | August 21, 2020 05:00 PM | December 01, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 41 days | 41 days | 41 days
6 | Yes | CMU1.1.3.1 | Auto Scheduled | ชั้นที่ 4 | 15 days | 4 |  |  | 7FS+150 days | October 17, 2018 8:00 AM | October 31, 2018 5:00 PM | October 20, 2018 05:00 PM | November 03, 2018 05:00 PM | December 01, 2018 05:00 PM | December 15, 2018 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
7 | Yes | CMU1.1.3.2 | Auto Scheduled | ชั้นที่ 3 | 15 days | 4 | 6FS+150 days |  | 8FS+150 days | March 31, 2019 8:00 AM | April 14, 2019 5:00 PM | April 09, 2019 05:00 PM | April 23, 2019 05:00 PM | May 15, 2019 05:00 PM | May 29, 2019 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
8 | Yes | CMU1.1.3.3 | Auto Scheduled | ชั้นที่ 2 | 15 days | 4 | 7FS+150 days |  | 9FS+150 days | September 12, 2019 8:00 AM | September 26, 2019 5:00 PM | October 01, 2019 05:00 PM | October 15, 2019 05:00 PM | October 27, 2019 05:00 PM | November 10, 2019 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
9 | Yes | CMU1.1.3.4 | Auto Scheduled | ชั้นที่ 1 | 15 days | 4 | 8FS+150 days |  | 10FS+150 days | February 24, 2020 8:00 AM | March 9, 2020 5:00 PM | March 22, 2020 05:00 PM | April 05, 2020 05:00 PM | April 09, 2020 05:00 PM | April 23, 2020 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
10 | Yes | CMU1.1.3.5 | Auto Scheduled | ชั้นใต้ดินและภายนอก | 15 days | 4 | 9FS+150 days |  |  | August 7, 2020 8:00 AM | August 21, 2020 5:00 PM | September 13, 2020 05:00 PM | September 27, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 41 days | Engineer
11 | Yes | CMU1.1.4 | Auto Scheduled | งานสำรวจอุปกรณ์ไฟฟ้า, สุขภัณฑ์และครุภัณฑ์ (ของเดิม) ก่อนดำเนินการปรับปรุง | 675 days | 3 |  |  |  | October 17, 2018 8:00 AM | August 21, 2020 5:00 PM | October 17, 2018 05:00 PM | August 21, 2020 05:00 PM | December 01, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 41 days | 41 days | 41 days
12 | Yes | CMU1.1.4.1 | Auto Scheduled | ชั้นที่ 4 | 15 days | 4 |  |  | 13FS+150 days | October 17, 2018 8:00 AM | October 31, 2018 5:00 PM | October 20, 2018 05:00 PM | November 03, 2018 05:00 PM | December 01, 2018 05:00 PM | December 15, 2018 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
13 | Yes | CMU1.1.4.2 | Auto Scheduled | ชั้นที่ 3 | 15 days | 4 | 12FS+150 days |  | 14FS+150 days | March 31, 2019 8:00 AM | April 14, 2019 5:00 PM | April 06, 2019 05:00 PM | April 20, 2019 05:00 PM | May 15, 2019 05:00 PM | May 29, 2019 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
14 | Yes | CMU1.1.4.3 | Auto Scheduled | ชั้นที่ 2 | 15 days | 4 | 13FS+150 days |  | 15FS+150 days | September 12, 2019 8:00 AM | September 26, 2019 5:00 PM | September 24, 2019 05:00 PM | October 08, 2019 05:00 PM | October 27, 2019 05:00 PM | November 10, 2019 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
15 | Yes | CMU1.1.4.4 | Auto Scheduled | ชั้นที่ 1 | 15 days | 4 | 14FS+150 days |  | 16FS+150 days | February 24, 2020 8:00 AM | March 9, 2020 5:00 PM | March 14, 2020 05:00 PM | March 28, 2020 05:00 PM | April 09, 2020 05:00 PM | April 23, 2020 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 0 days | Engineer
16 | Yes | CMU1.1.4.5 | Auto Scheduled | ชั้นใต้ดินและภายนอก | 15 days | 4 | 15FS+150 days |  |  | August 7, 2020 8:00 AM | August 21, 2020 5:00 PM | September 02, 2020 05:00 PM | September 16, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 41 days | 41 days | 41 days | Engineer
17 | Yes | CMU1.1.5 | Auto Scheduled | งานเอกสารขออนุมัติใช้วัสดุ, Shop Drawing และครุภัณฑ์ของโครงการ | 106 days | 3 |  |  |  | October 17, 2018 8:00 AM | January 30, 2019 5:00 PM | October 22, 2018 05:00 PM | February 04, 2019 05:00 PM | June 22, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 610 days | 610 days | 610 days
18 | Yes | CMU1.1.5.1 | Auto Scheduled | แบบ Shop Drawing ชั้นที่ 4 | 20 days | 4 |  |  | 19,25SS+14 days,26SS+14 days | October 17, 2018 8:00 AM | November 5, 2018 5:00 PM | October 17, 2018 05:00 PM | November 05, 2018 05:00 PM | October 01, 2018 05:00 PM | October 20, 2018 05:00 PM | As Soon As Possible |  | No | 610 days | 610 days | 0 days | Engineer
19 | Yes | CMU1.1.5.2 | Auto Scheduled | แบบ Shop Drawing ชั้นที่ 3 | 20 days | 4 | 18 |  | 20FS-7 days | November 6, 2018 8:00 AM | November 25, 2018 5:00 PM | November 13, 2018 05:00 PM | December 02, 2018 05:00 PM | July 13, 2020 05:00 PM | August 01, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
20 | Yes | CMU1.1.5.3 | Auto Scheduled | แบบ Shop Drawing ชั้นที่ 2 | 20 days | 4 | 19FS-7 days |  | 21FS-7 days | November 19, 2018 8:00 AM | December 8, 2018 5:00 PM | November 30, 2018 05:00 PM | December 19, 2018 05:00 PM | July 26, 2020 05:00 PM | August 14, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
21 | Yes | CMU1.1.5.4 | Auto Scheduled | แบบ Shop Drawing ชั้นที่ 1 | 20 days | 4 | 20FS-7 days |  | 22FS-7 days | December 2, 2018 8:00 AM | December 21, 2018 5:00 PM | December 19, 2018 05:00 PM | January 07, 2019 05:00 PM | August 08, 2020 05:00 PM | August 27, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
22 | Yes | CMU1.1.5.5 | Auto Scheduled | แบบ Shop Drawing ชั้นใต้ดิน | 20 days | 4 | 21FS-7 days |  | 23FS-7 days | December 15, 2018 8:00 AM | January 3, 2019 5:00 PM | January 07, 2019 05:00 PM | January 26, 2019 05:00 PM | August 21, 2020 05:00 PM | September 09, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
23 | Yes | CMU1.1.5.6 | Auto Scheduled | แบบ Shop Drawing ภายนอกอาคาร | 20 days | 4 | 22FS-7 days |  | 24FS-7 days | December 28, 2018 8:00 AM | January 16, 2019 5:00 PM | January 24, 2019 05:00 PM | February 12, 2019 05:00 PM | September 03, 2020 05:00 PM | September 22, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 0 days | Engineer
24 | Yes | CMU1.1.5.7 | Auto Scheduled | แบบ Shop Drawing landscape | 20 days | 4 | 23FS-7 days |  |  | January 10, 2019 8:00 AM | January 29, 2019 5:00 PM | February 13, 2019 05:00 PM | March 04, 2019 05:00 PM | September 16, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 611 days | 611 days | 611 days | Engineer
25 | Yes | CMU1.1.5.8 | Auto Scheduled | แบบ Shop Drawing งานปรับปรุง ครุภัณฑ์ | 92 days | 4 | 18SS+14 days |  |  | October 31, 2018 8:00 AM | January 30, 2019 5:00 PM | November 12, 2018 05:00 PM | February 11, 2019 05:00 PM | July 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 610 days | 610 days | 610 days | Engineer
26 | Yes | CMU1.1.5.9 | Auto Scheduled | แบบ Shop Drawing งานจัดซื้อครุภัณฑ์ | 92 days | 4 | 18SS+14 days |  |  | October 31, 2018 8:00 AM | January 30, 2019 5:00 PM | November 07, 2018 05:00 PM | February 06, 2019 05:00 PM | July 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 610 days | 610 days | 610 days | Engineer
27 | Yes | CMU1.1.6 | Auto Scheduled | งานตรวจทดสอบระบบ, งานอบรมผู้ใช้อาคาร และ As-Built Drawing | 30 days | 3 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 22, 2018 05:00 PM | November 20, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 686 days | 686 days | 686 days
28 | Yes | CMU1.1.6.1 | Auto Scheduled | ชั้นที่ 4 | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 27, 2018 05:00 PM | November 25, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
29 | Yes | CMU1.1.6.2 | Auto Scheduled | ชั้นที่ 3 | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 26, 2018 05:00 PM | November 24, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
30 | Yes | CMU1.1.6.3 | Auto Scheduled | ชั้นที่ 2 | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 22, 2018 05:00 PM | November 20, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
31 | Yes | CMU1.1.6.4 | Auto Scheduled | ชั้นที่ 1 | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 29, 2018 05:00 PM | November 27, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
32 | Yes | CMU1.1.6.5 | Auto Scheduled | ชั้นใต้ดิน | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 24, 2018 05:00 PM | November 22, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
33 | Yes | CMU1.1.6.6 | Auto Scheduled | ทั้งอาคาร | 30 days | 4 |  |  |  | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 23, 2018 05:00 PM | November 21, 2018 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 686 days | 686 days | 686 days | Engineer
34 | Yes | CMU1.1.7 | Auto Scheduled | งานบริหารงานก่อสร้างและงานอื่น ๆ | 0 days | 3 |  |  |  | October 17, 2018 8:00 AM | October 17, 2018 8:00 AM | October 20, 2018 05:00 PM | October 19, 2018 05:00 PM | October 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 716 days | 716 days | 716 days | Engineer
35 | Yes | CMU1.2 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้น 4 | 471 days | 2 |  |  |  | October 17, 2018 8:00 AM | January 30, 2020 5:00 PM | October 17, 2018 05:00 PM | January 30, 2020 05:00 PM | June 23, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 0 days | 245 days | 0 days
36 | Yes | CMU1.2.1 | Auto Scheduled | งานรื้อถอน ชั้น 4 (รื้อขนไป) | 30 days | 3 |  |  | 39FS+45 days,40FS+45 days,51,63SS+14 days,80,109,140,180FS+14 days,186FS+14 days,198FS+14 days,199FS+14 days,200FS+14 days,238FS+14 days | October 17, 2018 8:00 AM | November 15, 2018 5:00 PM | October 17, 2018 05:00 PM | November 15, 2018 05:00 PM | March 11, 2018 05:00 PM | April 09, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | General worker
37 | Yes | CMU1.2.2 | Auto Scheduled | งานสถาปัตยกรรม ชั้น 4 | 396 days | 3 |  |  |  | December 31, 2018 8:00 AM | January 30, 2020 5:00 PM | October 17, 2018 05:00 PM | November 16, 2019 05:00 PM | September 06, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 326 days | 245 days | 245 days
38 | Yes | CMU1.2.2.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 39,41,42 |  |  | March 1, 2019 8:00 AM | March 30, 2019 5:00 PM | March 13, 2019 05:00 PM | April 11, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 551 days | Skilled carpenter
39 | Yes | CMU1.2.2.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 36FS+45 days |  | 38,43 | December 31, 2018 8:00 AM | February 28, 2019 5:00 PM | January 05, 2019 05:00 PM | March 05, 2019 05:00 PM | July 15, 2020 05:00 PM | September 12, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 0 days | General worker
40 | Yes | CMU1.2.2.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 36FS+45 days |  | 41,42 | December 31, 2018 8:00 AM | January 29, 2019 5:00 PM | January 03, 2019 05:00 PM | February 01, 2019 05:00 PM | August 14, 2020 05:00 PM | September 12, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 0 days | General worker
41 | Yes | CMU1.2.2.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 40 |  | 38,43 | January 30, 2019 8:00 AM | February 28, 2019 5:00 PM | February 05, 2019 05:00 PM | March 06, 2019 05:00 PM | August 14, 2020 05:00 PM | September 12, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 0 days | Skilled carpenter
42 | Yes | CMU1.2.2.5 | Auto Scheduled | งานบันได | 30 days | 4 | 40 |  | 38,43 | January 30, 2019 8:00 AM | February 28, 2019 5:00 PM | February 05, 2019 05:00 PM | March 06, 2019 05:00 PM | August 14, 2020 05:00 PM | September 12, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 0 days | General worker
43 | Yes | CMU1.2.2.6 | Auto Scheduled | งานสี | 30 days | 4 | 39,41,42 |  |  | March 1, 2019 8:00 AM | March 30, 2019 5:00 PM | March 10, 2019 05:00 PM | April 08, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 551 days | 551 days | 551 days | General worker
44 | Yes | CMU1.2.2.7 | Auto Scheduled | งานสุขภัณฑ์ | 315 days | 4 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 20, 2018 05:00 PM | August 30, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
45 | Yes | CMU1.2.2.7.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 46FS+135 days |  | 47FS+135 days | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | September 11, 2019 05:00 PM | September 25, 2019 05:00 PM | April 24, 2020 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
46 | Yes | CMU1.2.2.7.2 | Auto Scheduled | ZONE T-2 กลาง | 15 days | 5 | 51,55 |  | 45FS+135 days | March 22, 2019 8:00 AM | April 5, 2019 5:00 PM | April 08, 2019 05:00 PM | April 22, 2019 05:00 PM | November 26, 2019 05:00 PM | December 10, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
47 | Yes | CMU1.2.2.7.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 15 days | 5 | 45FS+135 days |  |  | January 16, 2020 8:00 AM | January 30, 2020 5:00 PM | February 15, 2020 05:00 PM | February 29, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 245 days | Sanitary-Plumber
48 | Yes | CMU1.2.3 | Auto Scheduled | งานระบบสุขาภิบาล ชั้น 4 | 408 days | 3 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
49 | Yes | CMU1.2.3.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
50 | Yes | CMU1.2.3.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 51FS+15 days |  | 52FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 17, 2019 05:00 PM | August 20, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
51 | Yes | CMU1.2.3.1.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 36 |  | 50FS+15 days,46,55SS | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 23, 2018 05:00 PM | March 28, 2019 05:00 PM | August 25, 2019 05:00 PM | December 28, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
52 | Yes | CMU1.2.3.1.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 50FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 09, 2019 05:00 PM | January 12, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
53 | Yes | CMU1.2.3.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
54 | Yes | CMU1.2.3.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 55FS+15 days |  | 56FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 25, 2019 05:00 PM | August 28, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
55 | Yes | CMU1.2.3.2.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 51SS |  | 54FS+15 days,46 | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 28, 2018 05:00 PM | April 02, 2019 05:00 PM | August 25, 2019 05:00 PM | December 28, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
56 | Yes | CMU1.2.3.2.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 54FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 24, 2019 05:00 PM | January 27, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
57 | Yes | CMU1.2.4 | Auto Scheduled | งานระบบไฟฟ้า ชั้น 4 | 117 days | 3 |  |  |  | November 30, 2018 8:00 AM | March 26, 2019 5:00 PM | October 21, 2018 05:00 PM | February 14, 2019 05:00 PM | June 11, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 555 days | 555 days | 555 days
58 | Yes | CMU1.2.4.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 30 days | 4 | 60FS+7 days |  |  | February 25, 2019 8:00 AM | March 26, 2019 5:00 PM | March 04, 2019 05:00 PM | April 02, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 555 days | 555 days | 555 days | Electrician
59 | Yes | CMU1.2.4.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 30 days | 4 | 60FS+7 days |  |  | February 25, 2019 8:00 AM | March 26, 2019 5:00 PM | March 05, 2019 05:00 PM | April 03, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 555 days | 555 days | 555 days | Electrician
60 | Yes | CMU1.2.4.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 63SS+30 days |  | 58FS+7 days,59FS+7 days | November 30, 2018 8:00 AM | February 17, 2019 5:00 PM | December 04, 2018 05:00 PM | February 21, 2019 05:00 PM | June 11, 2020 05:00 PM | August 29, 2020 05:00 PM | As Soon As Possible |  | No | 555 days | 555 days | 0 days | Electrician
61 | Yes | CMU1.2.4.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 63SS+30 days |  |  | November 30, 2018 8:00 AM | February 17, 2019 5:00 PM | December 04, 2018 05:00 PM | February 21, 2019 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 592 days | 592 days | 592 days | Electrician
62 | Yes | CMU1.2.4.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 63SS+30 days |  |  | November 30, 2018 8:00 AM | February 17, 2019 5:00 PM | December 04, 2018 05:00 PM | February 21, 2019 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 592 days | 592 days | 592 days | Electrician
63 | Yes | CMU1.2.5 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้น 4 | 165 days | 3 | 36SS+14 days |  | 62SS+30 days,60SS+30 days,61SS+30 days,65,214,219FS-15 days,224,230,244FS-7 days,250FS-7 days | October 31, 2018 8:00 AM | April 13, 2019 5:00 PM | October 31, 2018 05:00 PM | April 13, 2019 05:00 PM | June 19, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Skilled carpenter
64 | Yes | CMU1.3 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้น 3 | 441 days | 2 |  |  |  | November 16, 2018 8:00 AM | January 30, 2020 5:00 PM | October 17, 2018 05:00 PM | December 31, 2019 05:00 PM | July 23, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 149 days | 245 days | 149 days
65 | Yes | CMU1.3.1 | Auto Scheduled | งานรื้อถอน ชั้น 3 (รื้อขนไป) | 30 days | 3 | 63 | 121 | 68FS+45 days,69FS+45 days,92SS | April 14, 2019 8:00 AM | May 13, 2019 5:00 PM | April 14, 2019 05:00 PM | May 13, 2019 05:00 PM | July 19, 2018 05:00 PM | August 17, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | General worker
66 | Yes | CMU1.3.2 | Auto Scheduled | งานสถาปัตยกรรม ชั้น 3 | 315 days | 3 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 23, 2018 05:00 PM | September 02, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
67 | Yes | CMU1.3.2.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 68,70,71 |  |  | August 27, 2019 8:00 AM | September 25, 2019 5:00 PM | August 31, 2019 05:00 PM | September 29, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 372 days | Skilled carpenter
68 | Yes | CMU1.3.2.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 65FS+45 days |  | 67,72 | June 28, 2019 8:00 AM | August 26, 2019 5:00 PM | June 28, 2019 05:00 PM | August 26, 2019 05:00 PM | October 02, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 0 days | General worker
69 | Yes | CMU1.3.2.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 65FS+45 days |  | 70,71 | June 28, 2019 8:00 AM | July 27, 2019 5:00 PM | June 28, 2019 05:00 PM | July 27, 2019 05:00 PM | April 15, 2019 05:00 PM | May 14, 2019 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 0 days | General worker
70 | Yes | CMU1.3.2.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 69 |  | 67,72 | July 28, 2019 8:00 AM | August 26, 2019 5:00 PM | July 28, 2019 05:00 PM | August 26, 2019 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 0 days | Skilled carpenter
71 | Yes | CMU1.3.2.5 | Auto Scheduled | งานบันได | 30 days | 4 | 69 |  | 67,72 | July 28, 2019 8:00 AM | August 26, 2019 5:00 PM | July 28, 2019 05:00 PM | August 26, 2019 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 0 days | General worker
72 | Yes | CMU1.3.2.6 | Auto Scheduled | งานสี | 30 days | 4 | 68,70,71 |  |  | August 27, 2019 8:00 AM | September 25, 2019 5:00 PM | August 30, 2019 05:00 PM | September 28, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 372 days | 372 days | 372 days | General worker
73 | Yes | CMU1.3.2.7 | Auto Scheduled | งานสุขภัณฑ์ | 315 days | 4 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 21, 2018 05:00 PM | August 31, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
74 | Yes | CMU1.3.2.7.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 75FS+135 days |  | 76FS+135 days | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | August 25, 2019 05:00 PM | September 08, 2019 05:00 PM | April 24, 2020 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
75 | Yes | CMU1.3.2.7.2 | Auto Scheduled | ZONE T-2 กลาง | 15 days | 5 | 80,84 |  | 74FS+135 days | March 22, 2019 8:00 AM | April 5, 2019 5:00 PM | March 24, 2019 05:00 PM | April 07, 2019 05:00 PM | November 26, 2019 05:00 PM | December 10, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
76 | Yes | CMU1.3.2.7.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 15 days | 5 | 74FS+135 days |  |  | January 16, 2020 8:00 AM | January 30, 2020 5:00 PM | January 28, 2020 05:00 PM | February 11, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 245 days | Sanitary-Plumber
77 | Yes | CMU1.3.3 | Auto Scheduled | งานระบบสุขาภิบาล ชั้น 3 | 408 days | 3 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
78 | Yes | CMU1.3.3.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
79 | Yes | CMU1.3.3.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 80FS+15 days |  | 81FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 16, 2019 05:00 PM | August 19, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
80 | Yes | CMU1.3.3.1.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 36 |  | 79FS+15 days,84SS,75 | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 16, 2018 05:00 PM | March 21, 2019 05:00 PM | January 09, 2019 05:00 PM | May 14, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
81 | Yes | CMU1.3.3.1.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 79FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 08, 2019 05:00 PM | January 11, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
82 | Yes | CMU1.3.3.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
83 | Yes | CMU1.3.3.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 84FS+15 days |  | 85FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 12, 2019 05:00 PM | August 15, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
84 | Yes | CMU1.3.3.2.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 80SS |  | 83FS+15 days,75 | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 16, 2018 05:00 PM | March 21, 2019 05:00 PM | January 09, 2019 05:00 PM | May 14, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
85 | Yes | CMU1.3.3.2.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 83FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 10, 2019 05:00 PM | January 13, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
86 | Yes | CMU1.3.4 | Auto Scheduled | งานระบบไฟฟ้า ชั้น 3 | 147 days | 3 |  |  |  | May 14, 2019 8:00 AM | October 7, 2019 5:00 PM | October 21, 2018 05:00 PM | March 16, 2019 05:00 PM | May 12, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 360 days | 360 days | 360 days
87 | Yes | CMU1.3.4.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 60 days | 4 | 89FS+7 days |  |  | August 9, 2019 8:00 AM | October 7, 2019 5:00 PM | August 18, 2019 05:00 PM | October 16, 2019 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 360 days | 360 days | 360 days | Electrician
88 | Yes | CMU1.3.4.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 60 days | 4 | 89FS+7 days |  |  | August 9, 2019 8:00 AM | October 7, 2019 5:00 PM | August 24, 2019 05:00 PM | October 22, 2019 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 360 days | 360 days | 360 days | Electrician
89 | Yes | CMU1.3.4.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 92SS+30 days |  | 88FS+7 days,87FS+7 days | May 14, 2019 8:00 AM | August 1, 2019 5:00 PM | May 20, 2019 05:00 PM | August 07, 2019 05:00 PM | May 12, 2020 05:00 PM | July 30, 2020 05:00 PM | As Soon As Possible |  | No | 360 days | 360 days | 0 days | Electrician
90 | Yes | CMU1.3.4.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 92SS+30 days |  |  | May 14, 2019 8:00 AM | August 1, 2019 5:00 PM | May 23, 2019 05:00 PM | August 10, 2019 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 427 days | 427 days | 427 days | Electrician
91 | Yes | CMU1.3.4.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 92SS+30 days |  |  | May 14, 2019 8:00 AM | August 1, 2019 5:00 PM | May 24, 2019 05:00 PM | August 11, 2019 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 427 days | 427 days | 427 days | Electrician
92 | Yes | CMU1.3.5 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้น 3 | 180 days | 3 | 65SS |  | 91SS+30 days,90SS+30 days,89SS+30 days,94,213FS-15 days,218FS-30 days,223FS-15 days,229FS-15 days,243FS-7 days,249FS-7 days | April 14, 2019 8:00 AM | October 10, 2019 5:00 PM | April 18, 2019 05:00 PM | October 14, 2019 05:00 PM | October 12, 2019 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Skilled carpenter
93 | Yes | CMU1.4 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้น 2 | 509 days | 2 |  |  |  | November 16, 2018 8:00 AM | April 7, 2020 5:00 PM | October 17, 2018 05:00 PM | March 08, 2020 05:00 PM | May 16, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 177 days | 177 days
94 | Yes | CMU1.4.1 | Auto Scheduled | งานรื้อถอน ชั้น 2 (รื้อขนไป) | 30 days | 3 | 92 | 152 | 97FS+45 days,98FS+45 days,121SS | October 11, 2019 8:00 AM | November 9, 2019 5:00 PM | October 15, 2019 05:00 PM | November 13, 2019 05:00 PM | June 04, 2018 05:00 PM | July 03, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | General worker
95 | Yes | CMU1.4.2 | Auto Scheduled | งานสถาปัตยกรรม ชั้น 2 | 368 days | 3 |  |  |  | March 22, 2019 8:00 AM | March 23, 2020 5:00 PM | October 17, 2018 05:00 PM | October 19, 2019 05:00 PM | October 04, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 192 days | 192 days
96 | Yes | CMU1.4.2.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 97,99,100 |  |  | February 23, 2020 8:00 AM | March 23, 2020 5:00 PM | March 08, 2020 05:00 PM | April 06, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 192 days | Skilled carpenter
97 | Yes | CMU1.4.2.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 94FS+45 days |  | 96,101 | December 25, 2019 8:00 AM | February 22, 2020 5:00 PM | December 29, 2019 05:00 PM | February 26, 2020 05:00 PM | February 09, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 0 days | General worker
98 | Yes | CMU1.4.2.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 94FS+45 days |  | 99,100 | December 25, 2019 8:00 AM | January 23, 2020 5:00 PM | January 01, 2020 05:00 PM | January 30, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 0 days | General worker
99 | Yes | CMU1.4.2.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 98 |  | 96,101 | January 24, 2020 8:00 AM | February 22, 2020 5:00 PM | February 04, 2020 05:00 PM | March 04, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 0 days | Skilled carpenter
100 | Yes | CMU1.4.2.5 | Auto Scheduled | งานบันได | 30 days | 4 | 98 |  | 96,101 | January 24, 2020 8:00 AM | February 22, 2020 5:00 PM | February 03, 2020 05:00 PM | March 03, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 0 days | General worker
101 | Yes | CMU1.4.2.6 | Auto Scheduled | งานสี | 30 days | 4 | 97,99,100 |  |  | February 23, 2020 8:00 AM | March 23, 2020 5:00 PM | March 11, 2020 05:00 PM | April 09, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 192 days | 192 days | 192 days | General worker
102 | Yes | CMU1.4.2.7 | Auto Scheduled | งานสุขภัณฑ์ | 315 days | 4 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 22, 2018 05:00 PM | September 01, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
103 | Yes | CMU1.4.2.7.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 104FS+135 days |  | 105FS+135 days | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | September 08, 2019 05:00 PM | September 22, 2019 05:00 PM | April 24, 2020 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
104 | Yes | CMU1.4.2.7.2 | Auto Scheduled | ZONE T-2 กลาง | 15 days | 5 | 113,109 |  | 103FS+135 days | March 22, 2019 8:00 AM | April 5, 2019 5:00 PM | April 07, 2019 05:00 PM | April 21, 2019 05:00 PM | November 26, 2019 05:00 PM | December 10, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
105 | Yes | CMU1.4.2.7.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 15 days | 5 | 103FS+135 days |  |  | January 16, 2020 8:00 AM | January 30, 2020 5:00 PM | February 10, 2020 05:00 PM | February 24, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 245 days | Sanitary-Plumber
106 | Yes | CMU1.4.3 | Auto Scheduled | งานระบบสุขาภิบาล ชั้น 2 | 408 days | 3 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
107 | Yes | CMU1.4.3.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
108 | Yes | CMU1.4.3.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 109FS+15 days |  | 110FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 17, 2019 05:00 PM | August 20, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
109 | Yes | CMU1.4.3.1.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 36 |  | 113SS,104,108FS+15 days | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 22, 2018 05:00 PM | March 27, 2019 05:00 PM | August 25, 2019 05:00 PM | December 28, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
110 | Yes | CMU1.4.3.1.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 108FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 08, 2019 05:00 PM | January 11, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
111 | Yes | CMU1.4.3.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 278 days | 245 days
112 | Yes | CMU1.4.3.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 113FS+15 days |  | 114FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 27, 2019 05:00 PM | August 30, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
113 | Yes | CMU1.4.3.2.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 109SS |  | 104,112FS+15 days | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 28, 2018 05:00 PM | April 02, 2019 05:00 PM | August 25, 2019 05:00 PM | December 28, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
114 | Yes | CMU1.4.3.2.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 112FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 19, 2019 05:00 PM | January 22, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
115 | Yes | CMU1.4.4 | Auto Scheduled | งานระบบไฟฟ้า ชั้น 2 | 147 days | 3 |  |  |  | November 10, 2019 8:00 AM | April 4, 2020 5:00 PM | October 20, 2018 05:00 PM | March 15, 2019 05:00 PM | May 12, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 180 days | 180 days | 180 days
116 | Yes | CMU1.4.4.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 60 days | 4 | 118FS+7 days |  |  | February 5, 2020 8:00 AM | April 4, 2020 5:00 PM | February 13, 2020 05:00 PM | April 12, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 180 days | 180 days | 180 days | Electrician
117 | Yes | CMU1.4.4.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 60 days | 4 | 118FS+7 days |  |  | February 5, 2020 8:00 AM | April 4, 2020 5:00 PM | February 14, 2020 05:00 PM | April 13, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 180 days | 180 days | 180 days | Electrician
118 | Yes | CMU1.4.4.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 121SS+30 days |  | 117FS+7 days,116FS+7 days | November 10, 2019 8:00 AM | January 28, 2020 5:00 PM | November 16, 2019 05:00 PM | February 03, 2020 05:00 PM | May 12, 2020 05:00 PM | July 30, 2020 05:00 PM | As Soon As Possible |  | No | 180 days | 180 days | 0 days | Electrician
119 | Yes | CMU1.4.4.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 121SS+30 days |  |  | November 10, 2019 8:00 AM | January 28, 2020 5:00 PM | November 18, 2019 05:00 PM | February 05, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 247 days | 247 days | 247 days | Electrician
120 | Yes | CMU1.4.4.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 121SS+30 days |  |  | November 10, 2019 8:00 AM | January 28, 2020 5:00 PM | November 21, 2019 05:00 PM | February 08, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 247 days | 247 days | 247 days | Electrician
121 | Yes | CMU1.4.5 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้น 2 | 180 days | 3 | 94SS |  | 120SS+30 days,119SS+30 days,118SS+30 days,123,212FS-15 days,217FS-30 days,222FS-15 days,228FS-15 days,242FS-7 days,248FS-7 days | October 11, 2019 8:00 AM | April 7, 2020 5:00 PM | October 15, 2019 05:00 PM | April 11, 2020 05:00 PM | June 04, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Skilled carpenter
122 | Yes | CMU1.5 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้น 1 | 686 days | 2 |  |  |  | November 16, 2018 8:00 AM | October 1, 2020 5:00 PM | October 17, 2018 05:00 PM | September 01, 2020 05:00 PM | November 20, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 0 days | 0 days
123 | Yes | CMU1.5.1 | Auto Scheduled | งานรื้อถอน ชั้น 1 (รื้อขนไป) | 30 days | 3 | 121 | 63 | 124,127FS+45 days,128FS+45 days,131FS+45 days,152SS,193SS,194SS,195SS,196SS,197SS,202SS,204SS,205SS,206SS,207SS | April 8, 2020 8:00 AM | May 7, 2020 5:00 PM | April 12, 2020 05:00 PM | May 11, 2020 05:00 PM | July 19, 2018 05:00 PM | August 17, 2018 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | General worker
124 | Yes | CMU1.5.2 | Auto Scheduled | งานโครงสร้างวิศวกรรม ชั้น 1 | 75 days | 3 | 123 |  |  | May 8, 2020 8:00 AM | July 21, 2020 5:00 PM | May 13, 2020 05:00 PM | July 26, 2020 05:00 PM | July 23, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 72 days | 72 days | 72 days | General worker
125 | Yes | CMU1.5.3 | Auto Scheduled | งานสถาปัตยกรรม ชั้น 1 | 548 days | 3 |  |  |  | March 22, 2019 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | April 16, 2020 05:00 PM | April 07, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 12 days | 12 days
126 | Yes | CMU1.5.3.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 127,129,130 |  |  | August 21, 2020 8:00 AM | September 19, 2020 5:00 PM | August 25, 2020 05:00 PM | September 23, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | Skilled carpenter
127 | Yes | CMU1.5.3.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 123FS+45 days |  | 126,132 | June 22, 2020 8:00 AM | August 20, 2020 5:00 PM | June 26, 2020 05:00 PM | August 24, 2020 05:00 PM | October 02, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
128 | Yes | CMU1.5.3.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 123FS+45 days |  | 129,130 | June 22, 2020 8:00 AM | July 21, 2020 5:00 PM | June 26, 2020 05:00 PM | July 25, 2020 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
129 | Yes | CMU1.5.3.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 128 |  | 126,132 | July 22, 2020 8:00 AM | August 20, 2020 5:00 PM | July 26, 2020 05:00 PM | August 24, 2020 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | Skilled carpenter
130 | Yes | CMU1.5.3.5 | Auto Scheduled | งานบันได | 30 days | 4 | 128 |  | 126,132 | July 22, 2020 8:00 AM | August 20, 2020 5:00 PM | July 26, 2020 05:00 PM | August 24, 2020 05:00 PM | November 01, 2018 05:00 PM | November 30, 2018 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
131 | Yes | CMU1.5.3.6 | Auto Scheduled | งานตกแต่งอื่น ๆ | 60 days | 4 | 123FS+45 days |  |  | June 22, 2020 8:00 AM | August 20, 2020 5:00 PM | June 26, 2020 05:00 PM | August 24, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 42 days | 42 days | 42 days | General worker
132 | Yes | CMU1.5.3.7 | Auto Scheduled | งานสี | 30 days | 4 | 127,129,130 |  |  | August 21, 2020 8:00 AM | September 19, 2020 5:00 PM | August 25, 2020 05:00 PM | September 23, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
133 | Yes | CMU1.5.3.8 | Auto Scheduled | งานสุขภัณฑ์ | 315 days | 4 |  |  |  | March 22, 2019 8:00 AM | January 30, 2020 5:00 PM | October 22, 2018 05:00 PM | September 01, 2019 05:00 PM | November 26, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 245 days | 245 days | 245 days
134 | Yes | CMU1.5.3.8.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 135FS+135 days |  | 136FS+135 days | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | August 24, 2019 05:00 PM | September 07, 2019 05:00 PM | April 24, 2020 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
135 | Yes | CMU1.5.3.8.2 | Auto Scheduled | ZONE T-2 กลาง | 15 days | 5 | 140,144 |  | 134FS+135 days,164FS+135 days | March 22, 2019 8:00 AM | April 5, 2019 5:00 PM | March 24, 2019 05:00 PM | April 07, 2019 05:00 PM | November 26, 2019 05:00 PM | December 10, 2019 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 0 days | Sanitary-Plumber
136 | Yes | CMU1.5.3.8.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 15 days | 5 | 134FS+135 days |  |  | January 16, 2020 8:00 AM | January 30, 2020 5:00 PM | January 24, 2020 05:00 PM | February 07, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 245 days | 245 days | 245 days | Sanitary-Plumber
137 | Yes | CMU1.5.4 | Auto Scheduled | งานระบบสุขาภิบาล ชั้น 1 | 408 days | 3 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 278 days | 44 days
138 | Yes | CMU1.5.4.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 278 days | 44 days
139 | Yes | CMU1.5.4.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 140FS+15 days |  | 141FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 13, 2019 05:00 PM | August 16, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
140 | Yes | CMU1.5.4.1.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 36 |  | 139FS+15 days,144SS,135,167FS+15 days | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 16, 2018 05:00 PM | March 21, 2019 05:00 PM | January 03, 2019 05:00 PM | May 08, 2019 05:00 PM | As Soon As Possible |  | No | 44 days | 44 days | 0 days | Sanitary-Plumber
141 | Yes | CMU1.5.4.1.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 139FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 13, 2019 05:00 PM | January 16, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
142 | Yes | CMU1.5.4.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 408 days | 4 |  |  |  | November 16, 2018 8:00 AM | December 28, 2019 5:00 PM | October 17, 2018 05:00 PM | November 28, 2019 05:00 PM | August 25, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 278 days | 44 days
143 | Yes | CMU1.5.4.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 144FS+15 days |  | 145FS+15 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 12, 2019 05:00 PM | August 15, 2019 05:00 PM | January 13, 2020 05:00 PM | May 17, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 0 days | Sanitary-Plumber
144 | Yes | CMU1.5.4.2.2 | Auto Scheduled | ZONE T-2 กลาง | 126 days | 5 | 140SS |  | 143FS+15 days,135,169FS+15 days | November 16, 2018 8:00 AM | March 21, 2019 5:00 PM | November 16, 2018 05:00 PM | March 21, 2019 05:00 PM | January 03, 2019 05:00 PM | May 08, 2019 05:00 PM | As Soon As Possible |  | No | 44 days | 44 days | 0 days | Sanitary-Plumber
145 | Yes | CMU1.5.4.2.3 | Auto Scheduled | ZONE T-3 ด้านหลัง อาคารใหม่ | 126 days | 5 | 143FS+15 days |  |  | August 25, 2019 8:00 AM | December 28, 2019 5:00 PM | September 04, 2019 05:00 PM | January 07, 2020 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 278 days | 278 days | 278 days | Sanitary-Plumber
146 | Yes | CMU1.5.5 | Auto Scheduled | งานระบบไฟฟ้า ชั้น 1 | 147 days | 3 |  |  |  | May 8, 2020 8:00 AM | October 1, 2020 5:00 PM | October 21, 2018 05:00 PM | March 16, 2019 05:00 PM | May 12, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 0 days | 0 days | 0 days
147 | Yes | CMU1.5.5.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 60 days | 4 | 149FS+7 days |  |  | August 3, 2020 8:00 AM | October 1, 2020 5:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Electrician
148 | Yes | CMU1.5.5.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 60 days | 4 | 149FS+7 days |  |  | August 3, 2020 8:00 AM | October 1, 2020 5:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Electrician
149 | Yes | CMU1.5.5.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 152SS+30 days |  | 148FS+7 days,147FS+7 days | May 8, 2020 8:00 AM | July 26, 2020 5:00 PM | May 12, 2020 05:00 PM | July 30, 2020 05:00 PM | May 12, 2020 05:00 PM | July 30, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Electrician
150 | Yes | CMU1.5.5.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 152SS+30 days |  |  | May 8, 2020 8:00 AM | July 26, 2020 5:00 PM | May 12, 2020 05:00 PM | July 30, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 67 days | 67 days | 67 days | Electrician
151 | Yes | CMU1.5.5.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 152SS+30 days |  |  | May 8, 2020 8:00 AM | July 26, 2020 5:00 PM | May 12, 2020 05:00 PM | July 30, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 67 days | 67 days | 67 days | Electrician
152 | Yes | CMU1.5.6 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้น 1 | 165 days | 3 | 123SS |  | 151SS+30 days,150SS+30 days,149SS+30 days,154SS,211FS-30 days,210FS-30 days,216FS-45 days,221FS-30 days,227FS-30 days,226FS-30 days,232FS-45 days,241FS-7 days,247FS-7 days | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 12, 2020 05:00 PM | September 23, 2020 05:00 PM | November 26, 2019 05:00 PM | May 08, 2020 05:00 PM | As Soon As Possible |  | No | 0 days | 0 days | 0 days | Skilled carpenter
153 | Yes | CMU1.6 | Auto Scheduled | หมวดงานปรับปรุงอาคาร ชั้นใต้ดิน | 533 days | 2 |  |  |  | April 6, 2019 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | April 01, 2020 05:00 PM | April 22, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 12 days | 12 days
154 | Yes | CMU1.6.1 | Auto Scheduled | งานรื้อถอน ชั้นใต้ดิน (รื้อขนไป) | 30 days | 3 | 152SS |  | 155,158FS+45 days,159FS+45 days,177SS,176SS,175SS,174SS | April 8, 2020 8:00 AM | May 7, 2020 5:00 PM | April 12, 2020 05:00 PM | May 11, 2020 05:00 PM | November 26, 2019 05:00 PM | December 25, 2019 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
155 | Yes | CMU1.6.2 | Auto Scheduled | งานโครงสร้างวิศวกรรม ชั้นใต้ดิน | 75 days | 3 | 154 |  |  | May 8, 2020 8:00 AM | July 21, 2020 5:00 PM | May 13, 2020 05:00 PM | July 26, 2020 05:00 PM | July 23, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 72 days | 72 days | 72 days | General worker
156 | Yes | CMU1.6.3 | Auto Scheduled | งานสถาปัตยกรรม ชั้นใต้ดิน | 398 days | 3 |  |  |  | August 19, 2019 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | November 18, 2019 05:00 PM | September 04, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 320 days | 12 days | 12 days
157 | Yes | CMU1.6.3.1 | Auto Scheduled | งานฝ้าเพดาน | 30 days | 4 | 158,160,161 |  |  | August 21, 2020 8:00 AM | September 19, 2020 5:00 PM | September 22, 2020 05:00 PM | October 21, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | Skilled carpenter
158 | Yes | CMU1.6.3.2 | Auto Scheduled | งานพื้น | 60 days | 4 | 154FS+45 days |  | 157,162 | June 22, 2020 8:00 AM | August 20, 2020 5:00 PM | June 26, 2020 05:00 PM | August 24, 2020 05:00 PM | February 09, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
159 | Yes | CMU1.6.3.3 | Auto Scheduled | งานผนัง | 30 days | 4 | 154FS+45 days |  | 160,161 | June 22, 2020 8:00 AM | July 21, 2020 5:00 PM | July 24, 2020 05:00 PM | August 22, 2020 05:00 PM | August 22, 2020 05:00 PM | September 20, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
160 | Yes | CMU1.6.3.4 | Auto Scheduled | งานประตูหน้าต่าง | 30 days | 4 | 159 |  | 157,162 | July 22, 2020 8:00 AM | August 20, 2020 5:00 PM | August 23, 2020 05:00 PM | September 21, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | Skilled carpenter
161 | Yes | CMU1.6.3.5 | Auto Scheduled | งานบันได | 30 days | 4 | 159 |  | 157,162 | July 22, 2020 8:00 AM | August 20, 2020 5:00 PM | August 23, 2020 05:00 PM | September 21, 2020 05:00 PM | March 10, 2020 05:00 PM | April 08, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 0 days | General worker
162 | Yes | CMU1.6.3.6 | Auto Scheduled | งานสี | 30 days | 4 | 158,160,161 |  |  | August 21, 2020 8:00 AM | September 19, 2020 5:00 PM | September 22, 2020 05:00 PM | October 21, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
163 | Yes | CMU1.6.3.7 | Auto Scheduled | งานสุขภัณฑ์ | 15 days | 4 |  |  |  | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | October 20, 2018 05:00 PM | November 03, 2018 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 395 days | 395 days | 395 days
164 | Yes | CMU1.6.3.7.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 15 days | 5 | 135FS+135 days |  |  | August 19, 2019 8:00 AM | September 2, 2019 5:00 PM | August 27, 2019 05:00 PM | September 10, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 395 days | 395 days | 395 days | Sanitary-Plumber
165 | Yes | CMU1.6.4 | Auto Scheduled | งานระบบสุขาภิบาล ชั้นใต้ดิน | 501 days | 3 |  |  |  | April 6, 2019 8:00 AM | August 18, 2020 5:00 PM | October 17, 2018 05:00 PM | February 29, 2020 05:00 PM | May 24, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 44 days | 44 days
166 | Yes | CMU1.6.4.1 | Auto Scheduled | งานระบบท่อจ่ายน้ำประปา | 126 days | 4 |  |  |  | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | October 21, 2018 05:00 PM | February 23, 2019 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 419 days | 419 days | 419 days
167 | Yes | CMU1.6.4.1.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 140FS+15 days |  |  | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 14, 2019 05:00 PM | August 17, 2019 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 419 days | 419 days | 419 days | Sanitary-Plumber
168 | Yes | CMU1.6.4.2 | Auto Scheduled | งานระบบท่อน้ำโสโครก ท่อน้ำทิ้งทั่วไป และท่ออากาศ | 126 days | 4 |  |  |  | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | October 21, 2018 05:00 PM | February 23, 2019 05:00 PM | June 02, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 44 days | 44 days | 44 days
169 | Yes | CMU1.6.4.2.1 | Auto Scheduled | ZONE T-1 ด้านหน้า อาคารเก่า | 126 days | 5 | 144FS+15 days |  | 170FS+300 days | April 6, 2019 8:00 AM | August 9, 2019 5:00 PM | April 06, 2019 05:00 PM | August 09, 2019 05:00 PM | May 24, 2019 05:00 PM | September 26, 2019 05:00 PM | As Soon As Possible |  | No | 44 days | 44 days | 0 days | Sanitary-Plumber
170 | Yes | CMU1.6.4.3 | Auto Scheduled | งานระบบระบายน้ำฝน | 75 days | 4 | 169FS+300 days |  |  | June 5, 2020 8:00 AM | August 18, 2020 5:00 PM | June 05, 2020 05:00 PM | August 18, 2020 05:00 PM | July 23, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 44 days | 44 days | 44 days | Sanitary-Plumber
171 | Yes | CMU1.6.5 | Auto Scheduled | งานระบบไฟฟ้า ชั้นใต้ดิน | 147 days | 3 |  |  |  | April 8, 2020 8:00 AM | September 1, 2020 5:00 PM | October 23, 2018 05:00 PM | March 18, 2019 05:00 PM | May 12, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 30 days | 30 days | 30 days
172 | Yes | CMU1.6.5.1 | Auto Scheduled | งานดวงโคมไฟฟ้า | 60 days | 4 | 174FS+7 days |  |  | July 4, 2020 8:00 AM | September 1, 2020 5:00 PM | July 08, 2020 05:00 PM | September 05, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 30 days | 30 days | 30 days | Electrician
173 | Yes | CMU1.6.5.2 | Auto Scheduled | งานสวิทช์, เต้ารับไฟฟ้า | 60 days | 4 | 174FS+7 days |  |  | July 4, 2020 8:00 AM | September 1, 2020 5:00 PM | July 08, 2020 05:00 PM | September 05, 2020 05:00 PM | August 07, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 30 days | 30 days | 30 days | Electrician
174 | Yes | CMU1.6.5.3 | Auto Scheduled | งานสายไฟฟ้า, ท่อร้อยสาย | 80 days | 4 | 154SS |  | 173FS+7 days,172FS+7 days | April 8, 2020 8:00 AM | June 26, 2020 5:00 PM | April 12, 2020 05:00 PM | June 30, 2020 05:00 PM | May 12, 2020 05:00 PM | July 30, 2020 05:00 PM | As Soon As Possible |  | No | 30 days | 30 days | 0 days | Electrician
175 | Yes | CMU1.6.5.4 | Auto Scheduled | งานสายลำโพง, ท่อร้อยสาย | 80 days | 4 | 154SS |  |  | April 8, 2020 8:00 AM | June 26, 2020 5:00 PM | April 15, 2020 05:00 PM | July 03, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 97 days | 97 days | 97 days | Electrician
176 | Yes | CMU1.6.5.5 | Auto Scheduled | งานสายระบบกล้องวงจรปิด, ท่อร้อยสาย | 80 days | 4 | 154SS |  |  | April 8, 2020 8:00 AM | June 26, 2020 5:00 PM | April 15, 2020 05:00 PM | July 03, 2020 05:00 PM | July 18, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 97 days | 97 days | 97 days | Electrician
177 | Yes | CMU1.6.6 | Auto Scheduled | งานครุภัณฑ์จัดจ้างหรือสั่งทำ ชั้นใต้ดิน | 165 days | 3 | 154SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 12, 2020 05:00 PM | September 23, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | Skilled carpenter
178 | Yes | CMU1.7 | Auto Scheduled | หมวดงานระบบคอมพิวเตอร์และแจ้งเหตุเพลิงไหม้ | 670 days | 2 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
179 | Yes | CMU1.7.1 | Auto Scheduled | งานระบบคอมพิวเตอร์ | 670 days | 3 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
180 | Yes | CMU1.7.1.1 | Auto Scheduled | ชั้นที่ 4 | 160 days | 4 | 36FS+14 days |  | 181 | November 30, 2018 8:00 AM | May 8, 2019 5:00 PM | November 30, 2018 05:00 PM | May 08, 2019 05:00 PM | April 24, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
181 | Yes | CMU1.7.1.2 | Auto Scheduled | ชั้นที่ 3 | 175 days | 4 | 180 | 182 | 182 | May 9, 2019 8:00 AM | October 30, 2019 5:00 PM | May 09, 2019 05:00 PM | October 30, 2019 05:00 PM | April 09, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
182 | Yes | CMU1.7.1.3 | Auto Scheduled | ชั้นที่ 2 | 175 days | 4 | 181 | 183 | 183,184 | October 31, 2019 8:00 AM | April 22, 2020 5:00 PM | October 31, 2019 05:00 PM | April 22, 2020 05:00 PM | April 09, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
183 | Yes | CMU1.7.1.4 | Auto Scheduled | ชั้นที่ 1 | 160 days | 4 | 182 | 180 |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 23, 2020 05:00 PM | September 29, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
184 | Yes | CMU1.7.1.5 | Auto Scheduled | ชั้นใต้ดิน | 160 days | 4 | 182 | 183SS |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 23, 2020 05:00 PM | September 29, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
185 | Yes | CMU1.7.2 | Auto Scheduled | ระบบแจ้งเหตุเพลิงไหม้ | 670 days | 3 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
186 | Yes | CMU1.7.2.1 | Auto Scheduled | ชั้นที่ 4 | 160 days | 4 | 36FS+14 days |  | 187 | November 30, 2018 8:00 AM | May 8, 2019 5:00 PM | November 30, 2018 05:00 PM | May 08, 2019 05:00 PM | April 24, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
187 | Yes | CMU1.7.2.2 | Auto Scheduled | ชั้นที่ 3 | 175 days | 4 | 186 | 188 | 188 | May 9, 2019 8:00 AM | October 30, 2019 5:00 PM | May 09, 2019 05:00 PM | October 30, 2019 05:00 PM | April 09, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
188 | Yes | CMU1.7.2.3 | Auto Scheduled | ชั้นที่ 2 | 175 days | 4 | 187 | 189 | 189,190 | October 31, 2019 8:00 AM | April 22, 2020 5:00 PM | October 31, 2019 05:00 PM | April 22, 2020 05:00 PM | April 09, 2018 05:00 PM | September 30, 2018 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
189 | Yes | CMU1.7.2.4 | Auto Scheduled | ชั้นที่ 1 | 160 days | 4 | 188 | 186 |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 23, 2020 05:00 PM | September 29, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
190 | Yes | CMU1.7.2.5 | Auto Scheduled | ชั้นใต้ดิน | 160 days | 4 | 188 | 189SS |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 23, 2020 05:00 PM | September 29, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
191 | Yes | CMU1.8 | Auto Scheduled | หมวดงานสีภายนอก งานซ่อมแซมและตกแต่งภายนอกอาคาร | 660 days | 2 |  |  |  | November 30, 2018 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | August 06, 2020 05:00 PM | December 16, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 507 days | 12 days | 12 days
192 | Yes | CMU1.8.1 | Auto Scheduled | งานสีภายนอกและงานซ่อมแซมพื้นผิวภายนอกอาคาร | 660 days | 3 |  |  |  | November 30, 2018 8:00 AM | September 19, 2020 5:00 PM | October 17, 2018 05:00 PM | August 06, 2020 05:00 PM | December 16, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 507 days | 12 days | 12 days
193 | Yes | CMU1.8.1.1 | Auto Scheduled | งานขัดลอกสีทาผนังเดิม | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 12, 2020 05:00 PM | September 23, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
194 | Yes | CMU1.8.1.2 | Auto Scheduled | น้ำยาทาปูนเก่า (สีรองพื้น) | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 12, 2020 05:00 PM | September 23, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
195 | Yes | CMU1.8.1.3 | Auto Scheduled | งานทาสีภายนอก (ทา 2 เที่ยว) ไม่รวมชั้นใต้ดิน | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 12, 2020 05:00 PM | September 23, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
196 | Yes | CMU1.8.1.4 | Auto Scheduled | งานทำความสะอาดและซ่อมแซมผนังกรุอิฐโชว์แนว (อ้างอิงราคางานขัดลอกสี) | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 12, 2020 05:00 PM | September 23, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
197 | Yes | CMU1.8.1.5 | Auto Scheduled | น้ำยาเคลือบผิวผนังอิฐโชว์แนว (อ้างอิงค่าทาน้ำยากันเชื้อรา) | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 12, 2020 05:00 PM | September 23, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
198 | Yes | CMU1.8.1.6 | Auto Scheduled | งานรื้อถอนแผ่นวัสดุกันซึมหลังคาดาดฟ้า (รื้อขนไป) | 90 days | 4 | 36FS+14 days |  |  | November 30, 2018 8:00 AM | February 27, 2019 5:00 PM | December 03, 2018 05:00 PM | March 02, 2019 05:00 PM | July 08, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 582 days | 582 days | 582 days | General worker
199 | Yes | CMU1.8.1.7 | Auto Scheduled | งานแผ่นวัสดุกันซึมแบบเป่าไฟผิวทราย | 90 days | 4 | 36FS+14 days |  |  | November 30, 2018 8:00 AM | February 27, 2019 5:00 PM | December 04, 2018 05:00 PM | March 03, 2019 05:00 PM | July 08, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 582 days | 582 days | 582 days | General worker
200 | Yes | CMU1.8.1.8 | Auto Scheduled | งานกันซึมชนิด Polyurethane สูตรน้ำมัน ชนิดยืดหยุ่นสูงเป็นพิเศษ | 90 days | 4 | 36FS+14 days |  |  | November 30, 2018 8:00 AM | February 27, 2019 5:00 PM | December 03, 2018 05:00 PM | March 02, 2019 05:00 PM | July 08, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 582 days | 582 days | 582 days | General worker
201 | Yes | CMU1.8.2 | Auto Scheduled | งานตกแต่งภายนอกอาคาร | 165 days | 3 |  |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | October 20, 2018 05:00 PM | April 02, 2019 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 12 days | 12 days | 12 days
202 | Yes | CMU1.8.2.1 | Auto Scheduled | ตะแกรงเหล็กฉีกกันนก XS-32 | 165 days | 4 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 12, 2020 05:00 PM | September 23, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
203 | Yes | CMU1.9 | Auto Scheduled | หมวดงานบริเวณ | 165 days | 2 |  |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | October 22, 2018 05:00 PM | April 04, 2019 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 12 days | 12 days | 12 days
204 | Yes | CMU1.9.1 | Auto Scheduled | งานรื้อถอน งานบริเวณ | 165 days | 3 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 12, 2020 05:00 PM | September 23, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
205 | Yes | CMU1.9.2 | Auto Scheduled | งานโครงสร้างวิศวกรรม งานบริเวณ | 165 days | 3 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 12, 2020 05:00 PM | September 23, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
206 | Yes | CMU1.9.3 | Auto Scheduled | งานสถาปัตยกรรม งานบริเวณ | 165 days | 3 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 12, 2020 05:00 PM | September 23, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | General worker
207 | Yes | CMU1.9.4 | Auto Scheduled | งานระบบไฟฟ้า งานบริเวณ | 165 days | 3 | 123SS |  |  | April 8, 2020 8:00 AM | September 19, 2020 5:00 PM | April 12, 2020 05:00 PM | September 23, 2020 05:00 PM | April 24, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 12 days | 12 days | 12 days | Electrician
208 | Yes | CMU1.10 | Auto Scheduled | หมวดงานครุภัณฑ์จัดซื้อ | 670 days | 2 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
209 | Yes | CMU1.10.1 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัว | 510 days | 3 |  |  |  | April 14, 2019 8:00 AM | September 4, 2020 5:00 PM | October 17, 2018 05:00 PM | March 09, 2020 05:00 PM | May 15, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 522 days | 27 days | 27 days
210 | Yes | CMU1.10.1.1 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้นใต้ดิน | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | August 29, 2020 05:00 PM | September 12, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
211 | Yes | CMU1.10.1.2 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้น 1 | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | September 01, 2020 05:00 PM | September 15, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
212 | Yes | CMU1.10.1.3 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้น 2 | 15 days | 4 | 121FS-15 days |  |  | March 24, 2020 8:00 AM | April 7, 2020 5:00 PM | March 31, 2020 05:00 PM | April 14, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Skilled carpenter
213 | Yes | CMU1.10.1.4 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้น 3 | 15 days | 4 | 92FS-15 days |  |  | September 26, 2019 8:00 AM | October 10, 2019 5:00 PM | October 05, 2019 05:00 PM | October 19, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Skilled carpenter
214 | Yes | CMU1.10.1.5 | Auto Scheduled | งานเฟอร์นิเจอร์ลอยตัวชั้น 4 | 15 days | 4 | 63 |  |  | April 14, 2019 8:00 AM | April 28, 2019 5:00 PM | April 21, 2019 05:00 PM | May 05, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 522 days | 522 days | 522 days | Skilled carpenter
215 | Yes | CMU1.10.2 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ | 525 days | 3 |  |  |  | March 30, 2019 8:00 AM | September 4, 2020 5:00 PM | October 17, 2018 05:00 PM | March 24, 2020 05:00 PM | April 30, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 522 days | 27 days | 27 days
216 | Yes | CMU1.10.2.1 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ ชั้น 1 | 30 days | 4 | 152FS-45 days |  |  | August 6, 2020 8:00 AM | September 4, 2020 5:00 PM | August 16, 2020 05:00 PM | September 14, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
217 | Yes | CMU1.10.2.2 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ ชั้น 2 | 30 days | 4 | 121FS-30 days |  |  | March 9, 2020 8:00 AM | April 7, 2020 5:00 PM | March 16, 2020 05:00 PM | April 14, 2020 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Skilled carpenter
218 | Yes | CMU1.10.2.3 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ ชั้น 3 | 30 days | 4 | 92FS-30 days |  |  | September 11, 2019 8:00 AM | October 10, 2019 5:00 PM | September 17, 2019 05:00 PM | October 16, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Skilled carpenter
219 | Yes | CMU1.10.2.4 | Auto Scheduled | งานซ่อมแซมเฟอร์นิเจอร์ ชั้น 4 | 30 days | 4 | 63FS-15 days |  |  | March 30, 2019 8:00 AM | April 28, 2019 5:00 PM | April 02, 2019 05:00 PM | May 01, 2019 05:00 PM | September 06, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 522 days | 522 days | 522 days | Skilled carpenter
220 | Yes | CMU1.10.3 | Auto Scheduled | งานผ้าม่าน | 510 days | 3 |  |  |  | April 14, 2019 8:00 AM | September 4, 2020 5:00 PM | October 17, 2018 05:00 PM | March 09, 2020 05:00 PM | May 15, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 522 days | 27 days | 27 days
221 | Yes | CMU1.10.3.1 | Auto Scheduled | งานผ้าม่าน ชั้น 1 | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | August 29, 2020 05:00 PM | September 12, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
222 | Yes | CMU1.10.3.2 | Auto Scheduled | งานผ้าม่าน ชั้น 2 | 15 days | 4 | 121FS-15 days |  |  | March 24, 2020 8:00 AM | April 7, 2020 5:00 PM | April 01, 2020 05:00 PM | April 15, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Skilled carpenter
223 | Yes | CMU1.10.3.3 | Auto Scheduled | งานผ้าม่าน ชั้น 3 | 15 days | 4 | 92FS-15 days |  |  | September 26, 2019 8:00 AM | October 10, 2019 5:00 PM | October 03, 2019 05:00 PM | October 17, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Skilled carpenter
224 | Yes | CMU1.10.3.4 | Auto Scheduled | งานผ้าม่าน ชั้น 4 | 15 days | 4 | 63 |  |  | April 14, 2019 8:00 AM | April 28, 2019 5:00 PM | April 24, 2019 05:00 PM | May 08, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 522 days | 522 days | 522 days | Skilled carpenter
225 | Yes | CMU1.10.4 | Auto Scheduled | งานป้าย | 510 days | 3 |  |  |  | April 14, 2019 8:00 AM | September 4, 2020 5:00 PM | October 17, 2018 05:00 PM | March 09, 2020 05:00 PM | May 15, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 522 days | 27 days | 27 days
226 | Yes | CMU1.10.4.1 | Auto Scheduled | งานป้าย ชั้นใต้ดิน | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | September 03, 2020 05:00 PM | September 17, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
227 | Yes | CMU1.10.4.2 | Auto Scheduled | งานป้าย ชั้น 1 | 15 days | 4 | 152FS-30 days |  |  | August 21, 2020 8:00 AM | September 4, 2020 5:00 PM | September 02, 2020 05:00 PM | September 16, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 27 days | 27 days | 27 days | Skilled carpenter
228 | Yes | CMU1.10.4.3 | Auto Scheduled | งานป้าย ชั้น 2 | 15 days | 4 | 121FS-15 days |  |  | March 24, 2020 8:00 AM | April 7, 2020 5:00 PM | March 31, 2020 05:00 PM | April 14, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Skilled carpenter
229 | Yes | CMU1.10.4.4 | Auto Scheduled | งานป้าย ชั้น 3 | 15 days | 4 | 92FS-15 days |  |  | September 26, 2019 8:00 AM | October 10, 2019 5:00 PM | October 04, 2019 05:00 PM | October 18, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Skilled carpenter
230 | Yes | CMU1.10.4.5 | Auto Scheduled | งานป้าย ชั้น 4 | 15 days | 4 | 63 |  |  | April 14, 2019 8:00 AM | April 28, 2019 5:00 PM | April 19, 2019 05:00 PM | May 03, 2019 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 522 days | 522 days | 522 days | Skilled carpenter
231 | Yes | CMU1.10.5 | Auto Scheduled | งานอื่นๆ | 15 days | 3 |  |  |  | August 6, 2020 8:00 AM | August 20, 2020 5:00 PM | October 20, 2018 05:00 PM | November 03, 2018 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 42 days | 42 days | 42 days
232 | Yes | CMU1.10.5.1 | Auto Scheduled | ตู้อลูมิเนียมพับขึ้นรูป พ่นสี ครอบตู้กดน้ำ | 15 days | 4 | 152FS-45 days |  |  | August 6, 2020 8:00 AM | August 20, 2020 5:00 PM | August 15, 2020 05:00 PM | August 29, 2020 05:00 PM | September 21, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 42 days | 42 days | 42 days | General worker
233 | Yes | CMU1.10.6 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ | 670 days | 3 |  |  |  | November 30, 2018 8:00 AM | September 29, 2020 5:00 PM | October 17, 2018 05:00 PM | August 16, 2020 05:00 PM | December 06, 2018 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 2 days | 2 days | 2 days
234 | Yes | CMU1.10.6.1 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้นใต้ดิน | 160 days | 4 | 236 |  |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
235 | Yes | CMU1.10.6.2 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้น 1 | 160 days | 4 | 236 |  |  | April 23, 2020 8:00 AM | September 29, 2020 5:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | April 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 2 days | Electrician
236 | Yes | CMU1.10.6.3 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้น 2 | 175 days | 4 | 237 |  | 235,234 | October 31, 2019 8:00 AM | April 22, 2020 5:00 PM | November 06, 2019 05:00 PM | April 28, 2020 05:00 PM | March 12, 2020 05:00 PM | September 02, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
237 | Yes | CMU1.10.6.4 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้น 3 | 175 days | 4 | 238 |  | 236 | May 9, 2019 8:00 AM | October 30, 2019 5:00 PM | May 15, 2019 05:00 PM | November 05, 2019 05:00 PM | March 12, 2020 05:00 PM | September 02, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
238 | Yes | CMU1.10.6.5 | Auto Scheduled | งานระบบควบคุมไฟฟ้าแสงสว่างด้วยคอมพิวเตอร์ ชั้น 4 | 160 days | 4 | 36FS+14 days |  | 237 | November 30, 2018 8:00 AM | May 8, 2019 5:00 PM | December 03, 2018 05:00 PM | May 11, 2019 05:00 PM | March 27, 2020 05:00 PM | September 02, 2020 05:00 PM | As Soon As Possible |  | No | 2 days | 2 days | 0 days | Electrician
239 | Yes | CMU1.10.7 | Auto Scheduled | งานระบบเครื่องเสียงประกาศ (ใช้ลำโพงของเดิม) | 539 days | 3 |  |  |  | April 7, 2019 8:00 AM | September 26, 2020 5:00 PM | October 17, 2018 05:00 PM | April 07, 2020 05:00 PM | April 16, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 530 days | 5 days | 5 days
240 | Yes | CMU1.10.7.1 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้นใต้ดิน | 7 days | 4 | 241 |  |  | September 20, 2020 8:00 AM | September 26, 2020 5:00 PM | September 28, 2020 05:00 PM | October 04, 2020 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 5 days | 5 days | 5 days | Electrician
241 | Yes | CMU1.10.7.2 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้น 1 | 7 days | 4 | 152FS-7 days |  | 240 | September 13, 2020 8:00 AM | September 19, 2020 5:00 PM | September 17, 2020 05:00 PM | September 23, 2020 05:00 PM | September 09, 2020 05:00 PM | September 15, 2020 05:00 PM | As Soon As Possible |  | No | 5 days | 5 days | 0 days | Electrician
242 | Yes | CMU1.10.7.3 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้น 2 | 7 days | 4 | 121FS-7 days |  |  | April 1, 2020 8:00 AM | April 7, 2020 5:00 PM | April 07, 2020 05:00 PM | April 13, 2020 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Electrician
243 | Yes | CMU1.10.7.4 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้น 3 | 7 days | 4 | 92FS-7 days |  |  | October 4, 2019 8:00 AM | October 10, 2019 5:00 PM | October 12, 2019 05:00 PM | October 18, 2019 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Electrician
244 | Yes | CMU1.10.7.5 | Auto Scheduled | งานเครื่องเสียงประกาศ ชั้น 4 | 7 days | 4 | 63FS-7 days |  |  | April 7, 2019 8:00 AM | April 13, 2019 5:00 PM | April 13, 2019 05:00 PM | April 19, 2019 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 537 days | 537 days | 537 days | Electrician
245 | Yes | CMU1.10.8 | Auto Scheduled | งานระบบกล้องวงจรปิด (ใช้กล้องวงจรปิดของเดิม) | 539 days | 3 |  |  |  | April 7, 2019 8:00 AM | September 26, 2020 5:00 PM | October 17, 2018 05:00 PM | April 07, 2020 05:00 PM | April 16, 2019 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | Yes | 530 days | 5 days | 5 days
246 | Yes | CMU1.10.8.1 | Auto Scheduled | งานกล้องวงจรปิด ชั้นใต้ดิน | 7 days | 4 | 247 |  |  | September 20, 2020 8:00 AM | September 26, 2020 5:00 PM | September 28, 2020 05:00 PM | October 04, 2020 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 5 days | 5 days | 5 days | Electrician
247 | Yes | CMU1.10.8.2 | Auto Scheduled | งานกล้องวงจรปิด ชั้น 1 | 7 days | 4 | 152FS-7 days |  | 246 | September 13, 2020 8:00 AM | September 19, 2020 5:00 PM | September 17, 2020 05:00 PM | September 23, 2020 05:00 PM | September 09, 2020 05:00 PM | September 15, 2020 05:00 PM | As Soon As Possible |  | No | 5 days | 5 days | 0 days | Electrician
248 | Yes | CMU1.10.8.3 | Auto Scheduled | งานกล้องวงจรปิด ชั้น 2 | 7 days | 4 | 121FS-7 days |  |  | April 1, 2020 8:00 AM | April 7, 2020 5:00 PM | April 08, 2020 05:00 PM | April 14, 2020 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 177 days | 177 days | 177 days | Electrician
249 | Yes | CMU1.10.8.4 | Auto Scheduled | งานกล้องวงจรปิด ชั้น 3 | 7 days | 4 | 92FS-7 days |  |  | October 4, 2019 8:00 AM | October 10, 2019 5:00 PM | October 12, 2019 05:00 PM | October 18, 2019 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 357 days | 357 days | 357 days | Electrician
250 | Yes | CMU1.10.8.5 | Auto Scheduled | งานกล้องวงจรปิด ชั้น 4 | 7 days | 4 | 63FS-7 days |  |  | April 7, 2019 8:00 AM | April 13, 2019 5:00 PM | April 12, 2019 05:00 PM | April 18, 2019 05:00 PM | September 29, 2020 05:00 PM | October 05, 2020 05:00 PM | As Soon As Possible |  | No | 537 days | 537 days | 537 days | Electrician