## Convert
ID | Active | WBS | Task_Mode | Name | Duration | Outline_Level | Predecessors | Early_Start | Early_Finish | Late_Start | Late_Finish | Constraint_Type | Constraint_Date | Summary | Successors | Resource_Names
1 | Yes | CMU1 | Auto Scheduled | Chiang Mai Library Renovation Project |  | 1 | [5 empty] | As Soon As Possible | NA | Yes
2 | Yes | CMU1.2 | Auto Scheduled | Renovation on the fourth floor |  | 2 | [5 empty] | As Soon As Possible | NA | Yes
3 | Yes | CMU1.2.1 | Auto Scheduled | Demolition work on the 4th floor (Dismantled) | 30 | 3 |  | Oct 17 '18 | Nov 15 '18 | Jun 23 '19 | Jul 22 '19 | As Soon As Possible | NA | No | 6FS+45d,7FS+45d,18,30SS+14d,33FS+14d,35FS+14d,38FS+14d,39FS+14d,40FS+14d,51FS+14d | General worker
4 | Yes | CMU1.2.2 | Auto Scheduled | Architecture Work on the Fourth Floor |  | 3 | [5 empty] | As Soon As Possible | NA | Yes
5 | Yes | CMU1.2.2.1 | Auto Scheduled | Ceiling work | 30 | 4 | 6,8,9 | Sep 18 '19 | Oct 17 '19 | Sep 06 '20 | Oct 05 '20 | Start No Earlier Than | Sep 18 '19 | No |  | Skilled carpenter
6 | Yes | CMU1.2.2.2 | Auto Scheduled | Floor work | 60 | 4 | 3FS+45d | Mar 06 '19 | May 04 '19 | Jul 08 '20 | Sep 05 '20 | Start No Earlier Than | Mar 06 '19 | No | 5,10 | General worker
7 | Yes | CMU1.2.2.3 | Auto Scheduled | Wall work | 30 | 4 | 3FS+45d | Feb 05 '19 | Mar 06 '19 | Jul 08 '20 | Aug 06 '20 | Start No Earlier Than | Feb 05 '19 | No | 8,9 | General worker
8 | Yes | CMU1.2.2.4 | Auto Scheduled | Door and Window Work | 30 | 4 | 7 | Jun 27 '19 | Jul 26 '19 | Aug 07 '20 | Sep 05 '20 | Start No Earlier Than | Jun 27 '19 | No | 5,10 | Skilled carpenter
9 | Yes | CMU1.2.2.5 | Auto Scheduled | Staircase | 30 | 4 | 7 | Mar 13 '19 | Apr 11 '19 | Aug 07 '20 | Sep 05 '20 | Start No Earlier Than | Mar 13 '19 | No | 5,10 | General worker
10 | Yes | CMU1.2.2.6 | Auto Scheduled | Painting work | 30 | 4 | 6,8,9 | Oct 18 '19 | Nov 16 '19 | Sep 06 '20 | Oct 05 '20 | Start No Earlier Than | Oct 18 '19 | No |  | General worker
11 | Yes | CMU1.2.2.7 | Auto Scheduled | Sanitary ware |  | 4 | [5 empty] | As Soon As Possible | NA | Yes
12 | Yes | CMU1.2.2.7.1 | Auto Scheduled | Zone T-1 the area in front of the original buidling | 15 | 5 | 13FS+135d | Nov 28 '19 | Dec 12 '19 | Apr 24 '20 | May 08 '20 | Start No Earlier Than | Nov 28 '19 | No | 14FS+135d | Sanitary-Plumber
13 | Yes | CMU1.2.2.7.2 | Auto Scheduled | Zone T-2 the area in the middle | 15 | 5 | 18,22 | May 05 '19 | May 19 '19 | Nov 26 '19 | Dec 10 '19 | Start No Earlier Than | May 05 '19 | No | 12FS+135d | Sanitary-Plumber
14 | Yes | CMU1.2.2.7.3 | Auto Scheduled | Zone T3 the area behind the new building | 15 | 5 | 12FS+135d | Jun 24 '20 | Jul 08 '20 | Sep 21 '20 | Oct 05 '20 | Start No Earlier Than | Jun 24 '20 | No |  | Sanitary-Plumber
15 | Yes | CMU1.2.3 | Auto Scheduled | Sanitation system work on the fourth floor |  | 3 | [5 empty] | As Soon As Possible | NA | Yes
16 | Yes | CMU1.2.3.1 | Auto Scheduled | Water supply pipe system work |  | 4 | [5 empty] | As Soon As Possible | NA | Yes
17 | Yes | CMU1.2.3.1.1 | Auto Scheduled | Zone T-1 the area in front of the original buidling | 126 | 5 | 18FS+15d | May 06 '19 | Sep 08 '19 | Jan 13 '20 | May 17 '20 | Start No Earlier Than | May 06 '19 | No | 19FS+15d | Sanitary-Plumber
18 | Yes | CMU1.2.3.1.2 | Auto Scheduled | Zone T-2 the area in the middle | 126 | 5 | 3 | Nov 16 '18 | Mar 21 '19 | Jul 23 '19 | Nov 25 '19 | As Soon As Possible | NA | No | 13,17FS+15d,22SS | Sanitary-Plumber
19 | Yes | CMU1.2.3.1.3 | Auto Scheduled | Zone T3 the area behind the new building | 126 | 5 | 17FS+15d | Nov 19 '19 | Mar 23 '20 | Jun 02 '20 | Oct 05 '20 | Start No Earlier Than | Nov 19 '19 | No |  | Sanitary-Plumber
20 | Yes | CMU1.2.3.2 | Auto Scheduled | Sewage pipe system, general sewer and air pipe |  | 4 | [5 empty] | As Soon As Possible | NA | Yes
21 | Yes | CMU1.2.3.2.1 | Auto Scheduled | Zone T-1 the area in front of the original buidling | 126 | 5 | 22FS+15d | May 23 '19 | Sep 25 '19 | Jan 13 '20 | May 17 '20 | Start No Earlier Than | May 23 '19 | No | 23FS+15d | Sanitary-Plumber
22 | Yes | CMU1.2.3.2.2 | Auto Scheduled | Zone T-2 the area in the middle | 126 | 5 | 18SS | Nov 26 '18 | Mar 31 '19 | Jul 23 '19 | Nov 25 '19 | Start No Earlier Than | Nov 26 '18 | No | 13,21FS+15d | Sanitary-Plumber
23 | Yes | CMU1.2.3.2.3 | Auto Scheduled | Zone T3 the area behind the new building | 126 | 5 | 21FS+15d | Nov 17 '19 | Mar 21 '20 | Jun 02 '20 | Oct 05 '20 | Start No Earlier Than | Nov 17 '19 | No |  | Sanitary-Plumber
24 | Yes | CMU1.2.4 | Auto Scheduled | Electrical system work on the 4th floor |  | 3 | [5 empty] | As Soon As Possible | NA | Yes
25 | Yes | CMU1.2.4.1 | Auto Scheduled | Electric lamp | 30 | 4 | 27FS+7d | Jul 30 '20 | Aug 28 '20 | Sep 06 '20 | Oct 05 '20 | Start No Earlier Than | Jul 30 '20 | No |  | Electrician
26 | Yes | CMU1.2.4.2 | Auto Scheduled | Switch and Electrical Socket | 30 | 4 | 27FS+7d | Sep 06 '20 | Oct 05 '20 | Sep 06 '20 | Oct 05 '20 | Start No Earlier Than | Sep 06 '20 | No |  | Electrician
27 | Yes | CMU1.2.4.3 | Auto Scheduled | Electrical work and conduits | 80 | 4 | 30SS+30d | Mar 24 '20 | Jun 11 '20 | Jun 11 '20 | Aug 29 '20 | Start No Earlier Than | Mar 24 '20 | No | 25FS+7d,26FS+7d | Electrician
28 | Yes | CMU1.2.4.4 | Auto Scheduled | Speaker cable work and conduit | 80 | 4 | 30SS+30d | May 04 '20 | Jul 22 '20 | Jul 18 '20 | Oct 05 '20 | Start No Earlier Than | May 04 '20 | No |  | Electrician
29 | Yes | CMU1.2.4.5 | Auto Scheduled | CCTV system work and conduit pipe | 80 | 4 | 30SS+30d | Mar 28 '20 | Jun 15 '20 | Jul 18 '20 | Oct 05 '20 | Start No Earlier Than | Mar 28 '20 | No |  | Electrician
30 | Yes | CMU1.2.5 | Auto Scheduled | Durable goods and made to order work on the fourth floor | 165 | 3 | 3SS+14d | Dec 13 '19 | May 25 '20 | Apr 09 '20 | Sep 20 '20 | Start No Earlier Than | Dec 13 '19 | No | 27SS+30d,28SS+30d,29SS+30d,43,45FS-15d,47,49,53FS-7d,55FS-7d | Skilled carpenter
31 | Yes | CMU1.7 | Auto Scheduled | Computer system and fire alarm system |  | 2 | [5 empty] | As Soon As Possible | NA | Yes
32 | Yes | CMU1.7.1 | Auto Scheduled | Computer system |  | 3 | [5 empty] | As Soon As Possible | NA | Yes
33 | Yes | CMU1.7.1.1 | Auto Scheduled | Fourth floor | 160 | 4 | 3FS+14d | Apr 08 '19 | Sep 14 '19 | Apr 29 '20 | Oct 05 '20 | Start No Earlier Than | Apr 08 '19 | No |  | Electrician
34 | Yes | CMU1.7.2 | Auto Scheduled | Fire Alarm System |  | 3 | [5 empty] | As Soon As Possible | NA | Yes
35 | Yes | CMU1.7.2.1 | Auto Scheduled | Fourth floor | 160 | 4 | 3FS+14d | Mar 18 '19 | Aug 24 '19 | Apr 29 '20 | Oct 05 '20 | Start No Earlier Than | Mar 18 '19 | No |  | Electrician
36 | Yes | CMU1.8 | Auto Scheduled | Exterior paint, repair and exterior decoration of the building |  | 2 | [5 empty] | As Soon As Possible | NA | Yes
37 | Yes | CMU1.8.1 | Auto Scheduled | Exterior paint and exterior surface repair |  | 3 | [5 empty] | As Soon As Possible | NA | Yes
38 | Yes | CMU1.8.1.6 | Auto Scheduled | Demolition of roof waterproofing (Dismantled) | 90 | 4 | 3FS+14d | Jul 01 '20 | Sep 28 '20 | Jul 08 '20 | Oct 05 '20 | Start No Earlier Than | Jul 01 '20 | No |  | General worker
39 | Yes | CMU1.8.1.7 | Auto Scheduled | Sand blasting waterproofing sheet material | 90 | 4 | 3FS+14d | Dec 06 '18 | Mar 05 '19 | Jul 08 '20 | Oct 05 '20 | Start No Earlier Than | Dec 06 '18 | No |  | General worker
40 | Yes | CMU1.8.1.8 | Auto Scheduled | Polyurethane waterproofing, ultra-flexible oil formula, resistant to UV light, Xander, Ardex or equivalent. | 90 | 4 | 3FS+14d | Dec 02 '18 | Mar 01 '19 | Jul 08 '20 | Oct 05 '20 | Start No Earlier Than | Dec 02 '18 | No |  | General worker
41 | Yes | CMU1.10 | Auto Scheduled | Durable Goods |  | 2 | [5 empty] | As Soon As Possible | NA | Yes
42 | Yes | CMU1.10.1 | Auto Scheduled | Floating furniture |  | 3 | [5 empty] | As Soon As Possible | NA | Yes
43 | Yes | CMU1.10.1.5 | Auto Scheduled | Floating furniture on the fourth floor | 15 | 4 | 30 | Jun 08 '20 | Jun 22 '20 | Sep 21 '20 | Oct 05 '20 | Start No Earlier Than | Jun 08 '20 | No |  | Skilled carpenter
44 | Yes | CMU1.10.2 | Auto Scheduled | Repair furniture work |  | 3 | [5 empty] | As Soon As Possible | NA | Yes
45 | Yes | CMU1.10.2.4 | Auto Scheduled | Furniture repair work on the fourth floor | 30 | 4 | 30FS-15d | Sep 05 '20 | Oct 04 '20 | Sep 06 '20 | Oct 05 '20 | Start No Earlier Than | Sep 05 '20 | No |  | Skilled carpenter
46 | Yes | CMU1.10.3 | Auto Scheduled | Curtain work |  | 3 | [5 empty] | As Soon As Possible | NA | Yes
47 | Yes | CMU1.10.3.4 | Auto Scheduled | Curtain on the fourth floor | 15 | 4 | 30 | Jul 09 '20 | Jul 23 '20 | Sep 21 '20 | Oct 05 '20 | Start No Earlier Than | Jul 09 '20 | No |  | Skilled carpenter
48 | Yes | CMU1.10.4 | Auto Scheduled | Signs |  | 3 | [5 empty] | As Soon As Possible | NA | Yes
49 | Yes | CMU1.10.4.5 | Auto Scheduled | Signs on the fourth floor | 15 | 4 | 30 | Jun 16 '20 | Jun 30 '20 | Sep 21 '20 | Oct 05 '20 | Start No Earlier Than | Jun 16 '20 | No |  | Skilled carpenter
50 | Yes | CMU1.10.6 | Auto Scheduled | TWO WIRE REMOTE CONTROL LIGHTING SYSTEM |  | 3 | [5 empty] | As Soon As Possible | NA | Yes
51 | Yes | CMU1.10.6.5 | Auto Scheduled | Two wire remote control lighting system for the fourth floor | 160 | 4 | 3FS+14d | Sep 09 '19 | Feb 15 '20 | Apr 29 '20 | Oct 05 '20 | Start No Earlier Than | Sep 09 '19 | No |  | Electrician
52 | Yes | CMU1.10.7 | Auto Scheduled | Sound system (Using previous speakers) |  | 3 | [5 empty] | As Soon As Possible | NA | Yes
53 | Yes | CMU1.10.7.5 | Auto Scheduled | Sound system for the forth floor | 7 | 4 | 30FS-7d | Jul 23 '20 | Jul 29 '20 | Sep 29 '20 | Oct 05 '20 | Start No Earlier Than | Jul 23 '20 | No |  | Electrician
54 | Yes | CMU1.10.8 | Auto Scheduled | CCTV system (Using the previous CCTV system) |  | 3 | [5 empty] | As Soon As Possible | NA | Yes
55 | Yes | CMU1.10.8.5 | Auto Scheduled | CCTV on the fourth floor | 7 | 4 | 30FS-7d | Aug 29 '20 | Sep 04 '20 | Sep 29 '20 | Oct 05 '20 | Start No Earlier Than | Aug 29 '20 | No |  | Electrician